## HVAC
[6 empty] | Date | 29 June 2024
[6 empty] | Quote # | 002
Attn: Mr. Taha Ghaznavi
Quotation for Extra work to be carried out for VRF Outdoor units - Gul Ahmed 7th Floor Tijarah Center Karachi
S. # | Description | Unit | Qty | Material Rate | Labour Rate | Material Amount | Labour Amount
1 | Making existing as built drawings of VRF system. | Job | 1 | 0 | 25000 | 0 | 25000
2 | Making new piping layout tree for Gree (copper sizing) of system. | Job | 1 |  | 25000 | 0 | 25000
3 | Removal of installed indoor units service / pressure tesr of evaporator coil reassembled and reintalled after wood work. | Nos | 32 | 0 | 12000 | 0 | 384000
4 | Supply and installation of isolation valve for indoor units (Gas + Liquid) Note: Gree will decide to install or not. |  |  |  |  | 0 | 0
| a) 1/4" Dia | Nos | 18 | 10000 | 2000 | 180000 | 36000
| b) 3/8" Dia | Nos | 7 | 11280 | 2000 | 78960 | 14000
| c) 1/2" Dia | Nos | 19 | 11875 | 2000 | 225625 | 38000
| d) 5/8" Dia | Nos | 7 | 13125 | 2000 | 91875 | 14000
| e) 3/4" Dia | No | 1 | 25625 | 2000 | 25625 | 2000
5 | Removal and dismantle of copper pipes power / controls cable including Regging lifting and shifitng of VRF condensing units at new location including supply and installation of newpran pads. | Unit | 5 |  | 15000 | 0 | 75000
6 | Removal of exisitng VRF condenser exhaust air GI sheet metal ducts and reinstallation of GI sheet metal ducts with new fittings hanger & supports including exhaust fans connections. | Job | 1 |  | 50000 | 0 | 50000
7 | Providing and installation of ventilation fan 42" x 42" for fresh air (for condensing unit) | No | 1 | 140000 | 10000 | 140000 | 10000
8 | Providing and fixing of flexible duct connector for condenser discharge. | Rft | 60 | 750 | 150 | 45000 | 9000
9 | Cleaning and painting (Primer + Epoxy) existing checker plates and platform for installation of condensing units | Job | 1 | 30000 | 40000 | 30000 | 40000
10 | Reconnecting of power / control wire for condensing units for relocated units. | Unit | 5 | 15000 | 5000 | 75000 | 25000
Sub Total Amount Rs | [5 empty] | 892085 | 747000
Total Amount Rs | [6 empty] | 1639085
Total Amount Rs
Note: Room or space required for keeping removed units with Lock and key.
For PIONEER ENGINEERING SERVICES

## eee
|  |  |  | Date | 29 June 2024
|  |  |  | Quotation # | 001
Attn: Mr. Taha Ghaznavi
Quotation
Extra work to be carried out for VRF Outdoor units - Gul Ahmed 7th Floor Tijarah Center Karachi
S. # | Description | Unit | Qty | Rate | Amount
1 | Removal of installaed indoor units service/ pressure tesr of evaporator coil re assebled and reintall adter wood work | Nos | 32 | 10000 | 320000
| Supply and installation of isolation valve for indoor units (Gas + Liquid) |  |  |  | 0
| Making existing as built drawings of VRF system. | Job | 1 | 25000 | 25000
| Makind new piping layout tree for Gree (copper sizing) of system | Job | 1 | 25000 | 25000
5 | Removal Reinstallation of GI sheet metal ducts with new fittings hanger & supports. |  |  |  | 0
6 | Providing and fixing of flexible duct connector for condenser discharge. | Rft | 800 | 6000 | 4800000
1 | Dismantle of copper refrigerent pipes electric power cable control wiring from condensing units. | Job | 1 | 1001 | 1001
2 | Remove all of existing exhaust air ducts |  |  | 1002 | 0
3 | Regging lifting and shifitng of VRF condensing units at new location. |  |  | 1003 | 0
4 | Providing and installation of Newpron pads for condensing units. |  |  | 1004 | 0
9 | Providing an installation of fresh air fans 8000 CFM for condensing units. |  |  | 1009 | 0
9 | Removal of refixing of cable tray. |  |  | 1010 | 0
Total Amount Rs |  |  |  |  | 1001
Note: Copper pipe and new GI Ducts rates already in BOQ, charged accordingly.
Terms & Conditions: 1) Above prices are exclusive of SST 2) Scaffolding included for installation of Platform.
For PIONEER ENGINEERING SERVICES