## Summary
LAMA Outlet |  |  |  | BILL OF QUANTITIES: SUMMARY
DOLMEN MALL, KARACHI |  |  |  | HVAC & FF WORKS
Running Bill
S.# | DESCRIPTION | SUPPLY (Rs.) | INSTALLATION (Rs.) | TOTAL (Rs.)
2 | HVAC WORK | 257648 | 88055.3 | 345703.3
3 | FIRE FIGHTING WORK | 58000 | 49000 | 107000
| Total Amount (Rs.) | 315648 | 137055.3 | 452703.3

## HVAC
LAMA Outlet | [11 empty] | BILL OF QUANTITIES
DOLMEN MALL, KARACHI | [11 empty] | HVAC WORKS
BILL OF QUANTITIES | [7 empty] | RUNNING BILL
S.# | DESCRIPTION |  | QTY | UNIT | SUPPLY RATE | INSTALLATION RATE | TOTAL AMOUNT | MATERIAL |  | LABOUR |  | TOTAL (Rs.)
[8 empty] | BILLED QTY | AMOUNT | BILLED QTY | AMOUNT
SECTION - A DUCTWORK WITH ACCESSORIES:
1 | Ductwork With Accessories:
Supply, fabrication, installation, testing and commissioning of Sheet Metal hand made / machine fabricated Duct Work as shown on the drawings and as per technical specification including all labour, material, accessories, tees, plenum, transition pieces, splitter dampers, special duct test holes, duct access doors, air deflector, as where required complete in respect and to the satisfaction of Engineer incharge.
| i. | 24 - Gauge | 350 | Sqft. | 550 | 80 | 220500 | 215.81 | 118695.5 | 215.81 | 17264.8 | 135960.3
Note: Contractor is advised to confirm the duct area as per site conditions before commencement of work.
2 | Ductwork Insulation:
| Supply, installation, testing and commissioning of Fiberglass Duct Insulation including aluminium foil kraft paper and canvas cloth, Anti Fungus Adhesive as shown on the drawings and as per technical specification including all labour, material and accessories required for insulation work complete in respect and to the satisfaction of Engineer incharge. | [10 empty] | 0
| i. | 25 mm Thick, 24 kg/m3 density, Fiberglass Insulation | 1000 | Sqft. | 250 | 50 | 300000 | 215.81 | 53952.5 | 215.81 | 10790.5 | 64743
Note: Contractor is advised to confirm the duct insulation area as per site conditions before commencement of work.
3 | Flexible Duct:
Supply, installation, testing and commissioning of Round Shape Flexible Duct Neoprene with Aluminium Foil Paper, as shown on the drawings and as per technical specification including all labour, material and accessories complete in all respect.
| i. | 8" Dia | 100 | Rft. | 550 | 100 | 65000 | 100 | 55000 | 100 | 10000 | 65000
| Note: Contractor is advised to confirm the running feet as per site conditions before commencement of work. | [5 empty] | 0 |  | 0 | 0 | 0 | 0
4 | Flexible Duct Connector:
| Supply, installation, testing and commissioning of 6" wide rubber impregnated canvas Flexible Duct Connector (imported type) between FCU's / Fans and Duct Work as shown on the drawings and as specified in technical specification including all labour, material, accessories, complete in respect and to the satisfaction of Engineer incharge. |  | 1 | Rft. | 750 | 100 | 850 |  | 0 | 0 | 0 | 0
5 | Duct Sound Liner:
| Supply, installation, testing and commissioning of Duct Sound Liner 25 mm thick, 32 kg/m3 density, as shown on the drawings and as per technical specifications including all labour, material and accessories, complete in respect and to the satisfaction of Engineer incharge. |  | 1 | Sqft. | 300 | 50 | 350 |  | 0 | 0 | 0 | 0
Note: Contractor is advised to confirm quantities as per site conditions before commencement of work.
Total Amount (Rs.) Section - A (Carried Forward to Summary)
SECTION - B AIR DEVICES
6 | Air Devices:
Supply, installation, testing and commissioning of Air Devices included with back opposed blade volume controller with accessible key operator, as shown on the drawings and as specified in technical specification including balancing of air flow rates, including all labour, material and accessories, complete in all respect and to the satisfaction of Engineer Incharge.
A. | Square Diffuser (T&B Model: AM)
| i. | 8" x 8" | 4 | Nos. | 4500 | 1000 | 22000 |  | 0 | 0 | 0 | 0
0
B | Supply Air Linear Slot Diffuser with Damper (T&B Model: 6000 Series)
| i. | 3/4", 2-Slot, 59" Long | 1 | Nos. | 9000 | 1000 | 10000 |  | 0 | 0 | 0 | 0
Note: Contractor is advised to confirm quantities as per site conditions before commencement of work.
Total Amount (Rs.) Section - B (Carried Forward to Summary)
SECTION - C DAMPERS:
7 | Volume Control Dampers:
| Supply, installation, testing and commissioning of opposed blade Quadrant Volume Control Dampers for Linear Slot Plenum, as shown on the drawings and as specified in technical specification including all labour, material and accessories, complete in all respect and to the satisfaction of Engineer Incharge. |  | 1 | Nos | 20000 | 5000 | 25000 | 1 | 20000 | 1 | 5000 | 25000
Note: Contractor is advised to confirm quantities as per site conditions before commencement of work.
Total Amount (Rs.) Section - C (Carried Forward to Summary)
SECTION - D MISCELLANEOUS
8 | Shop Drawings and As-Built Drawing
| Preparation of shop drawings and take approval prior to execution of construction work at site. After completion of construction, prepare as-built drawing as per construction at site and take approval by consultant. |  | 1 | Job | 10000 | 10000 | 20000 | 1 | 10000 | 1 | 10000 | 20000
9 | Testing, Balancing and Commissioning:
| Testing, Balancing and commissioning of specialties and duct work including the cost of all labor, material, replacements, repair etc. required to be carried out by a separate agency and the result and test data to be submitted to the Engineer In charge for approval prior starting maintenance period, complete in all respect. |  | 1 | Job | 0 | 35000 | 35000 | 1 | 0 | 1 | 35000 | 35000
| Total Amount (Rs.) Section - D (Carried Forward to Summary) | [5 empty] | 698700 |  | 257648 |  | 88055.3 | 345703.3

## FF
LAMA Outlet | [11 empty] | BILL OF QUANTITIES
DOLMEN MALL, KARACHI | [11 empty] | FIRE FIGHTING WORKS
BILL OF QUANTITIES | [7 empty] | RUNNING BILL
S.# | DESCRIPTION |  | QTY | UNIT | SUPPLY RATE | INSTALLATION RATE | TOTAL AMOUNT | MATERIAL |  | LABOUR |  | TOTAL (Rs.)
[8 empty] | BILLED QTY | AMOUNT | BILLED QTY | AMOUNT
FIRE FIGHTING WORKS:
SECTION - A FIRE SPRINKLERS
1 | Supply & installation of following Quick Response FM/UL listed sprinkler by Tyco/Reliable of 68 Degree C temperature Rating (Red Bulb) as per specifications including all accessories as per drawings and specifications
| i) | Quick Response Pendent Type | 1 | Nos. | 7000 | 1000 | 8000 | 4 | 28000 | 4 | 4000 | 32000
Total Amount (Rs.) Section - A (Carried Forward to Summary)
SECTION - B FIRE EXTINGUISHERS
2 | Supply and installation of below mentioned Portable Fire extinguishers with Wall mount brackets as indicated on the drawings, as per specifications and Engineers Recommendation.
| i) | 6 Kg C02 wall mounted fire extinguisher | 4 | Nos. | 27000 | 1000 | 112000 |  | 0 | 0 | 0 | 0
| ii) | 5 Kg Dry powder wall mounted fire extinguisher | 4 | Nos. | 17000 | 1000 | 72000 |  | 0 | 0 | 0 | 0
Total Amount (Rs.) Section - B (Carried Forward to Summary)
SECTION - C MISCELLANEOUS
3 | Hanger and Supports
| Supply & installation of UL/FM hangers, Rods, Anchors and supports Expansion Joints and Seismic Supports for fire piping work as per NFPA-20 by Fisher/Hilti/Sikla/Link and as per Specification including support load calculations. |  | 1 | Job | 20000 | 10000 | 30000 | 1 | 20000 | 1 | 10000 | 30000
4 | Shop Drawings and As-Built Drawings
| Preparation of shop drawings and take approval prior to execution of construction work at site. After completion of construction, prepare as-built drawing as per construction at site and take approval by consultant. |  | 1 | Job | 10000 | 10000 | 20000 | 1 | 10000 | 1 | 10000 | 20000
5 | Testing, Balancing and Commissioning:
| Testing, Balancing and commissioning of Fire Fighting System, including valves, specialties and the cost of all labor, material, replacements, repair etc. required to be carried out all tests by a separate agency and the result and test data to be submitted to the Engineer In charge for approval prior starting maintenance period, complete in all respect. |  | 1 | Job | 0 | 25000 | 25000 | 1 | 0 | 1 | 25000 | 25000
| Total Amount (Rs.) Section - C (Carried Forward to Summary) | [5 empty] | 267000 |  | 58000 |  | 49000 | 107000