## MEZZ
Pioneer Services
Measurement Sheet For Running Bill.
IMTIAZ SUPER MARKET (THE PLACE).
24 Nov 2021
Mezzanine Floor
BOQ | Grid | FLOOR HVAC PLAN (SUPPLY,RETURN & EXHAUST AIR DUCT ) DWG NO…..
ITEM |  | Description | Width inch | Height inch | Length ft | Area Sq.ft.
| FCU 3 | Reducer | 41.5 | 11.5 | 1.66 | 12.1733
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 5 | 29.1667
|  | Reducer | 25.5 | 9.5 | 1.5 | 8.5 | 28 | fcu | 5 FCU CLAIM DUCT
|  |  | 23.5 | 9.5 |  |  | 9 | fcu
|  | Supply Air Duct | 23.5 | 9.5 | 11 | 60.5 | 2 | faf
|  | Reducer | 23.5 | 9.5 | 1.5 | 7.25 | 1 | eaf
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 12 | 50
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 5 | 20.8333
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 5 | 20.8333
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 3 nos | Drop neck | 16.5 | 16.5 | 0.5 | 8.25
TOTAL | [5 empty] | 220.241
| FCU 4 | Reducer | 41.5 | 11.5 | 2 | 14.6667
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 8 | 46.6667
|  | Reducer | 25.5 | 9.5 | 1.5 | 8.5
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 13 | 71.5
|  | Reducer | 23.5 | 9.5 | 1.5 | 7.75
|  |  | 19.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 13 | 62.8333
|  | Reducer | 19.5 | 9.5 | 1.5 | 6.75
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 8 | 33.3333
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 4 nos | Drop neck | 16.5 | 16.5 | 0.5 | 11
TOTAL | [5 empty] | 263.9115
| FCU 5 | Reducer | 41.5 | 11.5 | 1.66 | 12.1733
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 8 | 46.6667
|  | Reducer | 25.5 | 9.5 | 1.5 | 8.5
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 14 | 77
|  | Reducer | 23.5 | 9.5 | 1.5 | 7.75
|  |  | 19.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 14 | 67.6667
|  | Reducer | 19.5 | 9.5 | 1.5 | 6.75
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 14 | 58.3333
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 4 nos | Drop neck | 16.5 | 16.5 | 0.5 | 11
TOTAL | [5 empty] | 296.7515
| FCU 6 | Reducer | 41.5 | 11.5 | 1.5 | 10.75
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 4 | 22
|  | Reducer | 23.5 | 9.5 | 1.5 | 7.75
|  |  | 19.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 9 | 43.5
|  | Reducer | 19.5 | 9.5 | 1.5 | 6.75
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 12 | 50
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 3 nos | Drop neck | 16.5 | 16.5 | 0.5 | 8.25
TOTAL | [5 empty] | 149.9115
| FCU 7 | Reducer | 41.5 | 11.5 | 1.83 | 13.42
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 2 | 11.6667
|  | Reducer | 25.5 | 9.5 | 1.5 | 8.5
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 9.5 | 52.25
|  | Reducer | 23.5 | 9.5 | 1 | 5.1667
|  |  | 19.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 10 | 48.3333
|  | Reducer | 19.5 | 9.5 | 1 | 4.5
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 10.5 | 43.75
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 4 nos | Drop neck | 16.5 | 16.5 | 0.5 | 11
TOTAL | [5 empty] | 199.4981
| FCU 8 | Reducer | 41.5 | 11.5 | 1.5 | 11
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 2 | 11.6667
|  | Reducer | 25.5 | 9.5 | 1.5 | 8.5
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 10.5 | 57.75
|  | Reducer | 23.5 | 9.5 | 1 | 5.1667
|  |  | 19.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 11 | 53.1667
|  | Reducer | 19.5 | 9.5 | 1 | 4.5
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 10.5 | 43.75
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 2.58 | 10.75
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 2.66 | 11.0833
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 2.83 | 11.7917
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 3 | 12.5
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 4 nos | Drop neck | 16.5 | 16.5 | 0.5 | 11
TOTAL | [5 empty] | 257.1823
| FCU 9 | Reducer | 41.5 | 11.5 | 2.5 | 18.3333
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 8 | 46.6667
|  | Reducer | 25.5 | 9.5 | 1.5 | 8.5
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 10.5 | 57.75
|  | Reducer | 23.5 | 9.5 | 1.5 | 7.75
|  |  | 19.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 10 | 48.3333
|  | End Cap | 19.5 | 9.5 |  | 1.2865
| 3 nos | Drop neck | 16.5 | 16.5 | 0.5 | 8.25
TOTAL | [5 empty] | 196.8698
| FCU 10 | Reducer | 41.5 | 11.5 | 1.5 | 11
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 12 | 70
|  | Reducer | 25.5 | 9.5 | 1 | 5.6667
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 9.5 | 52.25
|  | End Cap | 23.5 | 9.5 |  | 1.5503
|  | Supply Air Duct | 19.5 | 9.5 | 10 | 48.3333
|  | End Cap | 19.5 | 9.5 |  | 1.2865
|  | Supply Air Duct | 17.5 | 7.5 | 7.5 | 31.25
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 5 | 20.8333
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 4 nos | Drop neck | 16.5 | 16.5 | 0.5 | 11
TOTAL | [5 empty] | 254.9931
| FCU 11 | Reducer | 41.5 | 11.5 | 1.5 | 11
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 2.5 | 14.5833
|  | Reducer | 25.5 | 9.5 | 1.5 | 8.5
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 8.5 | 46.75
|  | Reducer | 23.5 | 9.5 | 1.5 | 7.25
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 3 | 12.5
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 3 nos | Drop neck | 16.5 | 16.5 | 0.5 | 8.25
TOTAL | [5 empty] | 109.7448
| FCU 14 | Reducer | 41.5 | 11.5 | 1.5 | 11
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 4 | 23.3333
|  | Reducer | 25.5 | 9.5 | 1.5 | 8.5
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 7 | 38.5
|  | Reducer | 23.5 | 9.5 | 1.5 | 7.75
|  |  | 19.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 9 | 43.5
|  | Reducer | 19.5 | 9.5 | 1.5 | 6.75
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 2.5 | 10.4167
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 4 nos | Drop neck | 16.5 | 16.5 | 0.5 | 11
TOTAL | [5 empty] | 161.6615
| FCU 15 | Reducer | 41.5 | 11.5 | 1.5 | 11
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 33.5 | 9.5 | 4 | 28.6667
|  | Reducer | 33.5 | 9.5 | 1.5 | 9.5
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 8.5 | 46.75
|  | Reducer | 23.5 | 9.5 | 1.5 | 7.75
|  |  | 19.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 11.5 | 55.5833
|  | Reducer | 19.5 | 9.5 | 1.5 | 6.75
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 2.5 | 10.4167
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 4 nos | Drop neck | 16.5 | 16.5 | 0.5 | 11
TOTAL | [5 empty] | 188.3281
| FCU 16 | Reducer | 41.5 | 11.5 | 1.5 | 11
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 3 | 17.5
|  | Reducer | 25.5 | 9.5 | 1.5 | 8.5
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 7.5 | 41.25
|  | Reducer | 23.5 | 9.5 | 1.5 | 7.75
|  |  | 19.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 13 | 62.8333
|  | Reducer | 19.5 | 9.5 | 1.5 | 6.75
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 4 | 16.6667
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 4 nos | Drop neck | 16.5 | 16.5 | 0.5 | 11
TOTAL | [5 empty] | 184.1615
| FCU 17 | Reducer | 41.5 | 11.5 | 1.5 | 11
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 3 | 17.5
|  | Reducer | 25.5 | 9.5 | 1.5 | 8.5
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 7 | 38.5
|  | Reducer | 23.5 | 9.5 | 1.5 | 7.75
|  |  | 19.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 13 | 62.8333
|  | Reducer | 19.5 | 9.5 | 1.5 | 6.75
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 5 | 20.8333
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 4 nos | Drop neck | 16.5 | 16.5 | 0.5 | 11
TOTAL | [5 empty] | 185.5781
| FCU 18 | Reducer | 41.5 | 11.5 | 1.5 | 11
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 2 | 11.6667
|  | Reducer | 25.5 | 9.5 | 1.5 | 8.5
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 9.66 | 53.13
|  | Reducer | 23.5 | 9.5 | 1.5 | 7.75
|  |  | 19.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 10.16 | 49.1067
|  | Reducer | 19.5 | 9.5 | 1.5 | 6.75
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 9.83 | 40.9583
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 4 nos | Drop neck | 16.5 | 16.5 | 0.5 | 11
TOTAL | [5 empty] | 200.7731
| FCU 19 | Reducer | 41.5 | 11.5 | 1.5 | 11
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 2 | 11.6667
|  | Reducer | 25.5 | 9.5 | 1.5 | 8.5
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 9.66 | 53.13
|  | Reducer | 23.5 | 9.5 | 1.5 | 7.75
|  |  | 19.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 10.16 | 49.1067
|  | Reducer | 19.5 | 9.5 | 1.5 | 6.75
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 9.83 | 40.9583
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 4 nos | Drop neck | 16.5 | 16.5 | 0.5 | 11
TOTAL | [5 empty] | 200.7731
| FCU 20 | Reducer | 41.5 | 11.5 | 1.5 | 11
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 2 | 11.6667
|  | Reducer | 25.5 | 9.5 | 1.5 | 8.5
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 9.66 | 53.13
|  | Reducer | 23.5 | 9.5 | 1.5 | 7.75
|  |  | 19.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 10.16 | 49.1067
|  | Reducer | 19.5 | 9.5 | 1.5 | 6.75
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 9.83 | 40.9583
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 4 nos | Drop neck | 16.5 | 16.5 | 0.5 | 11
TOTAL | [5 empty] | 200.7731
| FCU 21 | Reducer | 41.5 | 11.5 | 1.5 | 11
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 2 | 11.6667
|  | Reducer | 25.5 | 9.5 | 1.5 | 8.5
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 9.66 | 53.13
|  | Reducer | 23.5 | 9.5 | 1.5 | 7.75
|  |  | 19.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 10.16 | 49.1067
|  | Reducer | 19.5 | 9.5 | 1.5 | 6.75
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 9.83 | 40.9583
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 4 nos | Drop neck | 16.5 | 16.5 | 0.5 | 11
TOTAL | [5 empty] | 200.7731
| FCU 22 | Supply Air Duct | 25.5 | 9.5 | 2 | 11.6667
|  | Reducer | 25.5 | 9.5 | 1.5 | 8.5
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 9.66 | 53.13
|  | Reducer | 23.5 | 9.5 | 1.5 | 7.75
|  |  | 19.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 10.16 | 49.1067
|  | Reducer | 19.5 | 9.5 | 1.5 | 6.75
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 9.83 | 40.9583
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| revise | Supply Air Duct | 23.5 | 9.5 | 4.83 | 26.565
|  | Supply Air Duct | 40.5 | 11.5 | 3.5 | 30.3333
|  | End Cap | 40.5 | 11.5 |  | 3.2344
| 4 nos | Drop neck | 16.5 | 16.5 | 0.5 | 11
TOTAL | [5 empty] | 249.9058
| FCU 23 | Reducer | 41.5 | 11.5 | 2.16 | 15.84
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 4.16 | 24.2667
|  | Reducer | 25.5 | 9.5 | 1.5 | 8.25
|  |  | 21.5 | 9.5
|  | Supply Air Duct | 21.5 | 9.5 | 6 | 31
|  | Reducer | 21.5 | 9.5 | 1.5 | 7
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 5.5 | 22.9167
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 8.5 | 35.4167
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 8.75 | 36.4583
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 8.75 | 36.4583
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 6 | 25
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 6.25 | 26.0417
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 6.25 | 26.0417
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 7 nos | Drop neck 15" dia | 16.5 | 16.5 | 1.25 | 48.125
TOTAL | [5 empty] | 349.1952
| FCU 24 | Reducer | 41.5 | 11.5 | 2.16 | 15.84
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 4.5 | 26.25
|  | Reducer | 25.5 | 9.5 | 1.5 | 8.25
|  |  | 21.5 | 9.5
|  | Supply Air Duct | 21.5 | 9.5 | 3.5 | 18.0833
|  | Reducer | 21.5 | 9.5 | 1.5 | 7.25
|  |  | 17.5 | 9.5
|  | Supply Air Duct | 17.5 | 9.5 | 5 | 22.5
|  | End Cap | 17.5 | 9.5 |  | 1.1545
| 4 nos | Drop neck 15" dia | 16.5 | 16.5 | 1.25 | 27.5
TOTAL | [5 empty] | 126.8278
| FCU 27 | Plenum Box | 47.5 | 11.5 | 1 | 9.8333
|  | Supply Air Duct | 19.5 | 9.5 | 14.16 | 68.44
|  | Reducer | 19.5 | 9.5 | 1.5 | 6.75
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 10 | 41.6667
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 3 nos | Drop neck | 16.5 | 16.5 | 0.5 | 8.25
TOTAL | [5 empty] | 135.8515
| FCU 29 | Reducer | 41.5 | 11.5 | 1.33 | 9.31
|  |  | 21.5 | 9.5
|  | Supply Air Duct | 21.5 | 9.5 | 3.5 | 18.0833
|  | End Cap | 21.5 | 9.5 |  | 1.4184
|  | Supply Air Duct | 19.5 | 9.5 | 12.5 | 60.4167
|  | Reducer | 19.5 | 9.5 | 1.5 | 6.75
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 7.5 | 31.25
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 9 | 37.5
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 3 nos | Drop neck | 16.5 | 16.5 | 0.5 | 8.25
TOTAL | [5 empty] | 174.8013
| FCU 30 | Reducer | 41.5 | 11.5 | 1.5 | 10.5
|  |  | 21.5 | 9.5
|  | Supply Air Duct | 21.5 | 9.5 | 5 | 25.8333
|  | Reducer | 21.5 | 9.5 | 1 | 5
|  |  | 19.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 5 | 24.1667
|  | Reducer | 19.5 | 9.5 | 1.5 | 6.75
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 4.5 | 18.75
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 2.5 | 10.4167
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 2.5 | 10.4167
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 2.5 | 10.4167
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 3 nos | Drop neck 15" dia | 16.5 | 16.5 | 1.25 | 20.625
TOTAL | [5 empty] | 146.5208
| FCU 31 | Reducer | 41.5 | 11.5 | 1.5 | 10.5
|  |  | 21.5 | 9.5
|  | Supply Air Duct | 21.5 | 9.5 | 6.5 | 33.5833
|  | Reducer | 21.5 | 9.5 | 1.5 | 7.25
|  |  | 17.5 | 9.5
|  | Supply Air Duct | 17.5 | 9.5 | 5 | 22.5
|  | Reducer | 17.5 | 9.5 | 1 | 4.3333
|  |  | 15.5 | 9.5
|  | Supply Air Duct | 15.5 | 9.5 | 4 | 16.6667
|  | End Cap | 15.5 | 9.5 |  | 1.0226
| 3 nos | Plenum Box | 11.5 | 13.5 | 4 | 50
|  | End Cap | 11.5 | 13.5 |  | 6.4688
| 6 nos | Drop neck 15" dia | 16.5 | 16.5 | 0.5 | 16.5
TOTAL | [5 empty] | 168.8247
| FCU 32 | Reducer | 41.5 | 11.5 | 2.33 | 16.31
|  |  | 21.5 | 9.5
|  | Supply Air Duct | 21.5 | 9.5 | 2.5 | 12.9167
|  | Reducer | 21.5 | 9.5 | 2 | 10
|  |  | 19.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 5 | 24.1667
|  | Reducer | 19.5 | 9.5 | 1 | 4.5
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 5 | 20.8333
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 4 nos | Drop neck 15" dia | 16.5 | 16.5 | 1.25 | 27.5
TOTAL | [5 empty] | 117.1381
| FCU 33 | Reducer | 41.5 | 11.5 | 2.16 | 15.12
|  |  | 21.5 | 9.5
|  | Supply Air Duct | 21.5 | 9.5 | 2.5 | 12.9167
|  | Reducer | 21.5 | 9.5 | 1.5 | 7.25
|  |  | 17.5 | 9.5
|  | Supply Air Duct | 17.5 | 9.5 | 4 | 18
|  | Reducer | 17.5 | 9.5 | 1.5 | 6.5
|  |  | 15.5 | 9.5
|  | Supply Air Duct | 15.5 | 9.5 | 4 | 16.6667
| 3 nos | Plenum Box | 11.5 | 13.5 | 4 | 50
|  | End Cap | 11.5 | 13.5 |  | 6.4688
| 6 nos | Drop neck 15" dia | 16.5 | 16.5 | 0.5 | 16.5
TOTAL | [5 empty] | 149.4221
| FCU 34 | Reducer | 41.5 | 11.5 | 1.66 | 11.8967
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 12.5 | 60.4167
|  | Reducer | 19.5 | 9.5 | 1.5 | 6.75
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 11.75 | 48.9583
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 19.5 | 9.5 | 3.5 | 16.9167
|  | End Cap | 19.5 | 9.5 |  | 1.2865
|  | Supply Air Duct | 17.5 | 7.5 | 6.5 | 27.0833
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 3.5 | 14.5833
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 3 nos | Drop neck 15" dia | 16.5 | 16.5 | 1.25 | 20.625
TOTAL | [5 empty] | 211.2508
| FCU 35 | Reducer | 41.5 | 11.5 | 2.66 | 18.62
|  |  | 21.5 | 9.5
|  | Supply Air Duct | 21.5 | 9.5 | 4 | 20.6667
|  | End Cap | 21.5 | 9.5 |  | 1.4184
|  | Supply Air Duct | 19.5 | 9.5 | 4 | 19.3333
|  | Reducer | 19.5 | 9.5 | 1.5 | 6.75
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 7 | 29.1667
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 6.5 | 27.0833
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 3 nos | Drop neck 15" dia | 16.5 | 16.5 | 1.25 | 20.625
TOTAL | [5 empty] | 145.4863
| FCU 13 | Reducer | 41.5 | 11.5 | 1.5 | 11
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 3 | 17.5
|  | Reducer | 25.5 | 9.5 | 1.5 | 8.5
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 8 | 44
|  | Reducer | 23.5 | 9.5 | 1.5 | 7.75
|  |  | 19.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 4.5 | 21.75
|  | Reducer | 19.5 | 9.5 | 1.25 | 5.625
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 4.5 | 18.75
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 18 | 75
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 4 nos | Drop neck | 16.5 | 16.5 | 0.5 | 11
TOTAL | [5 empty] | 222.6979
| FCU 28 | Reducer | 41.5 | 11.5 | 1.66 | 11.62
|  |  | 21.5 | 9.5
|  | Supply Air Duct | 21.5 | 9.5 | 4 | 20.6667
|  | End Cap | 21.5 | 9.5 |  | 1.4184
|  | Supply Air Duct | 19.5 | 9.5 | 10.5 | 50.75
|  | Reducer | 19.5 | 9.5 | 1 | 4.5
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 8.5 | 35.4167
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 3 nos | Drop neck | 16.5 | 16.5 | 0.5 | 8.25
TOTAL | [5 empty] | 133.5332
| FCU 1 | Reducer | 41.5 | 11.5 | 1.66 | 12.1733
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 2 | 11.6667
|  | Reducer | 25.5 | 9.5 | 1 | 5.6667
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 10 | 55
|  | Reducer | 23.5 | 9.5 | 1 | 5.1667
|  |  | 19.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 6 | 29
|  | Reducer | 19.5 | 9.5 | 1 | 4.5
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 3 | 12.5
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 4 nos | Drop neck | 16.5 | 16.5 | 0.5 | 11
TOTAL | [5 empty] | 147.5848
| FCU 12 | Reducer | 41.5 | 11.5 | 1.66 | 12.1733
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 8.5 | 49.5833
|  | Reducer | 25.5 | 9.5 | 3.33 | 18.5925
|  |  | 25.5 | 6.5
|  | Supply Air Duct | 25.5 | 6.5 | 3.66 | 19.52
|  | Reducer | 25.5 | 6.5 | 2.83 | 14.3858
|  |  | 19.5 | 9.5
|  | Supply Air Duct | 19.5 | 9.5 | 3 | 14.5
|  | Reducer | 19.5 | 9.5 | 1 | 4.5
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 18.5 | 77.0833
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 10 | 41.6667
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 31.5 | 7.5 | 2.5 | 16.25
|  | Supply Air Duct | 17.5 | 7.5 | 6.33 | 26.375
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 6.33 | 26.375
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 4 nos | Drop neck | 16.5 | 16.5 | 0.5 | 11
TOTAL | [5 empty] | 335.6508
| FCU 25 | Reducer | 41.5 | 11.5 | 2 | 14.3333
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 5.5 | 30.25
|  | End Cap | 23.5 | 9.5 |  | 1.5503
| 2 nos | Drop neck | 16.5 | 16.5 | 1 | 11
TOTAL | [5 empty] | 57.1337
| FCU 26 | Reducer | 41.5 | 41.5 | 2.75 | 30.7083
|  |  | 41.5 | 9.5
|  | Reducer | 41.5 | 9.5 | 1.5 | 10.5
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 9.5 | 52.25
|  | End Cap | 23.5 | 9.5 |  | 1.5503
| 2 nos | Drop neck | 16.5 | 16.5 | 1 | 11
TOTAL | [5 empty] | 106.0087
| FCU 37 | Reducer | 41.5 | 11.5 | 1.66 | 11.62
|  |  | 21.5 | 9.5
|  | Supply Air Duct | 21.5 | 9.5 | 6.5 | 33.5833
|  | End Cap | 21.5 | 9.5 |  | 1.4184
|  | Supply Air Duct | 19.5 | 9.5 | 6 | 29
|  | End Cap | 21.5 | 9.5 |  | 1.4184
|  | Supply Air Duct | 19.5 | 7.5 | 5 | 22.5
|  | End Cap | 19.5 | 7.5 |  | 1.0156
| 2 nos | Drop neck | 16.5 | 16.5 | 1 | 11
TOTAL | [5 empty] | 111.5558
| FCU 2 | Reducer | 41.5 | 11.5 | 1.5 | 11
|  |  | 25.5 | 9.5
|  | Supply Air Duct | 25.5 | 9.5 | 2.66 | 15.5167
|  | Reducer | 25.5 | 9.5 | 1.5 | 8.5
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 8 | 44
|  | Supply Air Duct | 17.5 | 7.5 | 3 | 12.5
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 1 nos | Drop neck | 16.5 | 16.5 | 0.5 | 2.75
TOTAL | [5 empty] | 95.1781
| FCU 36 | Reducer | 41.5 | 11.5 | 1.5 | 10.75
|  |  | 23.5 | 9.5
|  | Supply Air Duct | 23.5 | 9.5 | 5 | 27.5
|  | Reducer | 23.5 | 9.5 | 1 | 4.8333
|  |  | 17.5 | 7.5
|  | Supply Air Duct | 17.5 | 7.5 | 8.5 | 35.4167
|  | End Cap | 17.5 | 7.5 |  | 0.91146
|  | Supply Air Duct | 17.5 | 7.5 | 7 | 29.1667
|  | End Cap | 17.5 | 7.5 |  | 0.91146
| 3 nos | Drop neck 15" dia | 16.5 | 16.5 | 1.25 | 20.625
TOTAL | [5 empty] | 130.1146
| EAD | Reducer | 13.5 | 13.5 | 1 | 4
|  |  | 13.5 | 7.5
|  | End Cap | 13.5 | 7.5 |  | 0.70312
|  | Exhaust Air Duct | 13.5 | 7.5 | 3 | 10.5
|  | Reducer | 13.5 | 7.5 | 1 | 3.3333
|  |  | 11.5 | 7.5
|  | Exhaust Air Duct | 11.5 | 7.5 | 19 | 60.1667
|  | End Cap | 11.5 | 7.5 |  | 0.59896
|  | Exhaust Air Duct | 11.5 | 7.5 | 15.25 | 48.2917
|  | End Cap | 11.5 | 7.5 |  | 0.59896
| 3 nos | Drop neck | 16.5 | 16.5 | 0.5 | 8.25
TOTAL | [5 empty] | 136.4427
| FAD A | Fresh Air Duct | 19.5 | 19.5 | 4 | 26
|  | End Cap | 19.5 | 19.5 |  | 5.2812
|  | Fresh Air Duct | 11.5 | 11.5 | 0.66 | 5.06
|  | Fresh Air Duct | 33.5 | 13.5 | 12 | 94
|  | Fresh Air Duct | 25.5 | 9.5 | 9.5 | 55.4167
|  | Plenum Box | 61.5 | 28.5 | 0.66 | 9.9
TOTAL | [5 empty] | 195.6579
GRAND TOTAL | [5 empty] | 7118.7078

## GROUND
Pioneer Services
Measurement Sheet For Running Bill.
Dafter Khwan NASTP
04-08-23
Ground Floor Layout
BOQ | Grid | FLOOR HVAC PLAN (SUPPLY,RETURN & EXHAUST AIR DUCT ) DWG NO…..
ITEM |  | Description | Width inch | Height inch | Length ft | Area Sq.ft.
10 | AHU 8 | Supply Air Duct | 32 | 14 | 3.75 | 28.8 |  | 17 | FCU
|  | Reducer | 32 | 14 | 1.5 | 10.8
|  |  | 28 | 12
|  | Supply Air Duct | 28 | 12 | 5.75 | 38.3 |  | 17 | FCU
|  | Reducer | 28 | 12 | 1.5 | 9 |  | 8 | FCU
|  |  | 20 | 12 |  |  |  | 1 | FAF
|  | Supply Air Duct | 20 | 17 | 3.75 | 20 |  | 2 | EAF
1 | Branch | Supply Air Duct | 16 | 6 | 17 | 44 |  | 2 | EAF
|  | End Cap | 16 | 6 |  | 0.7 |  | 2 | EAF
2 | Branch | Supply Air Duct | 16 | 6 | 11.83 | 43.4 |  | 2 | EAF
|  | End Cap | 16 | 6 |  | 0.7 |  | 2 | EAF
3 | Branch | Supply Air Duct | 16 | 6 | 7.5 | 27.5 |  | 2 | EAF
|  | End Cap | 16 | 6 |  | 0.7 |  | 2 | EAF
4 | Branch | Supply Air Duct | 16 | 6 | 7.5 | 27.5 |  | 2 | EAF
|  | End Cap | 16 | 6 |  | 0.7 |  | 2 | EAF
TOTAL | [5 empty] | 252.1
11 | AHU 12 | Supply Air Duct | 38 | 16 | 3.75 | 33.8 |  | 17 | FCU
|  | Reducer | 38 | 16 | 1.5 | 13.3
|  |  | 38 | 14
|  | Supply Air Duct | 38 | 14 | 6 | 52 |  | 17 | FCU
1 | Branch | Supply Air Duct | 16 | 6 | 11.25 | 41.3 |  | 2 | EAF
|  | End Cap | 16 | 6 |  | 0.7 |  | 2 | EAF
2 | Branch | Supply Air Duct | 16 | 6 | 10.5 | 38.5 |  | 2 | EAF
|  | End Cap | 16 | 6 |  | 0.7 |  | 2 | EAF
TOTAL | [5 empty] | 180.3
| 24 nos | Drop neck | 15 | 15 | 2 | 240
TOTAL | [5 empty] | 240
| FCU - 12 # 02 | Reducer | 34 | 12 | 3'-6" | 21
|  |  | 18 | 4
|  | Supply Air Duct | 18 | 8 | 12' | 52
|  | Reducer | 18 | 8 | 18" | 6
|  |  | 16 | 6
|  | Supply Air Duct | 16 | 6 | 6' -6" | 22.66
TOTAL | [5 empty] | 101.66
1 | FAHU 10 | Duct Connections |  |  |  | 150 | 672.4 | 17 | FCU
2 | FAHU 11 | Duct Connections |  |  |  | 150 |  | 17 | FCU
TOTAL | [5 empty] | 300
GRAND TOTAL | [5 empty] | 2514.86
TOTAL DUCTS QUANTITIES SUMMARY (SQ.FT.)
Ground Floor Fcu Units Supply Air Ducts | [5 empty] | 2514.86
Mezzanine Floor Fcu Units Supply Air Ducts | [5 empty] | 7118.7078
GRAND TOTAL OF DUCT WORKS. | [5 empty] | 9633.5678
TOTAL DUCTS QUANTITIES SUMMARY (SQ.FT.)
Ground Floor Fcu Units Supply Air Ducts
Fresh Air Ducts
Exhaust Air Ducts
GRAND TOTAL OF DUCT WORKS.