## 31 Oct
Form No.04
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: | PAF |  |  | Contractor: | Pioneer Services |  |  | Project Manager:
Project: | NICVD |  |  | Works/Contract: |  |  |  | Date | 2024-10-31
Submission Date: |  | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Man power | Completed |  |  |  | Remarks
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion
| Ducting & hanging supports installation work in progress | Ground Foor ZONE-A |  | 4
| Ducting & hanging supports installation work in progress | Ground Foor ZONE-B
| Condensate drain installation work in progress | Ground Foor ZONE-B
| Drain work in progress | First Foor ZONE-B

## 2 Nov
Form No.04
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: | PAF |  |  | Contractor: | Pioneer Services |  |  | Project Manager:
Project: | NICVD |  |  | Works/Contract: |  |  |  | Date | 2024-11-02
Submission Date: |  | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Man power | Completed |  |  |  | Remarks
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion
| Ducting & hanging supports installation work in progress | Ground Foor ZONE-A |  | 5
| Ducting & hanging supports installation work in progress | Ground Foor ZONE-B
| Drain work in progress | First Foor ZONE-B |  | 2

## 4 Nov
Form No.04
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: | PAF |  |  | Contractor: | Pioneer Services |  |  | Project Manager:
Project: | NICVD |  |  | Works/Contract: |  |  |  | Date | 2024-11-04
Submission Date: |  | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Man power | Completed |  |  |  | Remarks
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion
| Ducting & hanging supports installation work in progress | Ground Foor ZONE-A |  | 5
| Ducting & hanging supports installation work in progress | Ground Foor ZONE-B
| Core cutting work in progress | First Foor ZONE-C |  | 2
| Condensate drain work in progress | First Foor ZONE-B |  | 3