## Sheet1
Precurement Schedule EY Office 21st & 2nd Floor DMC Karachi
Description | Approved Brand | Approval Stauts | Delivery
HVAC
Supply of hangers & supports | INDEX | Approved | 1 weeks
Ducting | ISL | Approved | 2 Weeks
Ducting Insulation | AEROFOAM | Approved | 5 Weeks
VAVs | IMS | Awaiting for the approval | 8-10 Weeks after approval
Fan coil Units | OAK | Awaiting for the approval | 8-10 Weeks after approval
Water cooled package unit | SABRO | Awaiting for the approval | 8-10 Weeks after approval
MS Pipe | PROTEK | Approved | Delivered at Site
Valves & specialities | SCON | Approved | 6 Weeks
Piping Insulation | AEROFOAM | Approved | 6 Weeks
Condensate Drain Piping with insulation | DADEX | Awaiting for the approval | 8 Weeks after approval
Air devices | MEHRAN | Awaiting for the approval | 12 Weeks after approval
Painting / Identification | BERGER | Approved | Delivered at Site
Plumbing Work
Plumbing fixtures | PORTA / GROHE | Approved | 8-10 Weeks
Hangers supports and related fittings | INDEX | Approved | 2 Weeks
FIRE Fighting
MS Fire Pipe | PROTEK | Approved | Delivered at Site
Seismic Bracing | INDEX | Approved | 2 Weeks
Fire Sprinklers | Reliable | Awaiting for the approval | 10-12 Weeks after approval
Fire Extinghuishers | SRI | Awaiting for the approval | 10-12 Weeks after approval
Fire Valves | Reliable | Awaiting for the approval | 10-12 Weeks after approval
Painting / Identification | BERGER | Approved | Delivered at Site