## sum
GSK Office |  | 2023-05-23
HVAC, Fire & Plumbing Work
SUMMARY OF WORK DONE
GSK OFFICE
S.No | Activity. | AMOUNT
A | 1st Running Bill | 10641214
B | Final Bill | 1867669.5
| TOTAL Work Done RS. | 12508883.5
LESS REBATE ____% RS.
TOTAL ESTIMATED COST OF PROJECT RS. |  | 12508883.5
| COVERED AREA | 10000
RATE PER SFT.
| Add Variations amount | 1879882
| Grand Total Amount | 14388765.5
| Add 4.5% Tax amount as discussed | 647494.4475
| Grand Total Amount | 15036259.9475
| Total Received | 15076754
| Receivable amount | -40494.0525

## GRAND SUMMARY
GSK Office |  | 2023-01-19
HVAC, Fire & Plumbing Work
SUMMARY OF FINAL BILL
S.No | Activity. | AMOUNT
A | HVAC | 1650172
B | Fire Fighting System | 171085.5
C | Date Cener AC Work | 46412
| TOTAL RS. | 1867669.5
LESS REBATE ____% RS.
TOTAL ESTIMATED COST OF PROJECT RS. |  | 1867669.5
| COVERED AREA | 10000
RATE PER SFT.

## HVAC BOQ
Bill of Quantities
ACMV Works
GSK Office
Dolmen Mall, Karachi.
S # |  | Description | Bill of Quantities |  |  |  | Previous Bill |  |  | Final Bill
[10 empty] | Material |  | Labour |  | Total Amount
|  |  | Unit | Qty | Material Rate | Labour Rate | Billed Qty | Material Amount | Labour Amount | Bill Qty | Amount | Bill Qty | Amount
All air conditioning & mechanical ventilation works shall be completed, tested and commissioned as per drawings, specifications and as per instruction of Consultant
1 |  | Supply, installation, testing and commissioning of of chilled water ducted fan coil & cooling water, water cooled package unit complete in all respects, ready to operate including supply and installation of all accessories, hanger steel base, vibration isolators, including interconnecting power & control wiring (terminal connection) with inlet & outlet cooling water connections, drain connection, flexible rubber duct connection / connector etc. complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
| 1.1 | DFCU-01 | No. | 1 | 0 | 12000 |  | 0 | 0 |  | 0 |  | 0 | 0
| 1.2 | WCPU-01 | No. | 1 | 0 | 25000 | 1 | 0 | 25000 |  | 0 |  | 0 | 0
1 |  | Supply, installation, testing and commissioning of of ducted fan coil unit of different capacities complete in all respects, ready to operate including supply and installation of all accessories, lindaptor supports, hanger steel base, vibration isolators, including interconnecting power & control wiring (terminal connection) with inlet & outlet chilled water connections, drain connection, flexible rubber duct connection / connector etc. complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
| 1.1 | DFCU-01 | No. | 1 |  | 12000 |  | 0 | 0 |  | 0 |  | 0 | 0
2 |  | Unloading, installation, testing and commissioning of VAV & CAV Boxes as per mentioned in schedule with digital thermostat controller, pressure sensor, control wiring, including supply & installation of flexible duct connection / connector, electrical connection, lindaptor support & hangers complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant.
| A | VAVs
| i. | VAV-01 | No. | 1 | 0 | 3500 |  | 0 | 0 |  | 0 | 1 | 3500 | 3500
| ii. | VAV-02 | No. | 1 | 0 | 3500 |  | 0 | 0 |  | 0 | 1 | 3500 | 3500
| iii. | VAV-03 | No. | 1 | 0 | 3500 |  | 0 | 0 |  | 0 | 1 | 3500 | 3500
| iv. | VAV-04 | No. | 1 | 0 | 3500 |  | 0 | 0 |  | 0 | 1 | 3500 | 3500
| v. | VAV-05 | No. | 1 | 0 | 3500 |  | 0 | 0 |  | 0 | 1 | 3500 | 3500
| vi. | VAV-06 | No. | 1 | 0 | 3500 |  | 0 | 0 |  | 0 | 1 | 3500 | 3500
| vii. | VAV-07 | No. | 1 | 0 | 3500 |  | 0 | 0 |  | 0 | 1 | 3500 | 3500
| viii. | VAV-08 | No. | 1 | 0 | 3500 |  | 0 | 0 |  | 0 | 1 | 3500 | 3500
| ix. | VAV-09 | No. | 1 | 0 | 3500 |  | 0 | 0 |  | 0 | 1 | 3500 | 3500
| x. | VAV-10 | No. | 1 | 0 | 3500 |  | 0 | 0 |  | 0 | 1 | 3500 | 3500
| xi. | VAV-11 | No. | 1 | 0 | 3500 |  | 0 | 0 |  | 0 | 1 | 3500 | 3500
| xii. | VAV-12 | No. | 1 | 0 | 3500 |  | 0 | 0 |  | 0 | 1 | 3500 | 3500
| xiii. | VAV-13 | No. | 1 | 0 | 3500 |  | 0 | 0 |  | 0 | 1 | 3500 | 3500
| xiv. | VAV-14 | No. | 1 | 0 | 3500 |  | 0 | 0 |  | 0 | 1 | 3500 | 3500
| xv. | VAV-15 | No. | 1 | 0 | 3500 |  | 0 | 0 |  | 0 | 1 | 3500 | 3500
| xvi. | VAV-16 | No. | 1 | 0 | 3500 |  | 0 | 0 |  | 0 | 1 | 3500 | 3500
| xvii. | VAV-17 | No. | 1 | 0 | 3500 |  | 0 | 0 |  | 0 | 1 | 3500 | 3500
| xviii. | VAV-18 | No. | 1 | 0 | 7000 |  | 0 | 0 |  | 0 | 1 | 7000 | 7000
| xix. | VAV-19 | No. | 1 | 0 | 7000 |  | 0 | 0 |  | 0 | 1 | 7000 | 7000
| xx. | VAV-20 | No. | 1 | 0 | 7000 |  | 0 | 0 |  | 0 | 1 | 7000 | 7000
| xxi. | VAV-21 | No. | 1 | 0 | 7000 |  | 0 | 0 |  | 0 | 1 | 7000 | 7000
| B | CAVs
| i. | CAV-01 | No. | 1 | 0 | 7000 |  | 0 | 0 |  | 0 | 1 | 7000 | 7000
| ii. | CAV-02 | No. | 1 | 0 | 7000 |  | 0 | 0 |  | 0 | 1 | 7000 | 7000
| iii. | CAV-03 | No. | 1 | 0 | 7000 |  | 0 | 0 |  | 0 | 1 | 7000 | 7000
3 |  | Supply & installation of valves & accessories for DFCU with lindaptor supports, hangers, flanges, gas kits, nut & bolts where it required, etc. complete in all respects as per specifications, drawings and as per instructions of consultant. | [5 empty] | 0 | 0
| 3.1 | Ball Valve
| i. | 25mm dia | Nos. | 4 | 4700 | 1000 | 4 | 18800 | 4000 | 0 | 0 |  | 0 | 0
| 3.2 | Strainers
| i. | 25mm dia | No. | 1 | 3500 | 1000 | 1 | 3500 | 1000 | 0 | 0 |  | 0 | 0
| 3.3 | Balancing Valve (with self sealing measuring nipples)
| i. | 25mm dia | No. | 1 | 7700 | 1000 | 1 | 7700 | 1000 | 0 | 0 |  | 0 | 0
| 3.4 | Thermometer 150mm Height Scale Type (with Thermo well) 0 ºC to 60 ºC | Nos. | 2 | 6500 | 1000 |  | 0 | 0 |  | 0 |  | 0 | 0
| 3.5 | Pressure Gauge with Ball Valve & Siphon, Liquid filled Dial type range 0 psi to 100 psi. (100mm dial Size) | Nos. | 2 | 8500 | 1000 |  | 0 | 0 |  | 0 |  | 0 | 0
| 3.6 | 2-Way Motorized Valve with Actuator (0-100% modulating)
| i. | 25mm dia | No. | 1 | 38000 | 3000 | 1 | 38000 | 3000 |  | 0 |  | 0 | 0
| 3.7 | Digital Decorative Thermostat Controller (BMS Interfacable) with Duct Mounted Sensor | No. | 1 | 18500 | 2000 | 1 | 18500 | 2000 |  | 0 |  | 0 | 0
| 3.8 | Control wiring from controller to sensors, motorized valve and power wiring, up to 15' radius | Job. | 1 | 5000 | 1500 | 1 | 5000 | 1500 |  | 0 |  | 0 | 0
4 |  | Supply & installation of SCH-40 M.S.(As per ASME & API standard, Heavy Quality with standard SCH 40 wall thickness) pipes & fitting for chilled & cooling water circulation system complete with bends, tees, unions, sockets, specials, lindaptor support, hangers & anchors, M.S. angle, U channel, roller support, bolts, rods, clamps, concrete fasteners etc as required to complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
| 4.1 | 25mm dia | Rm | 80 | 1250 | 595 | 37 | 46250 | 22015 | 20 | 25000 | 20 | 11900 | 36900
5 |  | Supply & installation of Pre Formed Polystyrene (Thermopore) insulation (32 kg/m3 density) for chilled water pipes, bends, tees, unions, sockets, valves and on specials protected with Kraft paper, wrapped with 8oz Canvas cloth than paint with anti fungus paint complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
| 5.1 | 25mm dia (chilled water pipes only) | Rm | 50 | 1000 | 280 |  | 0 | 0 |  | 0 | 0 | 0 | 0
6 |  | Supply, installation of Ventilation Fans including electrical connection, flexible duct connection / connector, lindaptor support & hangers complete in all respects ready to operate as per drawings, specification and as per instruction of consultant.
| 6.1 | RAF-01 | No. | 1 | 191000 | 5000 | 1 | 191000 | 5000 | 0 | 0 | 0 | 0 | 0
| 6.2 | TAF-01 Wall Mounted Fan (50 cfm) | No. | 1 | 35000 | 3000 | 1 | 35000 | 3000 | 0 | 0 | 0 | 0 | 0
7 |  | Supply, fabrication and installation of machine made G.I sheet metal duct different sections supply, return, fresh & exhaust air including plenums, splitter dampers, guide vanes, flexible duct connector / connection, access door, transformation, plenums chambers, wooden frame, anchors supports & hangers complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | Sqm | 820 | 3500 | 920 | 864 | 3024000 | 794880 | 81.59 | 285565 | 81.59 | 75062.8 | 360627.8
8 |  | Supply & installation of adhesive 20mm thick rubber foam (XLPE) insulation with aluminum foil over supply & return duct and plenums, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqm | 820 | 3480 | 600 | 864 | 3006720 | 518400 | 81.59 | 283933.2 | 81.59 | 48954 | 332887.2
9 |  | Supply & installation of acoustical duct sound liner (adhesive 12mm thick) in supply air & return air duct etc, complete in all respects ready to operate as per drawings, specification and as per instruction of consultant. | Sqm | 85 | 3000 | 600 | 42 | 126000 | 25200 |  | 0 |  | 0 | 0
10 |  | Supply & installation of aluminum fabricated, powder coated grills, diffusers and registers etc for supply, return, exhaust & fresh air of different sizes (Grade A) wooden frame, lindaptor supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
| 10.1 | Supply & Return Air Diffuser with Damper | Sqm | 5 | 48000 | 7500 |  | 0 | 0 | 5 | 240000 | 5 | 37500 | 277500
| 10.2 | S.S Wire Mesh with G.I Frame | Sqm | 2.5 | 25000 | 7800 | 1.5 | 37500 | 11700 |  | 0 |  | 0 | 0
| 10.3 | Linear Slots 6000 Series with bird mesh
| i. | 1 Slot of 20mm | Rm | 22 | 4197 | 700 |  | 0 | 0 | 21 | 88137 | 21 | 14700 | 102837
| ii. | 2 Slots of 3/4" | Rm | 50 | 5100 | 700 |  | 0 | 0 | 50.4 | 257040 | 50.4 | 35280 | 292320
| 10.4 | Disc Valves
| i. | 150mm dia | Nos. | 12 | 2800 | 1000 |  | 0 | 0 | 12 | 33600 | 12 | 12000 | 45600
11 |  | Supply & installation of flexible duct including hangers, jubilee clamp complete in all respects as per specification, drawings & as per instruction of consultant.
| 11.1 | 150mm dia | Rm | 120 | 690 | 150 | 90 | 62100 | 13500 | 20 | 13800 | 20 | 3000 | 16800
| 11.2 | 200mm dia | Rm | 3 | 1066 | 160 |  | 0 | 0 |  | 0 |  | 0 | 0
12 |  | Supply & installation of butterfly damper for above flexible duct with gas kits, nut bolts, complete in all respects, ready to operate as per specification, drawings & as per instruction of consultant.
| 12.1 | 150mm dia | Nos. | 90 | 2800 | 800 | 92 | 257600 | 73600 | 2 | 5600 | 2 | 1600 | 7200
| 12.2 | 200mm dia | No. | 1 | 3500 | 1000 |  | 0 | 0 |  | 0 |  | 0 | 0
13 |  | Supply, Installation of Volume Control Damper in 16 SWG G.I sheet metal with gas kits, nut bolts, etc, complete in all respects ready to operate as per specification, drawings and as per instruction, approval of consultant. | Sqm | 3 | 3500 | 700 | 1.15 | 4025 | 805 | 0 | 0 |  | 0 | 0
14 |  | Supply & istallation of uPVC (Sch 40.) drain pipe insulated with 3/8" thick rubber foam insulation including clamps, bends, tees, drain plugs, sockets, protection treatment, PVC tape wrapping, lindaptor supports & hangers complete in all respects as per specifications, drawings & as per instructions of Consultant.
| 14.1 | 25mm dia | Rm | 45 | 2800 | 400 | 11 | 30800 | 4400 | 0 | 0 | 0 | 0 | 0
15 |  | Painting & Identification work on pipes & exhaust duct, supports, hangers etc. complete in all respects with one coat of ICI make Red lead oxide primer & two coats of ICI make enamel paint as per instruction of Consultant. | Job. | 1 | 25000 | 12000 | 1 | 25000 | 12000 |  | 0 |  | 0 | 0
16 |  | Testing, balancing and commissioning of water & air side of the system (from independent agency) complete in all respects including flow measurement & balancing, temp, pressure, electrical data of related equipment etc. as per specifications and as per instructions of Consultant. | Job. | 1 | 50000 | 15000 | 1 | 50000 | 15000 | 1 | 50000 |  | 0 | 50000
17 |  | Making of Shop drawings on Auto CAD 2016 with section details, equipment foundation details and Making of As Built drawings, Documentation Technical / Operational Manual & LOG Book for each equipment as per instruction of Consultant. | Job. | 1 | 20000 | 18000 | 0.5 | 10000 | 9000 | 0.5 | 10000 | 0.5 | 9000 | 19000
|  | Certified/Qualified full time Health and Safety Supervisor other than the Resident Engineer/Site Supervisor, having prior expertise in HVAC H&S area. | Job. | 1 | [6 empty] | 0 |  | 0 | 0
|  | Total Cost of ACMV Works Rs. | [5 empty] | 6997495 | 1546000 |  |  |  |  | 1650172

## Data Center AC work
Bill of Quantities
Data Centre AC Works
GSK Office
Dolmen Mall, Karachi.
S # |  | Description | Bill of Quantities |  |  |  | Previous Bill |  |  | Final Bill
[10 empty] | Material |  | Labour |  | Total Amount
|  |  | Unit | Qty | Material Rate | Labour Rate | Billed Qty | Material Amount | Labour Amount | Bill Qty | Amount | Bill Qty | Amount
All air conditioning & mechanical ventilation works shall be completed, tested and commissioned as per drawings, specifications and as per instruction of Consultant
1 |  | Supply, installation, testing and commissioning of of chilled water ducted fan coil & cooling water, water cooled package unit complete in all respects, ready to operate including supply and installation of all accessories, hanger steel base, vibration isolators, including interconnecting power & control wiring (terminal connection) with inlet & outlet cooling water connections, drain connection, flexible rubber duct connection / connector etc. complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
| 1.1 | DFCU-01 | No. | 1 | 0 | 12000 | 1 | 0 | 12000 |  | 0 |  | 0 | 0
| 1.2 | WCPU-01 | No. | 1 | 0 | 12000 |  | 0 | 0 |  | 0 |  | 0 | 0
2 |  | Supply, installation, testing and commissioning of VAV Boxe with digital thermostat controller, pressure sensor, control wiring, including supply & installation of flexible duct connection, electrical connection, support & hangers complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
| 2.1 | VAV-01 | No. | 1 |  |  |  | 0 | 0
3 |  | Supply & installation of valves & accessories for DFCU & WCPU with supports, hangers, flanges, gas kits, nut & bolts where it required, etc. complete in all respects as per specifications, drawings and as per instructions of consultant.
| A | For DFCU, Chilled Water Connection
| 3.1 | Ball Valve
| i. | 25mm dia | Nos. | 4 | 4700 | 1000 | 2 | 9400 | 2000 | 0 | 0 |  | 0 | 0
| 3.2 | Strainers
| i. | 25mm dia | No. | 1 | 3500 | 1000 | 1 | 3500 | 1000 | 0 | 0 |  | 0 | 0
| 3.3 | Balancing Valve (with self sealing measuring nipples)
| i. | 25mm dia | No. | 1 | 8700 | 1000 | 1 | 8700 | 1000 | 0 | 0 |  | 0 | 0
| 3.4 | Thermometer 6" Height Scale Type (with Thermo well) 0 ºC to 60 ºC | Nos. | 2 | 6500 | 1000 | 2 | 13000 | 2000 | 0 | 0 |  | 0 | 0
| 3.5 | Pressure Gauge with Ball Valve & Siphon, Liquid filled Dial type range 0 psi to 100 psi. (4" dial Size) | Nos. | 2 | 7700 | 1000 | 2 | 15400 | 2000 | 0 | 0 |  | 0 | 0
| 3.6 | 2-Way Motorized Valve with Actuator (0-100% modulating)
| i. | 25mm dia | No. | 1 | 38000 | 3000 |  | 0 | 0 | 0 | 0 |  | 0 | 0
| 3.7 | Digital Decorative Thermostat Controller (BMS Interfacable) with Duct Mounted Sensor | No. | 1 | 18500 | 2000 |  | 0 | 0 | 0 | 0 |  | 0 | 0
| 3.8 | Control wiring from controller to sensors, motorized valve and Power wiring, up to 15' radius | Job. | 1 | 5000 | 1500 |  | 0 | 0 | 0 | 0 |  | 0 | 0
| B | For WCPU Cooling Water Connection
| 3.9 | Ball Valve
| i. | 25mm dia | Nos. | 4 | 4700 | 1000 |  | 0 | 0 | 0 | 0 |  | 0 | 0
| 3.1 | Strainers
| i. | 25mm dia | No. | 1 | 3500 | 1000 |  | 0 | 0 | 0 | 0 |  | 0 | 0
| 3.11 | Balancing Valve (with self sealing measuring nipples)
| i. | 25mm dia | No. | 1 | 8700 | 1000 |  | 0 | 0 | 0 | 0 |  | 0 | 0
| 3.12 | Flexible Connector
| i. | 25mm dia | Nos. | 2 | 7500 | 1000 |  | 0 | 0 | 0 | 0 |  | 0 | 0
| 3.13 | 2-Way Motorized Valve with Actuator (0-100% modulating)
| i. | 25mm dia | No. | 1 | 38000 | 1000 |  | 0 | 0 | 0 | 0 |  | 0 | 0
| 3.14 | Flow Switch | No. | 1 | 12000 | 3000 | 1 | 12000 | 3000 | 0 | 0 |  | 0 | 0
| 3.15 | Digital Decorative Thermostat Controller (BMS Interfacable) with Duct Mounted Sensor | Lot | 1 | 18500 | 2000 |  | 0 | 0 | 0 | 0 |  | 0 | 0
| 3.16 | Control wiring from controller to sensors, motorized valve and Power wiring, up to 15' radius | Job. | 1 | 5000 | 1500 |  | 0 | 0 | 0 | 0 |  | 0 | 0
4 |  | Supply & installation of SCH-40 M.S.(As per ASME & API standard, Heavy Quality with standard SCH 40 wall thickness) pipes & fitting for chilled & cooling water circulation system complete with bends, tees, unions, sockets, specials, lindaptor support, hangers & anchors, M.S. angle, U channel, roller support, bolts, rods, clamps, concrete fasteners etc as required to complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
| 4.1 | 25mm dia | Lot | 1 | 60000 | 15000 | 1 | 60000 | 15000 | 0 | 0 |  | 0 | 0
5 |  | Supply & installation of Pre Formed Polystyrene (Thermopore) insulation (32 kg/m3 density) for chilled water pipes, bends, tees, unions, sockets, valves and on specials protected with Kraft paper, wrapped with 8oz Canvas cloth than paint with anti fungus paint complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Chilled Water Pipes
| 5.1 | 25mm dia | Lot | 1 | 77000 | 17000 | 1 | 77000 | 17000 | 0 | 0 |  | 0 | 0
6 |  | Supply, fabrication and installation of machine made G.I sheet metal duct for supply & return air duct, complete in all respects including splitter dampers, guide vanes, flexible duct connection, access door, transformation, plenums chambers, lindaptor, supports, hangers, anchors, wooden frame complete in all respects ready to operate as per drawings, specification, instruction of consultant. | Sqm | 35 | 3500 | 920 | 32 | 112000 | 29440 | 0 | 0 |  | 0 | 0
7 |  | Supply & installation of adhesive 19mm thick insulation with aluminum foil over supply & return duct, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqm | 35 | 3000 | 650 | 32 | 96000 | 20800 | 0 | 0 |  | 0 | 0
8 |  | Supply & installation of acoustical duct sound liner (adhesive 12mm thick) in supply air duct complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Sqm | 12 | 2500 | 600 | 4 | 10000 | 2400 | 0 | 0 |  | 0 | 0
9 |  | Supply & installation of aluminum fabricated, powder coated grills, diffusers and registers etc for supply, return, exhaust & fresh air of different sizes (Grade A) wooden frame, lindaptor supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
| 9.1 | Linear Bar Grill 4,000 Series
| i. | 150mm width | Rm | 5 | 3000 | 280 |  | 0 | 0 | 7.9 | 23700 | 7.9 | 2212 | 25912
| 9.2 | Return Air Grill
| i. | 400mm x 300mm | Nos. | 2 | 5500 | 1000 |  | 0 | 0 | 2 | 11000 | 2 | 2000 | 13000
10 |  | Supply and installation of Back Draft Damper framing in 16 SWG G.I sheet & auto gravity shutter in 26 SWG sheet, with gas kits, nut botls. complete in all respects ready to operate as per specification, drawings & as per instruction of Consultant.
| 10.1 | 500mm x 200mm | Nos. | 4 | 4800 | 1000 | 2 | 9600 | 2000 | 0 | 0 |  | 0 | 0
11 |  | Supply and installation of fire damper with linkage & fuse etc, complete in all respects as per specifications, drawings & as per instructions of Consultant.
| 11.1 | 400mm x 300mm | Nos. | 2 | 7000 | 1500 | 3 | 21000 | 4500 | 0 | 0 |  | 0 | 0
12 |  | Supply, Installation, testing and commissioning of uPVC (Sch 40.) drain pipe insulated with 3/8" thick rubber foam insulation including clamps, bends, tees, drain plugs, sockets, protection treatment, PVC tape wrapping complete in all respects as per specifications, drawings & as per instructions of Consultant.
| 12.1 | 25mm dia | Lot | 1 | 38000 | 12000 | 1 | 38000 | 12000 | 0 | 0 |  | 0 | 0
13 |  | Testing, balancing and commissioning of water & air side of the system (from independent agency) complete in all respects including flow measurement & balancing, temp, pressure, electrical data of related equipment etc. as per specifications and as per instructions of Consultant. | Job. | 1 | 25000 | 5000 | 1 | 25000 | 5000 | 0 | 0 |  | 0 | 0
14 |  | Making of Shop drawings on Auto CAD 2016 with section details, equipment foundation details and Making of As Built drawings, Documentation Technical / Operational Manual & LOG Book for each equipment as per instruction of Consultant. | Job. | 1 | 10000 | 5000 | 0.5 | 5000 | 2500 | 0.5 | 5000 | 0.5 | 2500 | 7500
|  | Total Cost of Works Rs. | [5 empty] | 515600 | 133640 |  |  |  |  | 46412

## FSS - BOQ
Bill of Quantities
Fire Suppression Services
GSK Office
11th. Floor Dolmen Mall, Karachi.
S # |  | Description | Bill of Quantities |  |  |  | Previous Bill |  |  | Final Bill
[10 empty] | Material |  | Labour |  | Total Amount
|  |  | Unit | Qty | Material Rate | Labour Rate | Billed Qty | Material Amount | Labour Amount | Bill Qty | Amount | Bill Qty | Amount
FIRE FIGHTING SERVICES
Supply, installation, testing & commissioning of fire suppression system including all equipment, pipe works and accessories ready to operate as per specifications, drawings and instructions of consultants.
1 |  | MS Sch-40 seamless pipes including all specials fittings UL listed & FM approved, threaded, welded joints, flexible pipe, flanges, coupling, masking plates, bends, tees, clamps, supports and hangers, sleeves, masking plates chiseling, cutting holes, making good where required, painting and protection treatment etc. Complete in all respects. | [5 empty] | 0 | 0
| i. | Dia 25 mm (Threaded fitting) | Rm. | 150 | 1635 | 650 | 171.65 | 280647.75 | 111572.5 | 20.3 | 33190.5 | 20.3 | 13195 | 46385.5
| ii. | Dia 32 mm (Threaded fitting) | Rm. | 50 | 2210 | 680 | 37.2 | 82212 | 25296 |  | 0 | 0 | 0 | 0
| iii. | Dia 40 mm (Threaded fitting) | Rm. | 50 | 2600 | 710 | 40.6 | 105560 | 28826 |  | 0 | 0 | 0 | 0
| iv. | Dia 50 mm (Threaded fitting) | Rm. | 40 | 3400 | 740 | 8.3 | 28220 | 6142 |  | 0 | 0 | 0 | 0
| v. | Dia 65 mm (Welded joints fitting) | Rm. | 40 | 5500 | 810 | 27.8 | 152900 | 22518 |  | 0 | 0 | 0 | 0
| vi. | Dia 75 mm (Welded joints fitting) | Rm. | 15 | 6990 | 880 | 25.5 | 178245 | 22440 |  | 0 | 0 | 0 | 0
2 |  | Fire extinguishers with fixing accessories. | [5 empty] | 0 | 0 |  |  | 0
| i. | Type Class B&C FX-3 (5 Kg. CO2 Carbon Dioxide Gas) | Nos. | 3 | 21500 | 700 |  | 0 | 0 | 3 | 64500 | 3 | 2100 | 66600
| ii. | Type Class A,B&C FX-4 (6 Kg. Dry Chemical Powder) | Nos. | 3 | 12500 | 700 |  | 0 | 0 | 3 | 37500 | 3 | 2100 | 39600
3 |  | Sprinkler Heads | [5 empty] | 0 | 0 |  |  | 0
| i. | Sprinkler Upright K = 5.6 (Opening Temperature 68ºc) | Nos. | 49 | 2200 | 700 | 51 | 112200 | 35700 |  | 0 | 0 | 0 | 0
| ii. | Sprinkler Pendent type with cover plate, K = 5.6 (Opening Temperature 57ºC) | Nos. | 25 | 2800 | 700 | 36 | 100800 | 25200 | 3 | 8400 | 3 | 2100 | 10500
4 |  | Making of As-Built & Shop Drawings on AutoCAD 2018 or latest version with sectional details complete in all respects as per instructions of consultant. | Job. | 1 | 15000 | 1000 | 0.5 | 7500 | 500 | 0.5 | 7500 | 0.5 | 500 | 8000
5 |  | Painting, identification and tagging to the installations and equipments. | Job. | 1 | 45000 | 15000 | 1 | 45000 | 15000 |  | 0 | 0 | 0 | 0
6 |  | Flushing of entire fire pipe work according to (NFPA-13). | Job. | 1 | 25000 | 5000 | 1 | 25000 | 5000 |  | 0 | 0 | 0 | 0
7 |  | Testing, and commissioning of entire fire fighting installation as per Consultant's approval. | Job. | 1 | 25000 | 7000 | 1 | 25000 | 7000 |  | 0 | 0 | 0 | 0
|  | Certified/Qualified full time Health and Safety Supervisor other than the Resident Engineer/Site Supervisor, having prior expertise in Firefighting H&S area. | Job. | 1 |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total Cost of Fire Suppression Services Rs. | [5 empty] | 1143284.75 | 305194.5 |  |  |  |  | 171085.5