## HVAC
[7 empty] | Date | 11 Jan 2025
Attn: Mr. Taha Ghaznavi
Variation for Extra work carried out for VRF Outdoor units - Gul Ahmed 7th Floor Tijarah Center Karachi
S. # | Description | Material Rate | Labour Rate | Over Head profit 10% | Total Rates | Unit | Qty | Amount
1 | Making existing as built drawings of VRF system. | 0 | 15000 | 0 | 15000 | Job | 1 | 15000
2 | Removal of installed indoor units wall mounted / cassette type | 0 | 7000 | 0 | 7000 | Nos | 20 | 140000
a) Dismantle of evaporator coil from indoor unit.
b) Wash with Karchar pump
c) Pressurized with nitrogen and test leak.
d) Satisfaction of leak test reassembled evaporator coil.
e) Clean all body and related parts.
f) Reassemble with evaporator coil and assembled whole unit.
g) Reassemble with evaporator coil and assembled whole unit.
3 | Reinstallation of wall mounted / cassette units at their new desired location. | 0 | 0 | 0 | 0 | Nos | 32 | 0
4 | Supply and installation of isolation valve for indoor units (Gas + Liquid) (Make Danfoss)
| a) 1/4" Dia | 10000 | 2000 | 1200 | 13200 | Nos | 5 | 66000
| b) 3/8" Dia | 11280 | 2000 | 1328 | 14608 | Nos | 25 | 365200
| c) 1/2" Dia | 11875 | 2000 | 1387.5 | 15262.5 | Nos | 5 | 76312.5
| d) 5/8" Dia | 13125 | 2000 | 1512.5 | 16637.5 | Nos | 22 | 366025
| e) 3/4" Dia | 25625 | 2000 | 2762.5 | 30387.5 | No | 3 | 91162.5
5 | Supply and installation of Fresh air tube axial fan wall mounted (7500 CFM) (Make BVN) | 601800 | 25000 | 62680 | 689480 | Nos | 2 | 1378960
6 | Supply and installation of exhaust air wall mounted fan (10000 CFM) (Make BVN) | 395300 | 25000 | 42030 | 462330 | Nos | 1 | 462330
7 | Providing and installation of electric cables and conduit for the fans. | 50000 | 30000 | 8000 | 88000 | Job | 1 | 88000
8 | Supply and installation of exhaust air ducting. (20 SWG) | 500 | 100 | 60 | 660 | Sft | 250 | 165000
9 | Removal of existing fan motor, serviced, replaced with new motor (Siemens) and re installation complete in all respect. | 108011 | 5000 | 11301.1 | 124312.1 | Job | 1 | 124312.1
10 | After installation of copper piping, flushing with nitrogen and freon. (Honeywell) | 57230 | 20000 | 7723 | 84953 | Jar | 2 | 169906
11 | Dismantle of copper pipes, power / controls cable from VRF condensing units. |  | 8000 | 800 | 8800 | Unit | 5 | 44000
12 | Regging, liftings and shifting of VRF condensing unit at new location. | 0 | 5000 | 500 | 5500 | Nos | 4 | 22000
13 | Providing and installation of motorized damper for fresh air units. 24 x 10 (Make Hoenywell) | 82195 | 5000 | 8719.5 | 95914.5 | No | 1 | 95914.5
Total Amount Rs | [7 empty] | 3670122.6
Note: (for item # 4) Please note that in the BOQ the new copper pipe rates were submitted with the old Y-joints and valves. However, during several meetings, it was decided to replace the old leaking valves with new ones. Accordingly, we installed the new valves as per the decision.
For PIONEER ENGINEERING SERVICES