## Basement Mezzanine PPR-Pipe
Pioneer Services
Measurement Sheet For Running Bill.
Project :- MEEZAN BANK LIMITED MAKKAH TOWER GUJRANWALA |  | MEEZAN BANK LIMITED MAKKAH TOWER, GUJRANWALA |  |  | Date: |  | 2025-03-10
Contractor:- PES |  |  |  |  | Drawing No.
Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H
BASEMENT MEZZANINE
Part-2: INTERNAL WATER SUPPLY SYSTEM
2.1 | Providing, fixing, jointing and testing Polypropylene Random (PPR) PN16 pressure pipe for cold, hot and hot water return water as per DIN 8077-8078 for pipes and DIN 16962,PN20 for fittings (polyfusion welded joints) inside building including fittings and specials (sockets, tees, elbows, bends, crosses, reducers, adaptor, plugs and union etc.) supported on walls or suspended from roof slab or run in chases including pipe hangers, supports, walls cutting for pipelines, complete in all respect as per specifications and drawings as well as directed by the Engineer.
32 mm dia
|  | Rft. | 1 | 1.83 |  |  | 1.83
|  |  | 1 | 0.41 |  |  | 0.41
| Vertical Pipe |  | 1 | 9 |  |  | 9
| This Bill Qty. | Rft. |  |  |  |  | 11.24
| 50 mm dia | Rft. | 1 | 5.25 |  |  | 5.25
|  |  | 1 | 0.5 |  |  | 0.5
|  |  | 1 | 4.33 |  |  | 4.33
|  |  | 1 | 1.08 |  |  | 1.08
|  |  | 1 | 0.5 |  |  | 0.5
| This Bill Qty. | Rft. |  |  |  |  | 11.66
| 75 mm dia | Rft. | 1 | 3.33 |  |  | 3.33
|  |  | 1 | 2.91 |  |  | 2.91
|  |  | 1 | 2.66 |  |  | 2.66
|  |  | 1 | 29.83 |  |  | 29.83
| Vertical Pipe |  | 1 | 9 |  |  | 9
| This Bill Qty. | Rft. |  |  |  |  | 47.73