## Gate Valve PPR
Pioneer Services
Measurement Sheet For Running Bill.
Project :- MEEZAN BANK LIMITED MAKKAH TOWER GUJRANWALA |  | MEEZAN BANK LIMITED MAKKAH TOWER, GUJRANWALA |  |  | Date: |  | 2025-03-10
Contractor:- PES |  |  |  |  | Drawing No.
Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H
GATE / BALL VALVE
2.2 | Providing and installing gate/ball valves of following nominal dia, of approved equivalent make ,including jointing ,fitting, painting, testing, complete in all respects to match with following PPR pipe diameters.
Gate Valve
25 mm dia
| GROUND FLOOR | Nos. | 5 |  |  |  | 5
| FIRST FLOOR | Nos. | 4 |  |  |  | 4
| SECOND FLOOR | Nos. | 4 |  |  |  | 4
| This Bill Qty. | Nos. |  |  |  |  | 13
32 mm dia
| BASEMENT | Nos. | 1 |  |  |  | 1
| This Bill Qty. | Nos. |  |  |  |  | 1
40 mm dia
| GROUND FLOOR | Nos. | 3 |  |  |  | 3
| FIRST FLOOR | Nos. | 3 |  |  |  | 3
| SECOND FLOOR | Nos. | 3 |  |  |  | 3
| This Bill Qty. | Nos. |  |  |  |  | 9
75 mm dia
| BASEMENT MEZZANINE FLOOR | Nos. | 1 |  |  |  | 1
| This Bill Qty. | Nos. |  |  |  |  | 1