## Summary-OF HVAC
SUMMARY OF PLUMBING
MEEZAN BANK LIMITED MAKKAH TOWER, GUJRANWALA
BOQ NO. | DESCRIPTION | Unit | No. | BASEMENT | BASEMENT MEZZANINE | GROUND FLOOR | FIRST FLOOR | SECOND FLOOR | THIRD FLOOR | CURRANT TOTAL
Part-2: INTERNAL WATER SUPPLY SYSTEM
1.1 | Providing and fixing Indian W.C ceramics ware including muslim shower, tee stop cock, double bibcock with flushing cistern of best quality including hockey pipe. Fixing connection pipes and all joints to services and drains. Plugging and screwing the structure as necessary and make good the same, complete in all respect as per specifications and drawings as well as directed by the Engineer. MODEL # PORTA (HD70) | Nos |  |  |  | 1 |  |  |  | 1
0.1 | Providing and fixing European W.C ceramics ware including muslim shower, tee stop cock with double bibcock, flushing cistern with hinged double seat and cover of best quality. Fixing connection pipes and all joints to services and drains. Plugging and screwing the structure as necessary and make good the same, complete in all respect as per specifications and drawings as well as directed by the Engineer. MODEL # PORTA (HD9N) | Nos |  |  |  | 9 |  |  |  | 9
1.4 | Providing and fixing wash hand basin vanity Under counter including basin mixer with waste coupling & bottle trap and fixing connection pipes, connections to water lines, nuts, washers, etc. complete in all respect as per specifications and drawings as well as directed by the Engineer. | Nos |  | 0 | 0 | 9 |  |  | 0 | 9
1.5 | Providing and fixing kitchen sink with mixer, waste coupling and tee stop cock including all necessary accessories required for installation, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Nos |  | 0 | 0 | 2 |  |  | 0 | 2
1.6 | Providing and fixing soap dispenser including all necessary accessories required for installation, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Nos |  |  |  | 2 |  |  | 0 | 2
1.7 | Providing and fixing chromium plated toilet paper holder including all necessary accessories required for installation, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Nos |  |  |  | 9 |  |  | 0 | 9
1.8 | Providing and fixing electrical hand dryer with automatic sensor having fastest drying time of 12 seconds, temperature of 104 Fahrenheit. hand dryer must have noise Level of 81dB and automatic shut off including all necessary accessories required for installation, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Nos |  |  |  | 2 |  |  | 0 | 2
2 | Providing and fixing towel rod including all necessary accessories required for installation, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Nos |  |  |  | 3 |  |  | 0 | 3
2.1 | Providing, fixing, jointing and testing Polypropylene Random (PPR) PN16 pressure pipe for cold, hot and hot water return water as per DIN 8077-8078 for pipes and DIN 16962,PN20 for fittings (polyfusion welded joints) inside building including fittings and specials (sockets, tees, elbows, bends, crosses, reducers, adaptor, plugs and union etc.) supported on walls or suspended from roof slab or run in chases including pipe hangers, supports, walls cutting for pipelines, complete in all respect as per specifications and drawings as well as directed by the Engineer.
| 25 mm dia | Rft | 1 |  |  | 250.94 | 224.28 | 193.23 |  | 668.45
| 32 mm dia | Rft | 1 | 24.16 | 11.24 | 335.96 | 410.71 | 410.71 |  | 1192.78
| 40 mm dia | Rft | 1 |  |  | 59.73 | 65.73 | 65.73 |  | 191.19
| 50 mm dia | Rft | 1 |  | 11.66 |  |  |  |  | 11.66
| 75 mm dia | Rft | 1 |  | 88.13 | 199.49 |  |  |  | 287.62
GATE / BALL VALVE
2.2 | Providing and installing gate/ball valves of following nominal dia, of approved equivalent make ,including jointing ,fitting, painting, testing, complete in all respects to match with following PPR pipe diameters.
| 25 mm dia | NOS. | 1 |  |  | 5 | 4 | 4 |  | 13
| 32 mm dia | NOS. | 1 | 1 | [5 empty] | 1
| 40 mm dia | NOS. | 1 |  |  | 3 | 3 | 3 |  | 9
| 75 mm dia | NOS. | 1 |  | 1 |  |  |  |  | 1
Part-3: INTERNAL SEWERAGE , VENTS & ROOF DRAINAGE
3.1 | Providing, fixing, jointing and testing uPVC pipe including all fittings such as tees, bends and reducers. Also it includes the cost of joint solutions & clamping to walls, ceiling hangers, supports, cutting through walls for pipelines and pipe fittings of the following diameters, complete in all respect as per specifications and drawings as well as directed by the Engineer.
| 50 mm dia | Rft | 1 |  |  | 49.61 | 69.93 | 69.38 |  | 188.92
| 75 mm dia | Rft | 1 |  | 56 |  |  |  |  | 56
| 100 mm dia | Rft | 1 | 158.32 | 44.31 | 325.85 | 233.67 | 223.41 |  | 985.56
| 100 mm dia (Riser Rain Pipe) | Rft | 1 |  |  | 168 | 104 | 104 | 104 | 480 | 1465.56
| 200 mm dia | Rft | 1 |  |  | 209.99 |  |  |  | 209.99
CLASS :D: BS 3505/PS 3051 (For Pressure Pipe)
| 2 inch dia pipe | Rft | 1 | 86.16 | [5 empty] | 86.16
FLOOR DRAIN
3.2 | Providing and fixing 4" dia Floor Drain with P-trap including Stainless Steel grating and cover of approved make including all necessary accessories required for installation, complete in all respect as per specifications and drawings as well as directed by the Engineer.
| 4" dia | NOS. | 1 |  | 4 | 17 | 16 | 15 |  | 52
CLEAN-OUT
3.3 | Providing and fixing 4" dia Clean-out for uPVC Pipes including Stainless Steel Cover Plate of approved make, core cutting of Slab concrete and its water proofed refilling as approved by Engineer In charge and complete in all respect.
| 4" dia | NOS. | 1 | 1 |  |  | 4 | 4 |  | 9