## Basement Mezzanine Upvc-Pipe
Pioneer Services
Measurement Sheet For Running Bill.
Project :- MEEZAN BANK LIMITED MAKKAH TOWER GUJRANWALA |  | MEEZAN BANK LIMITED MAKKAH TOWER, GUJRANWALA |  |  | Date: |  | 2025-03-10
Contractor:- PES |  |  |  |  | Drawing No.
Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H
BASEMENT MEZZANINE FLOOR
Part-3: INTERNAL SEWERAGE , VENTS & ROOF DRAINAGE
3.1 | Providing, fixing, jointing and testing uPVC pipe including all fittings such as tees, bends and reducers. Also it includes the cost of joint solutions & clamping to walls, ceiling hangers, supports, cutting through walls for pipelines and pipe fittings of the following diameters, complete in all respect as per specifications and drawings as well as directed by the Engineer.
| 75 mm dia | Rft. | 1 | 46.5 |  |  | 46.5
|  |  | 1 | 5.5 |  |  | 5.5
| Vertical Pipe |  | 2 | 2 |  |  | 4
| This Bill Qty. | Rft. |  |  |  |  | 56
| 100 mm dia | Rft. | 1 | 10.5 |  |  | 10.5
|  |  | 1 | 1.58 |  |  | 1.58
|  |  | 1 | 11.58 |  |  | 11.58
|  |  | 1 | 9.83 |  |  | 9.83
|  |  | 1 | 1 |  |  | 1
|  |  | 1 | 2.08 |  |  | 2.08
|  |  | 1 | 0.66 |  |  | 0.66
|  |  | 1 | 1.08 |  |  | 1.08
| Vertical Pipe |  | 3 | 2 |  |  | 6
| This Bill Qty. | Rft. |  |  |  |  | 44.31