## Floor Drain
Pioneer Services
Measurement Sheet For Running Bill.
Project :- MEEZAN BANK LIMITED MAKKAH TOWER GUJRANWALA |  | MEEZAN BANK LIMITED MAKKAH TOWER, GUJRANWALA |  |  | Date: |  | 2025-03-12
Contractor:- PES |  |  |  |  | Drawing No.
Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H
FLOOR DRAIN
3.2 | Providing and fixing 4" dia Floor Drain with P-trap including Stainless Steel grating and cover of approved make including all necessary accessories required for installation, complete in all respect as per specifications and drawings as well as directed by the Engineer.
Floor Drains 4" Dia
| BASEMENT MEZZANINE FLOOR | Nos. | 4 |  |  |  | 4
| GROUND FLOOR | Nos. | 17 |  |  |  | 17
| FIRST FLOOR | Nos. | 16 |  |  |  | 16
| SECOND FLOOR | Nos. | 15 |  |  |  | 15
| This Bill Qty. | Nos. |  |  |  |  | 52

## COP
Pioneer Services
Measurement Sheet For Running Bill.
Project :- MEEZAN BANK LIMITED MAKKAH TOWER GUJRANWALA |  | MEEZAN BANK LIMITED MAKKAH TOWER, GUJRANWALA |  |  | Date: |  | 2025-03-12
Contractor:- PES |  |  |  |  | Drawing No.
Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H
CLEAN-OUT
3.3 | Providing and fixing 4" dia Clean-out for uPVC Pipes including Stainless Steel Cover Plate of approved make, core cutting of Slab concrete and its water proofed refilling as approved by Engineer In charge and complete in all respect.
CLEAN OUT 4" Dia
| BASEMENT | Nos. | 1 |  |  |  | 1
| FIRST FLOOR | Nos. | 4 |  |  |  | 4
| SECOND FLOOR | Nos. | 4 |  |  |  | 4
| This Bill Qty. | Nos. |  |  |  |  | 9