## drain 1.25
Form No.04
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: | Patient Aid Foundation (PAF) |  |  | Contractor: | Pioneer Services |  |  | Project Manager: |  | Israr Ahmed
Project: | NICVD |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-02-10 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day: |  | 18
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1-1/4" | zone A G.F | RFT | 150 | 0 | 22 | 22 | 14.67% | 14% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-03-10 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1-1/4" | zone A G.F | RFT | 150 | 22 | 22 | 44 | 29.33% | 14% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-04-10 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1-1/4" | zone B G.F | RFT | 150 | 44 | 21 | 65 | 43.33% | 47% | Unit Connection Work remaining (OFM)

## split unit
Form No.04
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: | Patient Aid Foundation (PAF) |  |  | Contractor: | Pioneer Services |  |  | Project Manager: |  | Israr Ahmed
Project: | NICVD |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-01-03 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day: |  | 3
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1/4'' and 1/2'' | zone A,B,C First Floor | RFT | 550 | 0 | 92 | 92 | 16.73% | 16% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-02-03 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1/4'' and 1/2'' | zone A,B,C Ground floor | RFT | 550 | 92 | 92 | 184 | 33.45% | 17% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-03-03 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1/4'' and 1/2'' | zone A,B,C Basement | RFT | 550 | 184 | 92 | 276 | 50.18% | 50% | Unit Connection Work remaining (OFM)

## copper 1 3-8
Form No.04
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: | Patient Aid Foundation (PAF) |  |  | Contractor: | Pioneer Services |  |  | Project Manager: |  | Israr Ahmed
Project: | NICVD |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 25/2/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day: |  | 3
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1 3/8'' | zone A,B,C First Floor | RFT | 33.5 | 0 | 12 | 12 | 35.82% | 36% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 26/2/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1 3/8'' | zone A,B,C Ground floor | RFT | 33.5 | 12 | 12 | 24 | 71.64% | 28% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 27/2/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1 3/8'' | zone A,B,C Basement | RFT | 33.5 | 24 | 9.5 | 33.5 | 100% |  | Unit Connection Work remaining (OFM)

## copper 1 1-8
Form No.04
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: | Patient Aid Foundation (PAF) |  |  | Contractor: | Pioneer Services |  |  | Project Manager: |  | Israr Ahmed
Project: | NICVD |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 21/2/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day: |  | 3
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1 1/8'' | zone A,B,C First Floor | RFT | 970 | 0 | 145 | 145 | 14.95% | 15% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 22/2/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day: |  | 3
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1 1/8'' | zone A,B,C Ground floor | RFT | 970 | 145 | 145 | 290 | 29.9% | 15% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 23/2/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1 1/8'' | zone A,B,C Basement | RFT | 970 | 290 | 147 | 437 | 45.05% | 15% | Unit Connection Work remaining (OFM)

## copper 7-8
Form No.04
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: | Patient Aid Foundation (PAF) |  |  | Contractor: | Pioneer Services |  |  | Project Manager: |  | Israr Ahmed
Project: | NICVD |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 18/2/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day: |  | 3
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 7/8'' | zone A,B,C First Floor | RFT | 163 | 0 | 55 | 55 | 33.74% | 33% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 19/2/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 7/8'' | zone A,B,C Ground floor | RFT | 163 | 55 | 55 | 110 | 67.48% | 33% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 20/2/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 7/8'' | zone A,B,C Basement | RFT | 163 | 110 | 53 | 163 | 100% |  | Unit Connection Work remaining (OFM)

## copper 3-4
Form No.04
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: | Patient Aid Foundation (PAF) |  |  | Contractor: | Pioneer Services |  |  | Project Manager: |  | Israr Ahmed
Project: | NICVD |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 15/2/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day: |  | 18
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/4'' | zone A,B,C First Floor | RFT | 430 | 0 | 143 | 143 | 33.26% | 34% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 16/2/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/4'' | zone A,B,C Ground floor | RFT | 430 | 143 | 143 | 286 | 66.51% | 26% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 17/2/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/4'' | zone A,B,C Basement | RFT | 430 | 286 | 114 | 400 | 93.02% | 7% | Unit Connection Work remaining (OFM)

## copper 5-8
Form No.04
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: | Patient Aid Foundation (PAF) |  |  | Contractor: | Pioneer Services |  |  | Project Manager: |  | Israr Ahmed
Project: | NICVD |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 20/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day: |  | 18
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 5/8'' | zone A First Floor | RFT | 1395 | 0 | 77.5 | 77.5 | 5.556% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 21/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 5/8'' | zone A First Floor | RFT | 1395 | 77.5 | 77.5 | 155 | 11.11% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 22/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 5/8'' | zone B First Floor | RFT | 1395 | 155 | 77.5 | 232.5 | 16.67% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 23/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 5/8'' | zone B First Floor | RFT | 1395 | 233 | 77.5 | 310.5 | 22.26% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 24/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 5/8'' | zone C First Floor | RFT | 1395 | 311 | 77.5 | 388.5 | 27.85% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 25/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 5/8'' | zone C First Floor | RFT | 1395 | 389 | 77.5 | 466.5 | 33.44% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 26/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 5/8'' | zone A Ground floor | RFT | 1395 | 467 | 77.5 | 544.5 | 39.03% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 27/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 5/8'' | zone A Ground floor | RFT | 1395 | 545 | 77.5 | 622.5 | 44.62% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 28/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 5/8'' | zone B Ground floor | RFT | 1395 | 623 | 77.5 | 700.5 | 50.22% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 29/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 5/8'' | zone B Ground floor | RFT | 1395 | 701 | 77.5 | 778.5 | 55.81% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 30/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 5/8'' | zone C Ground floor | RFT | 1395 | 779 | 77.5 | 856.5 | 61.4% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 31/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 5/8'' | zone C Ground floor | RFT | 1395 | 857 | 77.5 | 934.5 | 66.99% | 6% | Unit Connection Work remaining (OFM)
935
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-01-02 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 5/8'' | zone A Basement | RFT | 1395 | 935 | 77.5 | 1012.5 | 72.58% | 1% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-02-02 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 5/8'' | zone A Basement | RFT | 1395 | 1013 | 20 | 1033 | 74.05% | 1% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-03-02 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 5/8'' | zone B Basement | RFT | 1395 | 1033 | 20 | 1053 | 75.48% | 3% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-04-02 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 5/8'' | zone B Basement | RFT | 1395 | 1053 | 30 | 1083 | 77.63% | 3% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-05-02 | Weather: |  | Temperature: |  |  |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 5/8'' | zone C Basement | RFT | 1395 | 1083 | 45 | 1128 | 80.86% | 2% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-06-02 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 5/8'' | zone C Basement | RFT | 1395 | 1128 | 33 | 1161 | 83.23% |  | Unit Connection Work remaining (OFM)

## copper 12mm
Form No.04
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: | Patient Aid Foundation (PAF) |  |  | Contractor: | Pioneer Services |  |  | Project Manager: |  | Israr Ahmed
Project: | NICVD |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-03-01 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day: |  | 18
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1/2'' | zone A First Floor | RFT | 1593 | 0 | 88.5 | 88.5 | 5.556% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-04-01 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1/2'' | zone A First Floor | RFT | 1593 | 88.5 | 88.5 | 177 | 11.11% | 2% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-05-01 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1/2'' | zone B First Floor | RFT | 1593 | 117 | 88.5 | 205.5 | 12.9% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-06-01 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1/2'' | zone B First Floor | RFT | 1593 | 206 | 88.5 | 294.5 | 18.49% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-07-01 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1/2'' | zone C First Floor | RFT | 1593 | 295 | 88.5 | 383.5 | 24.07% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-08-01 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1/2'' | zone C First Floor | RFT | 1593 | 384 | 88.5 | 472.5 | 29.66% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-09-01 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1/2'' | zone A Ground floor | RFT | 1593 | 473 | 88.5 | 561.5 | 35.25% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-10-01 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1/2'' | zone A Ground floor | RFT | 1593 | 562 | 88.5 | 650.5 | 40.83% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-11-01 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1/2'' | zone B Ground floor | RFT | 1593 | 651 | 88.5 | 739.5 | 46.42% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-12-01 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1/2'' | zone B Ground floor | RFT | 1593 | 740 | 88.5 | 828.5 | 52.01% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 13/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1/2'' | zone C Ground floor | RFT | 1593 | 829 | 88.5 | 917.5 | 57.6% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 14/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1/2'' | zone C Ground floor | RFT | 1593 | 918 | 88.5 | 1006.5 | 63.18% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 15/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1/2'' | zone A Basement | RFT | 1593 | 1007 | 88.5 | 1095.5 | 68.77% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 16/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1/2'' | zone A Basement | RFT | 1593 | 1096 | 88.5 | 1184.5 | 74.36% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 17/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1/2'' | zone B Basement | RFT | 1593 | 1185 | 88.5 | 1273.5 | 79.94% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 18/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1/2'' | zone B Basement | RFT | 1593 | 1274 | 88.5 | 1362.5 | 85.53% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 19/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/8'' | zone C Basement | RFT | 1593 | 1363 | 88.5 | 1451.5 | 91.12% | 9% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 20/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 1/2'' | zone C Basement | RFT | 1593 | 1452 | 141 | 1593 | 100% |  | Unit Connection Work remaining (OFM)

## Ducting
Form No.04
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: | Patient Aid Foundation (PAF) |  |  | Contractor: | Pioneer Services |  |  | Project Manager: |  | Israr Ahmed
Project: | NICVD |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-09-10 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day: |  | 24
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone A First Floor | Sqft | 7050 | 0 | 294 | 294 | 4.17% | 9% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-10-10 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone A First Floor | Sqft | 7050 | 588 | 294 | 882 | 12.51% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-11-10 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone B First floor | Sqft | 7050 | 822 | 294 | 1116 | 15.83% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-12-10 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone B First floor | Sqft | 7050 | 1176 | 294 | 1470 | 20.85% | 4% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 13/10/2024 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone C First floor | Sqft | 7050 | 1470 | 294 | 1764 | 25.02% | 4% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 14/10/2024 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone C First floor | Sqft | 7050 | 1764 | 294 | 2058 | 29.19% | 4% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 15/10/2024 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone A Ground floor | Sqft | 7050 | 2058 | 294 | 2352 | 33.36% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 16/10/2024 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone A Ground floor | Sqft | 7050 | 2352 | 294 | 2646 | 37.53% | 4% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 17/10/2024 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone B Ground floor | Sqft | 7050 | 2646 | 294 | 2940 | 41.7% | 4% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 18/10/2024 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone B Ground floor | Sqft | 7050 | 2940 | 294 | 3234 | 45.87% | 4% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 19/10/2024 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone C Ground floor | Sqft | 7050 | 3234 | 294 | 3528 | 50.04% | 4% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 20/10/24 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone C Ground floor | Sqft | 7050 | 3528 | 294 | 3822 | 54.21% | 4% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 21/10/24 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone A Basement | Sqft | 7050 | 3822 | 294 | 4116 | 58.38% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 22/10/24 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone A Basement | Sqft | 7050 | 4116 | 294 | 4410 | 62.55% | 4% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 23/10/24 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone B Basement | Sqft | 7050 | 4410 | 294 | 4704 | 66.72% | 4% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 24/10/24 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone B Basement | Sqft | 7050 | 4704 | 294 | 4998 | 70.89% | 4% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 25/10/24 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone C Basement | Sqft | 7050 | 4998 | 294 | 5292 | 75.06% | 4% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 26/10/24 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone C Basement | Sqft | 7050 | 5292 | 294 | 5586 | 79.23% | 4% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 27/10/24 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone C Basement | Sqft | 7050 | 5586 | 294 | 5880 | 83.4% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 28/10/24 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone C Basement | Sqft | 7050 | 5880 | 294 | 6174 | 87.57% | 4% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 29/10/24 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone C Basement | Sqft | 7050 | 6174 | 294 | 6468 | 91.74% | 3% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 30/10/24 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone C Basement | Sqft | 7050 | 6221 | 47 | 6268 | 88.91% | 1% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 31/10/24 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone C Basement | Sqft | 7050 | 6268 | 24 | 6292 | 89.25% | 1% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-01-11 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of G.I ducting | zone C Basement | Sqft | 7050 | 6292 | 24 | 6316 | 89.59% | 5% | Unit Connection Work remaining (OFM)

## duct insulation
Form No.04
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: | Patient Aid Foundation (PAF) |  |  | Contractor: | Pioneer Services |  |  | Project Manager: |  | Israr Ahmed
Project: | NICVD |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 24/11/2024 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day: |  | 12
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
10 | Installation of duct insulation | zone A First Floor | Sqft | 4900 | 0 | 408 | 408 | 8.327% | 17% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 25/11/2024 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of duct insulation | zone B First Floor | Sqft | 4900 | 816 | 408 | 1224 | 24.98% | 8% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 26/11/2024 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of duct insulation | zone C First floor | Sqft | 4900 | 1224 | 408 | 1632 | 33.31% | 9% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 27/11/2024 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of duct insulation | zone A Ground floor | Sqft | 4900 | 1632 | 408 | 2040 | 41.63% | 8% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 28/11/2024 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of duct insulation | zone B Ground floor | Sqft | 4900 | 2040 | 408 | 2448 | 49.96% | 8% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 29/11/2024 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of duct insulation | zone C Ground floor | Sqft | 4900 | 2448 | 408 | 2856 | 58.29% | 9% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 30/11/2024 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of duct insulation | zone A Basement | Sqft | 4900 | 2856 | 408 | 3264 | 66.61% | 8% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-01-12 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of duct insulation | zone B Basement | Sqft | 4900 | 3264 | 408 | 3672 | 74.94% | 8% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-02-11 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
10 | Installation of duct insulation | zone C Basement | Sqft | 4900 | 3672 | 408 | 4080 | 83.27% | 2% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-03-11 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of duct insulation | zone A Ground Riser | Sqft | 4900 | 4080 | 75 | 4155 | 84.8% | 1% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-04-11 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of duct insulation | zone A First Riser | Sqft | 4900 | 4155 | 50 | 4205 | 85.82% | 1% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-05-11 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of duct insulation | zone A basement riser | Sqft | 4900 | 4205 | 38 | 4243 | 86.59% | 13% | Unit Connection Work remaining (OFM)

## copper pipe
Form No.04
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: | Patient Aid Foundation (PAF) |  |  | Contractor: | Pioneer Services |  |  | Project Manager: |  | Israr Ahmed
Project: | NICVD |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-03-01 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day: |  | 18
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/8'' | zone A First Floor | RFT | 2443 | 0 | 135.7 | 135.7 | 5.555% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-04-01 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/8'' | zone A First Floor | RFT | 2443 | 135.7 | 135.7 | 271.4 | 11.11% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-05-01 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/8'' | zone B First Floor | RFT | 2443 | 271 | 135.7 | 406.7 | 16.65% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-06-01 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/8'' | zone B First Floor | RFT | 2443 | 407 | 135.7 | 542.7 | 22.21% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-07-01 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/8'' | zone C First Floor | RFT | 2443 | 543 | 135.7 | 678.7 | 27.78% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-08-01 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/8'' | zone C First Floor | RFT | 2443 | 679 | 135.7 | 814.7 | 33.35% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-09-01 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/8'' | zone A Ground floor | RFT | 2443 | 815 | 135.7 | 950.7 | 38.92% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-10-01 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/8'' | zone A Ground floor | RFT | 2443 | 951 | 135.7 | 1086.7 | 44.48% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-11-01 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/8'' | zone B Ground floor | RFT | 2443 | 1087 | 135.7 | 1222.7 | 50.05% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-12-01 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/8'' | zone B Ground floor | RFT | 2443 | 1223 | 135.7 | 1358.7 | 55.62% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 13/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/8'' | zone C Ground floor | RFT | 2443 | 1359 | 135.7 | 1494.7 | 61.18% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 14/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/8'' | zone C Ground floor | RFT | 2443 | 1495 | 135.7 | 1630.7 | 66.75% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 15/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/8'' | zone A Basement | RFT | 2443 | 1631 | 135.7 | 1766.7 | 72.32% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 16/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/8'' | zone A Basement | RFT | 2443 | 1767 | 135.7 | 1902.7 | 77.88% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 17/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/8 | zone B Basement | RFT | 2443 | 1903 | 135.7 | 2038.7 | 83.45% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 18/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/8'' | zone B Basement | RFT | 2443 | 2039 | 135.7 | 2174.7 | 89.02% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 19/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/8'' | zone C Basement | RFT | 2443 | 2175 | 135.7 | 2310.7 | 94.58% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 20/1/2025 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Refrigerant pipe dia 3/8'' | zone C Basement | RFT | 2443 | 2311 | 132 | 2443 | 100% |  | Unit Connection Work remaining (OFM)

## drain pipe
Form No.04
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: | Patient Aid Foundation (PAF) |  |  | Contractor: | Pioneer Services |  |  | Project Manager: |  | Israr Ahmed
Project: | NICVD |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-02-10 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day: |  | 18
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1" | zone A G.F | RFT | 1768 | 0 | 98 | 98 | 5.543% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-03-10 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1" | zone A G.F | RFT | 1768 | 98 | 98 | 196 | 11.09% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-04-10 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1" | zone B G.F | RFT | 1768 | 196 | 98 | 294 | 16.63% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-05-10 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1" | zone B G.F | RFT | 1768 | 294 | 98 | 392 | 22.17% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-06-10 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1" | zone C G.F | RFT | 1768 | 392 | 98 | 490 | 27.71% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-07-10 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1" | zone C G.F | RFT | 1768 | 490 | 98 | 588 | 33.26% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-08-10 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1" | zone A Ist floor | RFT | 1768 | 588 | 98 | 686 | 38.8% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-09-10 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1" | zone A Ist floor | RFT | 1768 | 686 | 98 | 784 | 44.34% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-10-10 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1" | zone B Ist floor | RFT | 1768 | 784 | 98 | 882 | 49.89% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-11-10 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1" | zone B Ist floor | RFT | 1768 | 882 | 98 | 980 | 55.43% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2024-12-10 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1" | zone C Ist floor | RFT | 1768 | 980 | 98 | 1078 | 60.97% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 13/10/24 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1" | zone C Ist floor | RFT | 1768 | 1078 | 98 | 1176 | 66.52% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 14/10/24 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1" | zone A Basement | RFT | 1768 | 1176 | 98 | 1274 | 72.06% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 15/10/24 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1" | zone A Basement | RFT | 1768 | 1274 | 98 | 1372 | 77.6% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 16/10/24 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1" | zone B Basement | RFT | 1768 | 1372 | 98 | 1470 | 83.14% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 17/10/24 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1" | zone B Basement | RFT | 1768 | 1470 | 98 | 1568 | 88.69% | 5% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 18/10/24 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1" | zone C Basement | RFT | 1768 | 1568 | 98 | 1666 | 94.23% | 6% | Unit Connection Work remaining (OFM)
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: |  |  |  | Contractor: |  |  |  | Project Manager:
Project: |  |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 19/10/24 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
9 | Installation of Upvc condensate drain pipe dia 1" | zone C Basement | RFT | 1768 | 1668 | 100 | 1768 | 100% | 5% | Unit Connection Work remaining (OFM)
c