## Sheet1
Bill Summary for the project Bank Al Habib Center Point |  |  |  |  | MOBILIZATION ADVANCE |  | RETENTION AMOUNT
Contract Amount |  |  |  | 44652803 | Contract Amount | 44652803 | DEDUCTION IN IPC 1 | 1639518
Mobilizatin adv |  |  |  | 6500000
| IPC-01 | IPC-02 | IPC-03 |  | Mod Ad received | 6500000
RUNNING BILL NO 1 | 35449032 | 6268508 |  | 41717540 |  |  | TOTAL RECEIVABLE | 1639518
Less Tax |  | 7.5% |  | 3128815.5 | DEDUCTION
[5 empty] | DEDUCTION IN IPC 1 | 6558071
Balance Payable |  |  |  | 38588724.5
Less Mobilization 20% |  | 20% |  | 7717744.9
Less Retention 5% |  | 5% |  | 1929436.225 | TOTAL | 6558071
Payable Amount |  |  |  | 28941543.375 | Extra deduct | -58071
Al ready received |  |  |  | 24592765.95
Net Payable |  |  |  | 4348777.425

## Grand
Bill Summary for the project UEP 17th Floor DMC Karachi
Contract Amount | 55163506 | Contract Amount | 55163506 | LESS Retention 5% | 2586024.4
|  | Verified (IPC-1 + IPC-02) | 58378100 | ADD SST 13% | 336183.172
|  | LESS Retention 5% | 2918905 | Gross | 2922207.572
Verified (IPC-1 + IPC-02) | 51720488 | Remaining | 55459195 | LESS SST TAX 20% | 67236.6344
|  | ADD SST 13% | 7209695.35 | LESS WHTAX 08% | 233776.6058
LESS Retention 5% | 2586024.4 | Gross Work Done | 62668890.35 | Remaining | 2621194.3318
|  | Amount Received | 47891047 |  |  |  | Verified BILL | 58378100
Remaining | 49134463.6 | Remaining | 14777843.35 |  |  |  | Less Mob | 11032701
|  | LESS SST TAX 20% | 1441939.07 |  | 14774871.1438 |  | Retention | 2918905
ADD SST 13% | 6387480.268 | LESS WHTAX 08% | 1182227.468 |  | 35032291 |  | Received | 36858346
|  | Remaining | 12153676.812 |  | 49807162.1438 |  | Remaining | 7568148
Gross Work Done | 55521943.868
2725077
LESS Remaining Mobilization Adv | 2545345.2
Net | 52976598.668 |  | 7171255.78
62334761.78
Amount Received | 27957346 |  | 4986780.9424 |  | 0
1434251.156
| 25019252.668 |  | 55913729.6816
11884018
LESS SST TAX 20% | 1277496.0536
LESS WHTAX 08% | 2001540.2134
18170858
Amount Receivable | 21740216.401 |  |  |  | 545015.4
17625842.6
1453668.64
16172173.96
|  |  | 56772507.401 |  | 16172173.96