## Table 1
Bill of Quantities
ACMV WORKS
Meezan Bank Head Office | [9 empty] | 2023-11-28
Karachi.
BILL OF QUANTITIES | [5 empty] | RUNNING BILL NO 1
S.NO. | DESCRIPTION | UNIT | QTY | MATERIAL | LABOUR | Material |  | Labour |  | TOTAL
|  |  |  | RATE | RATE | Bill Qty | Amount | Bill Qty | Amount | AMOUNT Rs.
All works shall be completed, tested and commissioned as per drawings, specifications and as per instruction of Consultant
1 | Unloading, rigging, lifting, installation, testing and commissioning of OWNER SUPPLIED Modular type Air Handling Units with VFD of different capacities complete in all respects, ready to operate with supply and fixing of all accessories, including hanger steel base, vibration isolators, including interconnecting power & control wiring (terminations) with inlet & outlet chilled water connections, drain connection, flexible rubber duct connection etc. complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
1.1 | GF-MAHU-01 | No. | 1 | 55000 | 40000 | 0 | 0 | 0 | 0 | 0
1.2 | FF-MAHU-01 | No. | 1 | 60000 | 45000 | 0 | 0 | 0 | 0 | 0
1.3 | TF-MAHU-01 | Nos. | 5 | 65000 | 50000 | 0 | 0 | 0 | 0 | 0
2 | Supply & installation of valves & accessories for MAHUs including supports, hangers, flanges, gas kits, nut & bolts etc. complete in all respects as per specifications, drawings and as per instructions of consultant. | [5 empty] | 0 | 0 | 0 | 0
2.1 | Butterfly Valve | [5 empty] | 0 | 0 | 0 | 0
i. | 2.5" dia (Lever Type) | Nos. | 4 | 15450 | 4000 |  | 0 | 0 | 0 | 0
ii. | 3" dia (Lever Type) | Nos. | 4 | 18375 | 4000 |  | 0 | 0 | 0 | 0
iii. | 4" dia (Gear Operated) | Nos. | 20 | 32500 | 5000 |  | 0 | 0 | 0 | 0
2.2 | Strainers | [5 empty] | 0 | 0 | 0 | 0
i. | 2.5" dia | No. | 1 | 30420 | 4000 |  | 0 | 0 | 0 | 0
ii. | 3" dia | No. | 1 | 40950 | 4000 |  | 0 | 0 | 0 | 0
iii. | 4" dia | Nos. | 5 | 58500 | 5000 |  | 0 | 0 | 0 | 0
2.3 | Balancing Valve (with self sealing measuring nipples) | [5 empty] | 0 | 0 | 0 | 0
i. | 2.5" dia | No. | 1 | 80400 | 4000 |  | 0 | 0 | 0 | 0
ii. | 3" dia | No. | 1 | 109500 | 4000 |  | 0 | 0 | 0 | 0
iii. | 4" dia | Nos. | 5 | 131000 | 5000 |  | 0 | 0 | 0 | 0
2.4 | Thermometer 6" Height Scale Type (with Thermo well) 0 ºC to 60 ºC | Nos. | 14 | 12000 | 1000 |  | 0 | 0 | 0 | 0
2.5 | Pressure Gauge with with Ball Valve & Siphon, Liquid filled Dial type range -ve 5 psi to 100 psi. (4" dial Size) | Nos. | 14 | 11000 | 1000 |  | 0 | 0 | 0 | 0
2.6 | 2-Way Motorized Valve with Actuator (0-100% modulating) | [5 empty] | 0 | 0 | 0 | 0
i. | 2" dia | No. | 1 | 87000 | 3000 |  | 0 | 0 | 0 | 0
ii. | 2.5" dia | No. | 1 | 165000 | 4000 |  | 0 | 0 | 0 | 0
iii. | 3" dia | Nos. | 5 |  | 5000 |  | 0 | 0 | 0 | 0
2.7 | Digital Decorative Thermostat Controller with Duct Sensor (BMS Interfacable) | Nos. | 7 | 45000 | 5000 |  | 0 | 0 | 0 | 0
2.8 | Fan Control Panel with incoming Ckt. Breaker, auto S/D starter with protections and safeties | Nos. | 7 | 55000 | 5000 |  | 0 | 0 | 0 | 0
2.9 | Control wiring from controller to sensors, motorized valve and Power wiring from FCP to fan, up to 15' radius | Lot | 7 | 20000 | 5000 |  | 0 | 0 | 0 | 0
3 | Supply, Installation, testing and commissioning of SCH-40 M.S.(As per ASME & API standard, Heavy Quality with standard SCH 40 wall thickness) pipes & fitting for chilled water circulation system complete with bends, tees, unions, sockets, specials, MS Pipe support, hangers & anchors, M.S. angle, U channel, Roller Support, bolts, rods, clamps, Concrete fasteners etc as required to complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of Consultant. | [5 empty] | 0 | 0 | 0 | 0
3.1 | 2.5" dia | Rft | 55 | 2850 | 400 |  | 0 | 0 | 0 | 0
3.2 | 3" dia | Rft | 110 | 3375 | 450 |  | 0 | 0 | 0 | 0
3.3 | 4" dia | Rft | 275 | 4450 | 500 |  | 0 | 0 | 0 | 0
3.4 | 5" dia | Rft | Rate only | 6450 | 600 |  | 0 | 0 | 0 | 0
3.5 | 6" dia | Rft | Rate only | 9200 | 900 |  | 0 | 0 | 0 | 0
3.6 | 8" dia | Rft | 200 | 12970 | 1200 |  | 0 | 0 | 0 | 0
4 | Supply, Installation of Pre Formed Polystyrene (Thermopore) insulation (32 kg/m3 density) for Internal chilled water pipes (GF to 5F), bends, tees, unions, sockets, valves and on specials protected with Kraft paper, wrapped with 8oz Canvas cloth than paint with Anti fungus paint complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of Consultant. | [5 empty] | 0 | 0 | 0 | 0
4.1 | 2.5" dia | Rft | 55 | 510 | 60 |  | 0 | 0 | 0 | 0
4.2 | 3" dia | Rft | 110 | 785 | 70 |  | 0 | 0 | 0 | 0
4.3 | 4" dia | Rft | 275 | 890 | 80 |  | 0 | 0 | 0 | 0
4.4 | 5" dia | Rft | Rate only | 1010 | 100 |  | 0 | 0 | 0 | 0
4.5 | 6" dia | Rft | Rate only | 1140 | 125 |  | 0 | 0 | 0 | 0
4.6 | 8" dia | Rft | 200 | 1390 | 150 |  | 0 | 0 | 0 | 0
5 | Supply & installation single split air conditioning units decorative type (inverter) of different capacities, including supply & installation of supports, brackets, rubber isolator, flashing, power wiring upto 15' + connection, complete in all respects ready to operate as per drawings, specification, instruction of consultant. | [5 empty] | 0 | 0 | 0 | 0
5.1 | AC-01 (2 Tr) | Nos. | 7 | 265000 | 5000 |  | 0 | 0 | 0 | 0
6 | Supply & installation of refrigerant pipes (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping + control wiring in G.I. for external / PVC for internal from outdoor unit to indoor unit, including gas charging if required complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | [5 empty] | 0 | 0 | 0 | 0
6.1 | AC-01 (2 Tr) | Rft | 182 | 1450 | 250 |  | 0 | 0 | 0 | 0
7 | Supply & installation of 18 SWG G.I. sheet metal tray for refrigerant pipes and control wiring exposed to weather complete in all respects including hangers, supports brackets complete in all respects ready to operate as per specification, drawings and as per instruction, approval of consultant. | Sqft | 150 | 850 | 150 |  | 0 | 0 | 0 | 0
8 | Supply, rigging, lifting, placement, installation, testing and commissioning of Ventilation Fans as per mentioned in schedule, including supply of vibration isolator, electrical connection, flexible duct connection, support & hangers complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | [5 empty] | 0 | 0 | 0 | 0
8.1 | B2-JF-01 | Nos. | 2 | 559000 | 8000 | 1 | 559000 | 1 | 8000 | 567000
8.2 | B2-EAF-01 | Nos. | 2 | 699000 | 11000 | 1 | 699000 | 1 | 11000 | 710000
8.3 | B2-FAF-01 | No. | 1 | 915000 | 15000 | 1 | 915000 | 1 | 15000 | 930000
8.4 | B1-JF-01 | Nos. | 2 | 535000 | 7000 | 1 | 535000 | 1 | 7000 | 542000
8.5 | B1-EAF-01 | Nos. | 2 | 869000 | 20000 | 1 | 869000 | 1 | 20000 | 889000
8.6 | GF-EAF-01 | No. | 1 | 27000 | 2000 | 1 | 27000 | 1 | 2000 | 29000
8.7 | FF-EAF-01 | No. | 1 | 27000 | 2000 | 1 | 27000 | 1 | 2000 | 29000
8.8 | FF-EAF-02 | No. | 1 | 53000 | 3000 | 1 | 53000 | 1 | 3000 | 56000
8.9 | TF-EAF-01 | Nos. | 5 | 27000 | 3000 | 1 | 27000 | 1 | 3000 | 30000
8.1 | TF-EAF-02 | Nos. | 5 | 53000 | 3000 | 1 | 53000 | 1 | 3000 | 56000
8.11 | FAF-01 | No. | 1 | 1075000 | 12000 | 1 | 1075000 | 1 | 12000 | 1087000
9 | Supply, fabrication and installation of machine made G.I sheet metal duct different sections supply, return, fresh & exhaust air including plenums, splitter dampers, guide vanes, flexible duct connector / connection, access door, transformation, plenums chambers, wooden frame, anchors supports & hangers complete in all respects ready to operate as per drawings, specification, instruction of Consultant. (for basement, MAHUs Room & Roof Area only) | Sqft | 7450 | 375 | 70 |  | 0 | 0 | 0 | 0
10 | Supply & installation of 3/4" thick adhesive rubber foam (XLPE) insulation with aluminum foil over fresh air duct only, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.. (for MAHUs Room only) | Sqft | 6166 | 480 | 40 |  | 0 | 0 | 0 | 0
11 | Supply and Installation of acoustical duct sound liner (adhesive with aluminum facing 19mm thick) in supply air duct complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Sqft | 5900 | 485 | 40 |  | 0 | 0 | 0 | 0
12 | Supply, fabrication and installation of pre-insulated ductwork of polyurethane foam panel with 52 Kg/m3 density, 20 mm thickness, coated on both sides with 80 micron thick aluminum foil complete with a 2 g/m2 layer for internal duct work including manufacturer's aluminum hardware glue, Hot Dipped galvanized hangers and supports, flexible duct connection, wooden frame, etc. Complete in all respects ready to operate as per drawings, specification and as per instruction of consultant. (for Floor Areas only) | Sqft | 49811 | 415 | 70 | 21320 | 8847800 | 15610.7 | 1092749 | 9940549
13 | Supply & installation of aluminum fabricated powder coated Fresh & Exhaust Air louvers including supply of wooden frame, rain protection sheet bird mesh etc complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Sqin | 21732 | 35 | 5 |  | 0 | 0 | 0 | 0
14 | Supply, Installation of Aluminum fabricated, powder coated Grills, Diffusers and Registers for supply air, return air, exhaust air & fresh air of different sizes (Grade A ) wooden frame, supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | [5 empty] | 0 | 0 | 0 | 0
14.1 | Supply, Return, Fresh, Exhaust Air Diffuser with Damper | Sqin | 54905 | 35 | 5 |  | 0 | 0 | 0 | 0
14.2 | Supply, Return, Fresh & Exhaust Air Grills / Transfer Grills | Sqin | 88163 | 35 | 5 |  | 0 | 0 | 0 | 0
14.3 | Supply, Return, Fresh & Exhaust Air Registers | Sqin | 550 | 35 | 5 |  | 0 | 0 | 0 | 0
14.4 | S.S. Wire Mesh with G.I Frame | Sqin | 70356 | 10 | 2 |  | 0 | 0 | 0 | 0
14.5 | Swirl Diffuser with Damper | [5 empty] | 0 | 0 | 0 | 0
i. | 12" dia | Nos. | 650 | 12500 | 500 |  | 0 | 0 | 0 | 0
14.5 | Supply & Return Air Linear Slot 6000 Series | [5 empty] | 0 | 0 | 0 | 0
i. | 2 Slot of 1" | Rft | 292 | 4750 | 300 |  | 0 | 0 | 0 | 0
14.6 | Supply & Return Air Linear Bar Grill 4000 Series | [5 empty] | 0 | 0 | 0 | 0
i. | 10" width | Rft | 20 | 4750 | 400 |  | 0 | 0 | 0 | 0
14.7 | Disc Valves | [5 empty] | 0 | 0 | 0 | 0
i. | 6" Dia | Nos. | 107 | 3000 | 300 |  | 0 | 0 | 0 | 0
15 | Supply & installation of flexible duct including hangers, jubilee clamp complete in all respects as per specification, drawings & as per instruction of consultant. | [5 empty] | 0 | 0 | 0 | 0
15.1 | 6" Dia | Rft | 25 | 450 | 100 |  | 0 | 0 | 0 | 0
16 | Supply & installation of butterfly damper for above flexible duct with gas kits, nut bolts, complete in all respects, ready to operate as per specification, drawings & as per instruction of Consultant. | [5 empty] | 0 | 0 | 0 | 0
16.1 | 6" Dia | Nos. | 5 | 1500 | 500 |  | 0 | 0 | 0 | 0 |  | 5096
17 | Supply, fabrication & installation of pre-insulated Volume Control Damper, blades to be constructed with extruded aluminum in airfoil shape with thermal isolation gape & shall have seals, pvc / aluminum profiles duct connection at both end etc. complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | Sqin | 53835 | 45 | 8 | 12468 | 561060 | 12468 | 99744 | 660804 |  | 5824
18 | Supply & installation of Volume Control Damper in 16 SWG G.I sheet metal with gas kits, nut bolts, complete in all respects, ready to operate as per specification, drawings & as per instruction of Consultant. | Sqin | 550 | 32 | 5 |  | 0 | 0 | 0 | 0 |  | 5200
19 | Supply, Installation of Motorized Damper with gas kits, nut bolts, including pressure transmeter, controller & control wiring, complete in all respects, ready to operate as per specification, drawings & as per instruction of Consultant. | Sqin | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 5200
20 | Supply and installation of Back Draft Damper in MS Sheet with gas kits, nut botls. complete in all respects ready to operate as per specification, drawings & as per instruction of Consultant. | Sqin | 5702 | 28 | 5 |  | 0 | 0 | 0 | 0 |  | 21320
21 | Supply and installation of Fire Damper with linkage & fuse complete in all respects ready to operate as per specification, drawings & as per instruction of Consultant. | Sqin | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
22 | Supply & installation of fire stop material (for passive fire fighting / smoke barrier) in all MEP openings and penetrations, either in slab or wall, complete in all respects, ready to operate as per fire stopper recommended material, and as per instruction of Consultant. | Lot | 1 | 45000 | 15000 |  | 0 | 0 | 0 | 0
23 | Supply, Installation, Testing and Commissioning of allied electrical works for ACMV Systems including Motor Control Centre, MCCs complete in all respects including weather proof sheet metal cabinet, bus bars, internal wiring, earth strip, connector strip, MCB, MCCB, Control fuses, magnetic connector, Overload relay, indication lights, voltmeter, ammeter, under voltage, phase reversible, phase failure device, selector switch, related civil works etc. complete in all respects as per schedule, specifications, drawings & as per instructions of | [5 empty] | 0 | 0 | 0 | 0
23.1 | MCC-01 (basement ventilation fans) | Job. | 1 | 415000 | 35000 |  | 0 | 0 | 0 | 0
24 | Supply, installation, testing and commissioning of interconnecting wiring, control wiring, power wiring from MCC, DB, panel to HVAC equipment with isolation switches near the equipment, including civil works related to complete wiring works etc. complete in all respects as per schedule, specifications, drawings & as per instructions of Consultant | Lot | 1 | 665000 | 45000 |  | 0 | 0 | 0 | 0
25 | Supply, installation, testing and commissioning of perforated cable trays made with 1.63mm SWG (16 Guage) painted G.I Sheet, including hanger, bracket, proper bends, cover of trays shall be made with 1.22mm SWG (18 guage) painted G.I sheet, complete in all respects, ready to operate as per schedule, specification, drawings and as per instruction of Consultant. | Lot | 1 | 515000 | 45000 |  | 0 | 0 | 0 | 0
26 | Supply, Installation, testing and commissioning of uPVC (Sch 40.) drain pipe insulated with 3/8" thick rubber foam insulation including clamps, bends, tees, drain plugs, sockets, protection treatment, PVC tape wrapping, hanger & supports etc, complete in all respects as per specifications, drawings & as per instructions of Consultant. | [5 empty] | 0 | 0 | 0 | 0
26.1 | 1" dia | Rft | 210 | 360 | 100 |  | 0 | 0 | 0 | 0
26.2 | 1.25" dia | Rft | 210 | 4515 | 100 |  | 0 | 0 | 0 | 0
26.3 | 1.5" dia | Rft | 40 | 475 | 125 |  | 0 | 0 | 0 | 0
26.4 | 2" dia | Rft | 198 | 560 | 150 |  | 0 | 0 | 0 | 0
27 | Painting & Identification work on chilled, cooling water pipes & exhaust duct, supports, hangers etc. complete in all respects with one coat of ICI make Red lead oxide primer & two coats of ICI make enamel paint as per instruction of Consultant. | Job. | 1 | 15000 | 45000 |  | 0 | 0 | 0 | 0
28 | Testing, balancing and commissioning of water & air side of the system (from independent agency) complete in all respects including flow measurement & balancing, temp, pressure, electrical data of related equipment etc. as per specifications and as per instructions of Consultant. | Job. | 1 | 0 | 90000 |  | 0 | 0 | 0 | 0
29 | Making of Shop drawings on Auto CAD latest version with section details and equipment foundation details, as per instruction of Consultant. | Job. | 1 | 10000 | 15000 |  | 0 | 0 | 0 | 0
30 | Making of As Built drawings on Auto CAD latest version with Documentation Technical / Operational Manual & LOG Book for each equipment as per instruction of Consultant. | Job. | 1 | 5000 | 10000 |  | 0 | 0 | 0 | 0
Total Cost of ACMV Works Rs. | [9 empty] | 15526353
78840000
[12 empty] | 8% SRB | 6307200
72532800
[12 empty] | 7% tx | 5077296
67455504
[12 empty] | 30% Mob | 20236651.2
[12 empty] | Rec | 1500000
[12 empty] | Rec | 7000000
[12 empty] | Rec | 8580000
[12 empty] | Rec | 2000000
[12 empty] | Tot rec | 19080000
[12 empty] | rem | 1156651.2
[10 empty] | mohsin traders chq | 1000000 |  | cash chq | 1050000
[10 empty] | mohsin traders chq | 1900000 |  | cash chq | 895000
[10 empty] | mohsin traders chq | 1900000 |  | cash chq | 950000
[10 empty] | mohsin traders chq | 1500000 |  | cash chq | 875000
[10 empty] | mohsin traders chq | 700000 |  | cash chq | 1350000
[11 empty] | 7000000 |  | cash chq | 975000
[13 empty] | cash chq | 1500000
[13 empty] | cash chq | 985000
8580000
15580000

## Finance
Financial Summary for the project Meezan Bank
|  |  |  | Contract Value | 78840000
|  |  |  | Less 8% SRB | 6307200
72532800
|  |  |  | Less 7% WHT | 5077296
|  |  |  | Net deal | 67455504
|  |  |  | Mob adv 30% | 20236651.2
|  |  |  | Adv received | 19830000
|  |  |  | Advance remaining | 406651.2
Receiving details
Bill # | Date | Submitted Amount | Verified Amount | Receiving date | Chq amount
1 | 2023-11-28 | 15526353
Total receiving till todate |  |  |  |  | 0
Net Receivable amount |  | 0 | 0 |  | 47625504