## Main summary
Retention Money |  | IPC 50 |  | IPC 49 |  | IPC 48 |  | IPC 47 |  | IPC 11 |  | IPC 10 |  | IPC 09 |  | IPC 08
Verified amount | 2525356 | Verified amount | 6275375 | Verified amount | 8517689 | Verified amount | 1662697 | Verified amount | 7841449 | Verified amount | 2325902 | Verified amount | 2060756 | Verified amount | 1104253 | Verified amount | 5226462
G.I Sheet Deduction | 0 | G.I Sheet Deduction | 195368 | G.I Sheet Deduction | 299100 | G.I Sheet Deduction | 0 | G.I Sheet Deduction | 184922 | G.I Sheet Deduction | 0 | G.I Sheet Deduction | 0 | G.I Sheet Deduction |  | G.I Sheet Deduction
| 2525356 |  | 6080007 |  | 8218589 |  | 1662697 |  | 7656527 |  | 2325902 |  | 2060756 |  | 1104253 |  | 5226462
Retention money 5% | 0 | Retention money 5% | 313768.75 | Retention money 5% | 425884.45 | Retention money 5% | 83134.85 | Retention money 5% | 392072.45 | Retention money 5% | 116295.1 | Retention money 5% | 103037.8 | Retention money 5% | 55212.65 | Retention money 5% | 261323.1
GCM 8% | 0 | GCM 8% | 486400.56 | GCM 8% | 657487.12 | GCM 8% | 133015.76 | GCM 8% | 612522.16 | GCM 8% | 186072.16 | GCM 8% | 164860.48 | GCM 8% | 88340.24 | GCM 8% | 418116.96
Income Tax 7.5% | 189401.7 | Income Tax 7.5% | 456000.525 | Income Tax 7.5% | 616394.175 | Income Tax 7.5% | 124702.275 | Income Tax 7.5% | 574239.525 | Income Tax 7.5% | 174442.65 | Income Tax 7.5% | 154556.7 | Income Tax 7.5% | 82818.975 | Income Tax 7.5% | 391984.65
Total Deductions | 189401.7 | Total Deductions | 1256169.835 | Total Deductions | 1699765.745 | Total Deductions | 340852.885 | Total Deductions | 1578834.135 | Total Deductions | 476809.91 | Total Deductions | 422454.98 | Total Deductions | 226371.865 | Total Deductions | 1071424.71
Net Payable Amount | 2335954.3 | Net Payable Amount | 4823837.165 | Net Payable Amount | 6518823.255 | Net Payable Amount | 1321844.115 | Net Payable Amount | 6077692.865 | Net Payable Amount | 1849092.09 | Net Payable Amount | 1638301.02 | Net Payable Amount | 877881.135 | Net Payable Amount | 4155037.29
Received amount | 2329611 | Received amount | 4498520 | Received amount | 7519228 | Received amount | 2610094 | Received amount | 6243243 | Received amount | 1560812 | Received amount | 1296810.714 | Received amount | 933750 | Received amount | 3850691
Remaining amount | 6343.3 | Remaining amount | 325317.165 | Remaining amount | -1000404.745 | Remaining amount | -1288249.885 | Remaining amount | -165550.135 | Remaining amount | 288280.09 | Remaining amount | 341490.306 | Remaining amount | -55868.865 | Remaining amount | 304346.29

## summ
Surgical Building IPC-51 | 214183.735
Surgical Building IPC-52 | 871349.16
Surgical Building (Waiting Area) | 34658.375
PSHCHIATRY IPC-08 | -119959.135
PSHCHIATRY IPC-10 | -228508.305
PSHCHIATRY IPC-11 | -156913.15
PSHCHIATRY IPC-12 | 448863.165
Total remaining | 1063673.845

## Main Building
Patient Aid Foundation (PAF)
Construction of New Surgical & OPD Complex at JPMC,Karachi
PLUMBING & HVAC WORKS
Summary of Bills
Description |  |  | Billed Amount
IPC - 20
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  | 724832
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 6107054
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | 2961315
Total Amount Received against IPC - 20 |  |  | 9793201
Retention Money 5% |  |  | 489660.05
Mobilization Advance 5% |  |  | 489660.05
GCM 8% |  |  | 783456.08
Income Tax 7.5% |  |  | 734490.075
Total Deductions |  |  | 2497266.255
Net Payable Amount |  |  | 7295934.745
IPC - 26
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  | 8169122.55
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | 1476445
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 1155005.86
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 1562807.66
Total Amount Received against IPC - 26 |  |  | 12363381.07
Retention Money 5% |  |  | 618169.0535
Mobilization Advance 5% |  |  | 618169.0535
GCM 8% |  |  | 989070.4856
Income Tax 7.5% |  |  | 927253.5802
Total Deductions |  |  | 3152662.1729
Net Payable Amount |  |  | 9210718.8972
IPC - 27
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
TOTAL COST OF PLUMBING WORKS Addtional ITEMS
COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 192962.6
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Total Amount Received against IPC - 27 |  |  | 192962.6
Retention Money 5% |  |  | 9648.13
Mobilization Advance 5% |  |  | 9648.13
GCM 8% |  |  | 15437.008
Income Tax 7.5% |  |  | 14472.195
Total Deductions |  |  | 49205.463
Net Payable Amount |  |  | 143757.137
IPC - 28
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  | 371475.41
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 14824
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | 45500
EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | 843676
TOTAL COST OF HVAC WORKS B.O.Q ITEMS
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Total Amount Received against IPC - 28 |  |  | 1275475.41
Retention Money 5% |  |  | 63773.7705
Mobilization Advance 5% |  |  | 63773.7705
GCM 8% |  |  | 102038.0328
Income Tax 7.5% |  |  | 95660.6557
Total Deductions |  |  | 325246.2295
Net Payable Amount |  |  | 950229.1804
IPC - 29
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 3852994.23
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 3023296.54
Total Amount |  |  | 6876290.77
RECOVERY OF OFM MATERIAL HVAC |  |  | 733809
Total Amount Received against IPC - 29 |  |  | 6142481.77
Retention Money 5% |  |  | 307124.0885
Mobilization Advance 5% |  |  | 307124.0885
GCM 8% |  |  | 491398.5416
Income Tax 7.5% |  |  | 460686.1327
Total Deductions |  |  | 1566332.8513
Net Payable Amount |  |  | 4576148.9186
IPC - 30
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  | 466489
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 58839
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 2571293.61
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 835199.8
Total Amount Received against IPC - 30 |  |  | 3931821.41
RECOVERY OF OFM MATERIAL HVAC |  |  | 213078.05
RECOVERY OF OFM MATERIAL PLUMBING |  |  | 561300
TOTAL OF OFM MATERIAL AMOUNT |  |  | 774378.05
Total Amount Received against IPC - 30 |  |  | 3157443.36
Retention Money 5% |  |  | 157872.168
Mobilization Advance 5% |  |  | 157872.168
GCM 8% |  |  | 252595.4688
Income Tax 7.5% |  |  | 236808.252
Total Deductions |  |  | 805148.0568
Net Payable Amount |  |  | 2352295.3032
IPC - 31
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  | 1424566.08
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 0
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | 58300
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | 295400
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | 1071515
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 0
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 3691841.98
Total Amount Received against IPC - 31 |  |  | 6541623.06
RECOVERY OF OFM MATERIAL HVAC |  |  | 0
RECOVERY OF OFM MATERIAL PLUMBING |  |  | 177500
TOTAL OF OFM MATERIAL AMOUNT
Total Amount Received against IPC - 31 |  |  | 6719123.06
Retention Money 5% |  |  | 335956.153
Mobilization Advance 5% |  |  | 335956.153
GCM 8% |  |  | 537529.8448
Income Tax 7.5% |  |  | 503934.2295
Total Deductions |  |  | 1713376.3803
Net Payable Amount |  |  | 5005746.6797
IPC - 34
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  | 1352002.85
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 24486
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | 216284
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | 325250
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | 0
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 2956878.68
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 419818.32
Total Amount Received against IPC - 34 |  |  | 5294719.85
RECOVERY OF OFM MATERIAL HVAC |  |  | 602592
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Total Amount Received against IPC - 34 |  |  | 4692127.85
Retention Money 5% |  |  | 234606.3925
Mobilization Advance 5% |  |  | 234606.3925
GCM 8% |  |  | 375370.228
Income Tax 7.5% |  |  | 351909.5888
Total Deductions |  |  | 1196492.6018
Net Payable Amount |  |  | 3495635.2483
IPC - 35
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  | 1724607.72
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 3383
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | 48725.82
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | 168848
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 1425294.8
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2 |  |  | 473508
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 12375.96
Total Amount Received against IPC - 35 |  |  | 3856743.3
RECOVERY OF OFM MATERIAL HVAC |  |  | 80576.8
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Total Amount Received against IPC - 35 |  |  | 3776166.5
Retention Money 5% |  |  | 188808.325
Mobilization Advance 5% |  |  | 188808.325
GCM 8% |  |  | 302093.32
Income Tax 7.5% |  |  | 283212.4875
Total Deductions |  |  | 962922.4575
Net Payable Amount |  |  | 2813244.0425
IPC - 36 |  |  | 0
IPC - 37
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Total Amount Received against IPC - 37 |  |  | 6418852
RECOVERY OF OFM MATERIAL HVAC |  |  | 169983
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Total Amount Received against IPC - 37 |  |  | 6248869
Income Tax 7.5% |  |  | 468665.175
Amount After tax |  |  | 5780203.825
Mobilization Advance 5% |  |  | 289010.1913
Retention money 5% |  |  | 289010.1913
GCM 8% |  |  | 462416.306
Total Deductions |  |  | 1040436.6885
Net Payable Amount |  |  | 4739767.1365
IPC - 39
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  | 70250
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 208330
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 98752
Total Amount Received against IPC - 39 |  |  | 377332
RECOVERY OF OFM MATERIAL HVAC
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Total Amount Received against IPC - 39 |  |  | 377332
Income Tax 7.5% |  |  | 28299.9
Amount After tax |  |  | 349032.1
Mobilization Advance 5% |  |  | 17451.605
Retention money 5% |  |  | 17451.605
GCM 8% |  |  | 27922.568
Total Deductions |  |  | 62825.778
Net Payable Amount |  |  | 286206.322
IPC - 40
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  | 826565
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | 430816
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 5354320
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 320142
Total Amount Received against IPC - 40 |  |  | 6931843
RECOVERY OF OFM MATERIAL HVAC |  |  | 124383
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Total Amount Received against IPC - 40 |  |  | 6807460
Income Tax 7.5% |  |  | 510559.5
Amount After tax |  |  | 6296900.5
Mobilization Advance 5% |  |  | 314845.025
Retention money 5% |  |  | 314845.025
GCM 8% |  |  | 503752.04
Total Deductions |  |  | 1133442.09
Net Payable Amount |  |  | 5163458.41
IPC - 42
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 3064107
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 427500
Total Amount Received against IPC - 42 |  |  | 3491607
RECOVERY OF OFM MATERIAL HVAC
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Total Amount Received against IPC - 42 |  |  | 3491607
Mobilization Advance 5% |  |  | 174580.35
Retention money 5% |  |  | 174580.35
GCM 8% |  |  | 279328.56
Income Tax 7.5% |  |  | 261870.525
Total Deductions |  |  | 890359.785
Net Payable Amount |  |  | 2601247.215
IPC - 43
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 24353979
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Total Amount Received against IPC - 43 |  |  | 24353979
RECOVERY OF OFM MATERIAL HVAC
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Total Amount Received against IPC - 42 |  |  | 24353979
Mobilization Advance 5% |  |  | 1217698.95
Retention money 5% |  |  | 1217698.95
GCM 8% |  |  | 1948318.32
Income Tax 7.5% |  |  | 1826548.425
Total Deductions |  |  | 6210264.645
Net Payable Amount |  |  | 18143714.355
Less Adhoc (now complete) |  |  | 2500000
15643714.355
Payment received (this payment given to bilal bhai he used this cash is office for misc click on it for details |  |  | 9775000
Service bank tax charges on above 10 Million payment deducted |  |  | 300000
given to taheriya sanitry in syedena tradind acc then given to nadeem bhai in his share |  |  | 1047396
given to taheriya sanitry in syedena tradind acc then given to nadeem bhai in his share |  |  | 1071018
given to taheriya sanitry in syedena tradind acc then given to nadeem bhai in his share |  |  | 1490814
given to taheriya sanitry in syedena tradind acc then given to nadeem bhai in his share |  |  | 1958826
given to taheriya sanitry in syedena tradind acc then given to nadeem bhai in his share |  |  | 431946
given to islamuddin & Sons |  |  | 158880
[7 empty] | 8000000 | 9700000
[7 empty] | 600000 | 291000
Remaining or extra paid |  |  | -590165.645 | Adjusted in IPC 44 Billing (main Building)
IPC - 44 | [7 empty] | 2512666
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | [7 empty] | 1581045
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | [5 empty] | 931621
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS |  |  |  |  | 3160586
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS |  |  |  |  | 1581045
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS |  |  |  |  | 1579541
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 13237538
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Gross Work Done Amount |  |  | 13237538
RECOVERY OF OFM MATERIAL HVAC |  |  | 2370257
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Net Work Done Amount |  |  | 10867281
Mobilization Advance 5% |  |  | 543364.05
Retention money 5% |  |  | 661876.9
GCM 8% |  |  | 869382.48
Income Tax 7.5% |  |  | 815046.075
Total Deductions |  |  | 2889669.505
Net Payable Amount |  |  | 7977611.495
Extra received in IPC 43 Billing |  |  | 593485
Extra received in IPC 6 Food court Billing |  |  | 668548
Extra received in IPC 42 payment
Remaining Amount |  |  | 6715578.495
Receiving Details
Fateh Steel |  |  | 128261
Fateh Steel |  |  | 137768 |  |  |  |  | 278839
Fateh Steel |  |  | 139084 |  |  |  |  | 326562
Burhani Tradeers |  |  | 210000
Iqbal Sons |  |  | 300000
Danish International |  |  | 300000
Bilal bhai name chq then give 320000 to easten and 180,000 to jes |  |  | 500000
Bilal bhai name chq |  |  | 500000
cash taken by bilal habib |  |  | 4600000
Tax amount on abouve 4,600,000 |  |  | 227027
Extra Paid |  |  | -326561.505
IPC - 45
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  | 755720.81
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 5829907.92
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2 |  |  | 2646623
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Gross Work Done Amount |  |  | 9232251.73
RECOVERY OF OFM MATERIAL HVAC
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Net Work Done Amount |  |  | 9232251.73
Mobilization Advance 5% |  |  | 461612.5865
Retention money 5% |  |  | 461612.5865
GCM 8% |  |  | 738580.1384
Income Tax 7.5% |  |  | 692418.8797
Total Deductions |  |  | 2354224.1911
Net Payable Amount |  |  | 6878027.5389
Receiving Details
Received Open chq |  |  | 850000
Received Open chq |  |  | 650000
Received Open chq |  |  | 750000
Received Open chq |  |  | 700000
Received Open chq |  |  | 800000
Received Open chq |  |  | 750000
Received Open chq |  |  | 600000
Received Open chq |  |  | 900000
Tax Amount |  |  | 278839
Extra paid in IPC 44 |  |  | 326562
Remaining |  |  | 272626.5389
IPC - 46
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 6644406
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Gross Work Done Amount |  |  | 6644406
RECOVERY OF OFM MATERIAL HVAC |  |  | 536112
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Net Work Done Amount |  |  | 6108294
Mobilization Advance 5% |  |  | 0
Retention money 5% |  |  | 332220.3
GCM 8% |  |  | 488663.52
Income Tax 7.5% |  |  | 458122.05
Total Deductions |  |  | 1279005.87
Net Payable Amount |  |  | 4829288.13
Add Excess Mob advance deducted |  |  | 924181
Net Payable Amount |  |  | 5753469.13
Receiving Details
Chq Rs (this chq hod with bilal bhai) 04-06-20 |  |  | 500000
Chq Rs (this chq hod with bilal bhai) 04-06-20 |  |  | 500000
Danish International |  |  | 300000
Chq in the name of Iqbal Sons |  |  | 400000
Chq in the name of Naseer uddin (Fateh Steel) |  |  | 390730
Orient water services against chemical and by pas feeder in zmv deal |  |  | 120528
Khan brothers for split valve deal in jpmc |  |  | 315900
Hold with bilal bhai |  |  | 500000
Hold with bilal bhai |  |  | 500000
Shabbir Brothers |  |  | 400000
Hold with bilal bhai |  |  | 700000
Nadeem Baloch |  |  | 306000
Tax deduction on 2,000,000 payment given to bilal bhai |  |  | 75000
Tahiri Sanitry |  |  | Awaiting for invoice
Islamuddin & Sons |  |  | Awaiting for invoice
Tax deduction on 700,000 payment given to bilal bhai |  |  | 22400
Islamuddin & Sons |  |  | 89073
2nd in the name of Iqbal Sons |  |  | 200000
Fateh steel |  |  | 250080
Cash cheque |  |  | 130745
Total receivings Rs |  |  | 5700456
Remaining amount |  |  | 53013.13
IPC - 47 |  |  |  |  | IPC - 47
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  |  |  | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  | TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS |  |  | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS |  |  | PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS |  |  | HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 7841449 |  | TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 9105284
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2 |  |  |  |  | TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  | TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Gross Work Done Amount |  |  | 7841449 |  | Gross Work Done Amount |  |  | 9105284
RECOVERY OF OFM MATERIAL HVAC |  |  |  |  | RECOVERY OF OFM MATERIAL HVAC
RECOVERY OF OFM MATERIAL PLUMBING |  |  |  |  | RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT |  |  |  |  | TOTAL OF OFM MATERIAL AMOUNT
Net Work Done Amount |  |  | 7841449 |  | Net Work Done Amount |  |  | 9105284
Mobilization Advance 5% |  |  | 0 |  | IPC -08 |  |  | 5226462
GI SHEET Deduction |  |  | 184922 |  | Grand Total |  |  | 14331746
Remaining amount |  |  | 7656527 | 7656527 | Mobilization Advance 5% |  |  | 0
Retention money 5% |  |  | 392072.45 | 612522.16 | Retention money 5% |  |  | 716587.3
GCM 8% |  |  | 612522.16 |  | GCM 8% |  |  | 1146539.68
Income Tax 7.5% |  |  | 574239.525 |  | Income Tax 7.5% |  |  | 1074880.95
Total Deductions |  |  | 1578834.135 |  | Total Deductions |  |  | 2938007.93
Net Payable Amount |  |  | 6077692.865 |  | Net Payable Amount |  |  | 11393738.07
Received amount |  |  | 6243243 | 304347 | Add JPMC Mosque Adhoc 60% of 1395,000 |  |  | 837000
Grand Total |  |  | -165550.135 |  | Total Amount Rs. |  |  | 12230738.07
Receiving Details
Receiving Details
Hold with bilal bhai |  |  | 900000
Hold with bilal bhai |  |  | 900000 |  | Hold with bilal bhai |  |  | 6900000
Hold with bilal bhai |  |  | 900000 | 6000000 | Fateh Steel |  |  | 1000069
Hold with bilal bhai |  |  | 900000 |  | Sultan Trader (Tahiri Sanitry) |  |  | 300000
Hold with bilal bhai |  |  | 900000 |  | M. Hussain & Co. (Tahiri Sanitry) |  |  | 200000
Hold with bilal bhai |  |  | 900000 |  | Iqbal Sons |  |  | 200000
Hold with bilal bhai |  |  | 600000 |  | Cash Cheque |  |  | 400000
Tax charges on above cash chqs |  |  | 243243 |  | Cash Cheque |  |  | 463000
Total receivings Rs |  |  | 6243243 |  | Cash Cheque |  |  | 300000
[5 empty] | Mosque payment Cash Cheque |  |  | 400000
IPC - 48 |  |  |  |  | Mosque payment Cash Cheque |  |  | 437000 | 10600069
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  | Total receivings Rs |  |  | 10600069 | 1630669.07
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS |  |  | Remaining amount |  |  | 1630669.07
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | [5 empty] | 2000000
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | [5 empty] | -369330.93
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 1662697
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2 |  |  |  |  | 15000000
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  | 1500000
Gross Work Done Amount |  |  | 1662697
RECOVERY OF OFM MATERIAL HVAC
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Net Work Done Amount |  |  | 1662697
Mobilization Advance 5% |  |  | 0
Retention money 5% |  |  | 83134.85
GCM 8% |  |  | 133015.76
Income Tax 7.5% |  |  | 124702.275
Total Deductions |  |  | 340852.885
Net Payable Amount |  |  | 1321844.115
Receiving Details
received adhoc payment 75% against IPC 48 (Given to Fateh Steel) |  |  | 1000058
received adhoc payment 75% against IPC 48 (Given to Fateh Steel) |  |  | 1000036
received adhoc payment 75% against IPC 48 (Given to Iqbal sons) |  |  | 300000
received adhoc payment 75% against IPC 48 (Given to Danish intl) |  |  | 150000
received adhoc payment 75% against IPC 48 (Given to Katys) |  |  | 150000
10000
[5 empty] | Remaining amount IPC 08 |  |  | 304346
Total receivings Rs |  |  | 2610094 |  | Remaining amount IPC 10 |  |  | 341490
Remaining amount |  |  | -1288249.885 |  | (05% of 24,097,699 ) retention amount released |  |  | 1204885
[5 empty] | Total remaining |  |  | 1850721
Summary of IPC 08, 09, 10, 47 & 47
[5 empty] | Extra paid in IPC 47 |  |  | 165550
IPC 48 remaining amount |  |  | -1288249.885 | 1204885 | Extra paid in IPC 48 |  |  | 1288250
IPC 47 remaining amount |  |  | -165550.135 |  | Extra paid in IPC 09 |  |  | 55869
IPC 08 remaining amount |  |  | 304346.29 |  | Net Remaining bal payable |  |  | 341052
IPC 09 remaining amount |  |  | -55868.865
IPC 10 remaining amount |  |  | 341490.306
(05% of 28376367 ) retention amount released |  |  | 1204885
Net Remaining bal payable |  |  | 341052.711
[5 empty] | 1912899 | 1850721 | 62178
IPC - 49
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  |  |  | 24097699
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  | 1204884.95
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 8517689
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Gross Work Done Amount |  |  | 8517689
RECOVERY OF OFM MATERIAL HVAC
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Net Work Done Amount |  |  | 8517689
LESS OFM |  |  | 299100
Net Work Done Amount |  |  | 8218589
Mobilization Advance 5% |  |  | 0
Retention money 5% |  |  | 425884.45 | ok
GCM 8% |  |  | 657487.12 | ok
Income Tax 7.5% |  |  | 616394.175
Total Deductions |  |  | 1699765.745
Net Payable Amount |  |  | 6518823.255
Receiving Details
Muhammad Raza Associates |  |  | 250000 | 1430000
Mustafa in jpmc copper piping deal |  |  | 200000
PREM ELECTRIC in the forum deal |  |  | 150000
Muhammad Asif |  |  | 150000
Fateh Ali Tajani |  |  | 100000
Arsalan Hussain |  |  | 50000
Haris traders (Noman FCU in the forum deal) |  |  | 180000
Mustafa in js bank shaheen deal) |  |  | 200000
Zafar Ahmed Khan |  |  | 50000
Mehboob Steel Pipe Industry Tube Traders) |  |  | 100000
Humayun Saeed |  |  | 150000
Saqib Enterprise (Shabbir Borhter) |  |  | 207090
Abdul Fahad Ghanchi (JES INStrumentation) |  |  | 300000
NKR in the forum deal |  |  | 390000
Masood Arif & Faiza Masood (Tech automation) |  |  | 400000
S. Abdullah (in js bank shaheen deal) |  |  | 381800
Rehana Rehman |  |  | 150000 |  |  |  | 1000405
Syedna Trading (Tahiri sanitry) |  |  | 500000
Bilal habib |  |  | 550000
Muhammad Ahsan (Flow tab in falcon deal) |  |  | 125000
Zara Engineers( in al hamd fire equipment deal) |  |  | 300000
Mohsin Ashraf (Air Flow) |  |  | 100000
Initially this payment made via Pay order of meezan bank for Gree payment in Indus but it was cancelled then) this payment received and direct transfer in mohsin traders account c/o bilal habib on 28-5-21 |  |  | 2300000
cash Adjustments |  |  | 235338
Total receivings Rs |  |  | 7519228
Remaining amount |  |  | -1000404.745 | Diesel tank installation remaining payment Rs 700,000 will be added in IPC 49
IPC - 50
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 6275375 | 6275375
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Gross Work Done Amount |  |  | 6275375
RECOVERY OF OFM MATERIAL HVAC | [6 empty] | 5630000
RECOVERY OF OFM MATERIAL PLUMBING | [6 empty] | 450400
TOTAL OF OFM MATERIAL AMOUNT | [6 empty] | 422250
Net Work Done Amount |  |  | 6275375 |  |  |  | 4757350
Mobilization Advance 5% |  |  | 0 |  |  | 464807
GI SHEET Deduction |  |  | 195368 |  |  | 349092
Remaining amount |  |  | 6080007 |  |  | 303067
Retention money 5% |  |  | 313768.75 |  |  | 1116966
GCM 8% |  |  | 486400.56
Income Tax 7.5% |  |  | 456000.525
Total Deductions |  |  | 1256169.835
Net Payable Amount |  |  | 4823837.165
Receiving Details |  |  |  | 3500000 | Net amount |  | 3652875
ADHOC Payment received |  |  | 3500000 | 3783783.7838 | Gross amount |  | 2622579
Received payment (this payment given to Fakhri brothers) |  |  | 789240 | 283783.7838 | 7.5% of gross |  | 6275454
cash adjustments |  |  | 173888 | 141891.8919 | diveded by 2
35392
Total receivings Rs |  |  | 4498520
Remaining amount |  |  | 325317.165
IPC - 51
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 4182733
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Gross Work Done Amount |  |  | 4182733
RECOVERY OF OFM MATERIAL HVAC
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Net Work Done Amount |  |  | 4182733
Mobilization Advance 5% |  |  | 0
Retention money 5% |  |  | 209136.65
GCM 8% |  |  | 334618.64
Income Tax 7.5% |  |  | 313704.975
Total Deductions |  |  | 857460.265
Total Payable Amount |  |  | 3325272.735
Receiving Details
Transfer to Mohsin Traders account (care off Bilal bhai) |  |  | 100000 |  | 100000
Transfer to Mohsin Traders account (care off Bilal bhai) |  |  | 125000 |  | 108108.1081
To Fakhri Against GST invoice |  |  | 1100934 |  | 8108.1081
To Madina steel Against GST invoice |  |  | 1250000 |  | 4054.0541
To Fakhri Against GST invoice |  |  | 481033
?????????????? |  |  | 45000
Tax adjustments on 125,000 & 100,000 |  |  | 9122
Total receivings Rs |  |  | 3111089
Remaining amount |  |  | 214183.735
Waiting Area
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 641189
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Gross Work Done Amount |  |  | 641189
RECOVERY OF OFM MATERIAL HVAC
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Net Work Done Amount |  |  | 523955
Mobilization Advance 5% |  |  | 0
Retention money 5%
GCM 8%
Income Tax 7.5% |  |  | 39296.625
Total Deductions |  |  | 39296.625
Total Payable Amount |  |  | 484658.375
Receiving Details
Transfer to Yasir siddique account (care off Bilal bhai) |  |  | 450000
128882.975
Total receivings Rs |  |  | 450000
Remaining amount |  |  | 34658.375
IPC-52 (Final Bill)
TOTAL COST OF Plumbing WORKS B.O.Q ITEMS |  |  | 542400
TOTAL COST OF Plumbing WORKS B.O.Q ITEMS |  |  | 330406
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Gross Work Done Amount
RECOVERY OF OFM MATERIAL HVAC |  |  | 5135263
RECOVERY OF OFM MATERIAL PLUMBING |  |  | 22899
TOTAL OF OFM MATERIAL AMOUNT
Net Work Done Amount |  |  | 6030968
LESS OFM |  |  | 1316520
Net Work Done Amount |  |  | 4714448
Mobilization Advance 5% |  |  | 0
Retention money 5% |  |  | 301548.4
GCM 8% |  |  | 377155.84
Income Tax 7.5% |  |  | 353583.6
Total Deductions |  |  | 1032287.84
Total Payable Amount |  |  | 3682160.16
Receiving Details
Transfer to Mohsin traders (care off Bilal bhai) |  |  | 1000000
To Madina steel Against GST invoice |  |  | 1250000
Tax adjustments |  |  | 60811
Transfer to Mohsin traders (care off Bilal bhai) |  |  | 500000
Total receivings Rs |  |  | 2810811
Remaining amount |  |  | 871349.16
FROM THIS BILL IPC 44 RETENTION MONEY DEDUCTED ON WORK DONE AMOUNT BEFORE THIS BILL RETENTION MONEY ALWAY DEDUCTED ON NET WORK DONE AMOUNT

## Psychiatry
CONSOLIDATED SUMMARY FOR THE PROJECT PSYCHIATRY DEPARTMENT - JPMC
Verified Bills (total 04 nos IPCs) | 11892770
LESS OFM | 5119523
Gross Payable | 6773247
Deductions
Mobilization advance 12% | 1427132.4
Retention 05% | 594638.5
Income Tax | 507993.525
Total Deductions | 2529764.425
Gross Payable | 4243482.575
Received | 4300000
Net Payable | -56517.425
SUMMARY FOR THE MOBILIZATION ADVANCE
Total Advance | 4300000
12% Deduct in IPCs (on gross amount before OFM) | 1427132.4
Remaining | 2872867.6
IPC-8 (PSYCHIATRY DEPARTMENT)
Net Work Done Amount | 3617793
LESS OFM | 1217722
Net Work Done Amount | 2400071 |  | Verified Bills | 11892770
Mobilization Advance 12% | 434135.16 |  | Less OFM | 5119523
Retention money 5% | 180889.65 |  |  | 6773247
GCM 8%
Income Tax 7.5% | 180005.325 |  | Mobilization Advance 10% | 677324.7
Total Deductions | 795030.135 |  | Retention money 5% | 594638.5
Total Payable Amount | 1605040.865 |  | Income Tax 7.5% | 507993.525
Receiving Details |  |  | Total Deductions | 1779956.725
Transfer to Ashfaq Ahmed account (care off Bilal bhai) | 350000 |  | Payable | 4993290.275
Cheque given to Shabbir Hussain Diwan | 500000 |  | Received | 4300000
Cheque given to Nadeem Iqbal | 500000 |  | Net Payable | 693290.275
Transfer to Mohsin Traders account (care off Bilal bhai) | 375000
1725000
|  | 1864864.8649 |  |  |  | -56517.425
Total receivings Rs | 1725000 | 139864.8649
Remaining amount | -119959.135 | 69932.4324
IPC-10 (PSYCHIATRY DEPARTMENT)
Net Work Done Amount | 1783974
LESS OFM | 1189631
Net Work Done Amount | 594343
Mobilization Advance 12% | 214076.88
Retention money 5% | 89198.7
GCM 8%
Income Tax 7.5% | 44575.725
Total Deductions | 347851.305
Total Payable Amount | 246491.695
Receiving Details
Transfer to Mohsin Traders account (care off Bilal bhai) | 475000
Total receivings Rs | 475000 | 475000
Remaining amount | -228508.305 | 513513.5135
38513.5135
IPC-11 (PSYCHIATRY DEPARTMENT) |  | 19256.7568
TOTAL COST OF Plumbing WORKS B.O.Q ITEMS | 1268695
TOTAL COST OF Plumbing WORKS B.O.Q ITEMS | 1320435
Net Work Done Amount | 2589130
LESS OFM | 553196
Net Work Done Amount | 2035934
Mobilization Advance 12% | 310695.6
Retention money 5% | 129456.5
GCM 8%
Income Tax 7.5% | 152695.05
Total Deductions | 592847.15
Total Payable Amount | 1443086.85
Receiving Details
1793461.52
Transfer to Bilal bhai account | 500000
Transfer to Madina steel works | 300000
Open crossed chq | 500000
Transfer to Madina steel works | 300000
1000000
Total receivings Rs | 1600000 | 1081081.0811
Remaining amount | -156913.15 | 81081.0811
40540.5405
IPC-12 (PSYCHIATRY DEPARTMENT)
TOTAL COST OF Plumbing WORKS B.O.Q ITEMS | 3005219
TOTAL COST OF Plumbing WORKS EXTRA Work | 896654
Net Work Done Amount | 3901873
LESS OFM | 2158974
Net Work Done Amount | 1742899
Mobilization Advance 12% | 468224.76
Retention money 5% | 195093.65
GCM 8%
Income Tax 7.5% | 130717.425
Total Deductions | 794035.835
Total Payable Amount | 948863.165 |  | 300000
Receiving Details
Transfer to Mohsin Traders account (care off Bilal bhai) | 500000
|  |  | Mod adv received | 4300000
|  |  | recovered | 1427132.4
2872867.6
Total receivings Rs | 500000 | 500000
Remaining amount | 448863.165 | 540540.5405
40540.5405
20270.2703
WHT on Cash Payment
[5 empty] | IPC # | Net amount | Gross amount | Tax 7.5% | half/ half
[5 empty] | IPC-51 | 100000 | 108108.1081 | 8108.1081 | 4054.0541
[5 empty] | IPC-52 | 1000000 | 1081081.0811 | 81081.0811 | 40540.5405
[5 empty] | IPC-08 | 1725000 | 1864864.8649 | 139864.8649 | 69932.4324
[5 empty] | IPC-10 | 475000 | 513513.5135 | 38513.5135 | 19256.7568
[5 empty] | IPC-11 | 1000000 | 1081081.0811 | 81081.0811 | 40540.5405
[5 empty] | IPC-12 | 500000 | 540540.5405 | 40540.5405 | 20270.2703

## Retention
JPMC Retention Money amount upto 5th Floor (IPC-50)
Total Amount |  |  | 6255597 | Click to listen Kiani Voice
Less already received amount |  |  | 1204885 | Adjusted in IPC 47
Remaining amount |  |  | 5050712 |  | Retention Working | Main building | Food Court | Mosque | PSHCHITRY
[5 empty] | Total amount with hold | 7600459.5888 | 1043611.948 | 40153.35 | 594638.5
[5 empty] | Received | 3534496 | 0 | 0 | 0
Released 50% amount |  |  | 2525356 |  | Remaining | 4065963.5888 | 1043611.948 | 40153.35 | 594638.5
Income Tax 7.5% |  |  | 189401.7
Net Payable Amount |  |  | 2335954.3
Receiving Details |  |  |  |  | Total Retention Remaining | 5744367.3868
ADHOC Payment received (transfer in mohsin traders account |  |  | 700000
this chq given to Shabbir borther against GSt invoice in the name of S A Khan traders) |  |  | 501000
this chq given to Iqbal sons against GST invoice) |  |  | 150000
Cash payment received( This cash use if our office cash) |  |  | 450000
this chq given to NKR Engineering against GSt invoice in al Hamd deal) |  |  | 275079
this chq given to Fateh steel against GSt invoice |  |  | 206910
46622
Total receivings Rs |  |  | 2329611
Remaining amount |  |  | 6343.3
Retention Working | Main building | Food Court | Mosque
Total amount with hold | 7600459.5888 | 1043611.948 | 40153.35
Received | 3534496 | 0 | 0
Remaining | 4065963.5888 | 1043611.948 | 40153.35
Total Retention Remaining | 5149728.8868

## Food Court
Patient Aid Foundation (PAF)
Construction of New Surgical & OPD Complex at JPMC,Karachi
FOOD COURT
PLUMBING & HVAC WORKS
Summary of Bills
IPC - 05 / Food Court Kitchen
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Total Amount Received against IPC - 5 |  |  | 5534433
RECOVERY OF OFM MATERIAL HVAC
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Total Amount Received against IPC - 5 |  |  | 5534433
Income Tax 7.5%
Amount After tax |  |  | 5534433
Mobilization Advance 5%
Retention money 5% |  |  | 276721.65
GCM 8% |  |  | 442754.64
Total Deductions |  |  | 719476.29
Net Payable Amount |  |  | 4814956.71
IPC - 06 / Food Court Kitchen
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  | 1687986
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 72284
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 1080781
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Total Amount Received against IPC - 6 |  |  | 2841051
RECOVERY OF OFM MATERIAL HVAC
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Total Amount Received against IPC - 6 |  |  | 2841051
Mobilization Advance 5%
Retention money 5% |  |  | 142052.55
GCM 8% |  |  | 227284.08
Income Tax 7.5% |  |  | 213078.825
Total Deductions |  |  | 582415.455
Net Payable Amount |  |  | 2258635.545
Verified 70% |  |  | 1581044.8815
| Bharmal-JPMC |  | 1291617
| Saeeed Sons-Falcon |  | 231879
| Remaining |  | 57548.8815
| Total received |  | 1581044.8815
IPC - 06 / Food Court Kitchen (remaining 30% bill)
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  | 1921680
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 72284
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 1047919
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2 |  |  | 118703
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Total Amount Received against IPC - 6 |  |  | 3160586
RECOVERY OF OFM MATERIAL HVAC
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Total Amount Received against IPC - 6 |  |  | 3160586
Mobilization Advance 5%
Retention money 5% |  |  | 158029.3
GCM 8% |  |  | 252846.88
Income Tax 7.5% |  |  | 237043.95
Total Deductions |  |  | 647920.13
Net Payable Amount |  |  | 2512665.87
Received in prv bill |  |  | 1581045
Payable amount |  |  | 931620.87
| Fakhri Brothers |  | 700169
| Fakhri Brothers |  | 700000
| KAYTESS |  | 200000
| Extra Receeived |  | -668548.13 | Adjusted in IPC 44 Billing (main Building)
Food Court IPC 07
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 1459846.96
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Gross Work Done Amount |  |  | 1459846.96
RECOVERY OF OFM MATERIAL HVAC
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Net Work Done Amount |  |  | 1459846.96
Mobilization Advance 5%
Retention money 5% |  |  | 72992.348
GCM 8% |  |  | 116787.7568
Income Tax 7.5% |  |  | 109488.522
Total Deductions |  |  | 299268.6268
Net Payable Amount |  |  | 1160578.3332
Receiving Details
| Abika Enterprises |  | 500000
| Naseeruddin H Lalani |  | 312244
| KATYS |  | 150000
| Iqbal Sons |  | 100000
| Cash cheque |  | 98334.3332
Food Court IPC 08
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 1884653
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | 820047
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 1936970
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2
TOTAL COST OF HVAC WORKS Addtional ITEMS Rate Analysis | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 584792
Gross Work Done Amount |  |  | 5226462
RECOVERY OF OFM MATERIAL HVAC
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Net Work Done Amount |  |  | 5226462
Mobilization Advance 5%
Retention money 5% |  |  | 261323.1 |  |  |  | Evaluation of tax on cash cheques
GCM 8% |  |  | 418116.96 |  |  |  | Cash chq amount in IPC 07 | 98334
Income Tax 7.5% |  |  | 391984.65 |  |  |  | Tax on amount | 106307.027
Total Deductions |  |  | 1071424.71 |  |  |  | 7.5% | 7973.027
Net Payable Amount |  |  | 4155037.29 |  |  |  | Divide by 02 | 3986.5135
Receiving Details
Evaluation of tax on cash cheques
5 -8- 20 Chq Rs (this chq hod with bilal bhai) |  |  | 900000 |  |  |  | Cash chq amount in IPC 08 | 2063000
15-8-20 Fateh Steel |  |  | 1000069 |  |  |  | Tax on amount | 2230270.2703
15-8-20 Sultan Trader (Tahiri Sanitry) |  |  | 300000 |  |  |  | 7.5% | 167270.2703
15-8-20 M. Hussain & Co. (Tahiri Sanitry) |  |  | 200000 |  |  |  | Divide by 02 | 83635.1351
15-8-20 Iqbal Sons |  |  | 200000
15-8-20 Cash Cheque (Hold with Rehan) |  |  | 400000
15-8-20 Cash Cheque (Hold with Rehan) |  |  | 463000
15-8-20 Cash Cheque (Hold with Rehan) |  |  | 300000
Deduct tax charges in IPC 08 cash cheques |  |  | 83635 |  |  |  | Evaluation of tax on cash cheques
Deduct tax charges in IPC 07 cash cheques |  |  | 3987 |  |  |  | Cash chq amount in IPC 47 | 6000000
Total receivings Rs |  |  | 3850691 |  |  |  | Tax on amount | 6486486.4865
Remaining amount |  |  | 304346.29 | Adjusted in IPC 47 Billing (main Building) |  |  | 7.5% | 486486.4865
[7 empty] | Divide by 02 | 243243.2432
Food Court IPC 09
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 1104253
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2
TOTAL COST OF HVAC WORKS Addtional ITEMS Rate Analysis | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Gross Work Done Amount |  |  | 1104253
RECOVERY OF OFM MATERIAL HVAC
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Net Work Done Amount |  |  | 1104253
Mobilization Advance 5% |  |  | 0
Retention money 5% |  |  | 55212.65
GCM 8% |  |  | 88340.24
Income Tax 7.5% |  |  | 82818.975
Total Deductions |  |  | 226371.865
Net Payable Amount |  |  | 877881.135
Receiving Details
Cash cheque (cashed chq) (from which rs 250,00 to tariq insult, 50,000 zakat bynadeem bhai and rs 100,000 given to nadeem bhai in his pett cash |  |  | 400000
Cash cheque (this chq cash and used in office pettty cash on 14-10-20 |  |  | 400000
Cash cheque (this chq given to Tube traders) |  |  | 100000
Tax 3.75% on cash chq amount |  |  | 33750 |  | Adjusted in IPC 10
Remaining amount |  |  | -55868.865
Food Court IPC 10
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  | 35200
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | 356165
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | 1546832
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS |  |  | 51566
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2 |  |  | 70993
TOTAL COST OF HVAC WORKS Addtional ITEMS Rate Analysis | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Gross Work Done Amount |  |  | 2060756
RECOVERY OF OFM MATERIAL HVAC
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Net Work Done Amount |  |  | 2060756
Mobilization Advance 5% |  |  | 0
Retention money 5% |  |  | 103037.8
GCM 8% |  |  | 164860.48
Income Tax 7.5% |  |  | 154556.7
Total Deductions |  |  | 422454.98
Net Payable Amount |  |  | 1638301.02
Verified 70% |  |  | 1146810.714
Receiving Details
Receiving on 15-12-20 (chq sent to shabbir bros then he returned this payment and this payment by bilal bhai in misc purchasing |  |  | 1107698
Remaining amount |  |  | 491490.306
paid to Iqbal sons |  |  | 150000
Remaining amount |  |  | 341490.306 |  | IPC 47 | -1288250
[5 empty] | IPC 48 | -568779
[5 empty] | IPC 8 | 304347
Food Court IPC 11 |  |  |  |  | IPC 9 | -55868
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  |  |  | IPC 10 | 341490
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS |  |  | Net amount | -1267060
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS Addtional ITEMS Rate Analysis | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Gross Work Done Amount |  |  | 2325902
RECOVERY OF OFM MATERIAL HVAC
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Net Work Done Amount |  |  | 2325902
Mobilization Advance 5% |  |  | 0
Retention money 5% |  |  | 116295.1
GCM 8% |  |  | 186072.16
Income Tax 7.5% |  |  | 174442.65
Total Deductions |  |  | 476809.91
Net Payable Amount |  |  | 1849092.09
Receiving Details
received payment against food court IPC 11 (this payment direct transfer to Mohsin Traders accounts c/o bilal habib & bilal bhai will use this cash for future expenses) |  |  | 1500000 |  | 1621621.6216
cash adjustemetn |  |  | 60812
Total receiving |  |  | 1560812
121621.6216
Remaining amount |  |  | 288280.09 |  | 60810.8108
52500

## JPMC MOSQUE
JPMC MOSQUE
Add JPMC Mosque Adhoc 60% of 1343,553 |  |  | 806131.8
Receiving Details
Mosque payment Cash Cheque |  |  | 400000
Mosque payment Cash Cheque |  |  | 437000
Total receivings Rs |  |  | 837000
Remaining amount |  |  | 558000
MOSQUE-2
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | 1343553
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2
TOTAL COST OF HVAC WORKS Addtional ITEMS Rate Analysis | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Gross Work Done Amount |  |  | 1343553
RECOVERY OF OFM MATERIAL HVAC
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Net Work Done Amount |  |  | 1343553 | 1343553
Mobilization Advance 5% |  |  | 0 | 0
Retention money 5%
GCM 8% |  |  |  | 107484.24
Income Tax 7.5% |  |  |  | 100766.475
Total Deductions
Net Payable Amount |  |  | 1343553 | 1135302.285
Receiving Details
Mosque payment Cash Cheque |  |  | 400000 | 400000
Mosque payment Cash Cheque |  |  | 437000 | 437000
Remaining amount |  |  | 506553 | 298302.285
Adjusted in IPC 48 |  |  | 506553
Remaining amount |  |  | NIL
MOSQUE-3
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | 803067
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2
TOTAL COST OF HVAC WORKS Addtional ITEMS Rate Analysis | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Gross Work Done Amount |  |  | 803067
RECOVERY OF OFM MATERIAL HVAC
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Net Work Done Amount |  |  | 803067
Mobilization Advance 5% |  |  | 0 |  | 102107
Retention money 5% |  |  | 40153.35 |  | 288280.09
GCM 8% |  |  | 64245.36 |  | 325317.165
Income Tax 7.5% |  |  | 60230.025 |  | 715704.255
Total Deductions |  |  | 164628.735
Net Payable Amount |  |  | 638438.265
Receiving Details
Adhoc payment received mosque bill # 3 (this payment direct transfer to Mohsin Traders accounts c/o bilal habib & bilal bhai will use this cash for future expenses) |  |  | 500000 | 540540.5405
cash adjustments |  |  | 20270 | 40540.5405
20270.2703
Remaining amount |  |  | 118168.265

## EYE WARD
EYE WARD BILL
TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS |  |  | 1309247
TOTAL COST OF PLUMBING WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
PLUMBING EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
HVAC EXTRA WORKS ( REFER ANNEXURE-A) | COST OF PLUMBING EXTRA WORKS | COST OF PLUMBING EXTRA WORKS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS
TOTAL COST OF HVAC WORKS B.O.Q ITEMS PART 2
TOTAL COST OF HVAC WORKS Addtional ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS | TOTAL COST OF PLUMBING WORKS B.O.Q ITEMS
Total Amount Received |  |  | 1309247
RECOVERY OF OFM MATERIAL HVAC
RECOVERY OF OFM MATERIAL PLUMBING
TOTAL OF OFM MATERIAL AMOUNT
Total Amount Received against |  |  | 1309247
Mobilization Advance 5%
Retention money 5%
GCM 8% |  |  | 104739.76
Income Tax 7.5% |  |  | 98193.525
Total Deductions |  |  | 202933.285
Net Payable Amount |  |  | 1106313.715
Extra paid |  |  | 43426
KATYS |  |  | 500000
Iqbal Sons |  |  | 300000
Islamuddin & Sons |  |  | 43775
Islamuddin & Sons |  |  | 33516
Islamuddin & Sons |  |  | 6973
Cash cheque (used in oct office salaries) |  |  | 178623.715

## Bills Summary
JPMC Billing Summary
Main Building |  |  |  | Food Court
Bill # | Verified Bills | Mobilization | Retention Money | Bill # | Verified Bills | Mobilization | Retention Money
IPC-20 | 9793201 | 489660.05 | 489660.05 | IPC-05 | 5534433 | 0 | 276721.65
IPC-26 | 12363381.07 | 618169.0535 | 618169.0535 | IPC-06 | 3160586 | 0 | 158029.3
IPC-27 | 192962.6 | 9648.13 | 9648.13 | IPC-07 | 1459846.96 | 0 | 72992.348
IPC-28 | 1275475.41 | 63773.7705 | 63773.7705 | IPC-08 | 5226462 | 0 | 261323.1
IPC-29 | 6142481.77 | 307124.0885 | 307124.0885 | IPC-09 | 1104253 | 0 | 55212.65
IPC-30 | 3157443.36 | 157872.168 | 157872.168 | IPC-10 | 2060756 |  | 103037.8
IPC-31 | 6719123.06 | 335956.153 | 335956.153 | IPC-11 | 2325902 |  | 116295.1
IPC-34 | 4692127.85 | 234606.3925 | 234606.3925
IPC-35 | 3776166.5 | 188808.325 | 188808.325
IPC-37 | 6248869 | 289010.1913 | 289010.1913
IPC-39 | 377332 | 17451.605 | 17451.605 | Total Amount Rs | 20872238.96 | 0 | 1043611.948
IPC-40 | 6807460 | 314845.025 | 314845.025 | Eye Ward
IPC-42 | 3491607 | 174580.35 | 174580.35 | Bill # | Verified Bills | Mobilization | Retention Money | 164951618.31
IPC-43 | 24353979 | 1217698.95 | 1217698.95 |  | 1309247 | 0 | 0
IPC-44 | 10867281 | 543364.05 | 661876.9
IPC-45 | 9232251.73 | 461612.5865 | 461612.5865
IPC-46 | 6108294 | 0 | 332220.3 | Total Amount Rs | 1309247 | 0 | 0
IPC-47 | 7841449 | 0 | 392072.45
IPC-48 | 1662697 | 0 | 83134.85 | Mosque
IPC-49 | 8517689 |  | 425884.45 | Bill # | Verified Bills | Mobilization | Retention Money
IPC-50 | 6275375 |  | 313768.75 |  | 1360000 | 0 | 0
IPC-51 | 4182733 |  | 209136.65
| 144079379.35 | 5424180.8888 | 7298911.1888 | Total Amount Rs | 1360000 | 0 | 0

## excess ret money amount
JPMC Billing Summary
Main Building (HVAC & Plumbing) |  |  |  |  | Food Court
Excess Retention money amount evaluation |  |  |  |  | Food Court
Bill # | Verified Bills | Net Payable amount | Retention Money deduct | Mobilization deducted | Bill # | Verified Bills | Mobilization | Retention Money
IPC-20 | 9793201 | 7295934.745 | 489660.05 | 489660.05 | IPC-05 | 5534433 | 0 | 276721.65
IPC-26 | 12363381.07 | 9210718.8972 | 618169.0535 | 618169.0535 | IPC-06 | 3160586 | 0 | 158029.3
IPC-27 | 192962.6 | 143757.137 | 9648.13 | 9648.13 | IPC-07 | 1459846.96 | 0 | 72992.348
IPC-28 | 1275475.41 | 950229.1804 | 63773.7705 | 63773.7705
IPC-29 | 6142481.77 | 4576148.9186 | 307124.0885 | 307124.0885 | Total Amount Rs | 10154865.96 | 0 | 507743.298
IPC-30 | 3157443.36 | 2352295.3032 | 157872.168 | 157872.168 | Eye Ward
IPC-31 | 6719123.06 | 5005746.6797 | 335956.153 | 335956.153 | Bill # | Verified Bills | Mobilization | Retention Money
IPC-34 | 4692127.85 | 3495635.2483 | 234606.3925 | 234606.3925 |  | 1309247 | 0 | 0
IPC-35 | 3776166.5 | 2813244.0425 | 188808.325 | 188808.325
IPC-37 | 6248869 | 4739767.1365 | 289010.1913 | 289010.1913
IPC-39 | 377332 | 286206.322 | 17451.605 | 17451.605 | Total Amount Rs | 1309247 | 0 | 0
IPC-40 | 6807460 | 5163458.41 | 314845.025 | 314845.025
IPC-42 | 3491607 | 2601247.215 | 174580.35 | 174580.35 | Mosque
IPC-43 | 24353979 | 15643714.355 | 1217698.95 | 1217698.95 | Bill # | Verified Bills | Mobilization | Retention Money
IPC-44 | 10867281 | 7977611.495 | 661876.9 | 543364.05 |  | 1360000 | 0 | 0
IPC-45 | 9232251.73 | 6878027.5389 | 461612.5865 | 461612.5865
IPC-46 | 5650171 | 4829288.13 | 332220.3 | -
IPC-47 |  | 7841449 | 392072.45 | -
IPC-48 |  | 1662697 | 83134.85 | -
IPC-49 |  | 8517689 | 425884.45 | -
IPC-50 |  | 6275375 | 313768.75
IPC-51 |  | 4182733 | 209136.65 | 0
Waiting area |  | 523955 | 0
IPC-52 |  | 3682160.16 | 301548.4
Total Amount Rs. | 115141313.35 | 112966928.7543 | 7600459.5888 | 5424180.8888 | Total Amount Rs | 1360000 | 0 | 0
Mobilization received on 28-09-2016 |  |  |  | 1500000
Mobilization received on 31-10-2016 |  |  |  | 1500000
Mobilization received on 28-02-2017 |  |  |  | 1500000
Extra Mobilization deducted |  |  |  | 924180.8888