## Sheet1
HVAC Work Schedule
Floors | Week 1 17-5-21 - 23-5-21 | Week 2 24-5-21 - 30-5-21 | Week 3 31-5-21 - 06-6-21 | Week 4 07-6-21 - 13-6-21 | Week 5 14-6-21 - 20-6-21 | Week 6 21-6-21 - 27-6-21 | Week 7 28-6-21 - 04-7-21 | Week 8 05-7-21 - 11-7-21
3rd Floor | [7 empty] | Handing Over
Ducting
Insulation
Copper Piping
Unit installation | After receive
Testing & Commissioning
Installation of HEPA Filters
2nd Floor
Ducting
Insulation
Copper Piping
Unit installation |  |  | After receive
Testing & Commissioning
1st Floor
Ducting
Insulation
Copper Piping
Unit installation |  |  |  | After receive
Testing & Commissioning
Upper Ground Floor
Ducting
Insulation
Copper Piping
Unit installation |  |  |  |  | After receive
Testing & Commissioning