## Summary
2021-09-23
Summary of Bill
Sr # | DESCRIPTION | AMOUNT (PKR)
1 | HVAC Work (3rd & Roof Floor) | 1410200.55
2 | HVAC Work (Upperground, 1st & 2nd Floor) | 3281625.8
3 | Additional work | 207900
Total Cost of Bill |  | 4899726.35
Received 1st payment on 15-05-21 |  | 1350000
|  |  | 57000 | Less for
Received 2nd payment on 17-07-21 |  | 1350000
|  |  | 4842726.35 | 2700000
Received 2nd payment on 24-09-21 |  | 1000000
|  |  | 3700000 |  | 166500
Net Payable amount |  | 1199726.35
|  |  | 1142726.35 |  |  | 4.5% | 3%
Note: Kindly release Rs ___________ from the above payable amount and rest of the amount will be release at the time of the settlement of final bill.
Thanking you,
Regards,
Nadeem Iqbal
Pioneer Engineering Services.

## revised summary material
PES/005/BT/02/22 |  | 2022-02-24
NTN # 1042854-2
Attn: Mr. Jaffar
Invoice for Material supplied for HVAC Work (Baitul Sukoon Cancer Hospital Karachi.)
Sr # | DESCRIPTION | Material Amount
1 | HVAC Work (3rd & Roof Floor) | 1159670
2 | HVAC Work (Upperground, 1st & 2nd Floor) | 2757685
3 | Total Amount | 3917355
* | Less Discount 11% | 430909.05
* | After Discount | 3486445.95
4 | Additional work | 207000
* | Less Deductions | 57000
Net Payable Amount Rs |  | 3636445.95
SST 13% |  | 472737.9735
Grand Payable Amount Rs |  | 4109183.9235
Thanking you,
Regards,
4841826
Pioneer Engineering Services.
M. Habib ur Rehman

## revised summary labour
PES/006/BT/02/22 |  | 2022-02-24
NTN # 1042854-2
Attn: Mr. Jaffar
Invoice for Labour charges for HVAC Work (Baitul Sukoon Cancer Hospital Karachi.)
Sr # | DESCRIPTION | Labour Amount
1 | HVAC Work (3rd & Roof Floor) | 424825
2 | HVAC Work (Upperground, 1st & 2nd Floor) | 929535
3 | Total Amount | 1354360
* | Less Discount 11% | 148979.6
Net Payable Amount Rs |  | 1205380.4
SST 13% |  | 156699.452
Grand Payable Amount Rs |  | 1362079.852
Thanking you,
Regards,
4841826
Pioneer Engineering Services.
M. Habib ur Rehman

## 3rd & roof Floor
BILL OF QUANTITIES FOR HVAC WORKS (3rd Floor & Roof) | [6 empty] | Bill
BOQ No. | Specification Reference | Description | Qty. | Unit | Material Unit Rate | Installation Unit Rate | Biiled Qtty | Biiled Amount
| 23 73 13 40 92 49 23 41 00 | Installation of Air Handling Unit, including the cost loading, unloading and placing on each floor, material or foundation or any other material or tool and equipment which may be required complete in all respects with necessary fittings and as per schedule and specifications.
E |  | AHU ‐ PCKG. ‐ 01 | 1 | No. |  | 35000 | 1 | 35000 | 0 | 35000
E |  | AHU ‐ TF ‐ 01 | 1 | No. |  | 5000 | 1 | 5000 | 0 | 5000
F |  | AHU ‐ TF ‐ 02 | 1 | No. |  | 5000 | 1 | 5000 | 0 | 5000
| 23 81 29 23 23 00 | Installation of DX Single Split Units along with control and termination power wiring, thermostats, flexible connector, vibration isolators complete in all respects, as per schedule, drawings and specifications. | [6 empty] | 0 | 0
|  | Indoor/Outdoor Units | [6 empty] | 0 | 0
A |  | SP‐TF‐01 / CU‐TF‐02 | 2 | Nos. |  | 5000 | 2 | 10000 | 0 | 10000
[9 empty] | 0 | 0
| 23 37 13 | Supply, Installation and Commissioning of fresh air intake louvers with sand trap, Aluminum constructed and powder coated finished as per specifications. | [6 empty] | 0 | 0
|  | Fresh Air Intake Louvers | [6 empty] | 0 | 0
A |  | 2.61 sq.ft (with 33% free area) | 1 | No. | 8350 | 1000 | 1 | 9350 | 8350 | 1000
A |  | 2.05 sq.ft (with 33% free area) | 1 | No. | 6560 | 1000 | 1 | 7560 | 6560 | 1000
|  | Exhaust Air Louvers | [6 empty] | 0 | 0
A |  | 1.75 sq.ft (with 41% free area) | 1 | No. | 5600 | 1000 | 1 | 6600 | 5600 | 1000
| 23 31 00 | Supply, Installation and Commissioning of G.I Sheet metal air ducts as per ASHRAE Standards for air ducting, plenums and other sheet fabrications including splitter dampers, take off, vanes elbows and other necessary fittings. | [6 empty] | 0 | 0
E |  | 26 Gauge | 35 | Sq ft. | 200 | 65 | 0 | 0 | 0 | 0
E |  | 24 Gauge | 1260 | Sq ft. | 220 | 65 | 1519 | 432915 | 334180 | 98735
A | 2000-07-23 | Supply, Installation & Commissioning of Glass wool insulation of 1" thickness for ducts. Complete in all respect as mentioned in the schedule & specifications. | 1295 | Sq ft. | 125 | 45 | 1370 | 232900 | 171250 | 61650
B | 2000-07-23 | Supply, installation & commissioning of 0.032" Aluminum cladding (G.I 26 SWG) over Exposed Ducts complete with all respects as mentioned in the schedule & specifications. | 1295 | Sq ft. | 200 | 50 | 458 | 114500 | 91600 | 22900
C | 2000-07-23 | 1" thick Glass Fibre sound liner for Air Ducting including accessories. | 1 | Job | 35000 | 10000 | 0 | 0 | 0 | 0
| 23 37 13 | Supply, installation and commissioning to Air Devices as per drawings and specifications. | [6 empty] | 0 | 0
|  | Sub Total (Page 01) | [5 empty] | 858825 | 0 | 0
| 23 37 13 | Supply Air Diffuser (S.A.D) (Contd.) | [6 empty] | 0 | 0
|  | 9x9 | 10 | Nos. | 2000 | 1000 | 3 | 9000 | 6000 | 3000
[9 empty] | 0 | 0
| 23 37 13 | Return Air Diffuser (R.A.D) (Contd.) | [6 empty] | 0 | 0
|  | 9x9 | 7 | Nos. | 2000 | 1000 | 8 | 24000 | 16000 | 8000
[9 empty] | 0 | 0
| 23 37 13 | Exhaust Air Diffuser (E.A.D) (Contd.) | [6 empty] | 0 | 0
|  | 12x12 | 1 | Nos. | 3500 | 1000 | 1 | 4500 | 3500 | 1000
|  | Supply, Installation and Commissioning of HEPA Filters in SAG as per drawings and specifications. | [6 empty] | 0 | 0
A |  | H14 filter (12''x12'') with S.S Housing | 5 | Nos. | 37400 | 3000 | 7 | 282800 | 261800 | 21000 |  | 6000 | 28000 | 34000 | 10% | 3400 | 37400
[9 empty] | 0 | 0
|  | Supply, Installation and Commissioning of Perforated HEPA Filter Diffuser as per drawings and specifications. | [6 empty] | 0 | 0
A |  | H14 filter (48''x24'') with S.S Housing | 8 | Nos. | 113300 | 3000 | 0 | 0 | 0 | 0 |  | 12000 | 35000 | 47000 | 10% | 4700 | 51700
A |  | H14 filter (24''x24'') with S.S Housing | 2 | Nos. | 51700 | 3000 | 0 | 0 | 0 | 0 |  | 35000 | 68000 | 103000 | 10% | 10300 | 113300
| 23 23 00 | Supply, Installation & Commissioning of Refrigerant Copper Piping with closed cell elastromeric insulation 20mm thick with supports, fittings, and accessories. | [6 empty] | 0 | 0
| AHU ‐ TF ‐ 01 | 1/2" diameter | 100 | Rft | 425 | 200 | 25 | 15625 | 10625 | 5000 |  |  | 1/2" diameter
|  | 5/8" diameter | 100 | Rft | 810 | 250 | 25 | 26500 | 20250 | 6250 |  |  | 2/5" diameter
| AHU ‐ TF ‐ 02 | 1/2" diameter | 98 | Rft | 425 | 200 | 25 | 15625 | 10625 | 5000 |  |  | 1/2" diameter
|  | 5/8" diameter | 98 | Rft | 810 | 250 | 25 | 26500 | 20250 | 6250 |  |  | 2/5" diameter
|  | For DX Split Units | [6 empty] | 0 | 0
| SP ‐ TF ‐ 01 | Ø 5/8 in. (Gas Piping) | 140 | Rft | 480 | 150 | 0 | 0 | 0 | 0
|  | Ø 3/8 in. (Liquid Piping) | 140 | Rft | 290 | 120 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0
|  | Sub Total (Page 02) | [5 empty] | 404550 | 0 | 0
| 23 21 14 | Supply, Installation and Commissioning of U‐PVC piping Class‐ D. with closed cell elastromeric 15mm thick Insulation for condensate drain including all cutting, fixing fitting, laying, cleaning, making good and supports complete in all respect as per drawings and specifications. | [6 empty] | 0 | 0
| AHU ‐ TF ‐ 01 | 3/4" diameter | 34 | Rft | 160 | 80 | 50 | 12000 | 8000 | 4000
| AHU ‐ TF ‐ 02 | 3/4" diameter | 8 | Rft | 160 | 80 | 38 | 9120 | 6080 | 3040
[9 empty] | 0 | 0
| 23 81 26 | Supply, Installation and Commissioning of Exhaust and Ventilation Fans with flexible connectors, vibration isolators and other accessories complete with all respect as per schedule & specifications. | [6 empty] | 0 | 0
|  | EF‐TF‐01 | 1 | No. | 32000 | 5000 | 1 | 37000 | 32000 | 5000
|  | VF-TF-01 | 1 | No. | 32000 | 5000 | 1 | 37000 | 32000 | 5000
[9 empty] | 0 | 0
|  | Supply, Installation and Commissioning of Dampers as per SMACNA standards and specifications. | [6 empty] | 0 | 0
| 23 33 13.13 | Volume Control Dampers (VCD) (Contd.) | [6 empty] | 0 | 0
|  | 12"x6" | 1 | No. | 2000 | 1000 | 2 | 6000 | 4000 | 2000
|  | 14"x8" | 1 | No. | 6500 | 1000 | 2 | 15000 | 13000 | 2000
|  | 18"x12" | 1 | No. | 4500 | 1000 | 1 | 5500 | 4500 | 1000
|  | 16''x10'' | 1 | No. | 3500 | 1000 | 1 | 4500 | 3500 | 1000
|  | 14"x6" | 1 | No. | 2500 | 1000 | 2 | 7000 | 5000 | 2000
A | 2000-09-23 | MISCELLANEOUS | [6 empty] | 0 | 0
B |  | Supply, Installation & commissioning of brass tags for Equipment and system including all accessories complete in all respect. | 1 | Job | 5000 | 2000 | 0 | 0 | 0 | 0
C |  | Supply, Installation & commissioning of foundation for pipes and equipment including all noise and Vibration controller as per drawings and specifications. | 1 | Job | 25000 | 8000 | 1 | 33000 | 25000 | 8000
D | 2000-09-23 | Supply, Installation & commissioning of hangers and supports for pipes and equipment including all noise and Vibration controller roller type and others as per drawings and specifications. | 1 | Job | 40000 | 20000 | 1 | 60000 | 40000 | 20000
|  | Painting on equipment / Hangers, Supports, Pipe etc as per specifications. | 1 | Job | 10000 | 5000 | 1 | 15000 | 10000 | 5000
F |  | Drawings | [6 empty] | 0 | 0
G |  | Shop Drawings as per specifications. | 1 | Job | 5000 | 5000 | 1 | 10000 | 5000 | 5000
|  | As Built Drawings as per specifications. | 1 | Job | 5000 | 5000 | 1 | 10000 | 5000 | 5000
H |  | Testing (3 months test run) & Commissioning with Air & water balancing | [6 empty] | 0 | 0
|  | HVAC System. | 1 | Job | 0 | 60000 | 1 | 60000 | 0 | 60000
I |  | Sundries | [6 empty] | 0 | 0
|  | Supply, installing and commissioning of items not listed in BOQ but required. | 1 | Job | 0 | 0 |  | 0 | 0 | 0
|  | Sub Total (Page 03) | [5 empty] | 321120 | 1159670 | 424825
|  | TOTAL COST FOR BILL | [5 empty] | 1584495 | 127563.7 | 46730.75
|  | Less Discount | [5 empty] | 174294.45 | 1032106.3 | 378094.25 | 1410200.55
|  | NET TOTAL FOR HVAC WORKS | [5 empty] | 1410200.55
Note: Quoted prices are exclusive of all taxes.

## UpperGround, 1st Floor & 2nd Fl
BILL OF QUANTITIES FOR HVAC WORKS (Upper Ground, 1st & 2nd Floor) | [6 empty] | Bill
BOQ No. | Specification Reference | Description | Qty. | Unit | Material Unit Rate | Installation Unit Rate | Biiled Qty | Biiled Amount
| 23 73 13 40 92 49 23 41 00 | Installation of Air Handling Unit, including the cost loading, unloading and placing on each floor, material or foundation or any other material or tool and equipment which may be required complete in all respects with necessary fittings and as per schedule and specifications.
E |  | AHU - UG - 01 | 1 | No. |  | 8000 | 1 | 8000 | Cost/Unit Capacity=96792 (Soorty OFM) | 0 | 8000
F |  | AHU - FF - 01 | 1 | No. |  | 8000 | 1 | 8000 |  | 0 | 8000
|  | AHU - FF - 02 | 1 | No. |  | 8000 | 1 | 8000 |  | 0 | 8000
G |  | AHU - FF - 03 | 1 | No. |  | 8000 | 1 | 8000 |  | 0 | 8000
E |  | AHU - FF - 04 | 1 | No. |  | 8000 | 1 | 8000 | Cost/Unit Capacity=96792 (Soorty OFM) | 0 | 8000
F |  | AHU - SF - 01 | 1 | No. |  | 8000 | 1 | 8000 |  | 0 | 8000
|  | AHU - SF - 02 | 1 | No. |  | 8000 | 1 | 8000 |  | 0 | 8000
G |  | AHU - SF - 03 | 1 | No. |  | 8000 | 1 | 8000 |  | 0 | 8000
|  | AHU - SF - 04 | 1 | No. |  | 8000 | 1 | 8000 |  | 0 | 8000
| 23 37 13 | Supply, Installation and Commissioning of fresh air intake louvers with sand trap, Aluminum constructed and powder coated finished as per specifications. | [7 empty] | 0 | 0
|  | Fresh Air Intake Louvers | [7 empty] | 0 | 0
A |  | 3.2 sft (with 33% free area) | 1 | No. | 9500 | 1000 | 1 | 10500 |  | 9500 | 1000
B |  | 3.6 sft (with 33% free area) | 1 | No. | 10500 | 1000 | 2 | 23000 |  | 21000 | 2000
C |  | 1.23 sft (with 33% free area) | 1 | No. | 7500 | 1000 |  | 0 |  | 0 | 0
A |  | 4.1 sft (with 33% free area) | 1 | No. | 15000 | 1000 |  | 0 |  | 0 | 0
B |  | 3.6 sft (with 33% free area) | 1 | No. | 10500 | 1000 |  | 0 |  | 0 | 0
B |  | 1.23 sft (with 33% free area) | 1 | No. | 7500 | 1000 |  | 0 |  | 0 | 0
C |  | 4.1 sft (with 33% free area) | 1 | No. | 15000 | 1000 |  | 0 |  | 0 | 0
| 23 31 00 | Supply, Installation and Commissioning of G.I Sheet metal air ducts as per ASHRAE Standards for air ducting, plenums and other sheet fabrications including splitter dampers, take off, vanes elbows and other necessary fittings. | [7 empty] | 0 | 0
E |  | 26 Gauge | 120 | Sq ft. | 200 | 65 | 0 | 0 |  | 0 | 0
E |  | 24 Gauge | 2055 | Sq ft. | 210 | 65 | 4748 | 1305700 |  | 997080 | 308620
E |  | 22 Gauge | 442 | Sq ft. | 220 | 65 | 0 | 0 |  | 0 | 0
A | 23 07 00 | Supply, Installation & Commissioning of Glass wool insulation of 1" thickness for ducts. Complete in all respect as mentioned in the schedule & specifications. | 2617 | Sq ft. | 110 | 45 | 3325 | 515375 |  | 365750 | 149625
B | 23 07 00 | Supply, installation & commissioning of 0.032" Aluminum cladding over Exposed Ducts complete with all respects as mentioned in the schedule & specifications. | 2617 | Sq ft. | 0 | 0 | 0 | 0 |  | 0 | 0
C | 23 07 00 | 1" thick Glass Fibre sound liner for Air Ducting including accessories. | 1 | Job | 50000 | 20000 | 0 | 0 |  | 0 | 0
| 23 37 13 | Supply, installation and commissioning to Air Devices as per drawings and specifications. | [7 empty] | 0 | 0
|  | Sub Total (Page 01) | [5 empty] | 1926575 |  | 0 | 0
| 23 37 13 | Supply Air Diffuser (S.A.D) (Contd.) | [7 empty] | 0 | 0
|  | 18x18 | 3 | Nos. | 6490 | 1000 | 3 | 22470 |  | 19470 | 3000
|  | 15x15 | 8 | Nos. | 4400 | 1000 | 8 | 43200 |  | 35200 | 8000
|  | 12x12 | 8 | Nos. | 2900 | 1000 | 10 | 39000 |  | 29000 | 10000
|  | 9x9 | 4 | Nos. | 900 | 500 | 5 | 7000 |  | 4500 | 2500
[10 empty] | 0 | 0
| 23 37 13 | Return Air Diffuser (R.A.D) (Contd.) | [7 empty] | 0 | 0
|  | 18x18 | 2 | Nos. | 6400 | 1000 | 2 | 14800 |  | 12800 | 2000
|  | 15x15 | 3 | Nos. | 4400 | 1000 | 3 | 16200 |  | 13200 | 3000
|  | 12x12 | 7 | Nos. | 2900 | 1000 | 7 | 27300 |  | 20300 | 7000
|  | 9x9 | 10 | Nos. | 900 | 500 | 11 | 15400 |  | 9900 | 5500
[10 empty] | 0 | 0
| 23 23 00 | Supply, Installation & Commissioning of Refrigerant Copper Piping with closed cell elastromeric insulation 20mm thick with supports, fittings, and accessories. | [7 empty] | 0 | 0
|  | 1/2" diameter | 43 | Rft | 425 | 200 | 85 | 53125 |  | 36125 | 17000
|  | 7/8" diameter | 43 | Rft | 810 | 250 | 85 | 90100 |  | 68850 | 21250
|  | 1/2" diameter | 82 | Rft | 425 | 200 | 82 | 51250 |  | 34850 | 16400
|  | 3/8" diameter | 82 | Rft | 315 | 180 |  | 0 |  | 0 | 0
|  | 1/2" diameter | 47 | Rft | 425 | 200 | 34 | 21250 |  | 14450 | 6800
|  | 3/8" diameter | 47 | Rft | 315 | 180 |  | 0 |  | 0 | 0
|  | 1/2" diameter | 50 | Rft | 425 | 200 | 34 | 21250 |  | 14450 | 6800
|  | 3/8" diameter | 50 | Rft | 315 | 180 |  | 0 |  | 0 | 0
|  | 1/2" diameter | 84 | Rft | 425 | 200 | 41 | 25625 |  | 17425 | 8200
|  | 7/8" diameter | 84 | Rft | 810 | 250 | 428 | 453680 |  | 346680 | 107000
|  | 1/2" diameter | 98 | Rft | 425 | 200 | 98 | 61250 |  | 41650 | 19600
|  | 3/8" diameter | 98 | Rft | 315 | 180 |  | 0 |  | 0 | 0
|  | 1/2" diameter | 75 | Rft | 425 | 200 | 42 | 26250 |  | 17850 | 8400
|  | 3/8" diameter | 75 | Rft | 315 | 180 |  | 0 |  | 0 | 0
|  | 1/2" diameter | 72 | Rft | 425 | 200 | 45 | 28125 |  | 19125 | 9000
|  | 3/8" diameter | 72 | Rft | 315 | 180 |  | 0 |  | 0 | 0
|  | 1/2" diameter | 105 | Rft | 425 | 200 | 52 | 32500 |  | 22100 | 10400
|  | 3/8" diameter | 105 | Rft | 315 | 180 |  | 0 |  | 0 | 0
|  | Sub Total (Page 02) | [5 empty] | 1049775 |  | 0 | 0
| 23 21 14 | Supply, Installation and Commissioning of U-PVC piping Class- D. with closed cell elastromeric 15mm thick Insulation for condensate drain including all cutting, fixing fitting, laying, cleaning, making good and supports complete in all respect as per drawings and specifications. | [7 empty] | 0 | 0
|  | 3/4" diameter | 35 | Rft | 160 | 80 | 51 | 12240 |  | 8160 | 4080
|  | 3/4" diameter | 38 | Rft | 160 | 80 | 9 | 2160 |  | 1440 | 720
|  | 3/4" diameter | 10 | Rft | 160 | 80 | 30 | 7200 |  | 4800 | 2400
|  | 3/4" diameter | 5 | Rft | 160 | 80 | 43 | 10320 |  | 6880 | 3440
|  | 3/4" diameter | 28 | Rft | 160 | 80 | 60 | 14400 |  | 9600 | 4800
|  | 3/4" diameter | 38 | Rft | 160 | 80 | 9 | 2160 |  | 1440 | 720
|  | 3/4" diameter | 10 | Rft | 160 | 80 | 31 | 7440 |  | 4960 | 2480
|  | 3/4" diameter | 5 | Rft | 160 | 80 | 38 | 9120 |  | 6080 | 3040
|  | 3/4" diameter | 28 | Rft | 160 | 80 | 72 | 17280 |  | 11520 | 5760
|  | Supply, Installation and Commissioning of Dampers as per SMACNA standards and specifications. | [7 empty] | 0 | 0
| 23 33 13.13 | Voume Control Dapmers (VCD) (Contd.) | [7 empty] | 0 | 0
|  | 14"x10" | 3 | No. | 3000 | 1000 | 0 | 0 |  | 0 | 0
|  | 24"x10" | 2 | No. | 5000 | 1000 | 4 | 24000 |  | 20000 | 4000
|  | 12"x8" | 3 | No. | 2000 | 1000 | 2 | 6000 |  | 4000 | 2000
|  | 16"x10" | 5 | No. | 3500 | 1000 | 5 | 22500 |  | 17500 | 5000
|  | 16"x8'' | 2 | No. | 3500 | 1000 | 2 | 9000 |  | 7000 | 2000
|  | 12''x6'' | 4 | No. | 3000 | 1000 | 5 | 20000 |  | 15000 | 5000
|  | 18"x10" | 6 | No. | 3750 | 1000 | 6 | 28500 |  | 22500 | 6000
|  | 16"x12" | 1 | No. | 3750 | 1000 | 1 | 4750 |  | 3750 | 1000
|  | 12"x10" | 2 | No. | 2400 | 1000 | 0 | 0 |  | 0 | 0
|  | 30"x12" | 1 | No. | 7500 | 1000 | 1 | 8500 |  | 7500 | 1000
|  | 14"x8'' | 2 | No. | 2300 | 1000 | 1 | 3300 |  | 2300 | 1000
A | 23 09 00 | MISCELLANEOUS | [7 empty] | 0 | 0
B |  | Supply, Installation & commissioning of brass tags for Equipment and system including all accessories complete in all respect. | 1 | Job | 20000 | 5000 | 0 | 0 |  | 0 | 0
C |  | Supply, Installation & commissioning of foundation for pipes and equipment including all noise and Vibration controller as per drawings and specifications. | 1 | Job | 60000 | 20000 | 1 | 80000 |  | 60000 | 20000
D | 23 09 00 | Supply, Installation & commissioning of hangers and supports for pipes and equipment including all noise and Vibration controller roller type and others as per drawings and specifications. | 1 | Job | 160000 | 20000 | 1 | 180000 |  | 160000 | 20000
|  | Painting on equipment / Hangers, Supports, Pipe etc as per specifications. | 1 | Job | 15000 | 10000 | 1 | 25000 |  | 15000 | 10000
F |  | Drawings | [5 empty] | 0 |  | 0 | 0
G |  | Shop Drawings as per specifications. | 1 | Job | 10000 | 5000 | 1 | 15000 |  | 10000 | 5000
|  | As Built Drawings as per specifications. | 1 | Job | 7000 | 5000 | 1 | 12000 |  | 7000 | 5000
H |  | Testing (3 months test run) & Commissioning with Air & water balancing | [7 empty] | 0 | 0
|  | HVAC System. | 1 | Job | 180000 | 10000 | 1 | 190000 |  | 180000 | 10000
I |  | Sundries | [7 empty] | 0 | 0
|  | Supply, installing and commissioning of items not listed in BOQ but required. | 1 | Job | 0 | 0 | 0 | 0 |  | 0 | 0
|  | Sub Total (Page 03) | [5 empty] | 710870 |  | 2757685 | 929535
|  | GRAND TOTAL FOR HVAC WORKS | [5 empty] | 3687220 |  | 303345.35 | 102248.85
|  | Less Discount | [5 empty] | 405594.2 |  | 2454339.65 | 827286.15
|  | Net Total Amount | [5 empty] | 3281625.8
Note: Quoted prices are exclusive of all taxes. | [10 empty] | 3281625.8