## rec details
Financail Summary for the project Imtiaz Super market DHA Phase VIII
[6 empty] | Contract Value | 26000000
Retention Hold 10%
[6 empty] | Payable amount | 26000000
Receiving details
Payment | Receiving date | Gross payment reeived | Tax rate | Tax deducted | SRB 20% | Chq amount | Remarks
Mobilization advance 25% | 2021-01-21 | 6500000 | 7.5% | 487500 | 0 | 6012500
Adhoc Payment against 1st bill | 2021-02-06 | 3000000 | 6.5% | 195000 | 0 | 2805000
Final payment 1st bill | 2021-11-17 | 1049580.0885 | 7% | 73470.6062 | 0 | 976109.4823
Adhoc Payment against 2nd bill
[8 empty] | 5580000 | 100000
90000
Total receiving till todate |  | 10549580.0885 | 0 | 755970.6062 |  | 9793609.4823 |  | 6000000
Net Receivable amount |  | 15450419.9115 |  |  |  | 16206390.5177 |  |  | 10000
-90000
3780000
283500
3496500

## Bill # 1
Imtiaz Store DHA
1st Bill Summary | Materrial | Labour
HVAC | 3146687 | 694538
Fire | 2217695 | 442028
Ttoal | 5364382 | 1136566
Discount 7.4333% | 397160.9262 | 84147.5505
Net Amount Receivable | 4967221.0738 | 1052418.4495
SST 13% | 0 | 136814.3984
Total amount |  | 6156453.9217
Less Mob advance 25% |  | 1504909.8808 | 25% on net amount before SST
Less Retention 10% |  | 601963.9523 | 10% on net amount before SST | 2350318.4845
Adhoc received |  | 3000000
Net Amount Receivable |  | 1049580.0885
1111932
Less Tax 7% |  | 73470.6062 |  |  |  | 109451
Less 20% SRB |  | 27362.8797 | 109451.5187 | 80% | 418441.937 | 1002481
Chq amount |  | 976109.4823
1003472.362
20% SRB did not deducted by client Imtiaz mistakenly, Mr. Urshan told that you will submit whole 100% SST amount to SRB There will be no issue and then i called to Mr. Zohaid Tax consultant he also endorsed this and said ok submit the whole amount

## Bill # 2
Imtiaz Store DHA
1st Bill Summary | Materrial | Labour
HVAC | 12142064 | 2589942
Fire | 3530785 | 618675 |  |  |  | Retention Money |  | Mobilization | 6500000
Total | 15672849 | 3208617 |  |  |  | 1st Bill | 601963.9523 | 1st Bill | 1504909.8808
Discount 7.4333% | 1160365.3926 | 237555.2859 |  |  |  | 2nd Bill | 1739574 | 2nd Bill | 4348936
Net Amount Receivable | 14512483.6074 | 2971061.7141 |  |  |  | 3rd Bill | 0 | 3rd Bill | 0
SST 13% | 0 | 386238.0228
Total amount |  | 17869783.3443
[6 empty] | Total hold | 2341537.9523 |  | 646154.1192
Less Mob advance 25% |  | 4370886.3304
Less Retention 10% |  | 1748354.5321
Net Amount Receivable |  | 11750542.4818
Adhoc received |  | 6000000
Net Payable |  | 5750542.4818
Less Tax 6% |  | 345032.5489
Less 20% SRB |  | 77247.6046 | 308990.4183 | 80% |  |  | 22300122.5703
12611405
Chq amount |  | 5405509.9329
9688717.5703
11384101.4035
1174473.7613
523052.4213
9686575.2209
|  |  |  | Loss | -2817797 |  | 2700000
|  |  |  | Liability | -2700000 |  | 6986575.2209
|  |  |  | Net loss | -5517797
|  |  |  | 2nd bill paymnt | -112287.0671
|  |  |  | after add retention | 2229250.8852
|  |  |  | after less remaining mob | 1583096.766
|  |  |  | 100% SRB 1st bill | 136814.3984
1446282.3676
|  |  |  | 80% SRB 1st bill | 308990.4183
|  |  |  | net profit | 1137291.9493