## Summery 1st IPC (hidden)
1st Running Bill
Total Construction
CONSTRUCTION OF NEW SURGICAL ONCOLOGY COMPLEX AT JPMC , KARACHI
Civil Works |  | SUMMARY
S # | BOQ # | Description | Previous Bill Amount | Current Bill Amount | Total Amount ( Rs)
Demolition Works
A | 01-1C | Demolition Works | 0 | #REF! | #REF!
B |  | Earth Work
| 01-2C | Excavation | 0 | #REF! | #REF!
| 01-4C | Back Filling ( out side source ) | 0 | #REF! | #REF!
| 01-5C | Stone Soling | 0 | #REF! | #REF!
C |  | Termite Control Treatment
| 01-6C | Termite | 0 | #REF! | #REF!
D |  | Reinforcement
| 01-7C | Steel Grade 70 | 0 | #REF! | #REF!
E |  | SUB-STRUCTURE
| 01-8C | Class 'E' concrete ( Lean for Foundation ) | 0 | #REF! | #REF!
| 01-10C | Class 'B' concrete (Footing / Foundation) | 0 | #REF! | #REF!
| 01-11C | Class 'A' concrete (Column up to plinth) | 0 | #REF! | #REF!
F |  | Water Proofing & Built up Roofing.
| 01-40C | Bitumen coating grade 10/20 | 0 | #REF! | #REF!
| Total ( A+B+C+D+E+F ) = G |  | 0 | #REF! | #REF! | #REF!
| I | Deduction Against Rebate @ 2.64 % | 0 | #REF! | #REF!
| H= G-I | Work done Amount after Rebate | 0 | #REF! | #REF! | #REF!
Extra Works detail
|  | Relocation of Electrical cables | 0 | 222300 | 222300
|  | Work done Amount including Extra Woks | 0 | #REF! | #REF!
DEDUCTIONS
| I | Recovery of OFM
| ia | Deduction Against Steel 91.23 tons @ 85500 per tons | 0 | -7800250.5 | -7800250.5
| ib | Deduction Against Cement @ 550/= Per Bag ( OPC ) [ 4184 bags ] | 0 | -2301200 | -2301200
| I | Total Amount after OFM Deduction | 0 | #REF! | #REF!
| ja | 10 % Of Retention Mooney | 0 | #REF! | #REF!
| jb | Mobilization Advance | 0 | -2000000 | -2000000
| J | Total Amount After deduction of Retention & Mobilization | 0 | #REF! | #REF!
|  | Deduction Income tax @7.5 % | 0 | #REF! | #REF!
| K | Total Payable Amount after all deductions | 0 | #REF! | #REF!

## Civil Works
PATIENT'S AID FOUNDATION - JPMC, KARACHI
CONSTRUCTION OF DEPARTMENT OF PSYCHIATRY & NEUROLOGY AT JPMC KARACHI
BILL OF QUANTITIES
Item No. | Description | Unit | Quantity | Rate | Total Amount (Rupees)
(1) | (2) | (3) | (4) | (5) | (6)
C. CIVIL WORKS
Providing, fabricating and applying at any elevation / height except where otherwise stated in the specific item of the Bill of Quantities including all material, labor, scaffolding & plant for the following items complete in all respects as per drawings, approved shop drawings, technical specifications, miscellaneous details and instructions by the Engineer.
EARTH WORKS
Ref. Sec.No. 1100
01-1C | Excavation in all kinds of sub-surface materials (soft/rock) upto any depths including disposal of surplus/rejected excavated materials to designated places at any lift. | Cft | 211225 | 17 | 3590825
01-3C | Fill and backfill with selected material obtained from from required excavation including compaction | Cft | 100000 | 4 | 400000
01-4C | Fill and backfill with selected material obtained from outside sources including compaction. | Cft | 34212 | 31 | 1060572
STONE SOLING
Ref. Sec.No. 1300
01-5C | 6" inch thick compacted stone soling under floor and plinth protection. | Sft | 26000 | 40 | 1040000
TERMITE CONTROL TREATMENT
Ref. Sec.No. 1600
01-6C | Provide and spray approved pesticide solution as per manufacturer's recommendation in excavated earth, consolidated layer or earth under floor etc., complete as per specifications by approved agency of Termite Control for building (ground floor area will be measured for payment). Warranty period to be mentioned and warranty Certificate to be provided by the Contractor for Ten years. | Sft | 26000 | 15 | 390000
REINFORCEMENT
Ref.Spec. No.2200
01-7C | Providing and laying reinforcement bars using hot rolled deformed billet steel bars conforming to ASTM A-706 Grade 60 with specified yield strength not less than 60000 psi nor more than 78000 psi and ratio of ultimate strength to yield strength not less than 1.25, including the cost of straightening, cutting, bending, binding, wastage and such overlaps as are not shown over the drawings, placing in position on chairs, tying with binding wires, etc., in all kinds of RCC work complete in all respects. | tonne | 1103 | 136735 | 150818705
PLAIN AND REINFORCED CONCRETE
Ref.Spec. No.2100, 2200, 2300
Providing and laying ready mix cement concrete including plant/ mixing, transporting, hoisitng, placing formwork scaffolding, vibrating and curing etc including the cost of formwork and its removal complete as per drawings and specifications (but excluding the cost of the reinforcement).
SUB-STRUCTURE
01-8C | Ready mix Class 'E' concrete using ordinary Portland cement (OPC) as shown on the drawings. | Cft | 15087 | 248 | 3741576
01-9C | Ready mix Class 'D' concrete using ordinary Portland cement (OPC) in steps, lift well, under plinth beams & plinth protection etc. | Cft | 623.2228 | 442 | 275464.4891
01-10C | Ready mix Class 'A' reinforced concrete using ordinary Portland cement (OPC) in following sub-structures as per design shown on the drawings:
| a) Footing / Foundations | Cft | 79492 | 405 | 32194260
| b) Plinth Beams | Cft | 8840 | 500 | 4420000
| c) Grade Slab | Cft | 12300 | 398 | 4895400
| c) Cable Trench, Oil Pit and Fuel Tank (Base & Wall) | Cft | 100 | 659 | 65900
| d) RCC planks with hooks | Cft | 124.6446 | 718 | 89494.7978
| e) Base walls and top slab (U.G.W.Tank and pump room) | Cft | 10000 | 504 | 5040000
01-11C | Ready mix Class 'A1' reinforced concrete using ordinary Portland cement (OPC) in following sub-structures as per design shown on the drawings:
b | b) Column upto Plinth | Cft | 3065 | 616 | 1888040
01-12C | Ready mix Class 'A2' reinforced concrete using ordinary Portland cement (OPC) in following sub-structures as per design shown on the drawings:
b | a) Lift walls upto Plinth | Cft | 618 | 626 | 386868
01-13C | Ready mix Class 'A' reinforced concrete using ordinary portland cement (OPC) in following super-structures as per design shown on the drawings:
a | Beams & Lintels | Cft | 42413 | 586 | 24854018
b | Slab & Projections | Cft | 57256 | 565 | 32349640
c | Ramps | Cft | 7229.3848 | 450 | 3253223.1522
d | Staircase (Waist slab, steps and Landing) | Cft | 3116.1141 | 632 | 1969384.1304
e | RCC Ribs | Cft | 2492.8913 | 565 | 1408483.587
f | R.C.C Purdi | Cft | 872.512 | 783 | 683176.862
g | OH Water Tank (Bottom slab, Wall and Top slab) | Cft | 900 | 502 | 451800
01-14C | Ready mix Class 'A1' Concrete using ordinary Portland cement (OPC) in following super - structures as per design shown on the drawings.
a | Columns | Cft | 24400 | 640 | 15616000
01-15C | Ready mix Class 'A2' Concrete using ordinary Portland cement (OPC) in following super - structures as per design shown on the drawings.
a | Lift Walls | Cft | 4019.7872 | 653 | 2624921.0601
01-16C | Precast pigmented Cement concrete Jali as per design fixed in approved pattern, set in 1:2 cement sand mortar, complete in all respect as shown on drawings. | Sft | 498.5783 | 179 | 89245.5087
01-17C | Providing and fixing pre-cast rainwater spouts complete in all respects as shown on drawings. | No. | 10 | 5000 | 50000
STRUCTURAL/ STAINLESS STEEL
Ref.Spec. No.3000, 3010
01-18C | Providing fabricating and fixing of mild steel doors including louvered, hardware fittings, enamel paint over anti-corrosive paint, complete in all respects as shown on the drawings & specifications and /or as directed by the Engineer.
a | Type STD1 | Kg. | 249.2891 | 276 | 68803.8
b | Type STD2 | Kg. | 186.9668 | 276 | 51602.85
c | Type STD3 | Kg. | 124.6446 | 276 | 34401.9
01-19C | Supply, fabrication and fixing of angle iron (size 2" x 2" x 1/4') 1/4" thick chequred plate with anchor 1/4" x 1" and 6" long at 12" c/c welded to channel including hardware, enamel paint over anti-corrosive paint, complete in all respects as specified and as shown on the drawings & as per manufacturer/ supplier requirement.
a | Chequred Plate | Kg. | 436.256 | 295 | 128695.5136
b | Angle | Kg. | 249.2891 | 263 | 65563.0413
c | Channel | Kg. | 249.2891 | 263 | 65563.0413
01-20C | Supply, fabricating and fixing of floor/ wall mounted stainless steel staircase hand railing complete in all respect as specified and as shown on the drawings.
a | Wall mounted | Rft | 405.0948 | 1920 | 777782.087
b | Floor Mounted | Rft | 311.6114 | 4805 | 1497292.8397
c | 2" dia SS hand railing on Ramp wall | Rft | 997.1565 | 1920 | 1914540.5217
01-21C | Providing and fixing MS 2 hrs fire rated door shutter with frame including hardwares and all other accessories, painting etc complete in all respect as per manufacturer specifications and/or as directed by the Engineer.
a | Type D3 | No. | 4.9858 | 113827 | 567516.677
01-22C | Providing and laying powder coated MS louvers/ fins section complete in all respects as per drawings, specifications and /or as directed by the Engineer. (Sample and shade as approved by the Architect) | Sft | 498.5783 | 1446 | 720944.1652
BLOCK MASONRY
Ref.Spec. No.4100
01-23C | Solid block masonry wall of the following thickness set in 1:6 cement sand mortar including stiffener columns, D.P.C. & curing etc. complete in all respect as shown on the drawings and as per specifications.
a | 4" thick | Cft | 2555.2136 | 447 | 1142180.4734
b | 6" thick | Cft | 46106.0247 | 416 | 19180106.2643
01-24C | Hollow block masonry wall on facade set in 1:6 cement sand mortar including filling Class -"D" cement concrete, reinforcement, stiffener columns, D.P.C. & curing etc. complete in all respect as shown on the drawings.
a | 6" thick | Cft | 28045.0272 | 425 | 11919136.5489
CARPENTARY AND JOINERY
Ref.Spec. No.4600, 6700
01-25C | Providing and fixing doors of the following types consisting of G.I.frame (16 SWG) and solid shutter with texture formica facing (tuff grade), golden teak lipping including 1:2:4 cement concrete filling in door frame, mortise lock with handle, beading, architrave, fittings, kick plates, polishing and enamel paint etc. complete in all respects as per drawings, schedule & specifications and/or as directed by the Engineer.
Ground Floor
a | Type D1 | Sft | 2748.4127 | 1917 | 5268707.0751
b | Type D2 | Sft | 3664.5502 | 1917 | 7024942.7667
c | Type D3 | Sft | 706.7347 | 1917 | 1354810.3907
d | Type D7 | Sft | 34.9005 | 1917 | 66904.2168
01-26C | Providing and fixing doors of the following types consisting of G.I.frame (16 SWG) and solid core shutter with texture formica facing (tuff grade), wood frame, brass oval head screw with brass cup washers, golden teak wood lipping, 6 mm wired glass, brown sealant, golden teak wood bead door shutters including 1:2:4 cement concrete filling in door frame, 6mm thick clear glass, mortise lock with handle, hydraulic door closers (overhead type) of approved quality , beading, architrave, fittings, kick plate (both side) polishing and enamel paint etc. complete in all respects as per drawings, schedule & specifications and/or as directed by the Engineer.
a | Type D4 double door (panel) | Sft | 1614.1471 | 1825 | 2945818.4932
b | Type D5 double door | Sft | 149.5735 | 1691 | 252928.7517
c | Type D9 double door sliding | Sft | 349.0048 | 2039 | 711620.7517
d | Type D11 double door | Sft | 119.6588 | 1691 | 202343.0014
ALUMINUM WORK
Ref.Spec. No. 6220, 6250
01-27C | Providing and fixing fully glazed powder coated aluminum windows and ventilators of approved manufacturer using outer frame 2mm thick 4" wide extended sections and sliding/ fly proof shutters 1.6mm thick section, glazed with distortion free 5mm thick clear glass including all hardware, PVC/ rubber gaskit and sealant complete as per schedule and specifications and/or as directed by the Engineer. (Sample and shade as approved by the Architect)
A. Windows
| a) Sliding Type W1, 2, 3, 6, 7, 8, 9, 12, 13 | Sft | 6360.6122 | 904 | 5749993.3954
B. Ventilators
| a) Sliding Type W4 & W10 | Sft | 2337.0856 | 1190 | 2781131.8614
C. Fixed Glazing
| a) Fixed Type W15, W33 | Sft | 306.6256 | 740 | 226902.9665
Glass Partition
01-28C | Providing and fixing of 6mm thick glass Aluminum powder coated partition with 2mm thick 2" x 4" section, complete in all respects as shown on drawings and/or as directed by the Engineer. (Sample and shade as approved by the Architect) | Sft | 299.147 | 1038 | 310514.5409
01-30C | Providing and laying powder coated aluminum raling fins on balcony section 2mm thick 3" x 1-1/2", aluminum pipe fins @ 10" clear spacing between horizontal aluminum fins and 4" x 1-3/4" x 2mm aluminum vertical pipe supports, all exposed aluminum profiles in white standard powder coating finish complete in all respects as per drawings, specifications and/or as directed by the Engineer. (Sample and shade as approved by the Architect) | Sft | 498.5783 | 1456 | 725929.9478
CABINETS, COUNTERS AND VANITY TOPS
01-31C | Providing, making and fixing 3/4" thick granite slab vanity top including of the following 2" thick precast RCC slab with 1/2" thick plaster both sides, wash basin hole/ cutting, painting/ polishing complete in all respects as per drawings, specifications and/or as directed by the Engineer. (Basic Price of Granite = 350/ Sft) | Sft | 1495.7348 | 1101 | 1646803.9957
01-32C | Providing, making and fixing kitchien cabinet of the following consisting of 3/4" thick granite slab top, 2" thick precast slab with 1/2" thick plaster both sides, sink hole/ cutting, painting/ polishing complete in all respects as per drawings, specifications and/or as directed by the Engineer. (Basic Price of Granite = 350/ Sft)
a | Wall Mounted | Sft | 685.5451 | 1276 | 874755.5587
b | Floor Mounted | Sft | 810.1897 | 1965 | 1592022.7092
01-33C | Providing, making and fixing counters of the following consisting of wall hanging/ floor mounted cabinets, drawers, partitions, shelves and shutters with3/4" thick MDF Lasani board with tuff formica (by Formite or equivalent) facing both sides, framing and lipping with deodar wood, 1/2" thick Corian top including all hardware fittings, complete in all respects as per drawings, specifications and/or as directed by the Engineer. (Sample and shade as approved by the Architect) | Sft | 810.1897 | 4943 | 4004767.5582
01-34C | Providing and fixing 3/4" golden teak wood bumper rail with polishing complete in all respects as per drawings, specifications and/or as directed by the Engineer. (Sample and shade as approved by the Architect) | Rft | 5484.3609 | 759 | 4162629.9
WATER PROOFING & BUILT-UP ROOFING
Ref.Spec. No. 6411
01-36C | Providing and laying water proofing treatment over roof slab complete as per drawing/ details specificationS and/or as directed by Engineer. | Sft | 17500 | 377 | 6597500
01-37C | Providing & fixing construction joints in grade slab included bitumex impregnated soft board with 3/8" x 3/8" inch rubber bitumin sealent complete in all respect as per drawings/ specifications and/ or as per direction of Engineer. | Rft | 125 | 255 | 31875
01-38C | Providing and laying Torch-Bonding 4mm (3/16") thick high performance water proofing, modified bitumen sheet membrane over a coat of primer (as per manufacturer's specifications & recommendations) on all structural concrete surfaces contact with earth for U.G.Tank including 2" thick class E concrete, 4" thick block masonry, 18 swg aluminum flashing, polysulphide sealant, wooden plug and galvanized screws 12" c/c all around tank complete as per drawing, specification and/or directed by the Engineer. | As per Addendum
01-39C | Providing and applying two coats of Acrylic cementious flexible coating (SIKA or equivalent) to all internal surfaces of UG Tank as per drawing and specification and as per direction of Architect. | Sft | 3500 | 58 | 203000
01-40C | Providing and applying two coats of cold bitumen grade 10/20 @ of 1.00 Kg./Sq.m. Per coat to all structural concrete surfaces in contact with earth as specified. | Sft | 42000 | 29 | 1218000
CEMENT PLASTER
Ref.Spec. No. 6251
01-41C | Providing and laying plaster with cement sand mortar with G.I. expanded metal lathe at the interfaces of structures of different materials including staging and curing complete in all respect and / or as directed by the Engineer.
a | 1/2" thick plaster with 1:6 cement sand mortar on Ceilings. | Sft | 81018.9674 | 35 | 2835663.8587
b | 1/2" thick plaster with 1:6 cement sand mortar on interior Walls. | Sft | 145834.1413 | 45 | 6562536.3587
c | 3/4" thick, 1:4 cement sand plaster to exterior surface. | Sft | 44248.8207 | 67 | 2964670.9837
d | 3/4" thick, 1:4 cement sand plaster in internal surfaces of water Tank. | Sft | 3500 | 52 | 182000
e | Colorcrete on exterior surface including base plaster | Sft | 6855.4511 | 112 | 767810.5217
FALSE CEILING
Ref.Spec. No. 6560
01-42C | Providing & Fixing perforated MS powder coated (12" x 48") false ceiling with suspension system of approved colour and pattern including all accessories for built-in light fixtures & G.I. bar hangers with 18 SWG G.I. adjuster at any elevation as shown on the drawings and specifications. | Sft | 9784.5984 | 261 | 2553780.1745
01-43C | Providing & Fixing gypsum board (24"x24" / 4' x 8') false ceiling with aluminum suspension system of approved colour and pattern including all accessories for built-in light fixtures & G.I. bar hangers with 18 SWG G.I. adjuster at any elevation as shown on the drawings and specifications. | Sft | 6232.2283 | 155 | 965995.3804
01-44C | Providing & Fixing non perforated MS powder coated (12" x 48") false ceiling with suspension system of approved colour and pattern including all accessories for built-in light fixtures & G.I. bar hangers with 18 SWG G.I. adjuster at any elevation as shown on the drawings and specifications. | Sft | 1869.6685 | 261 | 487983.4728
FLOOR AND WALL FINISHES
Ref.Spec. No. 6600, 6531, 2300, 6521
01-45C | 4" thick Ready mix Class 'D' cement concrete under floor, foot path & plinth protection etc. | Sft | 21812.7989 | 104 | 2268531.087
01-46C | Providing and laying Porcelain tile in floor (Matt/Semi Glazed) full body of approved manufacturer / colour / shade and design laid over 1-1/2" or 2" thick base of Class 'C' concrete, setting tile in cement slurry, filling the joint with matching filling, washing, cleaning and curing, complete in all respects floor pattern as per drawings, specifications and/or as directed by the Engineer. (at any elevation)
Ground Floor
a | Size 24" x 24" | Sft | 82514.7022 | 356 | 29375233.9739
b | Size 12" x 24" | Sft | 9348.3424 | 356 | 3328009.8913
01-47C | Providing and laying Porcelain tile Skirting of approved manufacturer / colour / shade and design laid over pattern a rough plaster base, setting tile in cement slurry, filling the joint with matching filling, washing, cleaning and curing, complete in all respects as per drawings, specifications and/or as directed by the Engineer. (at any elevation)
a | Size 24" x 6" | Sft | 498.5783 | 355 | 176995.2826
01-48C | Providing and laying dado Porcelain Glazed tile 5'-0" high of approved manufacturer / colour / shade and design over pattern a rough plaster base, setting tile in cement slurry, filling the joint with matching filling, washing, cleaning and curing, complete in all respects, as per drawings, specifications and/or as directed by the Engineer. (at any elevation)
a | Size 24" x 24" cladding/ wain coat | Sft | 60764.2255 | 356 | 21632064.2935
b | Size 24" x 12" | Sft | 39886.2609 | 356 | 14199508.8696
01-49C | Providing and laying Granite Tlies in floor 24" x 24" x 3/4" thick of approved quality / colour / shade and laid over 1-1/2" or 2" thick base concrete, setting tile in cement slurry, filling the joint with white cement, grinding, polishing, washing, cleaning and curing etc. complete in all respects floor pattern as per drawings, specifications and/or as directed by the Engineer. (at any elevation) | Sft | 436.256 | 1217 | 530923.5255
01-50C | Providing and laying Granite Tlies 12" x 6" x 1/2" skirting of approved quality / colour / shade and base plaster, setting tile in cement slurry, filling the joint with white cement, grinding, polishing, washing, cleaning and curing etc. complete in all respects floor pattern as per drawings, specifications and/or as directed by the Engineer. (at any elevation) | Sft | 124.6446 | 1219 | 151941.725
01-51C | Providing and laying Granite Tlies 24" x 24" x 3/4" thick cladding/waincoat upto 5'-0" high of approved quality / colour / shade with base paster, setting tile in cement slurry, filling the joint with white cement, grinding, polishing, washing, cleaning and curing etc. complete in all respects floor pattern as per drawings, specifications and/or as directed by the Engineer. (at any elevation)
a | upto 5ft high | Sft | 498.5783 | 1205 | 600786.8043
b | upto false ceiling height | Sft | 1121.8011 | 1212 | 1359622.9174
01-52C | Providing and fixing of cladding porcelain tiles (CITY Tiles) on walls of approved quality / colour / shade with base paster, setting tile in cement slurry, filling the joint with white cement, washing, cleaning and curing etc. complete in all respects floor pattern as per drawings, specifications and/or as directed by the Engineer. (at any elevation) | Sft | 436.256 | 359 | 156615.8962
01-53C | Providing and applying 1/2 inch thick wash terrazo consisting of 1:1-1/2 white cement:dana (chips) graded, U Aluminum groove 1 x 1/2" (H) with seaer (Fospak) complete in all respect and/or as directed by the Engineer. (at any elevation) | Sft | 44248.8207 | 342 | 15133096.663
01-54C | Providing and laying Granite on tread, riser, landing and ramp of approved quality / colour / shade and over pattern a base of Class 'C' concrete, setting tile in cement slurry, filling the joint with white cement, grinding, polishing with round nosing, washing, cleaning and curing etc. complete in all respects floor pattern as per drawings, specifications and/or as directed by the Engineer. (at any elevation) (Basic Price of Granite = 500/ Sft)
| a) 3/4" Thick on Tread & Landing | Sft | 2368.2467 | 1142 | 2704537.7761
| b) 1/2" Thick on Riser | Sft | 1256.4172 | 944 | 1186057.8532
01-55C | Providing and laying wash terrazo in ramp floor 3/4" thick consisting of 1:1-1/2 grey cement:dana (chips) graded, approved quality / colour / shade / and laid over 1-1/2" or 2" thick base concrete, wasing, cleaning ad curing etc. complete in all respect and/or as as per drawings, specifications and/or as directed by the Engineer. (at any elevation) | Sft | 7478.6739 | 300 | 2243602.1739
01-56C | Providing & fixing 3mm thick vinyl antistatic seamless flooring with covered skirting returned a minimum 0f 4" or equalant, complete in all respects as per manufacturer's specifications and/or as directed by the Engineer. | Sft | 2181.2799 | 274 | 597670.6902
01-57C | Providing & fixing 3mm thick vinyl antistatic seamless wainscoat complete in all respects as per manufacturer's specifications and/or as directed by the Engineer.
a) | a) Upto 5' - 0" | Sft | 1526.8959 | 248 | 378670.1891
01-58C | Providing and laying C.C. Chequred tile (12" x 12") of approaved quality manufacture and base of Class C concrete, setting tile in cement slurry, filling the joint with cement, washing, cleaning and curing etc. complete in all respects floor pattern as per drawings, specifications and/or as directed by the Engineer. | Sft | 3739.337 | 220 | 822654.1304
01-59C | Providing and laying P.C.C. (1:2:4) floor on U.G.Water tank and service emergency staircase, curing, complete in all respects floor pattern as per darwings, specifitions and/or as directed by the Engineer. | Sft | 6232.2283 | 78 | 486113.8043
01-60C | Providing and fixing PCC Jali from approved manufacture design and pattern including joint with 1:2 cement mortar curing etc., complete in all respect as per drawings, specifications and/or as directed by the Engineer. | Sft | 373.9337 | 179 | 66934.1315
PAINTING
Ref.Spec. No. 6700
01-61C | Providing and applying 3 coats of Plastic Emulsion Paint of approved shade over a coat of primer of the approved manufacturer to all internal surfaces including smooth filling complete as per specifications in any floor/height. | Sft | 176995.2826 | 37 | 6548825.4565
01-62C | Providing and applying 3 coats of Anti microbial Paint of approved shade over a coat of primer of the approved manufacturer to all internal surfaces including smooth filling complete as per specifications in any floor/height. | Sft | 36458.5353 | 42 | 1531258.4837
01-63C | Providing and applying 3 coats of weather shield on exterior surfaces of approved shade over a coat of primer of the approved manufacturer to all internal surfaces including smooth filling complete as per specifications in any floor/height. | Sft | 373.9337 | 42 | 15705.2152
EXTERNAL DEVELOPMENT
01-64C | Preparation of sub-grade including cutting and filling upto 12" thick, levelling, dressing, compaction 95% modified AASHTO density minimum required complete in all respects as shown on drawings and/or as directed by the Engineer. | Sft | 10000 | 10 | 100000
01-65C | Aggregate sub-base (6" thick) course complete in all respects as shown on drawings and/or as directed by the Engineer. | Cft | 5000 | 53 | 265000
01-66C | Aggregate base (6" thick) course complete in all respects as shown on drawings and/or as directed by the Engineer. | Cft | 2500 | 53 | 132500
01-67C | Bituminous binder course (60 mm thick) including prime coat complete in all respects as shown on drawings and/or as directed by the Engineer. | Sft | 10000 | 162 | 1620000
01-68C | Bituminous wearing course (40 mm thick) including tack coat complete in all respects as shown on drawings and/or as directed by the Engineer. | Sft | 10000 | 130 | 1300000
01-69C | Providing and laying pre-cast kerb block (size 12"x18"x6' thick) including setting, jointing, pointing in cement sand mortar (1:4), earth works, class -"E" concrete etc. complete in all respects as shown on drawing and/or as directed by the Engineer. | Rft | 875 | 289 | 252875
01-70C | Providing, laying and fixing deodar wood bench, 2" thick wood plank (Size 6'-0" x 1'-4" x 1'-6") complete in all respects as shown on drawing and/or as directed by the Engineer. | Nos. | 185 | 17742 | 3282270
01-71C | Providing and fixing Granite over RCC seats on external area complete in all respects as shown on drawing and/or as directed by the Engineer. (Basic Price of Granite = 350/ Sft) | Nos. | 6 | 24415 | 146490
MISCELLANEOUS ITEMS
01-72C | Providing, supplying and fixing aluminum curtain railing of approved quality or manufacturer complete in all respects as shown on drawing and/or as directed by the Engineer. | Sft | 2212.441 | 235 | 519923.6427
01-73C | Development of lawn grass by providing nad planting comprising of the following: | Sft | 3116.1141 | 100 | 311611.413
a | Rough dressing of the area upto required level
b | Garden soil (sweet earth) upto 6" thick
c | Cow dung manure fertilizer as shown on drawing or approved by the consultant
d | Preparation of bed for final finishing including sprinkiling water and raking.
e | Greasing of approved quality by dibbling pace of grass roots 3" apart including watering, weeding till such time the grass is set and become green and is fit for moving, complete as above (a to e) and a sdirected by the consultant.
f | Waterproofing with approve waterproof chemical mixed with 2" thick screed layed on surfaces.
| TOTAL COST OF CIVIL WORKS (carried over to summary) |  |  |  | 510481502 | 510481510.3379 | -8.3379
-0.020587

## Communication Works (Str Cable)
PATIENT'S AID FOUNDATION - JPMC, KARACHI
CONSTRUCTION OF DEPARTMENT OF PSYCHIATRY & NEUROLOGY AT JPMC KARACHI
BILL OF QUANTITIES
Item No. | Description | Unit | Quantity | Rate | Total Amount (Rupees)
(1) | (2) | (3) | (4) | (5) | (6)
T. COMMUNICATION SYSTEMS
Supply, installation, configuration, programming, testing, commissioning and training of the following items of work (unless specifically stated otherwise) including all material, labour, tools, plant, storage, transpotation, accessories, etc., required for proper completion of each item as per specifications (General specifications for Electrical Works Section - 8001 and General Technical Requirements for Communication Works Section– 8002 shall be applicable to all relevant BOQ items).
STRUCTURED CABLING NETWORK Ref. Sec. 8001, 8002, 8230, 8290, 8312
01-1T | 12" x 3" size solid bottom sheet steel cable trunking with cover including joints, bends, mounting brackets hanger complete with all accessories. | Rft. | 1875 | 1280 | 2400000
01-2T | 12" x 3" ladder type sheet steel cable trunking including joints, bends, mounting brackets hanger complete with all accessories. | Rft. | 75 | 650 | 48750
01-3T | 1" dia PVC conduit installed concealed including all installation and mounting accessories. | Rft. | 13146 | 30 | 394380
01-4T | Wiring of RJ45 telecommunication wall outlet from relevant Floor Distributor with CAT-6A UTP LSZH cable in already installed conduit / cable trunking. | Nos. | 414 | 6050 | 2504700
01-5T | Following type CAT-6A UTP RJ45 telecommunication wall outlet with sheet steel back box and face plate including all installation accessories. |  |  |  | 0
a | One Port | Nos. | 111 | 1270 | 140970
b | Two Port | Nos. | 146 | 2000 | 292000
01-6T | Two Port CAT-6A UTP RJ45 telecommunication floor / furniture outlet with furniture mount backbox and face plate including all installation accessories. | Nos. | 5 | 2000 | 10000
01-7T | Following type CAT-6A UTP LSZH Giga Speed patch cord with RJ45 connectors at both ends. |  |  |  | 0
a | 1 meter (3ft.) long CAT-6A UTP LSZH Giga Speed patch cord with RJ45 connectors at both ends. | Nos. | 163 | 900 | 146700
b | 3 meter (3ft.) long CAT-6A UTP LSZH Giga Speed patch cord with RJ45 connectors at both ends | Nos. | 93 | 1140 | 106020
01-8T | 1 meter (3ft.) long CAT-6A UTP LSZH Giga Speed patch cord with RJ45 connectors at one end and required IDC connector at another end. | Nos. | 159 | 600 | 95400
01-9T | 1 meter (3ft.) long single pair patch cord with required IDC connector at both ends. | Nos. | 159 | 600 | 95400
01-10T | CAT-6A UTP Giga Speed loaded 24 port modular (RJ45) jack patch panels, 19" rack installed in floor/wall mounted cabinet including built-in rear cable management with all mounting accessories. | Nos. | 21 | 25350 | 532350
01-11T | 19" Rack mounted Front Cable Management with all installation accessories. | Nos. | 21 | 3760 | 78960
01-12T | Following type Intermediate Disconnection Module (IDC) with mounting frame including all installation accessories |  |  |  | 0
a | 10-Pair | Nos. | 25 | 6360 | 159000
b | 100-Pair | Nos. | 8 | 21000 | 168000
01-13T | 16 SWG Main Distribution Frame (MDF) for installation of Intermediate Disconnection Module (IDC) for 1000 pair with mounting frame including 25% expansion capacity with all installation and mounting accessories. | No. | 1 | 175000 | 175000
01-14T | 25 Pair CAT-5 UTP LSZH backbone cable in already installed PVC Conduit / cable trunking | Rft. | 375 | 235 | 88125
01-15T | Layer-2 Managed Ethernet PoE Access Switch having 24x10/100/1000 Mbps BASE-T out sensing ports SFP+ Module 2x10G ethernet uplink ports over fiber optic including power supply, all interconnecting cabling, required accessories.(Cisco Catalyst 2960 X / approved equivalent). | Nos. | 21 | 420000 | 8820000
01-16T | SFP+ Transceiver Multi Mode (10 Gbps) | Nos. | 43 | 85000 | 3655000
01-17T | Layer-3 Managed Ethernet Core Switch having 48 port SFP+ Module for downlink to access switch and 6 port QSFP uplink module for core to core connection over fiber optic power supply, all interconnecting cabling, required accessories. (Cisco Nexus 9300 / approved equivalent). | Nos. | 3 | 4600000 | 13800000
01-18T | SFP+ Transceiver Multi Mode (10 Gbps) | Nos. | 63 | 85000 | 5355000
01-19T | QSFP Transceiver Multi Mode (40 Gbps) | Nos. | 5 | 125000 | 625000
01-20T | SFP Transceiver Copper (1 Gbps) | Nos. | 10 | 52800 | 528000
01-21T | PABX having CPU duplication in hot/standby mode, power supply duplicated in hot/standby mode, including MDF, tele maintanance terminal computer, call accounting software, automatic call distribution system, mainteinance free backup batteries for 2 hours, 1 x operator console, DISA facility, BGM, stablizer with 1 x ISDN PRI expanbale upto to 2 x ISDN PRI and 8 x analog trunk line expandable upto 10 analog trunk line, 140 x analog extension expandable upto 250 analog extension, 1 x Digital Extension, 10 x SIP Licenses. Complete in all respect for satisfactory operation of the entire system. (Alcatel-Lucent ALE OXE / approved equivalent) | Job. | 1 | 4039500 | 4039500
01-22T | Analog Set with CLI (Alcatel-Lucent / approved equivalent). | Nos. | 63 | 4125 | 259875
01-23T | Digital Telephone Set with all installation accessories. (Alcatel-Lucent / approved equivalent). | No. | 1 | 16500 | 16500
01-24T | SIP Telephone with Power over Ethernet (PoE) Technology with all essential interconnecting cables as required including installation and mounting accessories. (Alcatel-Lucent / approved equivalent). | Nos. | 13 | 26200 | 340600
01-25T | Media Converter from CAT-6A copper cable to single mode fiber optic cable with connectors and internal power suppy including all mounting and installation accessories. | No. | 1 | 49375 | 49375
01-26T | Network Security Firewall IT Security Equipment, power supply including all essentail subscription licenses for 3 years, 24/7 update, interconneccting cabling, power supply as required with all installation and mounting accessoreis. Complete in all respect. (Fortigate 501 E / approved equivalent). | No. | 1 | 2110000 | 2110000
01-27T | Wireless Controller having licenses, power supply, required interfaces, including all essentail interconnecting cabling as required with all installation and mounting accessories. Complete in all respect. (Cisco 3504 / approved equivalent). | No. | 1 | 765000 | 765000
01-28T | Wireless Access Point with POE or power adaptor including all installation and mounting accessories. Complete in all respect. (Cisco 1832 / approved equivalent) | No. | 31 | 40800 | 1264800
01-29T | 12 core 50um / 125um Multimode (OM4) LSZH optical fibre back bone cable in already installed conduit / cable trunking | Rft. | 813 | 200 | 162600
01-30T | Following type Duplex LC loaded multimode (OM4) module rack mountable fibre optic patch panel with pigtails and splice trays including all installation accessories |  |  |  | 0
a | 12 port | Nos. | 5 | 36600 | 183000
b | 48 port | Nos. | 3 | 60600 | 181800
01-31T | 1 meter (3ft.), Multi Mode (OM4) Fiber Optic Duplex Multi Mode (OM4) Patch Cord with required connectors at both ends. | Nos. | 105 | 2000 | 210000
| Following sizes 19" Rack with plexiglass door including hoops, side management, cable trays, fan for cooling, required Power Distribution Unit and power sockets, Power cabling in PVC concealed conduit from UDB to relevant Rack. Complete in all respect. |  |  |  | 0
a | 27U (600 mm x 600 mm) | Nos. | 5 | 46800 | 234000
b | 42U (800 mm x 600 mm) | No. | 1 | 105000 | 105000
| 4 inch ( Internal Diameter ) of underground uPVC Class 'D' pipes including all accessories, pipe range spacers, pull rope, pull boxes, sand bed, excavation & selected backfilling from excavation, complete in all respects. | Rft. | 88 | 925 | 81400
| RCC Handhole of size 2 ft (Length) x 2 ft (Width) x 2ft (Depth) with heavy duty C.I cover of size 1.5 ft x 1.5 ft including all civil works as required complete in all respect. | Job. | 1 | 35000 | 35000
| Appropriate size pull box for accomodating 2 x 4 inch dia class "D" uPVC pipe as shown on drawing. | Job. | 1 | 25000 | 25000
| Total Cost of Communication Works Carried over to Summary |  |  |  | 50282205
95022465

## Communication Works (CCTV)
PATIENT'S AID FOUNDATION - JPMC, KARACHI
CONSTRUCTION OF DEPARTMENT OF PSYCHIATRY & NEUROLOGY AT JPMC KARACHI
BILL OF QUANTITIES
Item No. | Description | Unit | Quantity | Rate | Total Amount (Rupees)
(1) | (2) | (3) | (4) | (5) | (6)
T. COMMUNICATION SYSTEMS
Supply, installation, configuration, programming, testing, commissioning and training of the following items of work (unless specifically stated otherwise) including all material, labour, tools, plant, storage, transpotation, accessories, etc., required for proper completion of each item as per specifications (General specifications for Electrical Works Section - 8001 and General Technical Requirements for Communication Works Section – 8002 shall be applicable to all relevant BOQ items).
| CCTV SYSTEM Ref. Spec. Sec. 8001, 8002, 8230, 8290, 8335 |  |  |  | 0
01-1T | 1" dia PVC conduit installed concealed including all installation and mounting accessories. | Rft. | 8125 | 30 | 243750
01-2T | Wiring from relevant CCTV Rack to IP camera with CAT-6A, UTP LSZH cable in already installed conduit. | Nos. | 144 | 6050 | 871200
01-3T | IP Bullet colour fixed camera having 5 megapixel resolution, 1/2.9 inch sensor with varifocal lens, power over ethernet (PoE) having video analytic function, H.264/265 compression including all installation and mounting accessories | Nos. | 118 | 117950 | 13918100
01-4T | Weather proof type IP Bullet colour fixed camera having 5 megapixel resolution, Built-in IR, 1/2.9 inch sensor with varifocal lens, power over ethernet (PoE) having video analytic function, H.264/265 compression including all installation and mounting accessories. (IP65 Rated) | Nos. | 18 | 117950 | 2123100
01-5T | Weather proof type IP dome colour PTZ camera with built-in IR having 2 mega pixel resolution with power supply, power adaptor / PoE injector, 1/3 inch image sensor, 30X Optical Zoom, 12 X Digital Zoom, 360 degree rotation, video analytic function, H.264/265 compression including required backbox, cover, all installation and mounting accessories. (IP65 Rated) | Nos. | 9 | 375750 | 3381750
01-6T | Layer-2 Managed Ethernet PoE Access Switch having 24x10/100/1000 Mbps BASE-T out sensing ports SFP+ Module 2x10G ethernet uplink ports over fiber optic including power supply, all interconnecting cabling, required accessories.(Cisco Catalyst 2960 X / approved equivalent). | Nos. | 10 | 420000 | 4200000
01-7T | SFP+ Transceiver Single Mode (10 Gbps) | Nos. | 20 | 85000 | 1700000
01-8T | Network Video Storage on H.264/265 compression standard and Raid 5 backup storage for 130 nos. of cameras with recording resolution at 1080p at 30 fps for 24 hours of 30 days with 25% expansion capacity for future use including central management server, latest operating windows, latest SQL server, camera management application software and licenses complete in all respect. | No. | 1 | 3425000 | 3425000
01-9T | 6 nos. 42" LED Full HD Monitor / Display, 1920x1080P resolution with all essentail interconnecting equipment, decoders, workstations, interconnecting cables, mounting brackets/frames, installation accessories etc. as required complete in all respect. | No. | 1 | 800000 | 800000
01-10T | Latest Generation Computer comprising 21 inch LED Display Screen, CPU with license operating system, licensed Antivirus, licensed with software, Keyboard, Mouse with all essential interconnecting cables as required for system operation. | No. | 1 | 462500 | 462500
01-11T | Operator Console with drawers and chairs for housing LED Displays, PTZ Controller, PA remote microphone, Telephone set and computer including all installation & mounting accessories. | No. | 1 | 650000 | 650000
01-12T | PTZ Controller with Keyboard including interconnecting cables with all installation accessories | No. | 1 | 160000 | 160000
01-13T | CAT-6A UTP Giga Speed loaded 24 port modular (RJ45) jack patch panels, 19" rack installed in floor/wall mounted cabinet including built-in rear cable management with all mounting accessories. | Nos. | 8 | 25350 | 202800
01-14T | 19" Rack mounted Front Cable Management with all installation accessories. | Nos. | 8 | 3760 | 30080
01-15T | 1 meter (3ft.) long CAT-6A UTP LSZH Giga Speed patch cord with RJ45 connectors at both ends. | Nos. | 144 | 900 | 129600
01-16T | 12 port Duplex LC loaded multimode (OM4) module rack mountable fibre optic patch panel with pigtails and splice trays including all installation accessories | Nos. | 5 | 38500 | 192500
01-17T | 18U (600 mm x 600 mm) 19" Rack with high performance epoxy paint suitable for corrosive environment, plexiglass door including hoops, side management, cable trays, fan for cooling and exhaust, required Power Distribution Unit and power sockets, Power cabling in PVC concealed conduit from UDB to relevant Rack complete in all respect. | Nos. | 5 | 46000 | 230000
01-18T | 1 meter (3ft.), Multi Mode (OM4) Fiber Optic Duplex Multi Mode (OM4) Patch Cord with required connectors at both ends. | Nos. | 20 | 6000 | 120000
| Total Cost of Communication Works Carried over to Summary |  |  |  | 32840380

## Communication Works (NAS)
PATIENT'S AID FOUNDATION - JPMC, KARACHI
CONSTRUCTION OF DEPARTMENT OF PSYCHIATRY & NEUROLOGY AT JPMC KARACHI
BILL OF QUANTITIES
Item No. | Description | Unit | Quantity | Rate | Total Amount (Rupees)
(1) | (2) | (3) | (4) | (5) | (6)
T. COMMUNICATION SYSTEMS
Supply, installation, configuration, programming, testing, commissioning and training of the following items of work (unless specifically stated otherwise) including all material, labour, tools, plant, storage, transpotation, accessories, etc., required for proper completion of each item as per specifications (General specifications for Electrical Works Section - 8001 and General Technical Requirements for Communication Works Section – 8002 shall be applicable to all relevant BOQ items).
ADDRESSABLE NURSE CALL SYSTEM Ref.Spec.Sec.8001,8002, 8212,8230,8240,8290, 8343
01-1T | Network Controller with required software, LCD Display, keypad Programmable Controlling functions and shall have capacity for 2 X 7Ah backup batteries with all essential interconnecting cables as required complete in all respect. | Job. | 1 | 110000 | 110000
01-2T | Network Splitter with all installation and mounting accessories. | Nos. | 13 | 8150 | 105950
01-3T | Nursing Call Station with LCD display with Programmable Controlling functions as required with all installation and mounting accessories. | Nos. | 13 | 350000 | 4550000
01-4T | Bed Call Station suitable for installation in bed head panel with all installation and mounting accessories. | Nos. | 198 | 13400 | 2653200
01-5T | Reset button with all installation and mounting accessories. | Nos. | 60 | 13400 | 804000
01-6T | Call Station Ceiling pull type with all installation and mounting accessories | Nos. | 60 | 10800 | 648000
01-7T | Addressable Overdoor Indicator with all installation and mounting accessories. | Nos. | 15 | 7850 | 117750
01-8T | Latest Generation Industrial Workstation comprising 21" LCD Screen, CPU with license operating system, license Antivirus, Nurse Call Software, Keyboard, Mouse with all essential interconnecting cables as required for system operation. | Nos. | 9 | 195000 | 1755000
01-9T | Following type cables for wiring of nurse call system in already installed PVC conduit / cable trunking. |  | 0 |  | 0
a | Manufacturer's recommended room wiringc between Call Station and Splitter in wards | Rft. | 2000 | 65 | 130000
b | Manufacturer's recommended Limb wiring between Addressable Overdoor Light Indicator, Nurse Station and Splitter in wards. | Rft. | 313 | 140 | 43820
c | Manufacturer's recommended Spine wiring between Splitter and Network Controller | Rft. | 1500 | 65 | 97500
01-10T | 1" dia PVC conduit installed concealed including all installation and mounting accessories | Rft. | 2500 | 30 | 75000
01-11T | One Port CAT-6A STP RJ45 telecommunication wall outlet with sheet steel back box and face plate including all installation accessories. | Nos. | 9 | 2000 | 18000
01-12T | Wiring of RJ45 telecommunication wall outlet from relevant Ward Distributor with CAT-6A UTP LSZH cable in already installed conduit / cable trunking | Nos. | 9 | 6050 | 54450
01-13T | CAT-6A UTP Giga Speed loaded 24 port modular (RJ45) jack patch panels, 19" rack installed in floor/wall mounted cabinet including built-in rear cable management with all mounting accessories. | No. | 1 | 25350 | 25350
01-14T | 19" Rack mounted Front Cable Management with all installation accessories. | No. | 1 | 3760 | 3760
01-15T | 1 meter (3ft.) long CAT-6A UTP LSZH Giga Speed patch cord with RJ45 connectors at both ends. | Nos. | 9 | 900 | 8100
01-16T | Layer-2 Managed Ethernet PoE Access Switch having 24x10/100/1000 Mbps BASE-T out sensing ports SFP+ Module 2x10G ethernet uplink ports over fiber optic including power supply, all interconnecting cabling, required accessories.(Cisco Catalyst 2960 X / approved equivalent). | No. | 1 | 420000 | 420000
01-17T | SFP+ Transceiver Single Mode (10 Gbps) | Nos. | 3 | 85000 | 255000
01-18T | 9U (600 mm x 600 mm) 19" Rack, plexiglass door including hoops, side management, cable trays, fans for cooling and exhaust, required Power Distribution Unit and power sockets, Power cabling in PVC concealed conduit from UDB to relevant Rack complete in all respect. | No. | 1 | 25000 | 25000
| Total Cost of Communication Works Carried over to Summary |  |  |  | 11899880

## Electrical Works
PATIENT'S AID FOUNDATION - JPMC, KARACHI
CONSTRUCTION OF DEPARTMENT OF PSYCHIATRY & NEUROLOGY AT JPMC KARACHI
BILL OF QUANTITIES
Item No. | Description | Unit | Quantity | Rate | Total Amount (Rupees)
(1) | (2) | (3) | (4) | (5) | (6)
E. ELECTRICAL WORKS
Supply, installation, testing and commissioning of the following items of work (unless specifically stated otherwise) including all material, labour, tool, plant, accessories, related civil works etc required for proper completion of each item as per specifications (Section-8001 "General Specifications for Electrical Works" shall be applicable to all BOQ items). The contractor is bound to submit all relevent data, information, literature, drawings, submittals etc. as per specifications & recommended manufacturers list to The engineer for necessary approvals.
Diesel Generator Set Ref Spec Sec: 8111, 8132, 8212, 8240
1E | 300 kVA DG set (prime rating) on roof top including sound proof canopy (IP-65), skid mounted fuel tank, control / instrument panel, motorized generator neutral disconnecting switch, control wiring to GCP, LT switch boards, and ATS etc., testing of DG sets with load bank, related civil works, all components and accessories, complete in all respect. | Job. | 3 | 7647500 | 22942500
2E | Generator Control Panel (as per single line diagram shown on drawings) with synchcronization, load sharing & AMF panel for two number 300 kVA DG sets including, control wiring inside and to DG set, LT switch board and ATS etc., all components and accessories, complete in all respect. | Job. | 1 | 2950000 | 2950000
3E | ATS panel suitable for 300 kVA DG set includes control wiring to DG set, GCP and LT switch board etc., all components and accessories, complete in all respect. | Job. | 3 | Deleted | Deleted
4E | Fuel System for Two 300 kVA DG Sets comprising of underground fuel storage tank of 8000 liters capacity manufactured as per DIN 6608 / ASME Section VIII Div I including manhole cover, vent pipe, fuel piping, automatic fuel pumps (with level sensor control), etc., civil works (RCC foundation, water resistant), all related components and accessories. complete in all respect. | Job. | 3 | 650000 | 1950000
5E | Spare parts as per Appendix "V" Volume - 1 of bidding documents. | Job. | 3 | 85000 | 255000
| Indoor Power Transformer Ref Spec Sec: 8121 |  |  |  | 0
6E | 1250 kVA distribution transformer (indoor), 11/0.415 kV, including control wiring to HT/LT switchboard, cable mounting channels, related civil works and all accessories, complete in all respect | Job. | 1 | 2415000 | 2415000
7E | Spare parts as per Appendix "V" Volume - 1 of bidding documents. | Job. | 1 | 460000 | 460000
| HT Switch Boards Refer Specs Sec: 8131 |  |  |  | 0
8E | HT switchboard (as shown on single line diagram shown on drawings) suitable for 500 MVA, BIL 75 kV, 11 kV voltage rating comprising of incoming protection panel with surge arrester and 2 Nos. transformer panels with earthing switches including vaccum circuit breaker, protective relays, indications lamps, metering equipment, push buttons, control wiring, interlocking, related civil works and all accessories complete in all respect | Job. | 5 | 1985000 | 9925000
9E | Rubber insulation mat, one meter wide, 6 mm thick for laying in front of HT panels (3 no.) suitable to provide insulation for 15 kV rating including all accessories, complete in all respect. | Job. | 4 | 50000 | 200000
10E | Danger boards having signs and designation on the external doors of each room (HT / LT / Generator / Transformer) and shock and first aid charts in all rooms including all accessories, complete in all respect. | Job. | 4 | 50000 | 200000
11E | Spare parts as per Appendix "V" Volume - 1 of bidding documents. | Job. | 4 | 100000 | 400000
| LT Switchboard Ref Spec Sec: 8132, 8212, 8240 |  |  |  | 0
12E | Following 14 SWG MS sheet, floor mounted LT Switch boards (as per single line diagram shown on drawings) including electrical & mechanical components, electrolytic tinned copper busbars, control wiring, related civil works and all accessories, complete in all respect. |  |  |  | 0
| a) MPB | Job. | 1 | 5961500 | 5961500
| b) EMPB-1 | Job. | 1 | 2015450 | 2015450
| c) EMPB-2 | Job. | 1 | Deleted | Deleted
| d) SMPB-GF | Job. | 1 | 300450 | 300450
| e) ESMPB-GF | Job. | 1 | 311000 | 311000
| f) USMPB-GF | Job. | 1 | 198600 | 198600
| g) SMPB-1F | Job. | 1 | 300450 | 300450
| h) ESMPB-1F | Job. | 1 | 311000 | 311000
| i) USMPB-1F | Job. | 1 | 198600 | 198600
| j) SMPB-2F | Job. | 1 | 300450 | 300450
| k) ESMPB-2F | Job. | 1 | 311000 | 311000
| l) USMPB-2F | Job. | 1 | 198600 | 198600
| m) SMPB-3F | Job. | 1 | 300450 | 300450
| n) ESMPB-3F | Job. | 1 | 311000 | 311000
| o) USMPB-3F | Job. | 1 | 198600 | 198600
| p) SMPB-RF | Job. | 1 | 300450 | 300450
| q) ESMPB-RF | Job. | 1 | 311000 | 311000
| r) USMPB-RF | Job. | 1 | 198600 | 198600
0
13E | LT Distribution Boards Ref Spec Sec: 8133, 8212, 8240 |  |  |  | 0
| Following 16 SWG MS sheet, recessed / surface mounted on wall or floor LT Distribution Boards (as per single line diagram shown on drawings) including electrical & mechanical components, electrolytic tinned copper busbars, control wiring, related civil works and all accessories, complete in all respect. |  |  |  | 0
| Ground Floor (LT Distribution Board Under Item No. 13E) |  |  |  | 0
| a) DB-GF-1.1 | Job. | 1 | 178625 | 178625
| b) DB-GF-2.1 | Job. | 1 | 178625 | 178625
| c) EDB-GF-1.1 | Job. | 1 | 164500 | 164500
| d) EDB-GF-2.1 | Job. | 1 | 164500 | 164500
| e) UDB-GF-1.1 | Job. | 1 | 134550 | 134550
| f) UDB-GF-2.1 | Job. | 1 | 134550 | 134550
| First Floor (LT Distribution Board Under Item No. 13E) |  |  |  | 0
| a) DB-1F-1.1 | Job. | 1 | 178625 | 178625
| b) DB-1F-2.1 | Job. | 1 | 178625 | 178625
| c) EDB-1F-1.1 | Job. | 1 | 164500 | 164500
| d) EDB-1F-2.1 | Job. | 1 | 164500 | 164500
| e) UDB-1F-1.1 | Job. | 1 | 134550 | 134550
| f) UDB-1F-2.1 | Job. | 1 | 134550 | 134550
| Second Floor (LT Distribution Board Under Item No. 13E) |  |  |  | 0
| a) DB-2F-1.1 | Job. | 1 | 178625 | 178625
| b) DB-2F-2.1 | Job. | 1 | 178625 | 178625
| c) EDB-2F-1.1 | Job. | 1 | 164500 | 164500
| d) EDB-2F-2.1 | Job. | 1 | 164500 | 164500
| EDB-2F-3.1 | Job. | 1 | 164500 | 164500
| f) UDB-2F-1.1 | Job. | 1 | 134550 | 134550
| UDB-2F-2.1 | Job. | 1 | 134550 | 134550
| UDB-2F-3.1 | Job. | 1 | 134550 | 134550
| 4th Floor (LT Distribution Board Under Item No. 13E) |  |  |  | 0
| a) DB-3F-1.1 | Job. | 1 | 178625 | 178625
| b) DB-3F-2.1 | Job. | 1 | 178625 | 178625
| c) EDB-3F-1.1 | Job. | 1 | 164500 | 164500
| d) EDB-3F-2.1 | Job. | 1 | 164500 | 164500
| c) EDB-3F-2.1 | Job. | 1 | 164500 | 164500
| d) EDB-3F-2.1 | Job. | 1 | 134550 | 134550
| e) EDB-3F-2.1 | Job. | 1 | 134550 | 134550
| e) EDB-3F-2.1 | Job. | 1 | 134550 | 134550
| Roof (LT Distribution Board Under Item No. 13E) |  |  |  | 0
| a) DB-RF-1.1 | Job. | 1 | 178625 | 178625
| b) EDB-RF-1.1 | Job. | 1 | 164500 | 164500
| c)UDB-RF-1.1 | Job. | 1 | 134550 | 134550
| Motor Control Center Ref Spec Sec: 8133, 8135, 8212, 8240 |  |  |  | 0
14E | Following 14 SWG MS sheet, wall / floor mounted motor control center (as per single line diagram shown on drawings) including electrical & mechanical components, control wiring, related civil works and all accessories complete in all respect. |  |  |  | 0
| a) MCC-WP | Job. | 1 | 552900 | 552900
| b) MCC-FP | Job. | 1 | 859400 | 859400
15E | Lockable Mushroom Switch including control cable, all accessories, complete in all respect. |  |  | 32500 | 0
| Light Fixtures Ref. Specs Sec. 8150, 8212, 8240 |  |  |  | 0
16E | Following light fixtures as per lighting fixture schedule (as shown on drawing) installed on surface or wall or floor or false ceiling or columns or masts complete with all accessories such as lamps, lamp holders, ballasts, starters, ignitors, capacitors, LED drivers as applicable, etc. including all relevant installation material as required and approved by the Engineer. (Note: The contractor shall be reponsible for compatibility of recessed mounted light fixtures with gypsum / aluminium / dampa etc., false ceiling types in coordination with architectural design.) Note: The light fixtures & components shall be certified by international accredited laboratory. |  |  |  | 0
| a) Type - B1 LED bulk head light bi-directional (around 600 lumens, 8W), IP54 or better, in/out cable arrangement, | Nos. | 63 | 4370 | 275310
| b) Type - B2 Wall recessed/steps LED light fixture (around 100 lumens, 5W), IP54 or better, in/ouT cable arrangement | Nos. | 63 | 4370 | 275310
| c) Type - D1 Surface mounted 6 inch dia downlight (equivalent to 1500 lumens, 18W output), fixed output LED driver (built-in), IP20 or better | Nos. | 875 | 3365 | 2944375
| d) Type - D2 Surface mounted 6 inch dia downlight (equivalent to 900 lumens, 12W output), fixed output driver (built-in), IP20 or better | Nos. | 188 | 3365 | 632620
| e) Type - D3 Surface mounted 6 inch dia downlight (equivalent to 500 lumens, 6W ouput), fixed output LED driver (Built-in), IP20 or better | Nos. | 188 | 3365 | 632620
| f) Type - F1 Surface mounted LED decorative light (1200 mm) (equivalent to 4000 lumens, 40W output), fixed output LED driver (built-in), IP20 or better | Nos. | 188 | 8300 | 1560400
| g) Type - F2 Recessed mounted LED panel (1200 mm) (equivalent to 4000 lumens, 40W output), fixed output LED driver (built-in), IP20 or better | Nos. | 125 | 8300 | 1037500
| Addendum Type - F3 Surface/suspended mounted LED panel (1200mm) Equivalent to 4000 LUMENS, 40W fixed LED output LED Driver (Built-in), IP20 | Nos. | 625 | 10690 | 6681250
| h) Type - P1 LED flood light fixture (equivalent to 5000 lumens, 62W), IP54 or better | Nos. | 31 | 10690 | 331390
| i) Type - G1 Wall or surface mounted or suspended, non maintained type emergency light fixture, emergency 375 lumens with ni-cd battery backup unit for 3 hours backup, IP20, make of reputed manufacturer | Nos. | 125 | 10525 | 1315625
| j) Type - G2 Wall or surface mounted or suspended, maintained type emergency light fixture, emergency 375 lumens with ni-cd battery backup unit for 3 hours backup, IP20, make of reputed manufacturer | Nos. | 125 | 10525 | 1315625
| k) Type - EX1 Wall or surface mounted or suspended, non maintained type exit light fixture with pictograms, with ni-cd battery backup unit for 3 hours backup, IP20, make of reputed manufacturer | Nos. | 125 | 8510 | 1063750
| HT Cables Refer Specs Sec: 8211 |  |  |  | 0
17E | 120 mm2, 3 core, 15/8.7 kV, copper conductor with PVC screen, XLPE insulation, PVC screen, copper shielding, PVC bedding, galvanized steel wire armoured, extruded PVC sheathed cable laid in already built cable trenches or PVC sleeves including tags, ties, color sleeves, cable glands, lugs, sleeves/pipes plugging all accessories, complete in all respect. | Rft. | 313 | 3970 | 1242610
18E | For item No. 18E terminaiton kit with color sleeves including all accessories, complete in all respect installed |  |  |  | 0
| a) HT Switchboard | Nos. | 3 | 45000 | 135000
| b) Power Transformer including cable termination support | Nos. | 3 | 50000 | 150000
| LT Cables Ref. Specs Sec. 8212, 8240 |  |  |  | 0
19E | Following sizes, 600/1000 V, Single core or multi core, copper conductor, PVC insulated, armoured / unarmoured, PVC Sheathed cable pulled in already installed surface mounted conduits or concealed conduits or cable tray or concrete ducts or underground in already excavated trenches or in already laid PVC pipes including tags, ties, lugs, termination kits, colour sleeves, cable glands, bushes etc., all related accessories, complete in all respect. |  |  |  | 0
| a) 1 core, 240 mm2, Cu/PVC/PVC | Rft. | 625 | 2325 | 1453125
| b) 4 core, 240 mm2, Cu/PVC/PVC | Rft. | 375 | 8500 | 3187500
| c) 4 core, 150 mm2, Cu/PVC/PVC | Rft. | 1875 | 5390 | 10106250
| d) 4 core, 70 mm2, Cu/PVC/PVC | Rft. | 1875 | 2570 | 4818750
| e) 4 core, 50 mm2, Cu/PVC/PVC | Rft. | 1875 | 1810 | 3393750
| f) 4 core, 35 mm2, Cu/PVC/PVC | Rft. | 5000 | 1265 | 6325000
| g) 4 core, 16 mm2, Cu/PVC/PVC | Rft. | 5000 | 595 | 2975000
Addendum | 1 core, 300 mm2, Cu/PVC/PVC | Rft. | 625 | 2325 | 1453125
| Wiring Refer Spec Sec: 8212, 8220, 8230, 8240, 8290 |  |  |  | 0
20E | Wiring of light circuits from distribution board (DB) to point/switch including wiring between switches on the same circuit with 3 no. (1 x 2.5 mm2 as phase, neutral & CPC) single core Copperconductor PVC cable complete with appropriate size concealed (minimum 1" dia) / surface mounted PVC conduit and all accessories etc. complete in all respects. | Nos. | 313 | 4100 | 1283300
21E | Wiring from light/exhaust fan point to switch with 3 no. (1 x 1.5 mm2 as phase, neutral & CPC) single core copper conductor PVC cable complete with appropriate size concealed (minimum 1" dia) / surface mounted PVC conduit, ceiling rose, 10 Amps light control gang switch, sheet steel back box, 3 core flexible cable and all accessories etc. complete in all respects. | Nos. | 875 | 2320 | 2030000
22E | Same as above item 01-06E but wiring from point to point | Nos. | 875 | 1210 | 1058750
23E | Wiring from light/exhaust fan to two-way switch with 3 no. (1 x 2.5 mm2 as phase, neutral & CPC) single core copper conductor PVC cable complete with appropriate size concealed (minimum 1" dia inconcrete slab) / surface mounted PVC conduit, ceiling rose, 10 Amps light control gang switch, sheet steel back box, 3 core flexible cable and all accessories etc. complete in all respects | Nos. | 21 | 4800 | 100800
24E | Wiring of 250 Volts socket outlets with following size single core, copper conductor PVC cables complete with appropriate size concealed (minimum 1" dia in concrete slab) / surface mounted PVC conduit and all accessories, etc. complete in all respects. |  |  |  | 0
| a) From Distribution Board (DB) to outlet with 3 no. (1 x 4.0 mm2 as as phase, neutral & CPC) | Nos. | 413 | 5175 | 2137275
| b) From outlet to outlet with (1 x 2.5 mm2 as phase, neutral & CPC) | Nos. | 2020 | 1640 | 3312800
25E | Wiring from distribution board to load break switch with 3 no. (1 x 6.0 mm2 as 3-phase, neutral & CPC) single core copper conductor PVC cable,complete with appropriate size concealed (minimum 1" dia in concrete slab) / surface mounted PVC conduit and all accessories, etc. complete in all respects. | Nos. | 125 | 7760 | 970000
26E | Wiring from distribution board to load break switch with 5 no. (1 x 6.0 mm2 as 3-phase, neutral & CPC) single core copper conductor PVC cable,complete with appropriate size concealed\ (minimum 1" dia in concrete slab) / surface mounted PVC conduit and all accessories, etc. complete in all respects. | Nos. | 63 | 12075 | 760725
| Wiring Accessories Ref. Specs Sec. 8220 |  |  |  | 0
27E | Following types of socket outlets including all accessories, complete in all respect. |  |  |  | 0
| a) 13 A, 250 V, 3 pin universal type, switch socket outlet with sheet steel back box. | Nos. | 1600 | 950 | 1520000
| b) 13 A, duplex, 250 V, 3 pin universal type, switch socket outlet with sheet steel back box. | Nos. | 250 | 2150 | 537500
| c) '13 A, 250 V, single phase spur outlet with sheet steel back box. | Nos. | 250 | 800 | 200000
| d) 15 A, 250 V, 3 pin switch socket outlet with sheet steel bck box | Nos. | 63 | 900 | 56700
| e) 20 A, 250 V, DP switch with neon lamp with sheet steel back box. | Nos. | 125 | 1350 | 168750
| f) 32 A, 250 V, IP65, 3 pin industrial socket with sheet steel back box | Nos. | 25 | 2800 | 70000
| f) 32 A, 250 V, IP65, 5 pin industrial socket with sheet steel back box | Nos. | 25 | 3250 | 81250
| Conduits & Pipes Ref. Specs Sec. 8230 |  |  |  | 0
28E | Following sizes of PVC conduit / pipes installed on surface / concealed in wall, slab & floor including pull wire and all accessories as required etc., complete in all respects. |  |  |  | 0
| a) 2" dia | Rft. | 781 | 125 | 97625
| b) 1-1/2" dia | Rft. | 781 | 75 | 58575
| c) 1-1/4" dia | Rft. | 781 | 50 | 39050
| Earthing Ref. Specs Sec. 8212, 8240 |  |  |  | 0
29E | 600 mm (L) x 600 mm (H) x 3 mm (T) tin plated copper Plate type earth electrode including earthing lead, R.C.C. inspection chamber with medium duty C.I cover, excavation, backfilling, and all accessories, etc., as shown on the drawings, complete in all respects. | Nos. | 13 | 85000 | 1105000
30E | 20 mm dia, 3 meter long copper cladded steel Rod type earth electrode including 2x70 mm2 PVC cable as earthing lead, clamp with nuts and bolts, R.C.C. inspection chamber with medium duty C.I cover, excavation, backfilling, and all accessories, etc., as shown on the drawings, complete in all respects. | Nos. | 20 | 55000 | 1100000
31E | Following sizes of single core PVC insulated copper conductor cable as earth continuity conductor (ECC) installed on surface or on already installed pipes / conduits / trenchs / cable tray etc., including tags, ties, lugs, termination kits, colour sleeves, cable glands, bushes etc., all related accessories, complete in all respect. |  |  |  | 0
| a) 70 mm2 | Rft. | 250 | 475 | 118750
| b) 35 mm2 | Rft. | 1250 | 255 | 318750
| c) 25 mm2 | Rft. | 4375 | 185 | 809375
| d) 16 mm2 | Rft. | 12375 | 120 | 1485000
32E | 300 mm (L) x 50 mm (H) x 6 mm (T) tinned copper earth connecting point, including all accessories, complete in all respect. | Nos. | 63 | 7500 | 472500
| Miscellaneous Items Ref. Specs Sec. 8290 |  |  |  | 0
33E | Following rating SP&N/TP&N load break switches AC-3 duty in IP65 enclosure of the following rating: |  |  |  | 0
| a) 32 Amp, SP&N | Nos. | 125 | 5250 | 656250
| b)32 Amp, TP&N | Nos. | 125 | 7800 | 975000
34E | Following rating recessed in wall SP&N/TP&N load break switches AC-3 duty in IP20 enclosure of the following rating: |  |  |  | 0
| a) 32 Amp, SP&N | Nos. | 125 | 5250 | 656250
35E | Floor mounted padestial with rain shed for installation of load break switch including epoxy paint with red oxide coating all civil works, finishing the floor as per original, water proofing, including all accessories, complete in all respect | Nos. | 375 | 2000 | 750000
36E | Following 16 SWG MS sheet appropriate size, recessed in / surface mounted on wall or installed on support structure MCCB / MCB box including electrical & mechanical components, electrolytic tinned copper busbars, control wiring, related civil works etc., as required and all accessories, complete in all respect. |  |  |  | 0
| a) 200 A, MCCB box | Nos. | 13 | 25000 | 325000
| b) 100 A, MCCB box | Nos. | 13 | 18000 | 234000
37E | Under floor outlet box with provision for 4 no. socket outlet as set of 2 No. 16 A Schuko + 13 A Flat Pin socket outlet on normal & UPS power supply & 2 No. one port CAT-6 STP Giga speed RJ 45 socket outlet including all accessories, complete in all respect. | Nos. | 63 | 8000 | 504000
38E | 300 mm x 38 mm under floor metalic duct with all accessories, complete in all | Rft. | 1875 | 995 | 1865625
39E | 300 mm x 300 mm x 38 mm junction box/pull box with all accessories, complete in all respect. | Nos. | 31 | 3500 | 108500
40E | Following sizes ceiling fan with blades, canopy, 3"x4"x5" size (14 SWG) thick recessed type fan clamp box with down rod 1/2" dia heavy gauge GI pipe maintaining the fan distance from finished floor level at nine (9) feet, fan mounting insulator and split pin and all accessories, complete in all respect. |  |  |  | 0
| a)56" Sweep | Nos. | 563 | 7350 | 4138050
41E | 14" sweep plastic body Louvre wall bracket fan complete with blades, regulator & moveing grill with motor, installed on wall or column including all accessories, complete in all respect. | Nos. | 125 | 6500 | 812500
42E | Following 16 SWG G.I sheet perforated cable tray with soild cover including proper manufactured flexible expansion coupler, elbows, risers, tees, crosses, internal & external bends and fittings, galvanized support structure, all accessories, compelete in all respects. (Note: Welded connection is not allowed and prohibited) |  |  |  | 0
| a) 36" X 4" | Rft. | 625 | 3410 | 2131250
| b) 24" X 4" | Rft. | 625 | 2500 | 1562500
| c) 12" X 4" | Rft. | 875 | 1505 | 1316875
| d) 6" x 4" | Rft. | 875 | 1065 | 931875
43E | UPS (30 min backup), three phase IN/three phase OUT), automatic & manual bypass operation capability, N+1 redundency provision, including industrial socket with plug for IN/OUT connections or any suitable arrangement, appropriate size wall / floor mounting racks for UPS and battery bank all accessories, complete in all respect. |  |  |  | 0
| a) 15 kVA, | Nos. | 8 | 1023500 | 8188000
| b) 20 kVA | Nos. | 8 | 1364665 | 10917320
| 30 kVA | Nos. | 5 | 2041250 | 10206250
| Total Cost of Electrical Works Carried over to Summary |  |  |  | 179511780

## Mechanical Works
PATIENT'S AID FOUNDATION - JPMC, KARACHI
CONSTRUCTION OF DEPARTMENT OF PSYCHIATRY & NEUROLOGY AT JPMC KARACHI
BILL OF QUANTITIES
Item No. | Description | Unit | Quantity | Rate | Total Amount (Rupees)
(1) | (2) | (3) | (4) | (5) | (6)
GAS PIPING WORKS Ref: Spec. No8460
(Entire under mentioned work will be executed by SSGC or their approved Contractors)
01-2M | Supply, Installation, testing and commisioning of Galvanized Steel Pipes, medium grade confirming to BS 1387 with all fittings sockets, bends, tees, elbows where required fixed to walls, ceilings and floors etc inclufing caps | [6 empty] | 0 | 0
| a) 3/4 in dia | R.ft | 31 | 330 | 10230 | 7000 | 217000 | -6670 | -206770
| b) 1/2 in dia | R.ft | 200 | 290 | 58000 | 3500 | 700000 | -3210 | -642000
01-2M | Providing and fixing of ball valves in gas piping network as per specifications and drawings of following diameter: | [6 empty] | 0 | 0
| a) 1/2 in dia | R.ft | 13 | 1950 | 25350 | 7000 | 91000 | -5050 | -65650
| Total Cost Of Mechanical (Gas Piping) Works |  |  |  | 93580 |  | 1008000 |  | -914420
#REF!

## Plumbing Works (UGT)
PATIENT'S AID FOUNDATION - JPMC, KARACHI
CONSTRUCTION OF DEPARTMENT OF PSYCHIATRY & NEUROLOGY AT JPMC KARACHI
BILL OF QUANTITIES 0F PLUMBING AND FIRE FIGHTING WORKS
Item No. | Description | Unit | Quantity | Rate | Total Amount (Rupees) | Rebate 12% |  | Tax |  | TC Margin
(1) | (2) | (3) | (4) | (5) | (6) | Rebate 12% | Amount after rebate | Tax 7.5% | Amount after Tax | TC Margin 10% | Amount After TC Margin
P. PIPING / PLUMBING WORKS
A. | Water Supply Ref: Spec. No5100 & 5180
1P | PPR cold and hot water pipes SDR - 6 (PN 20) conforming to DIN 8077 & DIN 8078 & fittings, SDR 6 (PN 25) conforming to DIN 16962 of following inner diameters (for unexposed piping)
| a) 1/2 inch Inner Dia. | R-Ft | 25 | 175 | 4375 | 525 | 3850 | 312 | 3538 | 354 | 3184
| b) 3/4 inch Inner Dia. | R-Ft | 1625 | 230 | 373750 | 44850 | 328900 | 26674 | 302226 | 30223 | 272003
| c) 1 inch Inner Dia. | R-Ft | 625 | 357 | 223125 | 26775 | 196350 | 15924 | 180426 | 18043 | 162383
| d) 1-1/4 inch Inner Dia. | R-Ft | 250 | 467 | 116750 | 14010 | 102740 | 8332 | 94408 | 9441 | 84967
| e) 1-1/2 inch Inner Dia. | R-Ft | 313 | 661 | 206893 | 24827 | 182066 | 14766 | 167300 | 16730 | 150570
| f) 2 inch Inner Dia. | R-Ft | 125 | 790 | 98750 | 11850 | 86900 | 7048 | 79852 | 7985 | 71867
| g) 2-1/2 inch Inner Dia. | R-Ft | 13 | 1320 | 17160 | 2059 | 15101 | 1225 | 13876 | 1388 | 12488
| h) 3 inch Inner Dia. | R-Ft | 13 | 3370 | 43810 | 5257 | 38553 | 3127 | 35426 | 3543 | 31883
2P | Electric Water Cooler
| h) 90 Ltr / hr | Nos. | 3 | 85000 | 255000 | 30600 | 224400 | 18199 | 206201 | 20620 | 185581
3P | Bronze gate valve of the following diameters.
| a) 3/4 inch | Nos. | 1 | 2600 | 2600 | 312 | 2288 | 186 | 2102 | 210 | 1892
| b) 1 inch Inner | Nos. | 6 | 3800 | 22800 | 2736 | 20064 | 1627 | 18437 | 1844 | 16593
| c) 1-1/4 inch | Nos. | 1 | 4670 | 4670 | 560 | 4110 | 333 | 3777 | 378 | 3399
| d) 1-1/2 inch | Nos. | 13 | 5950 | 77350 | 9282 | 68068 | 5520 | 62548 | 6255 | 56293
| e) 2 inch | Nos. | 9 | 8340 | 75060 | 9007 | 66053 | 5357 | 60696 | 6070 | 54626
| f) 2-1/2 inch | Nos. | 11 | 33220 | 365420 | 43850 | 321570 | 26079 | 295491 | 29549 | 265942
| g) 3 inch | Nos. | 5 | 38800 | 194000 | 23280 | 170720 | 13845 | 156875 | 15688 | 141187
| h) 4 inch | Nos. | 3 | 48900 | 146700 | 17604 | 129096 | 10470 | 118626 | 11863 | 106763
4P | C.P. brass double bib tap with muslim shower of following diameter
| a) 3/4 inch | Nos. | 118 | 4350 | 513300 | 61596 | 451704 | 36633 | 415071 | 41507 | 373564
5P | Electric Water Heater Including gate valve and all other accesspries of the following capacity.
| a) 12 US Gallons | No | 5 | 36000 | 180000 | 21600 | 158400 | 12846 | 145554 | 14555 | 130999
| b) 25 US Gallons | No | 4 | 44000 | 176000 | 21120 | 154880 | 12561 | 142319 | 14232 | 128087
| c) 35 Gallons | No | 4 | 53500 | 214000 | 25680 | 188320 | 15273 | 173047 | 17305 | 155742
B. | PLUMBING FIXTURES Ref: Spec. No 5100 & 5180
6P | Europen water closet (Coupled) including all other necessary accessories as specified & required for installation. | Nos. | 115 | 24000 | 2760000 | 331200 | 2428800 | 196976 | 2231824 | 223182 | 2008642
7P | Europen water closet (Coupled) for disable including all other necessary accessories as specified & required for installation. | Nos. | 3 | 31500 | 94500 | 11340 | 83160 | 6744 | 76416 | 7642 | 68774
8P | Pedestal type wash basin with all other accessories as specified & required for installation. | Nos. | 43 | 18045 | 775935 | 93112 | 682823 | 55377 | 627446 | 62745 | 564701
9P | Counter type wash basin for all other accessories as specified & required for installation. | Nos. | 64 | 18505 | 1184320 | 142118 | 1042202 | 84523 | 957679 | 95768 | 861911
10P | Pedestal type wash basin for disable with all other accessories as specified & required for installation. | Nos. | 3 | 15000 | 45000 | 5400 | 39600 | 3212 | 36388 | 3639 | 32749
11P | Imported galss mirror of Belgium origin as specified. | SM | 975 | 5600 | 5460000 | 655200 | 4804800 | 389669 | 4415131 | 441513 | 3973618
12P | C.P towel rail as specified. | Nos. | 45 | 2200 | 99000 | 11880 | 87120 | 7065 | 80055 | 8006 | 72049
13P | C.P toilet paper holder as specified. | Nos. | 118 | 1400 | 165200 | 19824 | 145376 | 11790 | 133586 | 13359 | 120227
14P | C.P Soap dispensor as Specified. | Nos. | 78 | 1350 | 105300 | 12636 | 92664 | 7515 | 85149 | 8515 | 76634
15P | Shower rose including all accessories as specified. | Nos. | 20 | 11075 | 221500 | 26580 | 194920 | 15808 | 179112 | 17911 | 161201
16P | Stainless stell single bowl kitchen sink with all accessories as specified & required for installation. | Nos. | 5 | 18400 | 92000 | 11040 | 80960 | 6566 | 74394 | 7439 | 66955
16P(a) | Stainless steel Sluice including all other accessories complete as specified and as per manufacture's recommendations. | Nos. | 8 | 82000 | 656000 | 78720 | 577280 | 46817 | 530463 | 53046 | 477417
C. | SANITARY DRAINAGE Ref: Spec. No 5100 & 5180
17P | uPVC soil,waste and vent pipes conforming to ASTM D-1785 of Schedule 40 & fittings D-2465 of Schedule 40 including fittings Compatible with pipe of following diameter:
| a) 1-1/2 inch | R-Ft | 513 | 270 | 138510 | 16621 | 121889 | 9885 | 112004 | 11200 | 100804
| b) 2 inch | R-Ft | 1075 | 351 | 377325 | 45279 | 332046 | 26929 | 305117 | 30512 | 274605
| c) 3 inch | R-Ft | 3250 | 584 | 1898000 | 227760 | 1670240 | 135456 | 1534784 | 153478 | 1381306
| d) 4 inch | R-Ft | 2250 | 630 | 1417500 | 170100 | 1247400 | 101164 | 1146236 | 114624 | 1031612
18P | Floor drains with stainless steel gratings and UPVC P- trap of the folllowing diameter as specified.
| a) 3 inch | Nos. | 125 | 4200 | 525000 | 63000 | 462000 | 37468 | 424532 | 42453 | 382079
19P | Floor trap with stainless steel gratings and UPVC P - trap of the following diameter as specified.
| a) 3 inch | Nos. | 138 | 2800 | 386400 | 46368 | 340032 | 27577 | 312455 | 31246 | 281209
20P | Floor cleanout with brass cover of the following diameter as specified
| a) 3 inch | Nos. | 15 | 5000 | 75000 | 9000 | 66000 | 5353 | 60647 | 6065 | 54582
| b) 4 inch | Nos. | 15 | 6000 | 90000 | 10800 | 79200 | 6423 | 72777 | 7278 | 65499
21P | Plug cleanout of the following diameter as specified
| a) 3 inch | Nos. | 58 | 1800 | 104400 | 12528 | 91872 | 7451 | 84421 | 8442 | 75979
| b) 4 inch | Nos. | 50 | 2100 | 105000 | 12600 | 92400 | 7494 | 84906 | 8491 | 76415
22P | C.I vent cowel for soil / waste pipe of the following diameter as specified.
| a) 3 inch | Nos. | 13 | 1800 | 23400 | 2808 | 20592 | 1670 | 18922 | 1892 | 17030
D. | RAIN WATER PIPING. Ref: Spec. No 5100 & 5180
23P | uPVC rain water pipes conforming to ASTM D-1785 of Schedule 40 & fittings D-2465 of Schedule 40 including jointing with solvent cement confirming to ASTM D-2564 compatible with pipe of following diameter:
| a) 4 inch | R-Ft | 375 | 630 | 236250 | 28350 | 207900 | 16861 | 191039 | 19104 | 171935
| b) 6 inch | R-Ft | 63 | 950 | 59850 | 7182 | 52668 | 4271 | 48397 | 4840 | 43557
24P | Cast Iron pipe conforming to BS 416 of following diameter as specified.
| 3 inch | R-Ft | 31 | 1450 | 44950 | 5394 | 39556 | 3208 | 36348 | 3635 | 32713
| 4 inch | R-Ft | 600 | 1750 | 1050000 | 126000 | 924000 | 74936 | 849064 | 84906 | 764158
25P | Cast Iron roof drains side inlet type of the following diameter as specified and as shown in the drawing.
| 3 inch | Nos. | 1 | 15000 | 15000 | 1800 | 13200 | 1071 | 12129 | 1213 | 10916
| 4 inch | Nos. | 1 | 18000 | 18000 | 2160 | 15840 | 1285 | 14555 | 1456 | 13099
26P | Cast Iron roof drains dome type of the following diameter as specified and as shown in the drawing.
| 3 inch | Nos. | 8 | 20000 | 160000 | 19200 | 140800 | 11419 | 129381 | 12938 | 116443
| 4 inch | Nos. | 1 | 25000 | 25000 | 3000 | 22000 | 1784 | 20216 | 2022 | 18194
27P | uPVC rain water shoes of following diameters
| a) 6 inch | Nos. | 1 | 12000 | 12000 | 1440 | 10560 | 856 | 9704 | 970 | 8734
| b) 4 inch | Nos. | 8 | 8700 | 69600 | 8352 | 61248 | 4967 | 56281 | 5628 | 50653
E. | EXTERNAL WATER SUPPLY SYSTEM Ref: Spec. No. 5100,5225,5213 & 5180
28P | Supply and installation of HDPE Pipes PE-100, (PN-16 & SDR-11) conforming to ISO-4427 : 1996 with fittings conforming to ISO-3458 including puddle flangesof following diametersas shown in drawings and as specified for filling OHWT. (O.D - Outer Diameter)
| a) Dia 3.54 inch (90 mm OD) | R-Ft | 500 | 1050 | 525000 | 63000 | 462000 | 37468 | 424532 | 42453 | 382079
29P | GI Pipes and fittings (Medium duty) of following diameters as specified (exposed piping on roof)
| a) Dia. 4 inch | R-Ft | 25 | 1720 | 43000 | 5160 | 37840 | 3069 | 34771 | 3477 | 31294
| b) Dia. 3 inch | R-Ft | 250 | 1440 | 360000 | 43200 | 316800 | 25692 | 291108 | 29111 | 261997
| c) Dia. 2-1/2 inch | R-Ft | 750 | 900 | 675000 | 81000 | 594000 | 48173 | 545827 | 54583 | 491244
| d) Dia. 2 inch | R-Ft | 563 | 687 | 386781 | 46414 | 340367 | 27604 | 312763 | 31276 | 281487
| e) Dia. 1-1/2 inch | R-Ft | 250 | 490 | 122500 | 14700 | 107800 | 8743 | 99057 | 9906 | 89151
| f) Dia. 3/4 inch | R-Ft | 100 | 330 | 33000 | 3960 | 29040 | 2355 | 26685 | 2669 | 24016
30P | Gate Valve in chamber of following diameter as shown on the drawing and as specified.
| a) Dia. 3 inch | Nos. | 1 | 43000 | 43000 | 5160 | 37840 | 3069 | 34771 | 3477 | 31294
31P | Dia 2" G.I overflow pipe for over head tank | R-Ft | 13 | 687 | 8931 | 1072 | 7859 | 637 | 7222 | 722 | 6500
32P | Cast iron cover with frame of following size (Light Duty)
| a) 2'-0" x 2'x0" | Nos. | 5 | 22000 | 110000 | 13200 | 96800 | 7850 | 88950 | 8895 | 80055
33P | G.I U-turn vent pipe of following diameter:
| a) Dia. 2 inch | Nos. | 5 | 6600 | 33000 | 3960 | 29040 | 2355 | 26685 | 2669 | 24016
34P | Galavanised M.S ladder rungs for roof tank as specified. | Nos. | 20 | 8000 | 160000 | 19200 | 140800 | 11419 | 129381 | 12938 | 116443
F. | EXTERNAL SEWERAGE SYSTEM
uPVC PIPE AND FITTINGS (SEWERAGE) Ref: Spec No. 5218 & 5180
35P | uPVC drainage pipe & fittings conforming to BS 3505 & BS 4346 of Calss 'B' as specified (below ground)
| a) Dia 6 inch | R-Ft | 13 | 1450 | 18850 | 2262 | 16588 | 1345 | 15243 | 1524 | 13719
| b) Dia 8 inch | R-Ft | 938 | 2188 | 2052344 | 246281 | 1806063 | 146472 | 1659591 | 165959 | 1493632
| c) Dia 10 inch | R-Ft | 94 | 4017 | 377598 | 45312 | 332286 | 26948 | 305338 | 30534 | 274804
| d) Dia 12 inch | R-Ft | 125 | 5577 | 697125 | 83655 | 613470 | 49752 | 563718 | 56372 | 507346
Gully Trap Ref. Spec. No 5100
36P | Chamber with Gully Trap of following size as shown on the drawing.
| a) 1'-6" x 1'-6" | Nos. | 14 | 30000 | 420000 | 50400 | 369600 | 29975 | 339625 | 33963 | 305662
| b) 2' x 2' | Nos. | 1 | 55000 | 55000 | 6600 | 48400 | 3925 | 44475 | 4448 | 40027
MANHOLES Ref. Spec. No. 5225 & 5233
37P | Manholes of following sizes comprising earthworks, plain cement concrete reinforced cement concrete, ladder rungs and C.I (Medium Duty) Cover with frame etc. Complete in all respect as shown on drawings.
| a) 3' x 3' | No | 23 | 80000 | 1840000 | 220800 | 1619200 | 131317 | 1487883 | 148788 | 1339095
| b) 2' x 2' | No | 1 | 65000 | 65000 | 7800 | 57200 | 4639 | 52561 | 5256 | 47305
SERVICE CONNECTION Ref: Spec. No 5270
38P | Service Connection with existing manhole complete in all respects and as approved by the Engineer. | No | 1 | 120000 | 120000 | 14400 | 105600 | 8564 | 97036 | 9704 | 87332
G. | FIRE FIGHTING Ref: Spec. No. 5150 & 5180
39P | Foam 9 litre | Nos | 5 | 11900 | 59500 | 7140 | 52360 | 4246 | 48114 | 4811 | 43303
40P | Dry Chemical powder 6 Kg | Nos | 33 | 6900 | 227700 | 27324 | 200376 | 16250 | 184126 | 18413 | 165713
41P | Carbon dioxide 5 kg | Nos | 3 | 14400 | 43200 | 5184 | 38016 | 3083 | 34933 | 3493 | 31440
42P | Seamless black steel pipe conforming to ASTM A-53 Schedule 40 and fittings conforming to BS - 534 of Following diameters as specified.
| a) Dia 4 inch | R-Ft | 140 | 2100 | 294000 | 35280 | 258720 | 20982 | 237738 | 23774 | 213964
| b) Dia 3 inch | R-Ft | 388 | 1660 | 644080 | 77290 | 566790 | 45967 | 520823 | 52082 | 468741
| c) Dia 2-1/2 inch | R-Ft | 875 | 1310 | 1146250 | 137550 | 1008700 | 81806 | 926894 | 92689 | 834205
43P | Fire Hose Cabinet including all accessories as shown on drawings and as specified. | Nos | 20 | 42500 | 850000 | 102000 | 748000 | 60663 | 687337 | 68734 | 618603
H. | EXTERNAL FIRE FIGHTING SYSTEM Ref: Spec. No. 5150 & 5180
44P | Seamless black steel pipe conforming to ASTM A-53 Schedule 40 and fittings conforming to BS - 534 of Following diameters as specified.(burried pipe wrapped with approved with anti corrosive tape)
| a) Dia 6 inch | R-Ft | 1000 | 3500 | 3500000 | 420000 | 3080000 | 249788 | 2830212 | 283021 | 2547191
45P | Cast Iron Gate Valve (PN-16) in chamber of following diameter as shown on the drawing and as specified
| a) Dia 6 inch | Nos. | 4 | 92202 | 368808 | 44257 | 324551 | 26321 | 298230 | 29823 | 268407
46P | Siamese Connection as shown on the drawing and as specified | Nos. | 1 | 70000 | 70000 | 8400 | 61600 | 4996 | 56604 | 5660 | 50944
Total Cost Of Plumbing Works Carried Over to Summary
P.PLUMBING WORKS
UNDERGROUND WATER TANK & PUMP ROOM
MS PIPES & PIPE FITTINGS Ref. Spec. No. 5214 & 5280
02b-1P | Supply and Installation of Seamless Black Steel pipe of Schedule 40 Grade B Conforming to ASTM - A53 with fittings conforming to ASTM A-234 including pipe supports as shown in the drawings and as specified (I.D - Internal Diameter)
| a) 6 in (I.D) | R.ft | 31 | 3370 | 104470 | 12536 | 91934 | 7456 | 84478 | 8448 | 76030
| b) 4 in (I.D) | R.ft | 119 | 2100 | 249900 | 29988 | 219912 | 17835 | 202077 | 20208 | 181869
| c) 2.5 in (I.D) | R.ft | 6 | 1310 | 7860 | 943 | 6917 | 561 | 6356 | 636 | 5720
POLY ETHYLENE PIPES & PIPE FITTINGS Ref. Spec 5213 & 5280.
02b-2P | Supply and installation of HDPE Pipes PE-100 (PN-10 & SDR-17) Conforming to ISO - 4427:1996 with fittings conforming to ISO -3458 including puddle flanges of following diameters as shown in drawings and as specified. (O.D - Ouer Diameter)
| a) 6.29 in or 160mm (O.D) | R.ft | 125 | 1870 | 233750 | 28050 | 205700 | 16682 | 189018 | 18902 | 170116
VALVES AND APPURTENANCES Ref. Spec. No 5220
02b-3P | Supply and installation of flanges ands Cast Iron Gate Valve of the following diameter as per BS 5154 or equivalent (PN-16)
| a) 6 in (I.D) | No. | 3 | 93202 | 279606 | 33553 | 246053 | 19955 | 226098 | 22610 | 203488
| b) 4 in (I.D) | No. | 9 | 52900 | 476100 | 57132 | 418968 | 33978 | 384990 | 38499 | 346491
| c) 2.5 in (I.D) | No. | 1 | 31460 | 31460 | 3775 | 27685 | 2245 | 25440 | 2544 | 22896
02b-4P | Supply and installation of flanges ends Cast Iron Check Valve of the following diameter conforming to BS 5153 or equivalent (PN-16)
| a) 4 in (I.D) | No. | 6 | 58880 | 353280 | 42394 | 310886 | 25213 | 285673 | 28567 | 257106
| b) 2.5 in (I.D) | No. | 1 | 30240 | 30240 | 3629 | 26611 | 2158 | 24453 | 2445 | 22008
02b-5P | Supply and installation of surage relief valve of following diameter including all accessoris as shown in the drawings and as specified.
| a) 2 in (I.D) | No. | 1 | 22567 | 22567 | 2708 | 19859 | 1611 | 18248 | 1825 | 16423
02b-6P | Supply and installation of brass foot valve with strainer of following size as shown in the drawqings and as specified.
| a) 4 in (I.D) | No. | 4 | 4500 | 18000 | 2160 | 15840 | 1285 | 14555 | 1456 | 13099
02b-7P | Supply and installation of float valve of copper alloy piston type conforming to BS 1212 including float shall be of copper conforming to BS 1968 including all accessories as shown in the drawingsand as specified.
| a) 6 in (I.D) | No. | 1 | 1800 | 1800 | 216 | 1584 | 128 | 1456 | 146 | 1310
02b-8P | Supply and installation of galvanized mild steel U-turned vent pipes with puddle flanges as shown in the drawings and as specified.
| a) 4 in (I.D) | No. | 10 | 8200 | 82000 | 9840 | 72160 | 5852 | 66308 | 6631 | 59677
PUMPING MACHINERY AND ACCESSORIES Ref. Spec. No. 5240
02b-9P | Supply & Insatalltion of Horizontal Centrifugal Pump and Motor of the following capacity and head including pressure gauges level switches and all accessories required to complete the job as shown in the drawings and as specified.
| Q = 125 US Gpm, H = 130 ft | No | 3 | 375000 | 1125000 | 135000 | 990000 | 80289 | 909711 | 90971 | 818740
02b-10P | Supply & Installation Deep Well Turbine Pump and Motor of the Following capacity and head including pressure gauges, pressure switches and all accessories required to complete the job as shown in the drawings and as specified.
| Q = 200 US Gpm, H = 260 ft | No | 2 | 1150000 | 2300000 | 276000 | 2024000 | 164146 | 1859854 | 185985 | 1673869
| Q = 50 US Gpm, H = 290 ft | No | 1 | 3520000 | 3520000 | 422400 | 3097600 | 251215 | 2846385 | 284639 | 2561746
02b-11P | Supply & Installation of Overhead Ganty with chain pulley of 2 Tonne capacity including all necessary fittings required to complete the job, as shown in the drawings and as specified. | No | 1 | 25000 | 25000 | 3000 | 22000 | 1784 | 20216 | 2022 | 18194
02b-12P | Supply and installaion of Flexible coupling of following sizes as shown on the drawings and as specified.
| a) 4 in (I.D) | No. | 4 | 32000 | 128000 | 15360 | 112640 | 9135 | 103505 | 10351 | 93154
02b-13P | Supply and installation of Water level indicator as shown in the Drawings and as specified. | No. | 1 | 72000 | 72000 | 8640 | 63360 | 5138 | 58222 | 5822 | 52400
02b-14P | Supply and installation of cast iron cover with frame of following sizes (Heavy Duty)
| a) 2ft x 2ft | No. | 5 | 19000 | 95000 | 11400 | 83600 | 6780 | 76820 | 7682 | 69138
| Total Cost Carried Over to Summary Of Cost |  |  |  | 46307153 | [5 empty] | 33700896 | 37100000 | finalized

## Summary
JINNAH POST GRADUATE MEDICAL CENTRE
CONSTRUCTION OF DEPARTMENT OF PSYCHIATRY & NEUROLOGY AT JPMC KARACHI
SUMMARY OF COST
| S. NO. | DESCRIPTION | REVISED CONTRACT VALUE
| 1 | CIVIL WORKS | Rs. | 510481502
| 2 | PLUMBING WORKS | Rs. | #REF!
| 3 | ELECTRICAL WORKS | Rs. | 179511780
| 4 | COMMUNICATION WORKS | Rs. | 95022465
| 5 | MECHANICAL WORKS
| 5.1 | INTERNAL GAS PIPING WORKS | Rs. | 93580
| A | TOTAL BID PRICE | Rs. | #REF!
| B | LESS OVERALL REBATE 11.758% | Rs. | #REF!
| C | FINAL CONTRACT VALUE (INCLUDING RAFT FOUNDATION AND ADDED 4H FLOOR) | Rs. | #REF!