## Sheet1
Project | BOQ Amount |  | Margin | after Margin | Tax 8.47% | After Tax | Mob advance | 1st payment | 2nd payment | 3rd payment | 4th payment | 5th payment | 6th payment | Remaing | Received Mobilization amount |  |  |  |  | 1st Bill amount | Received Mobilization amount
Al-Hamd International |  | 9590696 | 5% | 9111161.2 | 771715.3536 | 8339445.8464 | 1667889 | 2782977 | [5 empty] | 3888579.8464 |  |  | 1822232.24 | 154343.0707 | 1667889.1693 |  |  | 8797910.1864
JS Bank Shaheen Complex | HVAC | 4330743 | 0 | 4330743 | 366813.9321 | 3963929.0679 | 964597 | 965372 | 963822 | 850000 | 723448 |  |  | 355746.7135 |  |  | 866148.6 | 73362.7864 | 792785.8136
| Plumbing | 938552 | 0 | 938552 | 79495.3544 | 859056.6456
Cafeteria | HVAC | 3119139 | 16.1% | 2616957.621 | 221656.3105 | 2395301.3105 | 0 | 565356 | 521235 | 1151128 | 0 | 157697 |  | 401732.5116 |  | 0
| Plumbing | 525348 | 16.43% | 439033.3236 | 37186.1225 | 401847.2011 | [9 empty] | 0
JS Bank The Forum | HVAC | 10705307 | 13.33% | 9278289.5769 | 785871.1272 | 8492418.4497 | 2009832 | 2000000 | 2038585 | 2032139 | 1524103 | 192039 |  | 363996.5712 |  | 0
| Plumbing | 1822655 | 0 | 1822655 | 154378.8785 | 1668276.1215
Vos

## Sheet2
JS Bank The Forum |  | JS Bank (1st Floor Shaheen Complex) |  | JS Bank (Cafeteria) |  | Al- Hamd International |  | Al- Hamd International
HVAC Work | 9278289.5769 | HVAC Work | 4330743 | HVAC Work | 2616957.621 | Plumbing Work | 5328288 | Plumbing Work | 5443125
Add Plumbing Work | 1822655 | Plumbing Work | 938552 | Plumbing Work | 439033.3236 | Less Tax 8.47% | 451305.9936 | Less rebate 6% | 326587.5
Total deal after TC margin | 11100944.5769 | Total deal | 5269295 | Total deal | 3055990.9446 | Net Total Deal Amount | 4876982.0064 | Net Total Deal Amount | 5116537.5
Less Tax 8.47% | 940250.0057 | Less Tax 8.47% | 446309.2865 | Less Tax 8.47% | 258842.433
Net Total Deal Amount | 10160694.5712 | Net Total Deal Amount | 4822985.7135 | Net Total Deal Amount | 2797148.5116 |  |  | Add variation amount | 211750
[8 empty] | Total amount | 5328287.5
Received Amount |  | Received Amount |  | Received Amount |  | Received Amount |  | Less Tax 8.47% | 451305.9513
Rec mob Advance 20% | 2009832 | Rec mob Advance 20% | 964597 | 1st Payment | 565356 | Rec mob Advance 20% | 1667889 | Net Total Deal Amount | 4876981.5488
1st Payment | 2000000 | 1st Payment | 965372 | 2nd Payment | 521235 | 1st Payment | 2782977
2nd Payment | 2038585 | 2nd Payment | 963822 | 3rd & 4th Payment | 1151128 |  | 0 | Received Amount
3rd Payment | 2032139 | 3rd Payment | 850000 | 5th Payment | 157697 |  |  | Rec mob Advance 20% | 1667889
4th Payment | 1524103 | 4th Payment | 723448 | 6th Payment |  |  |  | 1st Payment | 2424478
5th Payment | 192039 | 5th Payment | [6 empty] | 0
6th Payment |  | 6th Payment
Total received amount | 9796698 | Total received amount | 4467239 | Total received amount | 2395416 | Total received amount | 4450866
Net Amount Receivable | 363996.5712 | Net Amount Receivable | 355746.7135 | Net Amount Receivable | 401732.5116 | Net Amount Receivable | 426116.0064
[8 empty] | Total received amount | 4092367
Add Vos amount | 666534 | Add Vos amount | 240867.1875
Less Margin | 99980.1 | Less Margin | 24086.7188 |  |  |  |  | Receivable | 784614.5488
Net | 566553.9 | Net | 216780.4688 |  |  |  |  | Add Retention | 266414
Less Tax 8.47% | 47987.1153 | Less Tax 8.47% | 18361.3057 |  |  |  |  | Total Receivable | 1051028.5488
VOs Receivable amount | 518566.7847 | Net Amount Receivable | 198419.163
Grand Receivable | 882563.3559 | Grand Receivable | 554165.8765
Project |  | Receivable Amount
JS Bank the Forum |  | 882563.3559
JS Bank (Shaheen Complex) |  | 554165.8765
JS Bank (Cafeteria) |  | 401732.5116
Al-Hamd International |  | 426116.0064
Total Receivable Rs |  | 2264577.7504

## Sheet3
S. # | Project | Value of Work | Vos | Gross | Less |  | Received | Remaining
| Falcon Mall | 152793355 | 6758340 | 159551695 | 4998000 | 154553695 | 145754153 | 8799542
| Imtiaz Super Store DHA Phase VIII | 25510943 | 0 | 25510943 | 0 | 25510943 | 21177292 | 4333651 | 6758340
JPMC (Mian Surgical Building)
| JPMC PSYCHIATRY DEPARTMENT) | [9 empty] | 41
37
78
7350000
2352000
4998000
3801542
20532513
21959906.9519