## Bill # 1
Item # | Description | Qty. | Unit | BOQ Rates |  | Running Bill # 1 |  |  |  | Total Billed Amount
[6 empty] | Material Amount |  | lnstallation Amount
|  |  |  | Material | Installation | Billed Qty | Billed Amount | Billed Qty | Billed Amount
DISMANTLING WORKS
1 | Motor Control Center (MCC)
a. | Dismantling of Motor Control Centre (MCC). | 1 | No. | 0 | 25000 |  | 0 | 1 | 25000 | 25000
2 | Wires, Cables, Conduites and Cable Tray
a. | Dismantling of wire, cables, conduites and cable tray for power supply, earthing and controls of HVAC system. | 1 | Job | 0 | 40000 |  | 0 | 1 | 40000 | 40000
3 | Meters and gages for HVAC Piping
a. | Dismantling of meters and gagues and accessories for HVAC piping.
4 | General-Duty Valves for HVAC Piping
| Dismantling of Chiller & Pumps valves complete with flanges and all other accessories for HVAC piping. | 1 | Job | 0 | 75000 |  | 0 | 1 | 75000 | 75000
5 | Chilled Water Piping
a. | Dismantling of chilled water piping system. | 1 | Job | 0 | 100000 |  | 0 | 1 | 100000 | 100000
6 | Fan Coil Units
| Dismantling of fan coil units with valve assembly and all other accessories, complete in all respect. | 42 | Nos | 0 | 1500 |  | 0 | 35 | 52500 | 52500
7 | Air-Cooled Water Chillers
a. | Dismantling of Existing Air-Cooled Chillers. | 3 | Nos | 0 | 25000 |  | 0 | 3 | 75000 | 75000
8 | Child Water Pumps
a. | Dismantling of Chilled Water Pumps. | 4 | Nos | 0 | 8000 |  | 0 | 4 | 32000 | 32000
TOTAL COST OF DISMANTLING WORKS
HVAC UPGRADATION WORKS.
230010 | General Requirements for HVAC System
a. | Making of Shop Drawings with sectional details complete in all respect for complete HVAC Systems as per Specifications | 1 | Job | 0 | 30000 |  | 0 | 1 | 30000 | 30000
b. | Making of As Built Drawings with sectional details complete in all respect for complete HVAC Systems as per Specifications | 1 | Job | 0 | 30000 |  | 0 | 0 | 0 | 0
c. | Shifting of equipment from Ground Floor to respective locations including Owner Supplied Equipment. | 1 | Job | 0 | 200000 |  | 0 | 1 | 200000 | 200000
d | Painting and identification works of all components, supports, hangers & brackets etc. complete in all respect as per drawings and specifications. | 1 | Job | 300000 | 75000 | 1 | 300000 | 1 | 75000 | 375000
e | Contractor to list and price below with quantities any additional item(s) and/or quantities which are not included but required to complete the lumpsum tender price for this section of works. Should the tenderer fail to insert any item(s) and/or quantities here, it will be deemed that this lumpsum price for the tender includes all items and no subsequent cliams for any additional item will be entertained.
230100 | Operation and maintenance of HVAC System
230113 | Operation and maintenance of HVAC System
a. | One month test run | 1 | Job | 0 | 90000 |  | 0 | 1 | 90000 | 90000
b. | Plant operation and mainteance of HVAC System for one year, seven days a weeks, from 10:Am to 11:Pm (one site engineer + one supervisor + Two mechanic + one electrician) | 1 | Job | 0 | 0 |  | 0 |  | 0 | 0
230500 | Common Work Results for HVAC
230513.13 | Motor Control Center (MCC)
a. | Supply, Installation of Motor Control Centre (MCC) complete in all respect including weather proof sheet metal cabinet, bus bars, internal wiring earth strip, connector strip, MCB, MCCB, Control fueses, magentic contactor, overload relay, indication lights, voltmeter, ammeter, under voltage phase reversible, phase failure device, selector switch, related civil works etc. complete in all respects for HVAC equipment including Owner supplied HVAC equipment as per scheudle, speicifications and drawings. | 1 | No | 1331000 | 75000 | 1 | 1331000 | 1 | 75000 | 1406000
230513.16 | Wires, Cables, Conduites and Cable Tray
a. | Supply and installation of of wire, cables, conduites and cable tray for power supply, earthing and controls of HVAC system complete in all respect as per drawings and specifications. | 1 | Job | 980000 | 165000 | 1 | 980000 | 1 | 165000 | 1145000
230519 | Meters and gages for HVAC Piping
a. | Supply, installation, testing and commissioning of meters and gagues and accessories for HVAC piping complete in all respect as per drawings and specifications
For Electric Chiller (s)
i. | Insertion type pipe mounted thermometers | 4 | Nos | 6000 | 700 | 4 | 24000 | 4 | 2800 | 26800
ii. | Pressure gauge | 4 | Nos | 5500 | 700 | 4 | 22000 | 4 | 2800 | 24800
iii. | gague cock | 4 | Nos | 700 | 300 | 4 | 2800 | 4 | 1200 | 4000
iv. | thermometer well | 4 | Nos | 400 | 200 | 4 | 1600 | 4 | 800 | 2400
v. | Flow switch | 2 | Nos | 14500 | 2000 | 2 | 29000 | 2 | 4000 | 33000
For Pumps
i. | Pressure gauge | 6 | Nos | 6000 | 700 | 6 | 36000 | 6 | 4200 | 40200
ii. | gague cock | 6 | Nos | 700 | 300 | 6 | 4200 | 6 | 1800 | 6000
230523 | General-Duty Valves for HVAC Piping
Supply, Installation, testing and commissioning of valves complete with flanges and all other accessories for HVAC piping complete in all respect as per drawings and specifications
Electric Chiller(s)
i. | Chilled Water Circuit
a. | Gate Valve
| 150 mm (6 inch) Diameter | 4 | Nos | 42500 | 1000 | 4 | 170000 | 4 | 4000 | 174000
b. | CFRV
| 150 mm (6 inch) Diameter | 2 | Nos | 87900 | 1000 | 2 | 175800 | 2 | 2000 | 177800
Primary Chilled Water Pump(s)
a. | Gate Valve
| 150 mm (6 inch) Diameter | 6 | Nos | 42500 | 1000 | 6 | 255000 | 6 | 6000 | 261000
b. | Check Valve
| 150 mm (6 inch) Diameter | 3 | Nos | 51000 | 1000 | 3 | 153000 | 3 | 3000 | 156000
c. | CFRV
| 150 mm (6 inch) Diameter | 3 | Nos | 87900 | 4000 | 3 | 263700 | 3 | 12000 | 275700
d | Stainer
| 150 mm (6 inch) Diameter | 3 | Nos | 49900 | 4000 | 3 | 149700 | 3 | 12000 | 161700
e | Flexible Connector
| 150 mm (6 inch) Diameter | 10 | Nos | 15000 | 1000 | 10 | 150000 | 10 | 10000 | 160000
Fan Coil Units
a. | Gate Valve
| 25 mm (1 inch) Diameter | 47 | Nos | 3300 | 700 | 35 | 115500 | 35 | 24500 | 140000
b. | Globe Valve
| 25 mm (1 inch) Diameter | 47 | Nos | 3900 | 700 | 35 | 136500 | 35 | 24500 | 161000
c. | Stainer
| 25 mm (1 inch) Diameter | 47 | Nos | 3200 | 700 | 0 | 0 | 0 | 0 | 0
d. | Motorized Valve
| 25 mm (1 inch) Diameter | 47 | Nos | 3000 | 700 | 35 | 105000 | 35 | 24500 | 129500
Miscellanous Valves
a. | Gate Valves
| 100 mm (4 inch) Diameter | 2 | Nos | 21900 | 1000 | 3 | 65700 | 3 | 3000 | 68700
| 50 mm (2 inch) Diameter | 2 | Nos | 9900 | 700 | 2 | 19800 | 2 | 1400 | 21200
| 25 mm (1 inch) Diameter | 2 | Nos | 3300 | 700 | 8 | 26400 | 8 | 5600 | 32000
230529.13 | Hangers and Supports for HVAC Piping
a. | Supply, Installation & Commissioning of hangers and supports for HVAC piping complete in all respect as per drawings and specifications. | 1 | Job | 277000 | 39500 | 1 | 277000 | 1 | 39500 | 316500
230529.16 | Hangers and Supports for HVAC Equipment
a. | Supply, Installation & Commissioning of hangers and supports for HVAC equipment complete in all respect as per drawings and specifications. | 1 | Job | 75000 | 27000 | 1 | 75000 | 1 | 27000 | 102000
230553 | Identification for HVAC Ducting, Piping and Equipment
a. | Supply, Installation & Commissioning of identification for HVAC ducting, piping and equipment complete in all respect as per drawings and specifications. | 1 | Job | 35000 | 10000 |  | 0 |  | 0 | 0
230700 | HVAC Insulation
230719.13 | Chilled Water Piping Insulation
a. | Supply and installation of premoulded polyurethane insulation of density 50 kg/m3 with bituminous karft paper facing for chilled water pipes, bends, tees, unions, sockets, valves and on speicals, wrapped with 8 oz. canvas cloth than painted with anti fungus paint, protected 26 SWG painted G.I. sheet metal cladding complete in all respect as per scheudle, specifications and drawings.
38 mm (1-1/2 inch) thickness
| 25 mm (1 inch) Diameter | 500 | Rft | 399 | 70 | 70 | 27930 | 70 | 4900 | 32830
50 mm (2 inch) thickness
| 250 mm (10 inch) Diameter | 90 | Rft | 1990 | 350 | 80 | 159200 | 80 | 28000 | 187200
| 200 mm (8 inch) Diameter | 60 | Rft | 1670 | 300 | 55 | 91850 | 55 | 16500 | 108350
| 150 mm (6 inch) Diameter | 120 | Rft | 1460 | 250 | 103 | 150380 | 103 | 25750 | 176130
b. | Supply, installation & commissioning of Chilled Water Valves insulation with anti fungus paint, protected 26 SWG painted G.I sheet metal cladding, complete in all respect as per drawings and specifications
| 150 mm (6 inch) Diameter | 21 | Nos | 3500 | 1000 | 21 | 73500 | 21 | 21000 | 94500
230719.26 | Condensate Drain Insulation
a. | Supply and installation of 6 mm thick Pre-moulded Armaflex Pipe Insulation complete in all respect as per schedule, specifications and drawings.
| 25 mm (1 inch) Diameter | 130 | Rft | 105 | 60 | 24 | 2520 | 24 | 1440 | 3960
230800 | Commissioning of HVAC
230813 | Testing, Adjusting and balancing for HVAC systems
a. | Testing, balancing and commissioning of HVAC system complete in all respect including one month test run, measurement and recording of pressure and electrical data and submission of technical/operation manual, LOG book for each related equipment as per specifications and drawings. | 1 | Job | 0 | 150000 |  | 0 | 1 | 150000 | 150000
230933 | System Automatic Control
a. | Supply, Installation & Commissioning of System Automatic control complete in all respect as per drawings and specifications. | 1 | Job | 2150000 | 150000 | 1 | 2150000 | 1 | 150000 | 2300000
232100 | HVAC Piping and Pumps
232113.23 | Hydronic Piping
a. | Supply, Installation, testing & Commissioning of M.S Schedule 40 (as per ASME & API standard, heavy quality with standard Schedule 40 thickness) pipes & fittings for chilled water circulation system with bends, tees, unions, sockets as required to complete in all respects ready to operate as per schedule, drawings and specifications.
| 25 mm (1 inch) Diameter | 500 | Rft | 280 | 100 | 70 | 19600 | 70 | 7000 | 26600
| 150 mm (6 inch) Diameter | 120 | Rft | 2477 | 300 | 103 | 255131 | 103 | 30900 | 286031
| 200 mm (8 inch) Diameter | 60 | Rft | 3160 | 350 | 55 | 173800 | 55 | 19250 | 193050
| 250 mm (10 inch) Diameter | 90 | Rft | 4800 | 400 | 80 | 384000 | 80 | 32000 | 416000
232113.26 | Condensate Drain Piping
a. | Supply, Installation, testing & Commissioning of UPVC Class D pipes & fittings for condensate drain system with bends, tees, unions, sockets as required to complete in all respects ready to operate as per schedule, drawings and specifications.
| 25 mm (1 inch) Diameter | 130 | Rft | 80 | 60 | 50 | 4000 | 50 | 3000 | 7000
232116 | Hydronic piping specialties
a. | Supply, Installation, testing & Commissioning of hydronic piping specialties alongwith flanges, coupling, unions complete in all respect as per drawings and specifications.
For Electric Chiller (s)
Strainers with blow off 20 mm dia ball valve
| 20 mm (3/4 inch) Diameter | 2 | Nos | 3000 | 600 | 2 | 6000 | 2 | 1200 | 7200
| Automatic Air Vent | 4 | Nos | 3500 | 600 | 4 | 14000 | 4 | 2400 | 16400
232119-13 | Open Type Expansion tank
a. | Supply, Installation, testing and commissioning of open type expansion tank PVC having 50 mm thick glass wool insulation covered with 26 Gauge Aluminum sheet with manhole cover, drain, over flow, quick fill, normal water connection complete in all respect as per drawings and specifications | 1 | No | 65000 | 15000 |  | 0 |  | 0 | 0
233100 | HVAC Ducts and Casings
233113.13 | Medium/Low pressure G.I. sheet metal ducting
a. | Supply, Installation, testing & Commissioning of medium/low pressure G.I. sheet metal ducting complete in all respect as per drawings and specifications.
| 22 gauge | 400 | Sq.ft | 260 | 70 |  | 0 |  | 0 | 0
233119 | Access door for Fan coil unit
a. | Supply, Installation, testing & Commissioning of access door for fan coil units complete in all respect as per drawings and specifications. | 1 | Lot | 175000 | 35000 |  | 0 |  | 0 | 0
233343 | Flexible Connectors
a. | Supply, Installation, testing & Commissioning of flexible connectors between blower section and air duct complete in all respect as per drawings and specifications. | 1 | Job | 170000 | 20000 | 1 | 170000 | 1 | 20000 | 190000
233346 | Flexible Duct
a. | Supply, Installation, testing & Commissioning of flexible duct complete in all respect as per drawings and specifications.
| 150 mm (6 inch) Diameter | 30 | Rft | 350 | 100 |  | 0 |  | 0 | 0
233700 | Air Outlets and inlets
233713 | Diffusers, Registers, and Grilles
Supply, Installation, testing & Commissioning of Diffusers, Registers and Grilles complete in all respect as per drawings and specifications.
a. | Supply Air Round Diffusers (SARD)
| 600mm (24" diameter) | 3 | Nos | 6500 | 1000 |  | 0 |  | 0 | 0
e. | Imperialine linear air diffuser 3/4" slot with volume control dampers with link to adjust the damper blade from the face of linear air diffuser complete in all respect as per drawings and specifications
| 3 Slot SALD 6 Feet Long. | 8 | Nos | 7900 | 1000 |  | 0 |  | 0 | 0
236419.13 | Air-Cooled Reciprocating compressor type Water Chillers
a. | Installation, testing & Commissioning of Air-Cooled Screw type Water Chiller complete in all respect as per drawings and specifications. | 2 | Nos | 0 | 50000 | 2 | 0 | 2 | 100000 | 100000
b. | Supply, installation, lifting, shifting & Commissioning of chilled Water pumps complete in all respect as per drawings and specifications. | 3 | Nos | 865000 | 20000 | 3 | 2595000 | 3 | 60000 | 2655000
238219 | Fan Coil Units
a. | Supply, Installation, testing & Commissioning of Fan Coil Units complete in all respect as per drawings and specifications. | 47 | Nos | 135000 | 1500 | 35 | 4725000 | 35 | 52500 | 4777500
TOTAL COST OF HVAC WORKS | [9 empty] | 17847551 | 2021-02-25
[9 empty] | Rec till to date | 13264500 | Bill | 17847551
[11 empty] | Tx 7.5% | 1338566.325
[10 empty] | 4583051 | net | 16508984.675
[11 empty] | rec | 13264500
[11 empty] | Payabe | 3244484.675
|  |  |  | Gross rec | 14340000
|  |  |  | Payable | 3507551

## Summary
2022-10-20
UPGRADATION OF AC PLANT ALLIED WORKS
THE FORUM SHOPPING MALL KARACHI
SUMMARY OF BILL
ITEM # | DESCRIPTION | TOTAL COST PAK RUPEES
xx | Dismantling Work | 399500
230010 | General Requirements for HVAC System | 605000
230100 | Operation and maintenance of HVAC System | 90000
230500 | Common Work Results for HVAC | 5025300
230700 | HVAC Insulation | 602970
230800 | Commissioning of HVAC | 150000
230933 | System Automatic Control | 2300000
232100 | HVAC Piping and Pumps | 952281
233100 | HVAC Ducts and Casings | 190000
233700 | Air Outlets and inlets | 0
236400 | Chillers | 2755000
238219 | Fan Coil Units | 4777500
| TOTAL COST OF HVAC WORKS | 17847551
1 | 47 Nos Gate Valves | 188000
2 | Chemo Feeder | 150000
| Total cost of additional Items | 338000
| Grand Total amount | 18185551
Note on A9: Mujahid:

## Sheet3
Item # | Description | Qty. | Unit | Rate |  | Amount |  | Total Cost
|  |  |  | Material | Installation | Material | Installation
DISMANTLING WORKS
1 | Motor Control Center (MCC)
a. | Dismantling of Motor Control Centre (MCC). | 1 | No. | 0 | 23000 | 0 | 23000 | 23000 | ok | 0 | 23000 | 0 | 1840 | 0 | 21160
2 | Wires, Cables, Conduites and Cable Tray
a. | Dismantling of wire, cables, conduites and cable tray for power supply, earthing and controls of HVAC system. | 1 | Job | 0 | 36800 | 0 | 36800 | 36800 | ok | 0 | 36800 | 0 | 2944 | 0 | 33856
3 | Meters and gages for HVAC Piping
a. | Dismantling of meters and gagues and accessories for HVAC piping.
4 | General-Duty Valves for HVAC Piping
| Dismantling of Chiller & Pumps valves complete with flanges and all other accessories for HVAC piping. | 1 | Job | 0 | 69000 | 0 | 69000 | 69000 | ok | 0 | 69000 | 0 | 5520 | 0 | 63480
5 | Chilled Water Piping
a. | Dismantling of chilled water piping system. | 1 | Job | 0 | 92000 | 0 | 92000 | 92000 | ok | 0 | 92000 | 0 | 7360 | 0 | 84640
6 | Fan Coil Units
| Dismantling of fan coil units with valve assembly and all other accessories, complete in all respect. | 42 | Nos | 0 | 1380 | 0 | 57960 | 57960 |  | 0 | 1380 | 0 | 110.4 | 0 | 1269.6
7 | Air-Cooled Water Chillers |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
a. | Dismantling of Existing Air-Cooled Chillers. | 3 | Nos | 0 | 23000 | 0 | 69000 | 69000 | ok | 0 | 23000 | 0 | 1840 | 0 | 21160
8 | Child Water Pumps
a. | Dismantling of Chilled Water Pumps. | 4 | Nos | 0 | 7360 | 0 | 29440 | 29440 | ok | 0 | 7360 | 0 | 588.8 | 0 | 6771.2
TOTAL COST OF DISMANTLING WORKS
HVAC UPGRADATION WORKS.
230010 | General Requirements for HVAC System
a. | Making of Shop Drawings with sectional details complete in all respect for complete HVAC Systems as per Specifications | 1 | Job | 0 | 27600 | 0 | 27600 | 27600 | half | 0 | 27600 | 0 | 2208 | 0 | 25392
b. | Making of As Built Drawings with sectional details complete in all respect for complete HVAC Systems as per Specifications | 1 | Job | 0 | 27600 | 0 | 27600 | 27600 |  | 0 | 27600 | 0 | 2208 | 0 | 25392
c. | Shifting of equipment from Ground Floor to respective locations including Owner Supplied Equipment. | 1 | Job | 0 | 184000 | 0 | 184000 | 184000 | ok | 0 | 184000 | 0 | 14720 | 0 | 169280
d | Painting and identification works of all components, supports, hangers & brackets etc. complete in all respect as per drawings and specifications. | 1 | Job | 276000 | 69000 | 276000 | 69000 | 345000 | half | 276000 | 69000 | 22080 | 5520 | 253920 | 63480
e | Contractor to list and price below with quantities any additional item(s) and/or quantities which are not included but required to complete the lumpsum tender price for this section of works. Should the tenderer fail to insert any item(s) and/or quantities here, it will be deemed that this lumpsum price for the tender includes all items and no subsequent cliams for any additional item will be entertained.
230100 | Operation and maintenance of HVAC System
230113 | Operation and maintenance of HVAC System
a. | One month test run | 1 | Job | 0 | 82800 | 0 | 82800 | 82800 |  | 0 | 82800 | 0 | 6624 | 0 | 76176
b. | Plant operation and mainteance of HVAC System for one year, seven days a weeks, from 10:Am to 11:Pm (one site engineer + one supervisor + Two mechanic + one electrician) | 1 | Job | 0 | 0 | 0 | 0 | 0
230500 | Common Work Results for HVAC
230513.13 | Motor Control Center (MCC)
a. | Supply, Installation of Motor Control Centre (MCC) complete in all respect including weather proof sheet metal cabinet, bus bars, internal wiring earth strip, connector strip, MCB, MCCB, Control fueses, magentic contactor, overload relay, indication lights, voltmeter, ammeter, under voltage phase reversible, phase failure device, selector switch, related civil works etc. complete in all respects for HVAC equipment including Owner supplied HVAC equipment as per scheudle, speicifications and drawings. | 1 | No | 1224520 | 69000 | 1224520 | 69000 | 1293520 | only supply | 1224520 | 69000 | 97961.6 | 5520 | 1126558.4 | 63480
230513.16 | Wires, Cables, Conduites and Cable Tray
a. | Supply and installation of of wire, cables, conduites and cable tray for power supply, earthing and controls of HVAC system complete in all respect as per drawings and specifications. | 1 | Job | 901600 | 151800 | 901600 | 151800 | 1053400 | half | 901600 | 151800 | 72128 | 12144 | 829472 | 139656
230519 | Meters and gages for HVAC Piping
a. | Supply, installation, testing and commissioning of meters and gagues and accessories for HVAC piping complete in all respect as per drawings and specifications
For Electric Chiller (s)
i. | Insertion type pipe mounted thermometers | 4 | Nos | 5520 | 644 | 22080 | 2576 | 24656 | 4 | 5520 | 644 | 441.6 | 51.52 | 5078.4 | 592.48
ii. | Pressure gauge | 4 | Nos | 5060 | 644 | 20240 | 2576 | 22816 | 4 | 5060 | 644 | 404.8 | 51.52 | 4655.2 | 592.48
iii. | gague cock | 4 | Nos | 644 | 276 | 2576 | 1104 | 3680 | 4 | 644 | 276 | 51.52 | 22.08 | 592.48 | 253.92
iv. | thermometer well | 4 | Nos | 368 | 184 | 1472 | 736 | 2208 | 4 | 368 | 184 | 29.44 | 14.72 | 338.56 | 169.28
v. | Flow switch | 2 | Nos | 13340 | 1840 | 26680 | 3680 | 30360 | 2 | 13340 | 1840 | 1067.2 | 147.2 | 12272.8 | 1692.8
| For Pumps | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
i. | Pressure gauge | 6 | Nos | 5520 | 644 | 33120 | 3864 | 36984 | 6 | 5520 | 644 | 441.6 | 51.52 | 5078.4 | 592.48
ii. | gague cock | 6 | Nos | 644 | 276 | 3864 | 1656 | 5520 | 6 | 644 | 276 | 51.52 | 22.08 | 592.48 | 253.92
230523 | General-Duty Valves for HVAC Piping
Supply, Installation, testing and commissioning of valves complete with flanges and all other accessories for HVAC piping complete in all respect as per drawings and specifications
Electric Chiller(s)
i. | Chilled Water Circuit
a. | Gate Valve
| 150 mm (6 inch) Diameter | 4 | Nos | 39100 | 920 | 156400 | 3680 | 160080 | 4 | 39100 | 920 | 3128 | 73.6 | 35972 | 846.4
b. | CFRV
| 150 mm (6 inch) Diameter | 2 | Nos | 80868 | 920 | 161736 | 1840 | 163576 | 2 | 80868 | 920 | 6469.44 | 73.6 | 74398.56 | 846.4
Primary Chilled Water Pump(s)
a. | Gate Valve
| 150 mm (6 inch) Diameter | 6 | Nos | 39100 | 920 | 234600 | 5520 | 240120 | 6 | 39100 | 920 | 3128 | 73.6 | 35972 | 846.4
b. | Check Valve
| 150 mm (6 inch) Diameter | 3 | Nos | 46920 | 920 | 140760 | 2760 | 143520 | 3 | 46920 | 920 | 3753.6 | 73.6 | 43166.4 | 846.4
c. | CFRV
| 150 mm (6 inch) Diameter | 3 | Nos | 80868 | 3680 | 242604 | 11040 | 253644 | 3 | 80868 | 3680 | 6469.44 | 294.4 | 74398.56 | 3385.6
d | Stainer
| 150 mm (6 inch) Diameter | 3 | Nos | 45908 | 3680 | 137724 | 11040 | 148764 | 3 | 45908 | 3680 | 3672.64 | 294.4 | 42235.36 | 3385.6
e | Flexible Connector
| 150 mm (6 inch) Diameter | 10 | Nos | 13800 | 920 | 138000 | 9200 | 147200 | 10 | 13800 | 920 | 1104 | 73.6 | 12696 | 846.4
Fan Coil Units
a. | Gate Valve
| 25 mm (1 inch) Diameter | 47 | Nos | 3036 | 644 | 142692 | 30268 | 172960 |  | 3036 | 644 | 242.88 | 51.52 | 2793.12 | 592.48
b. | Globe Valve
| 25 mm (1 inch) Diameter | 47 | Nos | 3588 | 644 | 168636 | 30268 | 198904 |  | 3588 | 644 | 287.04 | 51.52 | 3300.96 | 592.48
c. | Stainer
| 25 mm (1 inch) Diameter | 47 | Nos | 2944 | 644 | 138368 | 30268 | 168636 |  | 2944 | 644 | 235.52 | 51.52 | 2708.48 | 592.48
d. | Motorized Valve
| 25 mm (1 inch) Diameter | 47 | Nos | 2760 | 644 | 129720 | 30268 | 159988 |  | 2760 | 644 | 220.8 | 51.52 | 2539.2 | 592.48
Miscellanous Valves
a. | Gate Valves
| 100 mm (4 inch) Diameter | 2 | Nos | 20148 | 920 | 40296 | 1840 | 42136 | 2 | 20148 | 920 | 1611.84 | 73.6 | 18536.16 | 846.4
| 50 mm (2 inch) Diameter | 2 | Nos | 9108 | 644 | 18216 | 1288 | 19504 | 2 | 9108 | 644 | 728.64 | 51.52 | 8379.36 | 592.48
| 25 mm (1 inch) Diameter | 2 | Nos | 3036 | 644 | 6072 | 1288 | 7360 | 2 | 3036 | 644 | 242.88 | 51.52 | 2793.12 | 592.48
230529.13 | Hangers and Supports for HVAC Piping
a. | Supply, Installation & Commissioning of hangers and supports for HVAC piping complete in all respect as per drawings and specifications. | 1 | Job | 254840 | 36340 | 254840 | 36340 | 291180 | half | 254840 | 36340 | 20387.2 | 2907.2 | 234452.8 | 33432.8
230529.16 | Hangers and Supports for HVAC Equipment
a. | Supply, Installation & Commissioning of hangers and supports for HVAC equipment complete in all respect as per drawings and specifications. | 1 | Job | 69000 | 24840 | 69000 | 24840 | 93840 | half | 69000 | 24840 | 5520 | 1987.2 | 63480 | 22852.8
230553 | Identification for HVAC Ducting, Piping and Equipment
a. | Supply, Installation & Commissioning of identification for HVAC ducting, piping and equipment complete in all respect as per drawings and specifications. | 1 | Job | 32200 | 9200 | 32200 | 9200 | 41400 |  | 32200 | 9200 | 2576 | 736 | 29624 | 8464
230700 | HVAC Insulation
230719.13 | Chilled Water Piping Insulation
a. | Supply and installation of premoulded polyurethane insulation of density 50 kg/m3 with bituminous karft paper facing for chilled water pipes, bends, tees, unions, sockets, valves and on speicals, wrapped with 8 oz. canvas cloth than painted with anti fungus paint, protected 26 SWG painted G.I. sheet metal cladding complete in all respect as per scheudle, specifications and drawings.
38 mm (1-1/2 inch) thickness
| 25 mm (1 inch) Diameter | 500 | Rft | 367.08 | 64.4 | 183540 | 32200 | 215740 |  | 367.08 | 64.4 | 29.3664 | 5.152 | 337.7136 | 59.248
50 mm (2 inch) thickness
| 250 mm (10 inch) Diameter | 90 | Rft | 1830.8 | 322 | 164772 | 28980 | 193752 | 90 | 1830.8 | 322 | 146.464 | 25.76 | 1684.336 | 296.24
| 200 mm (8 inch) Diameter | 60 | Rft | 1536.4 | 276 | 92184 | 16560 | 108744 | 60 | 1536.4 | 276 | 122.912 | 22.08 | 1413.488 | 253.92
| 150 mm (6 inch) Diameter | 120 | Rft | 1343.2 | 230 | 161184 | 27600 | 188784 | 120 | 1343.2 | 230 | 107.456 | 18.4 | 1235.744 | 211.6
b. | Supply, installation & commissioning of Chilled Water Valves insulation with anti fungus paint, protected 26 SWG painted G.I sheet metal cladding, complete in all respect as per drawings and specifications
| 150 mm (6 inch) Diameter | 21 | Nos | 3220 | 920 | 67620 | 19320 | 86940 | 21 | 3220 | 920 | 257.6 | 73.6 | 2962.4 | 846.4
230719.26 | Condensate Drain Insulation
a. | Supply and installation of 6 mm thick Pre-moulded Armaflex Pipe Insulation complete in all respect as per schedule, specifications and drawings.
| 25 mm (1 inch) Diameter | 130 | Rft | 96.6 | 55.2 | 12558 | 7176 | 19734 |  | 96.6 | 55.2 | 7.728 | 4.416 | 88.872 | 50.784
230800 | Commissioning of HVAC
230813 | Testing, Adjusting and balancing for HVAC systems
a. | Testing, balancing and commissioning of HVAC system complete in all respect including one month test run, measurement and recording of pressure and electrical data and submission of technical/operation manual, LOG book for each related equipment as per specifications and drawings. | 1 | Job | 0 | 138000 | 0 | 138000 | 138000 |  | 0 | 138000 | 0 | 11040 | 0 | 126960
230933 | System Automatic Control
a. | Supply, Installation & Commissioning of System Automatic control complete in all respect as per drawings and specifications. | 1 | Job | 1978000 | 138000 | 1978000 | 138000 | 2116000 | 500000 | 1978000 | 138000 | 158240 | 11040 | 1819760 | 126960
232100 | HVAC Piping and Pumps
232113.23 | Hydronic Piping
a. | Supply, Installation, testing & Commissioning of M.S Schedule 40 (as per ASME & API standard, heavy quality with standard Schedule 40 thickness) pipes & fittings for chilled water circulation system with bends, tees, unions, sockets as required to complete in all respects ready to operate as per schedule, drawings and specifications.
| 25 mm (1 inch) Diameter | 500 | Rft | 257.6 | 92 | 128800 | 46000 | 174800 |  | 257.6 | 92 | 20.608 | 7.36 | 236.992 | 84.64
| 150 mm (6 inch) Diameter | 120 | Rft | 2278.84 | 276 | 273460.8 | 33120 | 306580.8 | 120 | 2278.84 | 276 | 182.3072 | 22.08 | 2096.5328 | 253.92
| 200 mm (8 inch) Diameter | 60 | Rft | 2907.2 | 322 | 174432 | 19320 | 193752 | 60 | 2907.2 | 322 | 232.576 | 25.76 | 2674.624 | 296.24
| 250 mm (10 inch) Diameter | 90 | Rft | 4416 | 368 | 397440 | 33120 | 430560 | 90 | 4416 | 368 | 353.28 | 29.44 | 4062.72 | 338.56
232113.26 | Condensate Drain Piping
a. | Supply, Installation, testing & Commissioning of UPVC Class D pipes & fittings for condensate drain system with bends, tees, unions, sockets as required to complete in all respects ready to operate as per schedule, drawings and specifications.
| 25 mm (1 inch) Diameter | 130 | Rft | 73.6 | 55.2 | 9568 | 7176 | 16744 |  | 73.6 | 55.2 | 5.888 | 4.416 | 67.712 | 50.784
232116 | Hydronic piping specialties
a. | Supply, Installation, testing & Commissioning of hydronic piping specialties alongwith flanges, coupling, unions complete in all respect as per drawings and specifications.
For Electric Chiller (s)
Strainers with blow off 20 mm dia ball valve
| 20 mm (3/4 inch) Diameter | 2 | Nos | 2760 | 552 | 5520 | 1104 | 6624 |  | 2760 | 552 | 220.8 | 44.16 | 2539.2 | 507.84
| Automatic Air Vent | 4 | Nos | 3220 | 552 | 12880 | 2208 | 15088 | 4 | 3220 | 552 | 257.6 | 44.16 | 2962.4 | 507.84
232119-13 | Open Type Expansion tank
a. | Supply, Installation, testing and commissioning of open type expansion tank PVC having 50 mm thick glass wool insulation covered with 26 Gauge Aluminum sheet with manhole cover, drain, over flow, quick fill, normal water connection complete in all respect as per drawings and specifications | 1 | No | 59800 | 13800 | 59800 | 13800 | 73600 |  | 59800 | 13800 | 4784 | 1104 | 55016 | 12696
233100 | HVAC Ducts and Casings
233113.13 | Medium/Low pressure G.I. sheet metal ducting
a. | Supply, Installation, testing & Commissioning of medium/low pressure G.I. sheet metal ducting complete in all respect as per drawings and specifications.
| 22 gauge | 400 | Sq.ft | 239.2 | 64.4 | 95680 | 25760 | 121440 |  | 239.2 | 64.4 | 19.136 | 5.152 | 220.064 | 59.248
233119 | Access door for Fan coil unit
a. | Supply, Installation, testing & Commissioning of access door for fan coil units complete in all respect as per drawings and specifications. | 1 | Lot | 161000 | 32200 | 161000 | 32200 | 193200 |  | 161000 | 32200 | 12880 | 2576 | 148120 | 29624
233343 | Flexible Connectors
a. | Supply, Installation, testing & Commissioning of flexible connectors between blower section and air duct complete in all respect as per drawings and specifications. | 1 | Job | 156400 | 18400 | 156400 | 18400 | 174800 |  | 156400 | 18400 | 12512 | 1472 | 143888 | 16928
233346 | Flexible Duct
a. | Supply, Installation, testing & Commissioning of flexible duct complete in all respect as per drawings and specifications.
| 150 mm (6 inch) Diameter | 30 | Rft | 322 | 92 | 9660 | 2760 | 12420 |  | 322 | 92 | 25.76 | 7.36 | 296.24 | 84.64
233700 | Air Outlets and inlets
233713 | Diffusers, Registers, and Grilles
Supply, Installation, testing & Commissioning of Diffusers, Registers and Grilles complete in all respect as per drawings and specifications.
a. | Supply Air Round Diffusers (SARD)
| 600mm (24" diameter) | 3 | Nos | 5980 | 920 | 17940 | 2760 | 20700 |  | 5980 | 920 | 478.4 | 73.6 | 5501.6 | 846.4
e. | Imperialine linear air diffuser 3/4" slot with volume control dampers with link to adjust the damper blade from the face of linear air diffuser complete in all respect as per drawings and specifications
| 3 Slot SALD 6 Feet Long. | 8 | Nos | 7268 | 920 | 58144 | 7360 | 65504 |  | 7268 | 920 | 581.44 | 73.6 | 6686.56 | 846.4
236419.13 | Air-Cooled Reciprocating compressor type Water Chillers
a. | Installation, testing & Commissioning of Air-Cooled Screw type Water Chiller complete in all respect as per drawings and specifications. | 2 | Nos | 0 | 46000 | 0 | 92000 | 92000 | 92000 | 0 | 46000 | 0 | 3680 | 0 | 42320
b. | Supply, installation, lifting, shifting & Commissioning of chilled Water pumps complete in all respect as per drawings and specifications. | 3 | Nos | 795800 | 18400 | 2387400 | 55200 | 2442600 | 2 | 795800 | 18400 | 63664 | 1472 | 732136 | 16928
238219 | Fan Coil Units
a. | Supply, Installation, testing & Commissioning of Fan Coil Units complete in all respect as per drawings and specifications. | 47 | Nos | 124200 | 1380 | 5837400 | 64860 | 5902260 |  | 124200 | 1380 | 9936 | 110.4 | 114264 | 1269.6
TOTAL COST OF HVAC WORKS | [7 empty] | 19280522.8
20957090
1676567.2
19280522.8