## rec details
Financail Summary for the project The Forum Shopping Mall
|  |  |  | Contract Value | 21000000 |  | Contract Value | 21000000
|  |  |  | Retention Hold 10% | 2100000 |  | Total Received | 13264500
|  |  |  | Payable amount | 18900000 |  | Net Payable | 7735500
Receiving details
Payment | Receiving date | Gross payment reeived | Tax 7.5% | Chq amount | Remarks | Remarks |  |  |  | 11340000
1st Payment adhoc | 2021-01-21 | 2500000 | 187500 | 2312500 | Depositted in DIB |  |  |  | 3780000 | 850500 |  | 3780000
1st Payment final | 2021-02-06 | 1280000 | 96000 | 1184000 | Depositted in DIB |  |  |  | 283500 | 10489500 |  | 283500
2nd Payment adhoc | 2021-02-15 | 1945946 | 145945.95 | 1800000.05 | Depositted in DIB |  |  |  | 3496500 |  |  | 3496500
2nd Payment adhoc | 2021-02-15 | 854054 | 64054.05 | 789999.95 | Depositted in DIB |  | 1800000
2nd Payment Final | 2021-02-22 | 980000 | 73500 | 906500 | Depositted in DIB |  | 790000 |  |  | 1800000 | 1800000 | 790000 | 906500
3rd Payment adhoc | 2021-03-03 | 2500000 | 187500 | 2312500 | Depositted in DIB |  | 2590000 |  |  | 790000 | 135000 | 59250 | 67987.5
3rd Payment final | 2021-03-13 | 1280000 | 96000 | 1184000 | Depositted in DIB |  | 3780000 |  |  | 906500 | 1935000 | 849250 | 974487.5
4th Payment adhoc | 2021-06-06 | 2000000 | 150000 | 1850000 | Depositted in DIB | 3780000 | 1190000 |  |  | 3496500
4th Payment adhoc | 2021-11-27 | 1000000 | 75000 | 925000 | Depositted in DIB | 11340000
[6 empty] | 850500 |  |  | 1190000 |  |  | 3758737.5
[6 empty] | 10489500 |  |  | 89250
Total receiving till todate |  | 14340000 | 1075500 | 13264500 |  |  |  |  | 1100750
Net Receivable amount |  |  |  | 5635500
Add Retention Money |  |  |  | 2100000
Total Payable Amount Rs |  |  |  | 7735500 |  |  | 906500
11340000
|  | 7170000 |  |  |  | 1280000 | 67987.5
[6 empty] | 12620000 |  |  | 1000000
[6 empty] | 946500 | 7.5%
[6 empty] | 11673500 |  |  | 75000
925000
3780000
283500
3496500

## rec details 2
Stages | Scope of work | Amount | Received | Due Date | Receiving date | Remarks
Stage l | Mobllizatlon advance for placement of various procurement orders. (Fitting of pipings, lnsulation & cladding work etc. | 3780000 | 3780000 | 2021-01-21 | 2021-02-06 | Late Received
Stage 2 | Procurement of pumps & accessaries, removal of existing and placement of new chlllers, fitting of MS pipes & valves at roof top | 3780000 | 3780000 | 2021-02-08 | 2021-02-22 | Late Received
Stage 3 | Procurement of Electrical DBs, Cables, Citble trays, MCC Panela & allied Items | 3780000 | 3780000 | 2021-02-23 | 2021-03-13 | Late Received
Stage 4 | Supply of New FCUs for Mall corridors & installation | 3780000 | 0 | 2021-03-10 |  | Payment due
Stage 5 | Commissioing & completion of project | 3780000 | 0 | 2021-03-30 |  | Payment due