## Sheet1
HVAC Work Schedule
Description | Month | November 2022 | [15 empty] | December 2022 | [30 empty] | January 2023
| Weeks | Week 1 | [31 empty] | Week 1 | [24 empty] | Week 4
| Week | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
GROUND FLOOR
Installation of hangers & supports | 03 Days
G. I Duct Fabrication | 03 Days
Duct Installation | 05 Days
Duct Leak Testing | 02 Days
Insulation | 04 Days
Painting / Identification | 03 Days
Installation of air devices | 04 Days
Testing & Commissioning | 05 Days
FIRST FLOOR
Installation of hangers & supports | 04 Days
G. I Duct Fabrication | 04 Days
Duct Installation | 06 Days
Duct Leak Testing | 02 Days
Insulation | 06 Days
Painting / Identification | 03 Days
Installation of air devices | 06 Days
Testing & Commissioning | 05 Days
Description | Month | November 2022 | [15 empty] | December 2022 | [30 empty] | January 2023
| Weeks | Week 1 | [31 empty] | Week 1 | [24 empty] | Week 4
| Week | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
SECOND FLOOR
Installation of hangers & supports | 05 Days
G. I Duct Fabrication | 06 Days
Duct Installation | 06 Days
Duct Leak Testing | 03 Days
Insulation | 08 Days
Painting / Identification | 03 Days
Installation of air devices | 05 Days
Testing & Commissioning | 05 Days
THIRD FLOOR
Installation of hangers & supports | 15 Days
G. I Duct Fabrication | 15 Days
Duct Installation | 15 Days
Duct Leak Testing | 15 Days
Insulation | 15 Days
Painting / Identification | 05 Days
Installation of air devices | 10 Days
Testing & Commissioning | 05 Days