## sum
M/S DWP Technologies PVT Ltd | [8 empty] | Date | 10 Augustt 2023
Suit No. 102, First Floor, Fortune Center, | [8 empty] | Invoice # | 075
Shahrah-e-Faisal, Karachi. | [8 empty] | NTN # | 4312149-7
NTN # 1547417-8
Mr. M. Ali Siddiqui
Attn: Mr. Farooq Tarmezi.
INVOICE
Running Bill for additional G.I Shet Metal duct & insulation - NASTP
S. # | Particulars | BILL OF QUANTITIES | [5 empty] | RUNNING BILL
|  | Unit | BOQ Qty | Material rate | Labour rate | Prv Qty | Billed Qty | Billed Qty | Mateial Amount | Labour Amount
1 | Supply, fabrication, and installation of G.I. Duct work using prime quality sheet metal as specified in the specifications and drawing. | Sqft | 14000 | 325 | 80 | 9023 | 4537 | 13560 | 4407000 | 1084800 | 70 | 13622
2 | Supply and installation of 1.5” thick, 24 kg/m3 density Glass Wool Insulation with 8 oz. Canvas cloth wrapping, antifungal paint around duct with adhesive and 2” wide adhesive tape as specified in the specifications and drawing. | Sqft | 14000 | 185 | 70 | 9023 | 4537 | 13560 | 2508600 | 949200 | 70
3 | Supply & installation of Pre-insulated flexible duct 8" Dia. | Rft | 300 | 350 | 100 | 275 | 25 | 300 | 105000 | 30000 | 20
4 | Providing and installation Jubilee clamp 10" for flexible duct. | Nos | 120 | 300 | 25 | 84 | 36 | 120 | 36000 | 3000 | 20
5 | Providing and installation of G.I sheet metal round neck 8" dia for fixing flexible duct. | Nos | 120 | 400 | 100 | 84 | 36 | 120 | 48000 | 12000 | 20
6 | Fabrication and installation of G.I sheet metal plenum box for supply air diffuser. | Nos | 60 | 1600 | 300 | 42 | 18 | 60 | 96000 | 18000 | 20
7 | Supply & installation of fiber glass insulation over supply air plenum including canvas cloth, antifungus paint etc complete in all respect | Nos | 60 | 1400 | 200 | 42 | 18 | 60 | 84000 | 12000 | 20
Sub Total Amount | [8 empty] | 7284600 | 2109000
Total Amount | [8 empty] | 9393600 |  |  |  | 6999000 | 2025000
SST 13% | [8 empty] | 1221168
Grand Total Amount | [8 empty] | 10614768 |  |  | 7113610 |  | 9024000
Received in Prv Bill | [8 empty] | 4979526.93
Total Payable Amount | [8 empty] | 5635241.07
Best Regards, | [13 empty] | 1173120
For Pioneer Services | [13 empty] | 10197120
5098560
5302502.4
PIONEER SERVICES

## G Floor
[7 empty] | Date | 19 May 2023
[7 empty] | Invoice # | 072
[7 empty] | NTN # | 4312149-7
M/S DWP Technologies PVT Ltd
Suit No. 102, First Floor, Fortune Center,
Shahrah-e-Faisal, Karachi.
NTN # 1547417-8
Mr. M. Ali Siddiqui
Attn: Mr. Farooq Tarmezi.
INVOICE
Running Bill for additional G.I Shet Metal duct & insulation - NASTP
S. # | Particulars | BILL OF QUANTITIES |  |  |  | RUNNING BILL
|  | Unit | BOQ Qty | Material rate | Labour rate | Billed Qty | Mateial Amount | Labour Amount
GROUND FLOOR
1 | Supply, fabrication, and installation of G.I. Duct work using prime quality sheet metal as specified in the specifications and drawing. | Sqft | 13000 | 325 | 80 | 318 | 103350 | 25440 | 70
2 | Supply and installation of 1.5” thick, 24 kg/m3 density Glass Wool Insulation with 8 oz. Canvas cloth wrapping, antifungal paint around duct with adhesive and 2” wide adhesive tape as specified in the specifications and drawing. | Sqft | 13000 | 185 | 70 | 318 | 58830 | 22260 | 70
3 | Supply & installation of Pre-insulated flexible duct 8" Dia. | Rft | 300 | 350 | 100 | 150 | 52500 | 15000 | 20
4 | Providing and installation Jubilee clamp 10" for flexible duct. | Nos | 120 | 300 | 25 | 60 | 18000 | 1500 | 20
5 | Providing and installation of G.I sheet metal round neck 8" dia for fixing flexible duct. | Nos | 120 | 400 | 100 | 60 | 24000 | 6000 | 20
6 | Fabrication and installation of G.I sheet metal plenum box for supply air diffuser. | Nos | 60 | 1600 | 300 | 30 | 48000 | 9000 | 20
7 | Supply & installation of fiber glass insulation over supply air plenum including canvas cloth, antifungus paint etc complete in all respect | Nos | 60 | 1400 | 200 | 30 | 42000 | 6000 | 20
Sub Total Amount | [6 empty] | 346680 | 85200
Total Amount | [6 empty] | 431880 |  |  | 6999000 | 2025000
SST 13% | [6 empty] | 56144.4
Grand Total Amount | [6 empty] | 488024.4 |  |  |  | 9024000
Best Regards, | [10 empty] | 1173120
For Pioneer Services | [10 empty] | 10197120
5098560
5302502.4
PIONEER SERVICES

## First Floor
[7 empty] | Date | 19 May 2023
[7 empty] | Invoice # | 072
[7 empty] | NTN # | 4312149-7
M/S DWP Technologies PVT Ltd
Suit No. 102, First Floor, Fortune Center,
Shahrah-e-Faisal, Karachi.
NTN # 1547417-8
Mr. M. Ali Siddiqui
Attn: Mr. Farooq Tarmezi.
INVOICE
Running Bill for additional G.I Shet Metal duct & insulation - NASTP
S. # | Particulars | BILL OF QUANTITIES |  |  |  | RUNNING BILL
|  | Unit | Billed Qty | Material rate | Labour rate | Approx Qty | Mateial Amount | Labour Amount
FIRST FLOOR
1 | Supply, fabrication, and installation of G.I. Duct work using prime quality sheet metal as specified in the specifications and drawing. | Sqft | 13000 | 325 | 80 | 1166.6 | 379145 | 93328 | 70
2 | Supply and installation of 1.5” thick, 24 kg/m3 density Glass Wool Insulation with 8 oz. Canvas cloth wrapping, antifungal paint around duct with adhesive and 2” wide adhesive tape as specified in the specifications and drawing. | Sqft | 13000 | 185 | 70 | 1120 | 207200 | 78400 | 70
3 | Supply & installation of Pre-insulated flexible duct 8" Dia. | Rft | 300 | 350 | 100 | 0 | 0 | 0 | 20
4 | Providing and installation Jubilee clamp 10" for flexible duct. | Nos | 120 | 300 | 25 | 0 | 0 | 0 | 20
5 | Providing and installation of G.I sheet metal round neck 8" dia for fixing flexible duct. | Nos | 120 | 400 | 100 | 0 | 0 | 0 | 20
6 | Fabrication and installation of G.I sheet metal plenum box for supply air diffuser. | Nos | 60 | 1600 | 300 | 0 | 0 | 0 | 20
7 | Supply & installation of fiber glass insulation over supply air plenum including canvas cloth, antifungus paint etc complete in all respect | Nos | 60 | 1400 | 200 | 0 | 0 | 0 | 20
Sub Total Amount | [6 empty] | 586345 | 171728
Total Amount | [6 empty] | 758073 |  |  | 6999000 | 2025000
SST 13% | [6 empty] | 98549.49
Grand Total Amount | [6 empty] | 856622.49 |  |  |  | 9024000
Best Regards, | [10 empty] | 1173120
For Pioneer Services | [10 empty] | 10197120
5098560
5302502.4
PIONEER SERVICES

## Second Floor
[7 empty] | Date | 19 May 2023
[7 empty] | Invoice # | 072
[7 empty] | NTN # | 4312149-7
M/S DWP Technologies PVT Ltd
Suit No. 102, First Floor, Fortune Center,
Shahrah-e-Faisal, Karachi.
NTN # 1547417-8
Mr. M. Ali Siddiqui
Attn: Mr. Farooq Tarmezi.
INVOICE
Running Bill for additional G.I Shet Metal duct & insulation - NASTP
S. # | Particulars | BILL OF QUANTITIES |  |  |  | RUNNING BILL
|  | Unit | Billed Qty | Material rate | Labour rate | Approx Qty | Mateial Amount | Labour Amount
SECOND FLOOR
1 | Supply, fabrication, and installation of G.I. Duct work using prime quality sheet metal as specified in the specifications and drawing. | Sqft | 13000 | 325 | 80 | 2145 | 697125 | 171600 | 70
2 | Supply and installation of 1.5” thick, 24 kg/m3 density Glass Wool Insulation with 8 oz. Canvas cloth wrapping, antifungal paint around duct with adhesive and 2” wide adhesive tape as specified in the specifications and drawing. | Sqft | 13000 | 185 | 70 | 2145 | 396825 | 150150 | 70
3 | Supply & installation of Pre-insulated flexible duct 8" Dia. | Rft | 300 | 350 | 100 | 0 | 0 | 0 | 20
4 | Providing and installation Jubilee clamp 10" for flexible duct. | Nos | 120 | 300 | 25 | 0 | 0 | 0 | 20
5 | Providing and installation of G.I sheet metal round neck 8" dia for fixing flexible duct. | Nos | 120 | 400 | 100 | 0 | 0 | 0 | 20
6 | Fabrication and installation of G.I sheet metal plenum box for supply air diffuser. | Nos | 60 | 1600 | 300 | 0 | 0 | 0 | 20
7 | Supply & installation of fiber glass insulation over supply air plenum including canvas cloth, antifungus paint etc complete in all respect | Nos | 60 | 1400 | 200 | 0 | 0 | 0 | 20
Sub Total Amount | [6 empty] | 1093950 | 321750
Total Amount | [6 empty] | 1415700 |  |  | 6999000 | 2025000
SST 13% | [6 empty] | 184041
Grand Total Amount | [6 empty] | 1599741 |  |  |  | 9024000
Best Regards, | [10 empty] | 1173120
For Pioneer Services | [10 empty] | 10197120
5098560
5302502.4
PIONEER SERVICES

## Third Floor
[7 empty] | Date | 19 May 2023
[7 empty] | Invoice # | 072
[7 empty] | NTN # | 4312149-7
M/S DWP Technologies PVT Ltd
Suit No. 102, First Floor, Fortune Center,
Shahrah-e-Faisal, Karachi.
NTN # 1547417-8
Mr. M. Ali Siddiqui
Attn: Mr. Farooq Tarmezi.
INVOICE
Running Bill for additional G.I Shet Metal duct & insulation - NASTP
S. # | Particulars | BILL OF QUANTITIES |  |  |  | RUNNING BILL
|  | Unit | Billed Qty | Material rate | Labour rate | Approx Qty | Mateial Amount | Labour Amount
THIRD FLOOR
1 | Supply, fabrication, and installation of G.I. Duct work using prime quality sheet metal as specified in the specifications and drawing. | Sqft | 13000 | 325 | 80 | 5394 | 1753050 | 431520 | 70
2 | Supply and installation of 1.5” thick, 24 kg/m3 density Glass Wool Insulation with 8 oz. Canvas cloth wrapping, antifungal paint around duct with adhesive and 2” wide adhesive tape as specified in the specifications and drawing. | Sqft | 13000 | 185 | 70 | 5394 | 997890 | 377580 | 70
3 | Supply & installation of Pre-insulated flexible duct 8" Dia. | Rft | 300 | 350 | 100 | 125 | 43750 | 12500 | 20
4 | Providing and installation Jubilee clamp 10" for flexible duct. | Nos | 120 | 300 | 25 | 24 | 7200 | 600 | 20
5 | Providing and installation of G.I sheet metal round neck 8" dia for fixing flexible duct. | Nos | 120 | 400 | 100 | 24 | 9600 | 2400 | 20
6 | Fabrication and installation of G.I sheet metal plenum box for supply air diffuser. | Nos | 60 | 1600 | 300 | 12 | 19200 | 3600 | 20
7 | Supply & installation of fiber glass insulation over supply air plenum including canvas cloth, antifungus paint etc complete in all respect | Nos | 60 | 1400 | 200 | 12 | 16800 | 2400 | 20
Sub Total Amount | [6 empty] | 2847490 | 830600
Total Amount | [6 empty] | 3678090 |  |  | 6999000 | 2025000
SST 13% | [6 empty] | 478151.7
Grand Total Amount | [6 empty] | 4156241.7 |  |  |  | 9024000
Best Regards, | [10 empty] | 1173120
For Pioneer Services | [10 empty] | 10197120
5098560
5302502.4
PIONEER SERVICES