## Table 2
IPC-01 (Ashrae Tech - 2nd Floor NASTP Building Karachi)
BILL OF QUANTITIES | [5 empty] | RUNNING BILL NO 1
Item # | Description | Qty. | Unit | Rate |  | BILLED QTY | Material Amount | Labour Amount | Total Cost
|  |  |  | Material | Installation
230010 | General Requirements for HVAC System
a. | Making Shop Drawings with sectional details complete in all respect for complete HVAC Systems as per Specifications | 1 | Job | 10000 | 20000 | 1 | 10000 | 20000 | 30000
b. | Making As Built Drawings with sectional details complete in all respect for complete HVAC Systems as per Specifications | 1 | Job | 5000 | 5000 | 1 | 5000 | 5000 | 10000
c. | Equipment foundations and shifting of equipment from Ground Floor to respective locations including Owner Supplied Equipment. | 1 | Job | 0 | 20000 | 1 | 0 | 20000 | 20000
e. | Contractor to list and price below with quantities any additional item(s) and/or quantities which are not included but required to complete the lumpsum tender price for this section of works. Should the tenderer fail to insert any item(s) and/or quantities here, it will be deemed that this lumpsum price for the tender includes all items and no subsequent cliams for any additional item will be entertained.
230100 | Operation and maintenance of HVAC System
230113 | Operation and maintenance of HVAC System
a. | One month test run | 1 | Job | 0 |  |  | 0 | 0 | 0
230500 | Common Work Results for HVAC
230513.13 | AHU ISOLATOR BOX
a. | Supply, Installation of AHU Isolator Box complete in all respect including weather proof sheet metal cabinet, bus bars, internal wiring earth strip, connector strip, , magentic contactor, overload relay, indication lights, voltmeter, ammeter, under voltage phase reversible, phase failure device, selector switch, related civil works etc. complete in all respects for HVAC equipment including Owner supplied HVAC equipment as per scheudle, speicifications and drawings. | 6 | Nos |  |  |  | 0 | 0 | 0
230513.16 | Wires, Cables, Conduites and Cable Tray
a. | Supply and installation of of wire, cables, conduites and cable tray for power supply, earthing and controls of HVAC system complete in all respect as per drawings and specifications. | 1 | Job | 150000 | 25000 | 2 | 300000 | 50000 | 350000
230516 | Expansion fittings and loops
a. | Supply and installation of expansion fittings and loops for HVAC system complete in all respect as per drawings and specifications. | 1 | Job | 40000 | 10000 | 1 | 40000 | 10000 | 50000
230519 | Meters and gages for HVAC Piping
a. | Supply, installation, testing and commissioning of meters and gagues and accessories for HVAC piping complete in all respect as per drawings and specifications
For Air Handling Unit (s)
i. | Insertion type pipe mounted thermometers | 12 | Nos |  |  |  | 0 | 0 | 0
ii. | Pressure gauge | 12 | Nos |  |  |  | 0 | 0 | 0
iii. | gague cock | 12 | Nos |  |  |  | 0 | 0 | 0
iv. | thermometer with well | 12 | Nos |  |  |  | 0 | 0 | 0
230523 | General-Duty Valves for HVAC Piping
Supply, installation, testing and commissioning of valves complete with flanges and all other accessories for HVAC piping complete in all respect as per drawings and specifications
Air Handling Units
a. | Gate Valve
| 32 mm (1-1/4 inch) Diameter | 2 | Nos | 12000 | 1500 | 2 | 24000 | 3000 | 27000
b. | CFRV | [5 empty] | 0 | 0 | 0
| 32 mm (1-1/4 inch) Diameter | 1 | Nos | 19500 | 1500 | 1 | 19500 | 1500 | 21000
c. | Motorized Valve | [5 empty] | 0 | 0 | 0
| 32 mm (1-1/4 inch) Diameter | 1 | Nos | 58000 | 2000 | 1 | 58000 | 2000 | 60000
Air Handling Units
a. | Gate Valve
| 38 mm (1-1/2 inch) Diameter | 4 | Nos |  |  |  | 0 | 0 | 0
b. | CFRV | [5 empty] | 0 | 0 | 0
| 38 mm (1-1/2 inch) Diameter | 2 | Nos |  |  |  | 0 | 0 | 0
c. | Motorized Valve | [5 empty] | 0 | 0 | 0
| 38 mm (1-1/2 inch) Diameter | 2 | Nos |  |  |  | 0 | 0 | 0
| Air Handling Units | [5 empty] | 0 | 0 | 0
a. | Gate Valve | [5 empty] | 0 | 0 | 0
| 50 mm (2 inch) Diameter | 6 | Nos |  |  |  | 0 | 0 | 0
b. | CFRV | [5 empty] | 0 | 0 | 0
| 50 mm (2 inch) Diameter | 3 | Nos |  |  |  | 0 | 0 | 0
c. | Motorized Valve | [5 empty] | 0 | 0 | 0
| 50 mm (2 inch) Diameter | 3 | Nos |  |  |  | 0 | 0 | 0
| Fan Coil Units | [5 empty] | 0 | 0 | 0
a. | Gate Valve | [5 empty] | 0 | 0 | 0
| 19 mm (3/4 inch) Diameter | 10 | Nos | 6000 | 1500 | 16 | 96000 | 24000 | 120000
b. | CFRV | [5 empty] | 0 | 0 | 0
| 19 mm (3/4 inch) Diameter | 5 | No | 10500 | 1500 | 8 | 84000 | 12000 | 96000
c. | Motorized Valve | [5 empty] | 0 | 0 | 0
| 19 mm (3/4 inch) Diameter | 5 | No | 25000 | 2000 | 8 | 200000 | 16000 | 216000
| Fan Coil Units | [5 empty] | 0 | 0 | 0
a. | Gate Valve | [5 empty] | 0 | 0 | 0
| 25 mm (1 inch) Diameter | 2 | Nos | 7800 | 1500 | 2 | 15600 | 3000 | 18600
b. | CFRV | [5 empty] | 0 | 0 | 0
| 25 mm (1 inch) Diameter | 1 | Nos | 17500 | 1500 | 1 | 17500 | 1500 | 19000
c. | Motorized Valve | [5 empty] | 0 | 0 | 0
| 25 mm (1 inch) Diameter | 1 | Nos | 35000 | 1500 | 1 | 35000 | 1500 | 36500
| Miscellanous Valves | [5 empty] | 0 | 0 | 0
a. | Gate Valves | [5 empty] | 0 | 0 | 0
| 32 mm (1-1/4 inch) Diameter | 1 | No |  |  |  | 0 | 0 | 0
| 38 mm (1-1/2 inch) Diameter | 1 | No |  |  |  | 0 | 0 | 0
| 50 mm (2 inch) Diameter | 1 | No | 21000 | 2000 | 1 | 21000 | 2000 | 23000
| 75 mm (3 inch) Diameter | 2 | Nos |  |  |  | 0 | 0 | 0
| Globe Valves | [5 empty] | 0 | 0 | 0
| 75 mm (3 inch) Diameter | 1 | No |  |  |  | 0 | 0 | 0
230526 | Hangers and Supports for HVAC Ducting | [5 empty] | 0 | 0 | 0
a. | Supply, Installation & Commissioning of hangers and supports for HVAC ducting complete in all respect as per drawings and specifications. | 1 | Job | 90000 | 20000 | 1 | 90000 | 20000 | 110000
230529.13 | Hangers and Supports for HVAC Piping | [5 empty] | 0 | 0 | 0
a. | Supply, Installation & Commissioning of hangers and supports for HVAC piping complete in all respect as per drawings and specifications. | 1 | Job | 115000 | 18000 | 1 | 115000 | 18000 | 133000
230529.16 | Hangers and Supports for HVAC Equipment | [5 empty] | 0 | 0 | 0
a. | Supply, Installation & Commissioning of hangers and supports for HVAC equipment complete in all respect as per drawings and specifications. | 1 | Job | 75000 | 20000 | 1 | 75000 | 20000 | 95000
230553 | Identification for HVAC Ducting, Piping and Equipment | [5 empty] | 0 | 0 | 0
a. | Supply, Installation & Commissioning of identification for HVAC ducting, piping and equipment complete in all respect as per drawings and specifications. | 1 | Job | 10000 | 10000 | 1 | 10000 | 10000 | 20000
230579 | Fire Stopping | [5 empty] | 0 | 0 | 0
a. | Supply, Installation & Commissioning of firestopping complete in all respect as per drawings and specifications. | 1 | Job |  |  |  | 0 | 0 | 0
230700 | HVAC Insulation
230713.13 | Duct Insulation
a. | Supply and installation of 50 mm thick Fiber Glass Insulation of density 24 kg/m3 with Aluminum Foil for Internal G.I. sheet metal ducts of different sections for supply and return air duct with Alumninum tape and protected with 8 oz Canvas Cloth wrapping than painted anti fungus paint complete in all respect as per schedule, specifications and drawings. | 4000 | Sq. Ft. | 180 | 50 | 3653 | 657540 | 182650 | 840190
230719.13 | Chilled Water Piping Insulation
a. | Supply and installation of premoulded polyurethane insulation of density 50 kg/m3 with bituminous karft paper facing for chilled water pipes, bends, tees, unions, sockets, valves and on speicals, wrapped with 8 oz. canvas cloth than painted with anti fungus paint, protected 26 SWG painted G.I. sheet metal cladding complete in all respect as per scheudle, specifications and drawings.
38 mm (1-1/2 inch) thickness
| 19 mm (3/4 inch) Diameter | 30 | Rft | 700 | 145 | 98 | 68600 | 14210 | 82810
| 25 mm (1 inch) Diameter | 210 | Rft | 975 | 155 | 60 | 58500 | 9300 | 67800
| 32 mm (1-1/4 inch) Diameter | 300 | Rft | 980 | 175 | 121 | 118580 | 21175 | 139755
| 38 mm (1-1/2 inch) Diameter | 60 | Rft | 1125 | 190 | 144 | 162000 | 27360 | 189360
| 50 mm (2 inch) Diameter | 240 | Rft | 1250 | 200 | 213 | 266250 | 42600 | 308850
| 50 mm (2 inch) thickness | [5 empty] | 0 | 0 | 0
| 63 mm (2-1/2 inch) Diameter | 220 | Rft | 1700 | 205 | 178 | 302600 | 36490 | 339090
| 75 mm (3 inch) Diameter | 80 | Rft | 1730 | 215 | 60 | 103800 | 12900 | 116700
230719.26 | Condensate Drain Insulation | [5 empty] | 0 | 0 | 0
a. | Supply and installation of 6 mm thick Pre-moulded Armaflex Pipe Insulation complete in all respect as per schedule, specifications and drawings. | [5 empty] | 0 | 0 | 0
| 25 mm (1 inch) Diameter | 140 | Rft | 180 | 50 | 240 | 43200 | 12000 | 55200
| 32 mm (1-1/4 inch) Diameter | 170 | Rft | 220 | 60 | 140 | 30800 | 8400 | 39200
| 38 mm (1-1/2 inch) Diameter | 120 | Rft | 390 | 70 | 40 | 15600 | 2800 | 18400
230800 | Commissioning of HVAC
230813 | Testing, Adjusting and balancing for HVAC systems
a. | Testing, balancing and commissioning of HVAC system complete in all respect including one month test run, measurement and recording of pressure and electrical data and submission of technical/operation manual, LOG book for each related equipment as per specifications and drawings. | 1 | Job | 0 | 60000 | 1 | 0 | 60000 | 60000
230900 | Instrumentation and Control for HVAC
230923 | Direct-Digital Control System
a. | Supply, Installation & Commissioning of direct-digital control system complete in all respect as per drawings and specifications. | 1 | Job | IMS JOB |  |  | 0 | 0 | 0
230926 | Building Management System
a. | Supply, Installation & Commissioning of Building Management system complete in all respect as per drawings and specifications. | 1 | Job | IMS JOB |  |  | 0 | 0 | 0
232100 | HVAC Piping and Pumps
232113.23 | Hydronic Piping
a. | Supply, Installation, testing & Commissioning of M.S Schedule 40 (as per ASME & API standard, heavy quality with standard Schedule 40 thickness) pipes & fittings for chilled water circulation system with bends, tees, unions, sockets as required to complete in all respects ready to operate as per schedule, drawings and specifications.
| 19 mm (3/4 inch) Diameter | 30 | Rft | 410 | 150 | 98 | 40180 | 14700 | 54880
| 25 mm (1 inch) Diameter | 210 | Rft | 690 | 190 | 60 | 41400 | 11400 | 52800
| 32 mm (1-1/4 inch) Diameter | 300 | Rft | 815 | 240 | 121 | 98615 | 29040 | 127655
| 38 mm (1-1/2 inch) Diameter | 60 | Rft | 925 | 290 | 144 | 133200 | 41760 | 174960
| 50 mm (2 inch) Diameter | 240 | Rft | 1255 | 330 | 213 | 267315 | 70290 | 337605
| 63 mm (2-1/2 inch) Diameter | 220 | Rft | 1980 | 190 | 178 | 352440 | 33820 | 386260
| 75 mm (3 inch) Diameter | 80 | Rft | 2500 | 415 | 60 | 150000 | 24900 | 174900
232113.26 | Condensate Drain Piping | [5 empty] | 0 | 0 | 0
a. | Supply, Installation, testing & Commissioning of UPVC Class D pipes & fittings for condensate drain system with bends, tees, unions, sockets as required to complete in all respects ready to operate as per schedule, drawings and specifications.
| 25 mm (1 inch) Diameter | 140 | Rft | 190 | 50 | 240 | 45600 | 12000 | 57600
| 32 mm (1-1/4 inch) Diameter | 170 | Rft | 240 | 60 | 140 | 33600 | 8400 | 42000
| 38 mm (1-1/2 inch) Diameter | 120 | Rft | 280 | 70 | 40 | 11200 | 2800 | 14000
232116 | Hydronic piping specialties
a. | Supply, Installation, testing & Commissioning of hydronic piping specialties alongwith flanges, coupling, unions complete in all respect as per drawings and specifications.
For Air Handling Unit(s)
i | Strainers with blow off 20 mm dia ball valve
| 32 mm (1-1/4 inch) Diameter | 1 | Nos |  |  |  | 0 | 0 | 0
| 38 mm (1-1/2 inch) Diameter | 2 | Nos |  |  |  | 0 | 0 | 0
| 50 mm (2 inch) Diameter | 3 | Nos | 22500 | 2000 | 3 | 67500 | 6000 | 73500
ii | For Fan Coil Unit(s)
Strainers with blow off 20 mm dia ball valve
| 19 mm (3/4 inch) Diameter | 5 | No |  |  |  | 0 | 0 | 0
| 25 mm (1 inch) Diameter | 6 | No | 10200 | 1500 | 8 | 81600 | 12000 | 93600
233100 | HVAC Ducts and Casings
233113.13 | Medium/Low pressure G.I. Sheet metal ducting
a. | Supply, Installation, testing & Commissioning of medium/low pressure G.I. sheet metal ducting complete in all respect as per drawings and specifications. | 4000 | Sq. Ft. | 360 | 60 | 3653 | 1315080 | 219180 | 1534260
i | 26 gauge (All chilled water piping shall have 26 Gauge G.I. Sheet Jacketting). | 1 | Job |  |  |  | 0 | 0 | 0
ii | 24 gauge | 2600 | Sq. Ft. |  |  |  | 0 | 0 | 0
iii. | 22 gauge | 3900 | Sq. Ft. |  |  |  | 0 | 0 | 0
233119 | Access door for AHU & Fan coil unit | [5 empty] | 0 | 0 | 0
a. | Supply, Installation, testing & Commissioning of access door for fan coil units complete in all respect as per drawings and specifications. | 14 | Nos | 0 | 0 |  | 0 | 0 | 0
233300 | Air Duct Accessories
233313 | Dampers
a. | Supply, Installation, testing & Commissioning of dampers complete in all respect as per drawings and specifications.
| Volume Control Damper | 1 | Lot | 86000 | 10000 | 1 | 86000 | 10000 | 96000
| Fire Damper | 1 | Lot | 78000 | 10000 | 1 | 78000 | 10000 | 88000
233343 | Flexible Connectors
a. | Supply, Installation, testing & Commissioning of flexible connectors between blower section and air duct complete in all respect as per drawings and specifications. | 1 | Lot | 74000 | 12000 | 1 | 74000 | 12000 | 86000
233700 | Air Outlets and inlets
233713 | Diffusers, Registers, and Grilles
Supply, Installation, testing & Commissioning of Diffusers, Registers and Grilles complete in all respect as per drawings and specifications.
a. | Supply Air Diffusers (SAD)
| 375x375 (15"x15") | 50 | Nos | 7200 | 1000 | 14 | 100800 | 14000 | 114800
| Supply Air Grills (SAG) | [5 empty] | 0 | 0 | 0
| 900x150 (36"x6") | 6 | Nos | 6800 | 1000 | 17 | 115600 | 17000 | 132600
| 600x150 (24"x6") | 10 | Nos | 4850 | 1000 | 17 | 82450 | 17000 | 99450
e. | Imperialine linear air diffuser 3/4" slot with volume control dampers with link to adjust the damper blade from the face of linear air diffuser complete in all respect as per drawings and specifications
| 3 slot , 6Ft Long SALD | 10 | Nos | 9800 | 1200 | 10 | 98000 | 12000 | 110000
| 3 slot , 6Ft Long RALD | 26 | Nos | 9800 | 1200 | 18 | 176400 | 21600 | 198000
b. | Return Air Diffusers (RAD) | [5 empty] | 0 | 0 | 0
| 375x375 (15"x15") | 30 | Nos | 7500 | 900 | 30 | 225000 | 27000 | 252000
234100 | Particulate Air Filters | [5 empty] | 0 | 0 | 0
234119 | Air Filters | [5 empty] | 0 | 0 | 0
a. | Panel Air Filters | [5 empty] | 0 | 0 | 0
| Supply, Installation, testing & Commissioning of Viscous oil type 2 inch (50 mm) thick cleanable type Air Filters complete in all respect as per drawings and specifications. | 1 | Lot | 45000 | 8000 | 1 | 45000 | 8000 | 53000
237300 | Air handling Units
237313.16 | Air handling units
a. | Installation, lifting, testing & Commissioning of air handling units complete in all respect as per drawings and specifications.
i | AHU - 04 (1600 CFM) | 1 | No | 0 |  |  | 0 | 0 | 0
iii. | AHU - 07 (2800 CFM) | 2 | Nos | 0 |  |  | 0 | 0 | 0
v | AHU - 10 (4000 CFM) | 1 | No | 0 |  |  | 0 | 0 | 0
| AHU - 14 (5600 CFM) | 2 | Nos | 0 |  |  | 0 | 0 | 0
238200 | Convection Heating and Cooling Units
238219 | Fan Coil Units
a. | Installation, testing & Commissioning of Fan Coil Units complete in all respect as per drawings and specifications.
| Ducted Type Unit | [5 empty] | 0 | 0 | 0
| FCU - 06 (600 CFM) | 5 | No | 0 | 4800 | 5 | 0 | 24000 | 24000
| FCU - 08 (800 CFM) | 3 | No | 0 | 4800 | 3 | 0 | 14400 | 14400
| TOTAL COST OF HVAC WORKS | [5 empty] | 6762050 | 1342675 | 8104725
Note: The above Prices are exclusive of all taxes, Taxes will be charged seperately.