## Invocice
|  | Date | 23 June 2023
|  | Invoice # | 3
M/S Bank Al-Falah Limited Pakistan |  | NTN # | 4312149-7
NTN # 0698202-6
Attn: Mr. Shujaat Ali
Invoice
Summary of Final Bill against Purchased Order # 227805
S.No | Description |  | Total Amount
i | Total Cost of Work (PO Amount Exclusive of Tax) |  | 12942096
| SRB 13% on Labour amount of Rs 2,467,170 |  | 320732.1
| Total Cost of Work Inclusive of Tax |  | 13262828.1
ii | Claimed amount 70% |  | 9283979.67
iii | Received Advance in previous Bill |  | 5766743.25
| Net Total Amount |  | 3517236.42
a | Material (Supply) 70% |  | 2462065.494
b | Labour (Services) 30% |  | 933779
c | Add 13% SST (Services): |  | 121391.27
| Total Payable Amount |  | 3517235.764
for PIONEER SERVICES
| Tax on material 4.5% & on lab 10% | 110792.9472 | 105517.027 | 0
| 4.23% Sales tax on Material | 104416.1976 |  | 0
| 20% SRB on Lab |  | 24278.254 | 0
3172231.3382

## Summary
|  |  | Date | 01 June 2023
|  |  | Invoice # | 2
M/S Bank Al-Falah Limited Pakistan |  |  | NTN # | 4312149-7
NTN # 0698202-6
Attn: Mr. Shujaat Ali
Invoice
Summary of Final Bill
S.No | Description | Material Amount | Labour Amount | Total Amount
i | 4th FLOOR A/B AHU UNIT | 946500 | 345000 | 1291500
ii | MEZZAINE B FLOOR AHU UNIT | 721600 | 311000 | 1032600
iii | GROUND A FLOOR AHU UNIT | 926500 | 342000 | 1268500
iv | ROOF TOP PLANT ROOM (CHILLERS) | 2130000 | 419000 | 2549000
| Sub Total Amount | 4724600 | 1417000 | 6141600
| Addition 18.5% | 874051 | 262145 | 1136196
| Grand Total Amount | 5598651 | 1679145 | 7277796
| SST 13% on labour | 0 | 218288.85 | 218288.85
| Grand Total after SST | 5598651 | 1897433.85 | 7496084.85
for PIONEER SERVICES
| Tax on material 4.5% & on lab 10% | 251939.295 | 189743.385
| 4.23% Sales tax on Material | 236822.9373
| 20% SRB on Lab |  | 43657.77
|  | 5109888.7677 | 1664032.695
6773921.4627

## Sheet1
REPAIRING AND REPLACEMENT AND MAINTENANCE WORKS OF CHILLERS AND COOLING TOWERS OVERHAULING OF BA BUILDING KARACHI
Bill of Quantities | [5 empty] | Final Bill
S.NO | DESCRIPTION | Qty | Unit | Material Rate | Labour Rate | Pre Qty | Final Qty | Material Amount | Labour Amount
4th FLOOR A/B AHU UNIT
1 | Replacement of Rubber isolator | 1 | Job | 30000 | 10000 | 0 | 1 | 30000 | 10000
2 | Complete Ahu floor Foundation,floor rusted coluum u channel with epoxy paint Replacement with insulation. | 1 | job | 20000 | 15000 | 0 | 1 | 20000 | 15000
3 | Replacement of motor bearing, Make SKF & FAG & motor foundation & belt guard safety cover | 1 | job | 30000 | 12000 | 0 | 1 | 30000 | 12000
4 | AHU motor complete overhauling without winding,blower repairing or replacement & balancing,shaft allighment,polishing & replacement of blower bearing,pillow block,make SKF & FAG with grease niple for relubrication.(And then show it by doing a grease injection test). | 1 | job | 90000 | 40000 | 0 | 1 | 90000 | 40000
5 | Water proof light inside AHU 40 watt | 2 | job | 5000 | 2000 | 0 | 2 | 10000 | 4000
6 | Replacement of evaporator drain tray & coil to coil tray & coil bottom & base Stainless Steel channel. | 1 | job | 30000 | 25000 | 0 | 1 | 30000 | 25000
7 | Coil descaling internal and external service | 1 | job | 20000 | 20000 | 0 | 1 | 20000 | 20000
8 | blower louvre epoxy paint with primer & hoiusing inside or outside | 1 | job | 25000 | 15000 | 0 | 1 | 25000 | 15000
9 | sound proof alluminium foil face EPDM foam insolation replacement inside & complete in all respect | 1 | job | 224000 | 54000 | 0 | 1 | 224000 | 54000
10 | supply canvas duct connector inside/ AHU room replace fire proof insulation with anti fungus paint with another paint | 250 | sq/ft | 160 | 80 | 0 | 250 | 40000 | 20000
11 | Complete AHU paint outside & AHU room oil base mate finish NIPPON paint. | 1 | job | 85000 | 35000 | 0 | 1 | 85000 | 35000
12 | gate valves,globe valve,moterized valve & strainer descalling of chilled water line | 1 | job | 25000 | 20000 | 0 | 1 | 25000 | 20000
13 | Pressure gauge 0.2-100 PSIG made in USA fix with pipe nipple and socket,gauge cock siphon | 1 | job | 20000 | 3000 | 0 | 1 | 20000 | 3000
14 | Chilled water line supply & return aslo anti fungus paint & another paint with EPS thermocol insulation. | 1 | job | 15000 | 10000 | 0 | 1 | 15000 | 10000
15 | AHU belt replacement make continental | 1 | job | 20000 | 2000 | 0 | 1 | 20000 | 2000
16 | water balancing | 1 | job | 0 | 10000 | 0 | 1 | 0 | 10000
17 | supply & installation of complete filter frame & alluminium air filter | 1 | job | 160000 | 20000 | 0 | 1 | 160000 | 20000
18 | Miscellanous work | 1 | job | 15000 | 10000 | 0 | 1 | 15000 | 10000
19 | door hinges & lock | 1 | job | 5000 | 2000 | 0 | 1 | 5000 | 2000
20 | Drain pipe STEELEX UPVC SCH40 with fitting size 1.5'' | 50 | Rft | 550 | 200 | 0 | 50 | 27500 | 10000
21 | Nut Bolts, Washers, Screws & Ribits Need Stainless Steel required . | 1 | job | 35000 | 5000 | 0 | 1 | 35000 | 5000
22 | inlet/outlet chilled water line thermometer supply & installation | 1 | job | 20000 | 3000 | 0 | 1 | 20000 | 3000
Sub Total Amount Rs | [5 empty] | 0 |  | 946500 | 345000
0
| MEZZAINE B FLOOR AHU UNIT |  |  |  |  | 0
0
1 | Replacement of Rubber isolator | 1 | job | 30000 | 10000 | 0 | 1 | 30000 | 10000
2 | Complete Ahu floor Foundation,floor rusted colum u channel with epoxy paint Replacement with insulation. | 1 | job | 20000 | 15000 | 0 | 1 | 20000 | 15000
3 | Replacement of motor bearing, Make SKF & FAG & motor foundation &+B34:B38 belt guard safety cover | 1 | job | 30000 | 20000 | 0 | 1 | 30000 | 20000
4 | AHU motor complete overhauling without winding,blower repairing or replacement & balancing,shaft allighment,polishing & replacement of blower bearing,pillow block,make SKF & FAG with grease niple for relubrication.(And then show it by doing a grease injection test). | 1 | job | 90000 | 30000 | 0 | 1 | 90000 | 30000
5 | Water proof light inside AHU 40 watt | 2 | Nos | 5000 | 2000 | 0 | 2 | 10000 | 4000
6 | Replacement of evaporator drain tray & coil bottom & base Stainless Steel channel. | 1 | job | 25000 | 15000 | 0 | 1 | 25000 | 15000
7 | Coil descaling internal and external service | 1 | job | 20000 | 20000 | 0 | 1 | 20000 | 20000
8 | blower louvre epoxy paint with primer & hoiusing inside or outside | 1 | job | 30000 | 20000 | 0 | 1 | 30000 | 20000
9 | sound proof alluminium foil face EPDM foam insolation replacement inside & complete in all respect. | 1 | job | 103750 | 25000 | 0 | 1 | 103750 | 25000
10 | supply canvas duct connector inside/ AHU room replace fire proof insulation with anti fungus paint with another paint | 250 | sq/ft | 200 | 100 | 0 | 250 | 50000 | 25000
11 | Complete AHU paint outside & AHU room oil base mate finish NIPPON paint. | 1 | job | 90000 | 40000 | 0 | 1 | 90000 | 40000
12 | gate valves,globe valve,moterized valve & strainer descalling of chilled water line | 1 | job | 25000 | 20000 | 0 | 1 | 25000 | 20000
13 | Pressure gauge 0.2-100 PSIG made in USA fix with pipe nipple and socket,gauge cock siphon | 1 | job | 20000 | 3000 | 0 | 1 | 20000 | 3000
14 | Chilled water line supply & return aslo anti fungus paint & another paint with EPS thermocol insulation. | 1 | job | 15000 | 10000 | 0 | 1 | 15000 | 10000
15 | AHU belt replacement make continental | 1 | job | 20000 | 2000 | 0 | 1 | 20000 | 2000
16 | water balancing | 1 | job | 0 | 10000 | 0 | 1 | 0 | 10000
17 | supply & installation of complete filter frame & alluminium air filter | 1 | job | 70350 | 15000 | 0 | 1 | 70350 | 15000
18 | Miscellanous work | 1 | job | 10000 | 10000 | 0 | 1 | 10000 | 10000
19 | door hinges & lock | 1 | job | 5000 | 2000 | 0 | 1 | 5000 | 2000
20 | Drain pipe STEELEX UPVC SCH40 with fitting size 1.5'' | 50 | rft | 550 | 200 | 0 | 50 | 27500 | 10000
21 | Nut Bolts, Washers, Screws & Ribits Need Stainless Steel required . | 1 | job | 30000 | 5000 | 0 | 1 | 30000 | 5000
Sub Total Amount Rs | [5 empty] | 0 |  | 721600 | 311000
0
| GROUND A FLOOR AHU UNIT |  |  |  |  | 0
[6 empty] | 0 |  | 0 | 0
1 | Replacement of Rubber isolator | 1 | job | 30000 | 10000 | 0 | 1 | 30000 | 10000
2 | Complete Ahu floor Foundation,floor rusted colum u channel with epoxy paint Replacement with insulation. | 1 | job | 20000 | 15000 | 0 | 1 | 20000 | 15000
3 | Replacement of motor bearing, Make SKF & FAG & motor foundation & belt guard safety cover | 1 | job | 30000 | 12000 | 0 | 1 | 30000 | 12000
4 | AHU motor complete overhauling without winding,blower repairing or replacement & balancing,shaft allighment,polishing & replacement of blower bearing,pillow block,make SKF & FAG with grease niple for relubrication.(And then show it by doing a grease injection test). | 1 | job | 90000 | 40000 | 0 | 1 | 90000 | 40000
5 | Water proof light inside AHU 40 watt | 2 | Nos | 5000 | 2000 | 0 | 2 | 10000 | 4000
6 | Replacement of evaporator drain tray & coil bottom & base Stainless Steel channel. | 1 | job | 30000 | 25000 | 0 | 1 | 30000 | 25000
7 | Coil descaling internal and external service | 1 | job | 20000 | 20000 | 0 | 1 | 20000 | 20000
8 | blower louvre epoxy paint with primer & hoiusing inside or outside | 1 | job | 25000 | 15000 | 0 | 1 | 25000 | 15000
9 | sound proof alluminium foil face EPDM foam insolation replacement inside & complete in all respect. | 1 | job | 224000 | 54000 | 0 | 1 | 224000 | 54000
10 | supply canvas duct connector inside/ AHU room replace fire proof insulation with anti fungus paint with another paint | 250 | sq/ft | 160 | 80 | 0 | 250 | 40000 | 20000
11 | Complete AHU paint outside & AHU room oil base mate finish NIPPON paint. | 1 | job | 85000 | 35000 | 0 | 1 | 85000 | 35000
12 | gate valves,globe valve,moterized valve & strainer descalling of chilled water line | 1 | job | 25000 | 20000 | 0 | 1 | 25000 | 20000
13 | Pressure gauge 0.2-100 PSIG made in USA fix with pipe nipple and socket,gauge cock siphon | 1 | job | 20000 | 3000 | 0 | 1 | 20000 | 3000
14 | Chilled water line supply & return aslo anti fungus paint & another paint with EPS thermocol insulation. | 1 | job | 15000 | 10000 | 0 | 1 | 15000 | 10000
15 | AHU belt replacement make continental | 1 | job | 20000 | 2000 | 0 | 1 | 20000 | 2000
16 | water balancing | 1 | job | 0 | 10000 | 0 | 1 | 0 | 10000
17 | supply & installation of complete filter frame & alluminium air filter | 1 | job | 160000 | 20000 | 0 | 1 | 160000 | 20000
18 | Miscellanous work | 1 | job | 15000 | 10000 | 0 | 1 | 15000 | 10000
19 | door hinges & lock | 1 | job | 5000 | 2000 | 0 | 1 | 5000 | 2000
20 | Drain pipe STEELEX UPVC SCH40 with fitting size 1.5'' | 50 | rft/ft | 550 | 200 | 0 | 50 | 27500 | 10000
21 | Nut Bolts, Washers, Screws & Ribits Need Stainless Steel required . | 1 | job | 35000 | 5000 | 0 | 1 | 35000 | 5000
Sub Total Amount Rs | [7 empty] | 926500 | 342000

## Sheet2
REPAIRING AND REPLACEMENT AND MAINTENANCE WORKS OF CHILLERS AND COOLING TOWERS OVERHAULING OF BA BUILDING KARACHI
Bill of Quantities | [5 empty] | Final Bill
S.NO | DESCRIPTION | Qty | Unit | Material Rate | Labour Rate | Pre Qty | Final Qty | Material Amount | Labour Amount
ROOF TOP PLANT ROOM (CHILLERS)
1 | Shell cooler evaporator & condenssor shell descaling required | 9 | Nos | 30000 | 20000 | 9 | 0 | 0 | 0
2 | Shell cooler old insulation removing and rust removing with flenge pipe coupler inlet outlet with epoxy primer and paint required & new EPDM aero flex pasting work. | 3 | Nos | 85000 | 45000 | 3 | 0 | 0 | 0
3 | Chiller Compressors Oil Analyses required. Labortery tested reports share, if required Compressors oil change/fill . | 6 | Nos | 0 | 10000 | 0 | 6 | 0 | 60000
4 | Chiller foundation & compreessor foundation & heat exchanger rust removing and new epoxy paint apply. | 6 | Nos | 15000 | 10000 | 6 | 0 | 0 | 0
5 | Heat Exchanger inlet/outlet gate valve 6" old valve removing and new valve installation make HATTERSLEY with flenges. | 12 | Nos | 165000 | 5000 | 12 | 0 | 0 | 0
6 | Condenssor pump Non-Return Valves 8" old valve removing and new valve installation make HATTERSLEY with flenges. | 4 | Nos | 190000 | 6000 | 4 | 0 | 0 | 0
7 | Chilled water & condenssor water lines gate valves 8" descalling required. | 7 | Nos | 10000 | 10000 | 7 | 0 | 0 | 0
8 | Primary , Secondary & Condenssor pumps with foundation repairing rust removing & epoxy paint with primer required . | 10 | Nos | 10000 | 10000 | 4 | 6 | 60000 | 60000
9 | Automatic Air Vent Brass 1" make HATTERSLEY with fittings of chilled water lines. | 4 | Nos | 5000 | 1000 | 0 | 4 | 20000 | 4000
10 | New Booster tank required. | 1 | Nos | 665000 | 15000 | 0 | 1 | 665000 | 15000
11 | Plant room cieling external side reapairing fiber material & internal side cieling repairing jumboloan. | 1 | job | 90000 | 30000 | 1 | 0 | 0 | 0
12 | Plant room internal side walls and beam girders,colum girders & M/S pipe enamel paint required. | 1 | job | 50000 | 40000 | 1 | 0 | 0 | 0
13 | Provide & installation gate valve 8'' dia Hattersley make. & With EPS thermocol insulation,fabric,anti fungus paint with almunium cladding. | 2 | Nos | 245000 | 8000 | 2 | 0 | 0 | 0
14 | fifth floor rooftop main chilled water line riser to plant room supply & return EPS thermocol insulation,fabric,anti fungus paint with almunium cladding/foundation stand clamp with epoxy paint | 400 | Rft | 2150 | 400 | 0 | 400 | 860000 | 160000
15 | Nut Bolts, Washers, Screws & Ribits Need Stainless Steel required . | 1 | job | 20000 | 10000 | 1 | 0 | 0 | 0
16 | Main Washrooms Exhausts Removal of existing ducts from riser and shafts / supply and installation of new G.I sheet metal ducts complete in all respect / supply & installation of hangers and supports with epoxy paint | 1500 | Sq/ft | 350 | 80 | 0 | 1500 | 525000 | 120000
Sub Total Amount Rs | [7 empty] | 2130000 | 419000
[8 empty] | 0 | 0
| 5TH FLOOR ELEVATOR & BMS ROOM FAN COIL UNITS 04 NOS | [6 empty] | 0 | 0
[8 empty] | 0 | 0
1 | Evaporator Coil descaling internal and external with epoxy paint. | 1 | Job | 10000 | 10000 |  |  | 0 | 0
2 | supply & installation of alluminium air filter | 1 | Job | 10000 | 10000 |  |  | 0 | 0
3 | Replacement of motor bearing, Make SKF & FAG | 1 | Job | 10000 | 8000 |  |  | 0 | 0
4 | Chilled water line supply & return aslo anti fungus paint & another paint with EPS thermocol insulation. | 1 | Job | 15000 | 8000 |  |  | 0 | 0
5 | gate valve make hartsley 6" provide & installation. | 6 | Nos | 8000 | 1000 |  |  | 0 | 0
6 | supply & installation of complete filter frame,bag filter & alluminium air filter for Fresh Air Unit | 1 | job | 27500 | 6000 |  |  | 0 | 0
8 | Nut Bolts, Washers, Screws & Ribits Need Stainless Steel required . | 1 | job | 20000 | 8000 |  |  | 0 | 0
Sub Total Amount Rs | [7 empty] | 0 | 0
ROOF TOP (COOLING TOWERS )
1 | Complete metal structure frame and other metal accessories & sand blasting with high quality zinc hot deep galvanizing required. | 6 | nos | 100000 | 80000 |  |  | 0 | 0
2 | Motor with gear box complete overhauling without winding,make SKF & FAG with grease niple for relubrication.(And then show it by doing a grease injection test). | 6 | nos | 65000 | 25000 |  |  | 0 | 0
3 | New Fan blade,New hub with alligment & balancing required. | 6 | nos | 65000 | 10000 |  |  | 0 | 0
4 | Upper hot water distribution basin with new showering box fiber material need & lower cool basin & fan stack frame & metal fan guard replaced with hot deep galvanizing & inspection door & fiber material minor repairing required. | 12 | Job | 12000 | 5000 |  |  | 0 | 0
5 | Complete new fills with new fills foundation fiber metarial f & louvers required | 6 | nos | 715000 | 50000 |  |  | 0 | 0
6 | Hydroplast showering pipe fittings joints leakege repairing & butterfly valve 4" replaced with flenge & main showering hyder flenge 8" replaced | 12 | nos | 17000 | 4000 |  |  | 0 | 0
7 | float ball valve stainless steel 1.5" need to be change. | 3 | nos | 27000 | 3000 |  |  | 0 | 0
8 | Gate valve brass 2" need to be change make HATTERSLEY. | 9 | nos | 12000 | 1500 |  |  | 0 | 0
9 | Schneider Motorized valve 8" Outlet side need to be change. | 3 | nos | 350000 | 6000 |  |  | 0 | 0
10 | Schneider Motorized valve 6" Inlet side need to be change. | 3 | nos | 265000 | 4000 |  |  | 0 | 0
11 | Cooling tower outside area walk way platform and complete m/s pipe with pipe foundation need to be epoxy paint with primer required. | 1 | job | 90000 | 60000 |  |  | 0 | 0
12 | electrical wires proper dress up upvc pipe fitting. | 1 | job | 30000 | 10000 |  |  | 0 | 0
13 | Nut Bolts, Washers, Screws & Ribits Need Stainless Steel required . | 1 | job | 100000 | 20000 |  |  | 0 | 0
Sub Total Amount Rs | [7 empty] | 0 | 0