## 22F Summary
Summary of Comparative Statement
ACMV Works
Bank Al Habib (22nd Floor)
Centrepoint, Karachi
S.No. | Description | M/s. Total Construction
|  | Material | Labour | Total
1 | Cutting dismantling and shifting of the existing ACMV works | 0 | 105000 | 105000
2 | Installation of fan coil units | 0 | 10500 | 10500
3 | Supply & installation of valves & accessories for FCU | 552620 | 31500 | 584120
4 | Supply & installation of M.S Pipes for chilled & Cooling water | 146475 | 34650 | 181125
5 | Supply & installation of fiber glass insulation | 144900 | 11025 | 155925
6 | Supply & installation of Drain Pipes | 33600 | 6300 | 39900
7 | Installation of VAV Boxes | 4737811 | 50400 | 4788211
8 | Supply & installation of ventilation fans | 456750 | 22050 | 478800
9 | Supply & installation of G.I ductwork | 5775000 | 693000 | 6468000
10 | Supply & installation of XLPE insulation | 6038000 | 578000 | 6616000
11 | Supply & installation of sound liner | 343380 | 34680 | 378060
12 | Supply & installation of Air Devices | 613726 | 93975 | 707701
13 | Supply & installation of flexible duct | 167530 | 34650 | 202180
14 | Supply & installation of butterfly damper | 303240 | 27615 | 330855
15 | Supply & installation of G.I Volume Control Damper | 286650 | 31500 | 318150
16 | Painting & identification work | 21000 | 15750 | 36750
17 | Testing & commissioning of air side | 0 | 52500 | 52500
18 | Making of Shop Drawings & AS BUILT drawings | 10500 | 15750 | 26250
| Total Cost of Works Rs. | 19631182 | 1848845 | 21480027

## 22F Estimate
Comparative Statement
ACMV Works
Bank Al Habib (22nd Floor)
Centrepoint, Karachi
M/s. TOTAL CONSTRUCTION
[5 empty] | MATERIAL |  | LABOUR |  | TOTAL
Sr. No. |  | DESCRIPTION | UNIT | QTY | RATE | AMOUNT | RATE | AMOUNT | AMOUNT
All works shall be completed, tested and commissioned as per drawings, specifications and as per instruction of Consultant
1 |  | Cutting dismantling and shifting of the existing ACMV works as per instruction of consultant, including cleaning the site and shifting the dismantled parts / material to suitable place given by client complete in all respects ready to operate as per drawings and as per instruction of consultant.
| 1.1 | ACMV Works i.e; FCU, Pipe, Vlaves, accessories, duct, insulation etc complete job as required. | Job. | 1 |  |  | 105000 | 105000 | 105000
2 |  | Unloading, installation, testing and commissioning of (Owner Supplied) of fan coil units of different capacities complete in all respects, ready to operate including supply and installation of all accessories, supports, hanger steel base, vibration isolators, including interconnecting power & control wiring (terminal connection) with inlet & outlet chilled water connections, drain connection, flexible rubber duct connection / connector etc. complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
| 2.1 | DFCU-01 | Nos. | 2 |  | 0 | 5250 | 10500 | 10500
3 |  | Supply & installation of valves & accessories for AHU with supports, hangers, flanges, gas kits, nut & bolts where it required, etc. complete in all respects as per specifications, drawings and as per instructions of consultant.
| 3.1 | Gate Valve
| i. | 25mm dia | Nos. | 8 | 8768 | 70144 | 1050 | 8400 | 78544
| 3.2 | Strainers
| i. | 25mm dia | Nos. | 2 | 7613 | 15226 | 1050 | 2100 | 17326
| 3.3 | Balancing Valve (with self sealing measuring nipples)
| i. | 25mm dia | Nos. | 2 | 19425 | 38850 | 1050 | 2100 | 40950
| 3.4 | Thermometer 150mm Height Scale Type (with Thermo well) 0 ºC to 60 ºC | Nos. | 4 | 11550 | 46200 | 1050 | 4200 | 50400
| 3.5 | Pressure Gauge with Ball Valve & Siphon, Liquid filled Dial type range 0 psi to 100 psi. (100mm dial Size) | Nos. | 4 | 9975 | 39900 | 1050 | 4200 | 44100
| 3.6 | 2-Way Motorized Valve with Actuator (0-100% modulating)
| i. | 25mm dia | Nos. | 2 | 92400 | 184800 | 1050 | 2100 | 186900
| 3.7 | Digital Decorative Thermostat Controller (BMS Interfacable) with Duct Mounted Sensor | Nos. | 2 | 57750 | 115500 | 1050 | 2100 | 117600
| 3.8 | Control wiring from controller to sensors, motorized valve and Power wiring up to 15' radius | Job. | 2 | 21000 | 42000 | 3150 | 6300 | 48300
4 |  | Supply & installation of SCH-40 M.S.(As per ASME & API standard, Heavy Quality with standard SCH 40 wall thickness) pipes & fitting for chilled & cooling water circulation system complete with bends, tees, unions, sockets, specials, support, hangers & anchors, M.S. angle, U channel, roller support, bolts, rods, clamps, concrete fasteners etc as required to complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
| 4.1 | 25mm dia | Rm | 30 | 3045 | 91350 | 735 | 22050 | 113400
| 4.2 | 32mm dia | Rm | 15 | 3675 | 55125 | 840 | 12600 | 67725
5 |  | Supply & installation of aluminum foil facing fiber glass (24 kg/m3 density) insulation with aluminum threaded tape, protected with 8oz canvas cloth than painted anti fungus paint, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
| 5.1 | 25mm dia | Rm | 30 | 2835 | 85050 | 210 | 6300 | 91350
| 5.2 | 32mm dia | Rm | 15 | 3990 | 59850 | 315 | 4725 | 64575
6 |  | Supply & istallation of uPVC (Sch 40.) drain pipe insulated with 3/8" thick rubber foam insulation including clamps, bends, tees, drain plugs, sockets, protection treatment, PVC tape wrapping, supports & hangers complete in all respects as per specifications, drawings & as per instructions of Consultant.
| 6.1 | 25mm dia | Rm | 20 | 1680 | 33600 | 315 | 6300 | 39900
7 |  | Supply & installation of VAV Boxes as per mentioned in schedule with digital thermostat controller, pressure sensor, control wiring, including supply & installation of flexible duct connection / connector, electrical connection, lindaptor support & hangers complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant.
| 7.1 | VAV-01 | No. | 1 | 295470 | 295470 | 3150 | 3150 | 298620
| 7.2 | VAV-02 | No. | 1 | 308700 | 308700 | 3150 | 3150 | 311850
| 7.3 | VAV-03 | No. | 1 | 285180 | 285180 | 3150 | 3150 | 288330
| 7.4 | VAV-04 | No. | 1 | 296205 | 296205 | 3150 | 3150 | 299355
| 7.5 | VAV-05 | Nos. | 3 | 308700 | 926100 | 3150 | 9450 | 935550
| 7.6 | VAV-06 | No. | 1 | 308700 | 308700 | 3150 | 3150 | 311850
| 7.7 | VAV-07 | No. | 1 | 285180 | 285180 | 3150 | 3150 | 288330
| 7.8 | VAV-08 | No. | 1 | 295470 | 295470 | 3150 | 3150 | 298620
| 7.9 | VAV-09 | Nos. | 2 | 295470 | 590940 | 3150 | 6300 | 597240
| 7.1 | VAV-10 | No. | 1 | 277463 | 277463 | 3150 | 3150 | 280613
| 7.11 | VAV-11 | Nos. | 2 | 295470 | 590940 | 3150 | 6300 | 597240
| 7.12 | VAV-12 | No. | 1 | 277463 | 277463 | 3150 | 3150 | 280613
8 |  | Supply, rigging, lifting, placement, installation, testing and commissioning of Ventilation Fans as per mentioned in schedule, including supply & installation of vibration isolator, electrical connection, flexible duct connection / connector, support & hangers complete in all respects ready to operate as per drawings, specification and as per instruction of consultant. | [8 empty] | 0
| 8.1 | TAF-01 | No. | 1 | 25200 | 25200 | 3150 | 3150 | 28350 | 22500 | 22500
| 8.2 | TAF-02 | Nos. | 2 | 65625 | 131250 | 3150 | 6300 | 137550 | 22500 | 22500
| 8.3 | TAF-03 | No. | 1 | 72450 | 72450 | 3150 | 3150 | 75600 | 22500 | 22500
| 8.4 | TAF-04 | Nos. | 2 | 72450 | 144900 | 3150 | 6300 | 151200 | 22500 | 22500
| 8.5 | TAF-05 | No. | 1 | 82950 | 82950 | 3150 | 3150 | 86100 | 22500 | 22500
9 |  | Supply, fabrication and installation of machine made G.I sheet metal duct different sections supply, return, fresh & exhaust air including plenums, splitter dampers, guide vanes, flexible duct connector / connection, access door, transformation, plenums chambers, wooden frame, anchors supports & hangers complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | Sqm | 1000 | 5775 | 5775000 | 693 | 693000 | 6468000
10 |  | Supply & installation of adhesive 20mm thick rubber foam (XLPE) insulation with aluminum foil over supply & return duct and plenums (except toilet exhaust duct), complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqm | 1000 | 6038 | 6038000 | 578 | 578000 | 6616000
11 |  | Supply & installation of acoustical duct sound liner adhesive with 12mm thick in supply air duct complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqm | 60 | 5723 | 343380 | 578 | 34680 | 378060
12 |  | Supply, installation of Aluminum fabricated, powder coated Grills, Diffusers and Registers for supply air, return air, exhaust air & fresh air of different sizes (Grade A ), wooden frame, supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
| 12.1 | Supply & Return Air Registers / Diffuser with Damper
| i. | 300mm x 300mm Square Diffuser | Nos. | 6 | 4200 | 25200 | 735 | 4410 | 29610
| ii. | 375mm x 375mm Square Diffuser | Nos. | 2 | 6038 | 12076 | 735 | 1470 | 13546
| ii. | 300mm dia Jet Diffuser | Nos. | 4 | 9450 | 37800 | 1050 | 4200 | 42000
| 12.2 | Supply & Return Air Grills
| i. | 450mm x 250mm | Nos. | 2 | 4725 | 9450 | 735 | 1470 | 10920
| 12.2 | S.S. Wire Mesh with G.I Frame | Sqm | 3 | 3150 | 9450 | 525 | 1575 | 11025
| 12.3 | Linear Slots 6,000 Series
| i. | 2 Slots of 20mm | Rm | 110 | 4725 | 519750 | 735 | 80850 | 600600
13 |  | Supply & installation of flexible duct including hangers, jubilee clamp complete in all respects as per specification, drawings & as per instruction of consultant.
| 13.1 | 150mm dia | Rm | 110 | 1523 | 167530 | 315 | 34650 | 202180
14 |  | Supply & installation of butterfly damper for above flexible duct with gas kits, nut bolts, complete in all respects, ready to operate as per specification, drawings & as per instruction of consultant.
| 14.1 | 150mm dia | Nos. | 105 | 2888 | 303240 | 263 | 27615 | 330855
15 |  | Supply, Installation of Volume Control Damper in 16 SWG G.I sheet metal with gas kits, nut bolts, etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqm | 6 | 47775 | 286650 | 5250 | 31500 | 318150
16 |  | Painting & Identification work on supports, hangers, platform of condensing units etc complete in all respects with one coat of ICI make Red lead oxide primer & two coats of ICI make enamel paint complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | Lot | 1 | 21000 | 21000 | 15750 | 15750 | 36750
17 |  | Testing, balancing and commissioning of water & air side of the system (from independent agency) complete in all respects including air measurement & balancing, temp, pressure & electrical data of related equipment etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Job. | 1 |  | 0 | 52500 | 52500 | 52500
18 |  | Making of Shop drawings on Auto CAD (latest version) with section details, equipment foundation details and Making of As Built drawings, Documentation Technical / Operational Manual & LOG Book for each equipment complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Job. | 1 | 10500 | 10500 | 15750 | 15750 | 26250
|  | Total Cost of Works Rs. |  |  |  | 19631182 |  | 1848845 | 21480027
Note:
1) | Electric power wiring / supply to be provided at equipment with isolation box by electrical contractor.
2) | Contractor is instructed to visit the site, understand the nature of work & then fill the rates accordingly and submit the quotation. No argument and discussion will be entertained after awarding of work.
3) | Miscellaneous work which was not included in BOQ but necessary to complete the project in all respects and ready to operate as per instructions of Consultant. (Bidder should mentioned the type of works).