## Sheet1
2023-06-03
M/S Director Development |  | Date |  | 12 May 2023
NASTP PAF Faisal Karachi |  | Invoice # |  | 001
|  | NTN # |  | 1338544-5
Release of Payment to M/S Pioneer for Supply and installation of Ducting insulation of HVAC Piping At Zone-B
1 | Supply of Additional 6" Pipe | 160 Rft
2 | Supply of Additional 4" Pipe | 460 Rft
3 | Supply of Additional 1" Pipe | 140 Rft
M/S Pioneer Has completed 85% work at site as per revised contract agreement.
Following are the details of completion of works
S.# | Description | Qty in BOQ | Work Done | Percentage
1 | Ducting | 9500 SQFT | 8075 SQFT | 85%
2 | Insulation | 9500 SQFT | 7600 SQFT | 80%
* | TOTAL | 0
3 | Piping | 2940 RFT | 2352 RFT | 80%
It is requested that payment of Rs 5,410,803/= and difference in initial payment amounting Rs 1,518,005 may be released as per payment schedule of 75% completion of work.
Thanking you in anticipation
Total Amount Rupees:
(Five Milliol Ninety Eight Thousand Five Hundred Sixty Only/=).
For PIONEER SERVICES.
PIONEER SERVICES