## HVAC
M/S Y.H Associates
15-08-23
NTN 4312149-7
BILL
DUCTING, INSULATION AND INSTALLATION OF HVAC PIPING AT ZONE - B GROUND FLOOR OF NASTP KARACHI BUILDING
BILL OF QUANTITIES | [5 empty] | RUNNING BILL
S. # | Description | Unit | Qty | Material Rate | Labour Rate | Billed Qty | Material Amount | Labour Amount | Total Amount
Machine Made G.I Sheet metal Duct
1 | Supply, Installation, testing & Commissioning of medium/low Machine made pressure G.I. sheet metal ducting complete in all respect. | Sqft | 9500 | 350 | 60 | 13432 | 4701200 | 805920 | 5507120
Fierglass insulation
2 | Supply and installation of 1 inch thick Fiber Glass Insulation of density 24 kg/m3 with Aluminum Foil, tape, Canvas Cloth & anti fungus paint complete in all respect. | Sqft | 9500 | 160 | 55 | 13432 | 2149120 | 738760 | 2887880
Air devices
3 | Supply & Installation of Supply air diffuser. 15 x 15 | Nos | 124 | 5500 | 800 | 128 | 704000 | 102400 | 806400
4 | Supply & Installation of Exhaust Air Register. | [5 empty] | 0 | 0 | 0
i | 09 x 09 | Nos | 39 | 2200 | 1000 | 29 | 63800 | 29000 | 92800
ii | 12 x 12 | Nos | 22 | 3500 | 1000 | 12 | 42000 | 12000 | 54000
5 | Supply and installation of Exhaust Air Louver as per drawings.
i | 28 x 12 | No | 2 | 7500 | 900 | 1 | 7500 | 900 | 8400
ii | 30 x 12 | No | 2 | 9000 | 900 | 1 | 9000 | 900 | 9900
6 | Supply and installation of volume control damper
i | 38 x 16 | Nos | 7 | 14500 | 1000 | 7 | 101500 | 7000 | 108500
ii | 32 x 14 | Nos | 4 | 10750 | 1000 | 4 | 43000 | 4000 | 47000
7 | Supply and installation of Fire Damper
i | 38 x 16 | Nos | 7 | 14500 | 1000 | 7 | 101500 | 7000 | 108500
ii | 32 x 14 | Nos | 4 | 11800 | 1000 | 4 | 47200 | 4000 | 51200
8 | Supply and installation of access door for fire / split damper. Size 18 x 18 | Nos | 11 | 8000 | 1000 | 0 | 0 | 0 | 0
9 | Supply and installation of flexbile duct connector for supply air duct only. | Rft | 200 | 650 | 80 | 200 | 130000 | 16000 | 146000
M.S SCH-40 Pipe and related material
10 | Providing and installation of temporary scaffolding for installation of chilled water riser (after completion of work removal of folding) | Job | 1 | 200000 | 75000 | 1 | 200000 | 75000 | 275000
11 | Installation of M.S Sch-40 Seamless chilled water pipe with comsumable material such as cutting discs, grinding disc, electrodes etc
i | 6" dia | Rft | 350 | 0 | 575 | 521 | 0 | 299575 | 299575
ii | 4" dia | Rft | 130 | 0 | 475 | 549 | 0 | 260775 | 260775
iii | 3" dia | Rft | 350 | 0 | 425 | 172 | 0 | 73100 | 73100
iv | 2-1/2" dia | Rft | 650 | 0 | 375 | 256 | 0 | 96000 | 96000
v | 2" dia | Rft | 400 | 0 | 325 | 148 | 0 | 48100 | 48100
vi | 1-1/2" dia | Rft | 200 | 0 | 275 | 179 | 0 | 49225 | 49225
vii | 1-1/4" dia | Rft | 320 | 0 | 250 | 159 | 0 | 39750 | 39750
viii | 1" dia | Rft | 180 | 0 | 225 | 84 | 0 | 18900 | 18900
ix | 3/4" dia | Rft | 200 | 0 | 175 | 0 | 0 | 0 | 0
12 | Providing and making of chilled water connection from main plant room for supply and return. | Job | 1 | 15000 | 20000 | 1 | 15000 | 20000 | 35000
13 | Supply and installation of related fittings for M.S SCH-40 Pipe fittings such as tee, elbow, reduser, gasket, nut washer etc. | Job | 1 | 400000 | 80000 | 1 | 400000 | 80000 | 480000
Premolded PU Insulation
14 | Supply and Intallation of premolded PU insulation over chilled water piping with 26 SWG G.I sheet metal cladding, kraft paper, canvas cloth etc complete in all respect.
Thickness 2"
i | 6" dia | Rft | 350 | 2580 | 285 | 521 | 1344180 | 148485 | 1492665
ii | 4" dia | Rft | 130 | 2080 | 255 | 549 | 1141920 | 139995 | 1281915
iii | 3" dia | Rft | 350 | 1730 | 235 | 172 | 297560 | 40420 | 337980
iv | 2-1/2" dia | Rft | 650 | 1700 | 230 | 256 | 435200 | 58880 | 494080
v | 2" dia | Rft | 400 | 1250 | 225 | 148 | 185000 | 33300 | 218300
Thickness 1-1/2"
i | 1-1/2" dia | Rft | 200 | 1125 | 215 | 179 | 201375 | 38485 | 239860
ii | 1-1/4" dia | Rft | 320 | 980 | 200 | 159 | 155820 | 31800 | 187620
iii | 1" dia | Rft | 180 | 975 | 180 | 84 | 81900 | 15120 | 97020
iv | 3/4" dia | Rft | 200 | 700 | 170 | 0 | 0 | 0 | 0
15 | Supply and installation of condensate drain with insulation.
i | 2" dia | Rft | 240 | 300 | 98 | 0 | 0 | 0 | 0
ii | 1-1/2" dia | Rft | 220 | 220 | 70 | 0 | 0 | 0 | 0
iii | 1" dia | Rft | 360 | 190 | 50 | 0 | 0 | 0 | 0
16 | Supply and installation of Hanger & supports for chilled water piping. | Job | 1 | 300000 | 75000 | 1 | 300000 | 75000 | 375000
17 | Supply and installation of red oxide Paint on pipes. | Job | 1 | 70000 | 38000 | 1 | 70000 | 38000 | 108000
18 | Removal of electrical cable trays | Job | 1 | 0 | 80000 | 1 | 0 | 80000 | 80000
Total Amount Rs | [8 empty] | 16415565
For PIONEER SERVICES
PIONEER SERVICES