## HVAC
M/S Y.H Associates | [8 empty] | 2023-08-15
[7 empty] | Invoice # |  | 82
[7 empty] | NTN # |  | 1338544-5
Bill
ENHANCEMENT OF SCOPE OF WORK (Additional Piping work Zone-B Ground Floor - NASTP Karachi Building.
BILL OF QUANTITIES | [7 empty] | RUNNING BILL
S. # | Description | Unit | Qty | Material Rate | Labour Rate | Material Amount | Rate | Billed Qty | Amount
Machine Made G.I Sheet metal Duct
1 | Supply, Installation, testing & Commissioning of medium/low Machine made pressure G.I. sheet metal ducting complete in all respect. | Sqft | 9500 | 350 | 60 | 3325000 | 570000 |  | 3895000
Fierglass insulation
2 | Supply and installation of 1 inch thick Fiber Glass Insulation of density 24 kg/m3 with Aluminum Foil, tape, Canvas Cloth & anti funguspaint complete in all respect. | Sqft | 9500 | 160 | 55 | 1520000 | 522500 |  | 2042500
Air devices
3 | Supply & Installation of Supply air diffuser. 15 x 15 | Nos | 124 | 5500 | 800 | 682000 | 99200 |  | 781200
4 | Supply & Installation of Exhaust Air Register. |  |  |  |  | 0 | 0 |  | 0
i | 09 x 09 | Nos | 39 | 2200 | 1000 | 85800 | 39000 |  | 124800
ii | 12 x 12 | Nos | 22 | 3500 | 1000 | 77000 | 22000 |  | 99000
5 | Supply and installation of Exhaust Air Louver as per drawings.
i | 28 x 12 | No | 2 | 7500 | 900 | 15000 | 1800 |  | 16800
ii | 30 x 12 | No | 2 | 9000 | 900 | 18000 | 1800 |  | 19800
6 | Supply and installation of volume control damper
i | 38 x 16 | Nos | 7 | 14500 | 1000 | 101500 | 7000 |  | 108500
ii | 32 x 14 | Nos | 4 | 10750 | 1000 | 43000 | 4000 |  | 47000
7 | Supply and installation of Fire Damper
i | 38 x 16 | Nos | 7 | 14500 | 1000 | 101500 | 7000 |  | 108500
ii | 32 x 14 | Nos | 4 | 11800 | 1000 | 47200 | 4000 |  | 51200
8 | Supply and installation of access door for fire / split damper. Size 18 x 18 | Nos | 11 | 8000 | 1000 | 88000 | 11000 |  | 99000
9 | Supply and installation of flexbile duct connector for supply air duct only. | Rft | 200 | 650 | 80 | 130000 | 16000 |  | 146000
M.S SCH-40 Pipe and related material
10 | Providing and installation of temporary scaffolding for installation of chilled water riser (after completion of work removal of folding) | Job | 1 | 200000 | 75000 | 200000 | 75000 |  | 275000
iv | 2-1/2" dia | Rft | 650 | 0 | 375 | 0 | 243750 |  | 243750
v | 2" dia | Rft | 400 | 0 | 325 | 0 | 130000 |  | 130000
vi | 1-1/2" dia | Rft | 200 | 0 | 275 | 0 | 55000 |  | 55000
vii | 1-1/4" dia | Rft | 320 | 0 | 250 | 0 | 80000 |  | 80000
viii | 1" dia | Rft | 180 | 0 | 225 | 0 | 40500 |  | 40500
ix | 3/4" dia | Rft | 200 | 0 | 175 | 0 | 35000 |  | 35000
12 | Providing and making of chilled water connection from main plant room for supply and return. | Job | 1 | 15000 | 20000 | 15000 | 20000 |  | 35000
13 | Supply and installation of related fittings for M.S SCH-40 Pipe fittings such as tee, elbow, reduser, gasket, nut washer etc. | Job | 1 | 400000 | 80000 | 400000 | 80000 |  | 480000
Premolded PU Insulation
1 | MS pipe 6” Sch-40 SMLS | Rft | 160 | 0 | 575 | 0 | 5105 | 160 | 816800
2 | MS pipe 4” Sch-40 SMLS | Rft | 460 | 0 | 475 | 0 | 2605 | 460 | 1198300
3 | MS pipe 1” Sch-40 SMLS | Rft | 140 | 0 | 425 | 0 | 523 | 140 | 73220
4 | Installation of MS pipe 6” Sch-40 SMLS | Rft | 160 | 0 | 425 | 0 | 575 | 160 | 92000
5 | Installation of MS pipe 4” Sch-40 SMLS | Rft | 460 | 0 | 425 | 0 | 475 | 460 | 218500
6 | Supply & Installation of pre-molded PU insulation of 2” thickness density 50 kg/m3 for chilled water piping, bends, tees, unions, sockets, valves and on special, wrapped with 8 oz canvas cloth than painted with anti fugus paint with 26 SWG G.I sheet complete in all respect on 6” pipe | Rft | 160 |  |  |  | 2865 | 160 | 458400
7 | Supply & Installation of pre-molded PU insulation of 2” thickness density 50 kg/m3 for chilled water piping, bends, tees, unions, sockets, valves and on special, wrapped with 8 oz canvas cloth than painted with anti fugus paint with 26 SWG G.I sheet complete in all respect on 4” pipe | Rft | 460 |  |  |  | 2335 | 460 | 1074100
8 | Installation of Gate Valves With, Insulation, Cladding flanges, gaskets, nut bolts, washers and etc | Each | 44 |  |  |  | 4000 | 44 | 176000
9 | Installation of CFRV Valves With, Insulation, Cladding flanges, gaskets, nut bolts, washers and etc | Each | 22 | 2580 | 285 | 56760 | 4000 | 22 | 88000
10 | Installation of Motorized Valves With, Insulation, Cladding flanges, gaskets, nut bolts, washers and etc | Each | 13 |  |  |  | 4000 | 13 | 52000
11 | Installation of Strainers With, Insulation, Cladding flanges, gaskets, nut bolts, washers and etc | Each | 22 |  |  |  | 4000 | 22 | 88000
12 | Installation of Thermometer with syphon and High-Pressure Sockets | Each | 26 |  |  |  | 1920 | 26 | 49920
13 | Installation of Pressure Gauges with Gauge Cock and High-Pressure Sockets | Each | 26 |  |  |  | 1920 | 26 | 49920
Total Amount | [8 empty] | 4435160
S. # | Description | Qty in Contract | Qty not required | Material Rate | Labour Rate | Material Amount | Rate |  | Amount
| Supply & Installation of pre-molded PU insulation over chilled water piping with 26 SWG G.I metal cladding, Kraft, paper Canvas cloth etc complete in all respect thickness 2”, 3" dia pipe. | 350 | 190 | 1965 |  |  | 1965 |  | 373350
| Supply & Installation of pre-molded PU insulation over chilled water piping with 26 SWG G.I metal cladding, Kraft, paper Canvas cloth etc complete in all respect thickness 2", 2 1/2” dia pipe. | 650 | 410 | 1930 |  |  | 1930 |  | 791300
| Installation of M.S Sch-40 Seamless Chilled Water pipe with consumable material such as cutting disc, grinding disc, electronics 3” dia. | 350 | 190 | 425 |  |  | 425 |  | 80750
| Installation of M.S Sch-40 Seamless Chilled Water pipe with consumable material such as cutting disc, grinding disc, electronics 2 1/2” dia. | 650 | 410 | 375 |  |  | 375 |  | 153750
Total Amount | [8 empty] | 1399150
For PIONEER SERVICES
PIONEER SERVICES