## Sheet1
M/S Director Development
NASTP PAF Faisal Karachi
2023-09-12
C.
M/S Director Development | [6 empty] | 12 May 2023
NASTP PAF Faisal Karachi | [6 empty] | 001
1338544-5
Enhancement of Scope of work for provision of HVAC System at Zone-B
1 | Supply of Additional 6" Pipe
2 | Supply of Additional 4" Pipe
3 | Supply of Additional 1" Pipe
M/S Pioneer Has completed 85% work at site as per revised contract agreement.
Following are the details of completion of works
S.# | Description | Unit | Qty Increased | Qty work done | Work done % | Rate | Total Amount Work Done
1 | Ducting | SFT | 6403.86 | 6403.86 | 100% | 410 | 2625582.6
2 | Insulation | SFT | 5703.858 | 5703.858 | 100% | 215 | 1226329.47
* | TOTAL
3 | Piping |  |  |  |  | 2352 RFT | 80%
Total Amount Rs | [6 empty] | 3851912.07
For PIONEER SERVICES.
PIONEER SERVICES