## Summary
TriFit Gym
COM-01, CLIFTON KARACHI.
COST SUMMARY OF FINAL BILL
2023-09-05
SR.NO. | DESCRIPTION |  | PREVIOUS AMOUNT | CURRENT AMOUNT | TOTAL AMOUNT
1 | ACMV WORKS | Rs. | 8200613 | 11285139.016 | 19485752.016
2 | FSS WORKS | Rs. | 4141364 | 1796878.15 | 5938242.15
3 | HVAC VARIATION | Rs. | 322054.36 | 5618453.2912 | 5940507.6512
| Total Work: Rs. |  | 12664031.36 | 18700470.4572 | 31364501.8172

## HVAC
IPC # FINAL BILL
ACMV Works
TriFit Gym Com-1 Clifton, Karachi.
Sr. No. |  | DESCRIPTION | BILL OF QUANTITES (AS PER CONTRACT) | [6 empty] | AS PER BILLING
|  |  | UNIT | QTY | Supply |  | Installation |  | Total Amount Rs. | Supply & Installation Qunatity |  |  | Supply Amount | Installation Amount | Supply & Installation Total Amount |  |  | % | Total
[5 empty] | Rate | Amount | Rate | Amount |  | Previous | Current | Total |  |  | Previous | Current | Total
|  | A | B | C | D | E = C x D | F | G = C x F | H = E + F | I | J = K - I | K | L = K x D | M = K x F | N | O = P - N | P = L + M | Q | R = Q x P
All works shall be completed, tested and commissioned as per drawings, specifications and as per instruction of Consultant
1 |  | Unloading, rigging, lifting, placement, installation, testing and commissioning of (OWNER SUPPLIED) VRF / VRV air conditioning units with multiple indoor evaporative units of different capacities with central controller complete in all respects, ready to operate including supply & installation of supports, brackets, flexible duct connector / connection, rubber isolators, flashing, power wiring from isolation box to unit (10' to 15' radius), control wiring termination etc, complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
| 1.1 | GF-CU-01 (4 Indoors + 1 Outdoor Condensing Unit Consisted of Different Modules) | Set | 0 |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
| 1.2 | GF-CU-02 (7 Indoors + 1 Outdoor Condensing Unit Consisted of Different Modules) | Set | 0 |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
2 |  | Unloading, installation, testing and commissioning of (OWNER SUPPLIED) single split units of different capacities including supply & installation of supports, brackets, rubber isolators, flashing, power wiring from isolation box to unit (10' to 15' radius), control wiring termination etc, complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
| 2.1 | FF-AC-01 | Nos. | 2 | 5250 | 10500 | 5250 | 10500 | 21000 |  | 3 | 3 | 15750 | 15750 |  | 31500 | 31500 | 100% | 31500
| 2.2 | SF-AC-01 | Nos. | 2 | 5250 | 10500 | 5250 | 10500 | 21000 |  | 2 | 2 | 10500 | 10500 |  | 21000 | 21000 | 100% | 21000
| 2.3 | SF-AC-02 | No. | 1 | 7350 | 7350 | 6300 | 6300 | 13650 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
| 2.4 | GF-CSU-02 | Nos. | 2 | 9450 | 18900 | 8400 | 16800 | 35700 | 2 | 1 | 3 | 28350 | 25200 | 13582 | 39968 | 53550 | 100% | 53550
| 2.5 | FF-CSU-01 | Nos. | 13 | 8925 | 116025 | 4725 | 61425 | 177450 | 3 | 0 | 3 | 26775 | 14175 | 11459 | 29491 | 40950 | 100% | 40950
| 2.6 | FF-CSU-02 | Nos. | 7 | 8925 | 62475 | 6300 | 44100 | 106575 | 20 | 0 | 20 | 178500 | 126000 | 101862 | 202638 | 304500 | 100% | 304500
| 2.7 | SF-CSU-01 | Nos. | 5 | 7875 | 39375 | 6300 | 31500 | 70875 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
| 2.8 | SF-CSU-02 | Nos. | 12 | 8925 | 107100 | 6300 | 75600 | 182700 | 17 | 0 | 17 | 151725 | 107100 | 86583 | 172242 | 258825 | 100% | 258825
3 |  | Supply & installation of refrigerant pipes for VRF Units (all hard pipes except 1/4") (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping including additional gas charging if required and installation of branch distributor (supplied with VRF / VRV units), supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
(VRF / VRV Units copper pipes sizes & quantities shall be vary according to the equipment brand / selection)
| 3.1 | 1/4" dia | Rft | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
| 3.2 | 3/8" dia | Rft | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0% | 0
| 3.3 | 1/2" dia | Rft | 160 | 945 | 151200 | 210 | 33600 | 184800 | 220.16 | 86.72 | 306.88 | 290001.6 | 64444.8 | 246685 | 107761.4 | 354446.4 | 100% | 354446.4
| 3.4 | 5/8" dia | Rft | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0% | 0
| 3.5 | 3/4" dia | Rft | 160 | 1375.5 | 220080 | 210 | 33600 | 253680 | 186.22 | 15 | 201.22 | 276778.11 | 42256.2 | 286428 | 32606.31 | 319034.31 | 100% | 319034.31
| 3.6 | 7/8" dia | Rft | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
| 3.7 | 1 1/8" dia | Rft | 160 | 2677.5 | 428400 | 231 | 36960 | 465360 | 40 | 71.39 | 111.39 | 298246.725 | 25731.09 | 112863 | 211114.815 | 323977.815 | 100% | 323977.815
| 3.8 | 1 3/8" dia (also for 1-1/4") | Rft | 160 | 3528 | 564480 | 236 | 37760 | 602240 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
| 3.9 | 1 5/8" dia (also for 1-1/2") | Rft | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
4 |  | Supply & installation of control wiring for VRF Units in G.I. for external / PVC for internal from outdoor unit to indoor units including microprocessor & central controller wiring & fixing / installation of central controller supplied with unit complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Lot | 1 | 525000 | 525000 | 131250 | 131250 | 656250 | 1 | 0 | 1 | 525000 | 131250 | 636638 | 19612 | 656250 | 100% | 656250
5 |  | Supply & installation of refrigerant pipes for Split Units (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping + control wiring for split units in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Soft Pipes for all Wall Mounted Units
| 5.1 | FF-AC-01 | Rft | 250 | 945 | 236250 | 189 | 47250 | 283500 |  | 68.81 | 68.81 | 65025.45 | 13005.09 |  | 78030.54 | 78030.54 | 100% | 78030.54
| 5.2 | SF-AC-01 | Rft | 220 | 945 | 207900 | 189 | 41580 | 249480 |  | 93.05 | 93.05 | 87932.25 | 17586.45 |  | 105518.7 | 105518.7 | 100% | 105518.7
| 5.3 | SF-AC-02 | Rft | 100 | 1260 | 126000 | 210 | 21000 | 147000 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
|  | Hard Pipes for all Cassette Type Units | [8 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
| 5.4 | GF-CSU-02 | Rft | 200 | 2159.85 | 431970 | 210 | 42000 | 473970 | 108 | 340.81 | 448.81 | 969362.2785 | 94250.1 | 245053 | 818559.3785 | 1063612.3785 | 100% | 1063612.3785
| 5.5 | FF-CSU-01 | Rft | 1500 | 1768.2 | 2652300 | 210 | 315000 | 2967300 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
| 5.6 | FF-CSU-02 | Rft | 580 | 2193.45 | 1272201 | 210 | 121800 | 1394001 | 914 | 611.71 | 1525.71 | 3346568.5995 | 320399.1 | 2111290 | 1555677.6995 | 3666967.6995 | 100% | 3666967.6995
| 5.7 | SF-CSU-01 | Rft | 340 | 1768.2 | 601188 | 210 | 71400 | 672588 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
| 5.8 | SF-CSU-02 | Rft | 740 | 2257.5 | 1670550 | 210 | 155400 | 1825950 | 929 | 531.52 | 1460.52 | 3297123.9 | 306709.2 | 2202724 | 1401109.1 | 3603833.1 | 100% | 3603833.1
6 |  | Supply & installation of 18 SWG powder quoted G.I. sheet metal tray with cover for refrigerant pipes and control wiring exposed to weather area and for main hall internal area complete in all respects including hangers, supports brackets complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqft | 1500 | 682.5 | 1023750 | 168 | 252000 | 1275750 | 1008 | 991.41 | 1999.41 | 1364597.325 | 335900.88 | 831837 | 868661.205 | 1700498.205 | 100% | 1700498.205
7 |  | Supply & installation of uPVC make class D SCH-40 pipe with 3/8" thick expanded rubber foam insulation, PVC tape wrapping for condensate drain including support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
| 7.1 | 1" dia | Rft | 850 | 1039.5 | 883575 | 126 | 107100 | 990675 | 175.35 | 475.63 | 650.98 | 676693.71 | 82023.48 | 198263 | 560454.19 | 758717.19 | 100% | 758717.19
| 7.2 | 1.25" dia | Rft | 390 | 633.15 | 246928.5 | 126 | 49140 | 296068.5 | 186.47 | 619.95 | 806.42 | 510584.823 | 101608.92 | 137328 | 474865.743 | 612193.743 | 100% | 612193.743
| 7.3 | 1.5" dia | Rft | 85 | 756 | 64260 | 126 | 10710 | 74970 |  | 226.72 | 226.72 | 171400.32 | 28566.72 |  | 199967.04 | 199967.04 | 100% | 199967.04
| 7.4 | 2" dia | Rft | 10 | 957.6 | 9576 | 126 | 1260 | 10836 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
| 7.4 | 3" dia | Rft | 80 | 1470 | 117600 | 137 | 10960 | 128560 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
8 |  | Supply & installation of air curtains including, supports, electrical connection / power wiring from isolation box to unit (10' to 15' radius) etc, complete in all respects ready to operate as per drawings, specification & as per instruction of consultant.
| 8.1 | 3 Feet length | Nos. | 4 | 85050 | 340200 | 5775 | 23100 | 363300 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
9 |  | Unloading, rigging, lifting, placement, installation, testing and commissioning of (OWNER SUPPLIED) heat recovery ventilator (HRV) as per mentioned in schedule, including supply & installation of duct mounted electronic temp controller with temp sensor, vibration isolator, starter panel, electrical connection, flexible duct connection / connector, power wiring from isolation box to unit (10' to 15' radius), support & hangers, complete in all respects ready to operate as per drawings, specification and as per instruction of consultant.
| 9.1 | GF-HRV-01 | No. | 1 | 52500 | 52500 | 26250 | 26250 | 78750 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
| 9.2 | GF-HRV-01 | No. | 1 | 52500 | 52500 | 26250 | 26250 | 78750 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
| 9.3 | GF-HRV-03 | No. | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
| 9.4 | FF-HRV-01 | No. | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
| 9.5 | FF-HRV-01 | No. | 1 | 36750 | 36750 | 26250 | 26250 | 63000 | 1 | 0 | 1 | 36750 | 26250 | 25466 | 37534 | 63000 | 100% | 63000
| 9.6 | SF-HRV-01 | No. | 1 | 36750 | 36750 | 26250 | 26250 | 63000 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
| 9.7 | SF-HRV-02 | No. | 1 | 36750 | 36750 | 26250 | 26250 | 63000 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
| 9.5 | SF-HRV-03 | No. | 1 | 52500 | 52500 | 26250 | 26250 | 78750 | 1 | 0 | 1 | 52500 | 26250 | 25466 | 53284 | 78750 | 100% | 78750
10 |  | Supply, fabrication and installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connection, access door, wooden frame, transformation, plenums chambers, anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant. | Sqft | 8500 | 346.5 | 2945250 | 95 | 807500 | 3752750 | 1348 | 3145.85 | 4493.85 | 1557119.025 | 426915.75 | 576882 | 1407152.775 | 1984034.775 | 100% | 1984034.775
11 |  | Supply and installation of rubber foam (XLPE) insulation adhesive with aluminum facing 12mm thick complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqft | 8500 | 294 | 2499000 | 79 | 671500 | 3170500 | 851 | 4413.64 | 5264.64 | 1547804.16 | 415906.56 | 307763 | 1655947.72 | 1963710.72 | 100% | 1963710.72
12 |  | Supply, fabrication and installation of epoxy painted M.S sheet metal welded duct of (18 Gauge) for condensing units exhaust air. complete in all respects including all changes in direction, transformation, plenums chambers, connection pecs of hood round to square, supports & hangers etc. complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant.. | Sqft | 900 | 682.5 | 614250 | 158 | 142200 | 756450 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
13 |  | Supply & installation of aluminum fabricated powder coated exhaust & fresh Air louvers including wooden frame, rain protection sheet bird mesh etc complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqin | 11600 | 25.2 | 292320 | 6 | 69600 | 361920 |  | 4322 | 4322 | 108914.4 | 25932 |  | 134846.4 | 134846.4 | 100% | 134846.4
14 |  | Supply, installation of Aluminum fabricated, powder coated Grills, Diffusers and Registers for supply air, return air, exhaust air & fresh air of different sizes (Grade A ), wooden frame, supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
| 14.1 | Fresh & Exhaust Air Register / Diffuser with Damper | Sqin | 14850 | 25.2 | 374220 | 6 | 89100 | 463320 |  | 13364 | 13364 | 336772.8 | 80184 |  | 416956.8 | 416956.8 | 100% | 416956.8
| 14.2 | Exhaust Air Disc Valves 6" dia | Nos. | 41 | 3360 | 137760 | 840 | 34440 | 172200 |  | 34 | 34 | 114240 | 28560 |  | 142800 | 142800 | 100% | 142800
15 |  | Supply & installation of Volume Control Damper in 16 SWG G.I sheet metal with gas kits, nut bolts, complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Sqin | 3500 | 25.2 | 88200 | 6 | 21000 | 109200 |  | 1251 | 1251 | 31525.2 | 7506 |  | 39031.2 | 39031.2 | 100% | 39031.2
16 |  | Painting & Identification work on supports, hangers, platform of condensing units etc complete in all respects with one coat of ICI make Red lead oxide primer & two coats of ICI make enamel paint complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | Lot | 1 | 288750 | 288750 | 36750 | 36750 | 325500 |  | 1 | 1 | 288750 | 36750 |  | 325500 | 325500 | 100% | 325500
17 |  | Testing, balancing and commissioning of air side of the system (from independent agency) complete in all respects including air measurement & balancing, temp, pressure & electrical data of related equipment etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Job. | 1 | 0 | 0 | 131250 | 131250 | 131250 |  | 1 | 1 | 0 | 131250 |  | 131250 | 131250 | 100% | 131250
18 |  | Making of Shop drawings on Auto CAD latest version with section details, equipment foundation details and Making of As Built drawings, Documentation Technical / Operational Manual & LOG Book for each equipment complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Job. | 1 | 26250 | 26250 | 26250 | 26250 | 52500 | 1 | 1 | 1 | 26250 | 26250 | 42443 | 10057 | 52500 | 100% | 52500
|  | Total Cost of Works Rs. |  |  |  | 19307158.5 |  | 3986685 | 23666068.5 |  |  |  | 16391540.676 | 3094211.34 | 8200613 | 11285139.016 | 19485752.016 |  | 19485752.016
Discount Rs.
Note:
1) | Electric power wiring / supply to be provided at outdoor, indoor units & other ACMV equipment with isolation box by electrical contractor.
2) | The refrigerant pipes sized + quantity provided for reference only. The contractor / supplier shall calculate the refrigerant pipes, sized & length as per the drawing provided and shall submitted refrigerant piping layout to consultant for approval.
3) | Contractor is instructed to visit the site, understand the nature of work & then fill the rates accordingly and submit the quotation. No argument and discussion will be entertained after awarding of work.
4) | Miscellaneous work which was not included in BOQ but necessary to complete the project in all respects and ready to operate as per instructions of Consultant. (Bidder should mentioned the type of works).

## Fire
IPC # FINAL BILL
ACMV Works
TriFit Gym Com-1 Clifton, Karachi.
Sr. No. |  | DESCRIPTION | BILL OF QUANTITES (AS PER CONTRACT) | [6 empty] | AS PER BILLING
|  |  | UNIT | QTY | Supply |  | Installation |  | Total Amount Rs. | Supply & Installation Qunatity |  |  | Supply Amount | Installation Amount | Supply & Installation Total Amount |  |  | % | Total
[5 empty] | Rate | Amount | Rate | Amount |  | Previous | Current | Total |  |  | Previous | Current | Total
Discount Rs.
|  | A | B | C | D | E = C x D | F | G = C x F | H = E + F | I | J = K - I | K | L = K x D | M = K x F | N | O = P - N | P = L + M | Q | R = Q x P
FIRE FIGHTING SERVICES
Supply, installation, testing & commissioning of fire suppression system including all equipment, pipe works and accessories ready to operate as per specifications, drawings and instructions of consultants.
1 |  | Fire hose cabinet double height 32" x 60" x 14", stainless steel front, powder coated back including 1" dia x 100 Rft. rubber hose reel, nozzle guide, lock shield valve, pressure regulating valve automatic & manual operation 180 deg. swing type, with 2-fire extinguishers as shown on drawing.
| 1.1 | Type FHC | No. | 1 | 393750 | 393750 | 10500 | 10500 | 404250 | 1 | 0 | 1 | 393750 | 10500 | 363825 | 40425 | 404250 | 100% | 404250
2 |  | Fire hose cabinet double height 32" x 60" x 14", stainless steel front, powder coated back including 1" dia x 100 Rft. rubber hose reel, automatic & manual operation 180 deg. swing type, nozzle guide, lock sheild valve, pressure regulating valve with 2-1/2" dia size obliuqe landing valve, 2-fire extinguishers as shown on drawing.
| 2.1 | Type FHC-LV | Nos. | 5 | 320250 | 1601250 | 7350 | 36750 | 1638000 | 5 | 0 | 5 | 1601250 | 36750 | 1474200 | 163800 | 1638000 | 100% | 1638000
3 |  | Fire department breeching connection 2 ways as per BSS 5041-3 including cabinet with breakable glass, SS frame & drain plug. | No. | 1 | 162750 | 162750 | 7350 | 7350 | 170100 | 1 | 0 | 1 | 162750 | 7350 |  | 170100 | 170100 | 100% | 170100
4 |  | MS Sch-40 seamless pipes including all specials fittings UL listed FM approved, threaded, welded joints, flexible pipe, flanges, coupling, masking plates, bends, tees, clamps, supports and hangers, sleeves, masking plates chiseling, cutting holes, making good where required, painting and protection treatment etc. Complete in all respects.
| 4.1 | Dia 1" (Threaded fitting) | Rft. | 20 | 724.5 | 14490 | 205 | 4100 | 18590 | [8 empty] | 100% | 0
| 4.2 | Dia 1-1/4" (Threaded fitting) | Rft. | 60 | 871.5 | 52290 | 221 | 13260 | 65550 |  | 66.66 | 66.66 | 58094.19 | 14731.86 | 58261 | 14565.05 | 72826.05 | 100% | 72826.05
| 4.3 | Dia 2" (Threaded fitting) | Rft. | 70 | 1438.5 | 100695 | 231 | 16170 | 116865 |  | 40 | 40 | 57540 | 9240 | 53424 | 13356 | 66780 | 100% | 66780
| 4.4 | Dia 2-1/2" (Welded joints fitting) | Rft. | 300 | 1879.5 | 563850 | 273 | 81900 | 645750 |  | 260.68 | 260.68 | 489948.06 | 71165.64 | 448891 | 112222.7 | 561113.7 | 100% | 561113.7
| 4.5 | Dia 4" (Welded joints fitting) | Rft. | 280 | 3360 | 940800 | 368 | 103040 | 1043840 | 299.82 | 146.73 | 446.55 | 1500408 | 164330.4 | 894183 | 770555.4 | 1664738.4 | 100% | 1664738.4
5 |  | Fire extinguishers with fixing accessories. | [15 empty] | 100% | 0
| 5.1 | Type Class B&C FX-3 (5 Kg. CO2 Carbon Dioxide Gas) | Nos. | 6 | 26250 | 157500 | 3150 | 18900 | 176400 |  | 8 | 8 | 210000 | 25200 |  | 235200 | 235200 | 100% | 235200
| 5.2 | Type Class A,B&C FX-4 (6 Kg. Dry Chemical Powder) | Nos. | 6 | 15750 | 94500 | 1050 | 6300 | 100800 |  | 9 | 9 | 141750 | 9450 |  | 151200 | 151200 | 100% | 151200
6 |  | C.I body Check valve with matching flanges. | [15 empty] | 100% | 0
| 6.1 | Size. 4" | No. | 1 | 50925 | 50925 | 5250 | 5250 | 56175 | [8 empty] | 100% | 0
7 |  | C.I body Gate valve with matching flanges. | [15 empty] | 100% | 0
| 7.1 | Dia. 2-1/2" | Nos. | 2 | 31395 | 62790 | 5250 | 10500 | 73290 |  | 2 | 2 | 62790 | 10500 | 65961 | 7329 | 73290 | 100% | 73290
8 |  | Making of As-Built & Shop Drawings on AutoCAD 2018 or latest version with sectional details complete in all respects as per instructions of consultant. | Job. | 1 | 15750 | 15750 | 10500 | 10500 | 26250 |  | 1 | 1 | 15750 | 10500 |  | 26250 | 26250 | 100% | 26250
9 |  | Painting, identification and tagging to the installations and equipments. | Job. | 1 | 52500 | 52500 | 36750 | 36750 | 89250 |  | 1 | 1 | 52500 | 36750 | 44625 | 44625 | 89250 | 100% | 89250
10 |  | Flushing of entire fire pipe work according to (NFPA-13). | Job. | 1 | 0 | 0 | 21000 | 21000 | 21000 |  | 1 | 1 | 0 | 21000 |  | 21000 | 21000 | 100% | 21000
11 |  | Testing, and commissioning of entire fire fighting installation as per Consultant's approval. | Job. | 1 | 0 | 0 | 26250 | 26250 | 26250 |  | 1 | 1 | 0 | 26250 |  | 26250 | 26250 | 100% | 26250
|  | Total Cost of Fire Suppression Services Rs. |  |  |  | 4263840 |  | 408520 | 4672360 |  |  |  | 4746530.25 | 453717.9 |  | 1796878.15 | 5200248.15 |  | 5200248.15
Note:
1) | Electric power wiring / supply to be provided at outdoor, indoor units & other ACMV equipment with isolation box by electrical contractor.
2) | The refrigerant pipes sized + quantity provided for reference only. The contractor / supplier shall calculate the refrigerant pipes, sized & length as per the drawing provided and shall submitted refrigerant piping layout to consultant for approval.
3) | Contractor is instructed to visit the site, understand the nature of work & then fill the rates accordingly and submit the quotation. No argument and discussion will be entertained after awarding of work.
4) | Miscellaneous work which was not included in BOQ but necessary to complete the project in all respects and ready to operate as per instructions of Consultant. (Bidder should mentioned the type of works).

## VARIATION
VARIATION ORDER
TriFit Gym
Com-1 Clifton, Karachi.
2023-09-09
Variation of Copper Pipe & G.I ducting - TRIFIT COM-1 Karachi
S. # | Description | Unit | Qty | Labour Rate |  |  |  | Amount
1 | Dismantling of copper piping from room area & installation of copper piping in corridor area. | Job | 1 | 175000 |  |  |  | 175000
2 | Dismantling of G.I Ducting & installation of G.I Ducting in corridor area. | Job | 1 | 75000 |  |  |  | 75000
Total Amount Rs. | [7 empty] | 250000
G.I DUCTING
BOQ Item # | Description | Unit | Quantity | Rate supply | Rate Labour |  |  | Total Amount
10 | Dismentling of Gi duct | sqft | 1362.4936 |  | 60 |  |  | 81749.616
10 | Installation of Gi duct | sqft | 387.9576 |  | 102 |  |  | 39571.6752
| TOTAL AMOUNT | [6 empty] | 121321.2912
Rate Analysis for Air Curtain - Main Entrance & Trifuel
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
A MATERIAL.
1 | Supply of air curtain 5 Feet Length. | No | 2 |  | 2 | 75000 | 150000
| Total. | [5 empty] | 150000 | 150000
B LABOUR.
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
2 | Installation of air curtain with hanging and supports. | No | 2 |  | 1 | 15000 | 15000
| Total. | [5 empty] | 15000 | 165000
C OTHER
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
| Total. | [6 empty] | 165000
| Total Rs. | [6 empty] | 165000
Sub-Contractor Margin: |  |  | 10% |  |  |  |  | 16500
Total Price | [7 empty] | 181500
Revised Rate Analysis for Kitchen Hood
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
A MATERIAL.
1 | Supply of single skinned stainless steel kitchen hood (120" x 42" x 24") including grease trap, grease filter exhaust connections and hangers supports. | No | 1 |  | 1 | 268450 | 268450
| Total. | [5 empty] | 268450 | 268450
B LABOUR.
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
1 | Installation of Fans with regging lifting & shifting of Fans including angle iron brackets, hangers, & supports. (OFM Material) | No | 2 |  | 2 | 15000 | 30000
2 | Installation of kitchen hood with hangers and supports. | No | 1 |  | 1 | 30000 | 30000
| Total. | [5 empty] | 60000 | 328450
C OTHER
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
| Total. | [6 empty] | 328450
| Total Rs. | [6 empty] | 328450
Sub-Contractor Margin: |  |  | 10% |  |  |  |  | 32845
Total Price | [7 empty] | 361295
M.S Plateform for condensing units with related material - TRI-FIT COM-1 Karachi
S. # | Description | Unit | Qty | Material Rate | Labour Rate | Material Amount | Labour Amount | Total Amount
1 | Providing & installation of M.S Checker plates 4mm thick. (1080 Sqft) | KG | 2850 | 350 | 105 | 997500 | 299250
2 | Supply & installation of M.S C-Channel 4" x 2" (660 Rft) | KG | 2730 | 300 | 70 | 819000 | 191100
3 | Supply & installation of M.S Angle iron 1-1/2" x 3/16" (1680 Rft) | KG | 1350 | 280 | 53 | 378000 | 71550
4 | Supply & installation of M.S Plate (37 Nos) (22" x 8" x 3/8") | KG | 320 | 350 | 70 | 112000 | 22400
5 | Supply & installation of M.S rectangular pipe 14 SWG 2" x 2" | Rft | 260 | 225 | 70 | 58500 | 18200
6 | Supply & installation of M.S rectangular pipe 16 SWG 1" x 1" | Rft | 220 | 110 | 53 | 24200 | 11660
7 | Supply & installation of M.S pipe 1/2" for railing. | Rft | 520 | 63 | 53 | 32760 | 27560
8 | Supply & installation of rawal bolts | Nos | 300 | 400 | 50 | 120000 | 15000
9 | Application of Painting with 02 coat primer and 02 coat of epoxy. | SQFT | 2680 | 150 | 53 | 402000 | 142040
Sub - Total Amount Rs | [5 empty] | 2943960 | 798760
Total Amount Rs | [5 empty] | 3742720
Sub-Contractor Margin 10% | [5 empty] | 374272
Grand Total Amount Rs | [5 empty] | 4116992 |  |  | 5031108.2912
Dated: | 2023-10-14
Project: | TRI-FIT COM-1
Contractor: M/s Pioneer Engineering Services | National Engineering Services
Rate Analysis for Charging of Refrigerant Gas in Ac unit
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
A MATERIAL.
| Honeywell USA Refrigerant Gas 11.5 kg |  | 2 |  | 2 |  | 55000
| Total. | [5 empty] | 110000
B LABOUR.
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
4 | Charging of Gas | Units | 43 |  | 43 | 850 | 36550
| Total. | [5 empty] | 36550 | 146550
C OTHER
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
| Total. | [6 empty] | 146550
| Total Rs. | [6 empty] | 146550
Sub-Contractor Margin: |  |  | 10% |  |  |  |  | 14655
Total Price | [7 empty] | 161205
Dated: | 2023-10-14
Project: | TRI-FIT COM-1
Contractor: M/s Pioneer Engineering Services | National Engineering Services
Rate Analysis for Exhaust Hood Fan Relocation
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
A MATERIAL.
Total.
B LABOUR.
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
1 | Rigging Lifting and Shifting of Hood Exhaust Fan. (OFM Material) | No | 2 |  | 2 | 10000 | 20000
3 | Dismantling of G.I Ducting | sqft | 100 |  | 100 | 60 | 6000
4 | Installation of Flexiable Connector with Exhaust Fan. | Rft | 10 |  | 10 | 400 | 4000
| Total. | [5 empty] | 30000 | 30000
C OTHER
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
| Total. | [6 empty] | 30000
| Total Rs. | [6 empty] | 30000
Sub-Contractor Margin: |  |  | 10% |  |  |  |  | 3000
Total Price | [7 empty] | 33000
Dated: | 2023-10-07
Project: | TRI-FIT COM-1
Contractor: M/s Pioneer Engineering Services | National Engineering Services
Rate Analysis for Exhaust system Against HRV
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
A MATERIAL.
1 | Supply of Hanging Support for hanging exhaust fan and ducting. | job | 1 |  | 1 | 20000 | 20000
| Total. | [5 empty] | 20000 | 20000
B LABOUR.
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
1 | Installation of Exhaust Fan. (OFM Material) | No | 4 |  | 4 | 8000 | 32000
2 | Installation of G.I Ducting. | Sqft | 350 |  | 350 | 442 | 154700
3 | Dismantling of G.I Ducting | sqft | 295 |  | 295 | 60 | 17700
4 | Installation of Flexiable Connector with Exhaust Fan. | Rft | 20 |  | 20 | 400 | 8000
5 | Installation of Hanging Support for Ducting and Exhaust fan. | job | 1 |  | 1 | 7000 | 7000
| Total. | [5 empty] | 212400 | 232400
C OTHER
S. # | Description | Unit | Quantity |  |  | Rate | Amount | Gross
|  |  | Actual | Waste | Total
| Total. | [6 empty] | 232400
| Total Rs. | [6 empty] | 232400
Sub-Contractor Margin: |  |  | 10% |  |  |  |  | 23240
Total Price | [7 empty] | 255640
Master servicing of complete VRF system - TRI-FIT COM-1 Karachi
S. # | Description | Unit | Qty | Labour Rate | Rate | Amount
1 | Master servicing of complete VRF system
A | 11 Nos. Cassette type Indoor units
i | Remove the front panels and any other removable parts on the indoor units
ii | Clean the coils with water pressure and karchar pump
iii | Remove and clean the soiled air filters
iv | Clean both the interior and exterior surfaces of the indoor units using a mild detergent and a soft cloth
B | 2 Nos. Outdoor condensing units | Job | 1 |  | 0 | 110000
i | Clean the condenser coils using a Karcher pump
ii | Clean the exterior of the outdoor units using a mild detergent and a soft cloth
iii | Remove dust and debris from electrical components, control boards, and cards. using air blower, Ensure all electrical connections are secure and free of corrosion
iv | Monitor the system's performance for a while to ensure it operates correctly
Sub - Total Amount Rs |  |  |  |  | 0 | 110000
Total Amount Rs |  |  |  |  | 110000
Pioneer Margin 25% |  |  |  |  | 27500
Grand Total Amount Rs |  |  |  |  | 137500 |  |  |  | 5618453.2912
5618453.2912

## MS-VO.
SUMMARY OF VO HVAC
TRIFIT LIMITED-T1 GYM CLIFTON KARACHI
BOQ NO. | DESCRIPTION | Unit | No. | GROUND FLOOR | FIRST FLOOR |  | CURRANT TOTAL
2 | Dismantling of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
|  | Sq.ft |  | 853.97 | 508.5236 |  | 1362.4936
3 | Installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
|  | Sq.ft |  | 204.08 | 183.8776 |  | 387.9576
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-07-11
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
GROUND FLOOR
10 | Supply, fabrication and installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connection, access door, wooden frame, transformation, plenums chambers, anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
Exhaust & Fresh Air Duct (DISMANTLING)
| Neck (12*4) |  | 2 | 1 | 0.33 | 0.5 | 1.33
| Duct (12*4) |  | 2 | 1 | 0.33 | 11.66 | 31.0156
| Elbow (12*4) L (2.33+.75 /2) |  | 2 | 1 | 0.33 | 1.54 | 4.0964
| Duct (12*4) |  | 2 | 1 | 0.33 | 2.66 | 7.0756
| End Cap (12*4) |  | 2 | 1 | 0.33 | 0 | 0.33
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 5.66 | 11.2068
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 1.16 | 2.2968
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Duct (12*6) |  | 2 | 1 | 0.5 | 12.25 | 36.75
| End Cap (12*6) |  | 2 | 1 | 0.5 | 0 | 0.5
| Duct (14*10) |  | 2 | 1.16 | 0.83 | 7.08 | 28.1784
| Duct (14*10) |  | 2 | 1.16 | 0.83 | 3.58 | 14.2484
| End Cap (14*10) |  | 2 | 1.16 | 0.83 | 0 | 0.97
| Neck (12*4) |  | 2 | 1 | 0.33 | 0.5 | 1.33
| Duct (12*4) |  | 2 | 1 | 0.33 | 4.25 | 11.305
| End Cap (12*4) |  | 2 | 1 | 0.33 | 0 | 0.33
| Neck (12*8) |  | 2 | 1 | 0.66 | 0.5 | 1.66
| Duct (12*8) |  | 2 | 1 | 0.66 | 3.33 | 11.0556
| Reducer (12+8)/2 (10+8)/2 |  | 2 | 0.83 | 0.75 | 1 | 3.16
| Duct (10*8) |  | 2 | 0.83 | 0.66 | 13.33 | 39.7234
| Reducer (10+8)/2 (8+8)/2 |  | 2 | 0.75 | 0.66 | 1 | 2.82
| Duct (8*8) |  | 2 | 0.66 | 0.66 | 3.75 | 9.9
| Reducer (8+8)/2 (8+6)/2 |  | 2 | 0.66 | 0.58 | 1 | 2.48
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 3.08 | 7.1456
| End Cap (8*6) |  | 2 | 0.66 | 0.5 | 0 | 0.33
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 6.66 | 13.1868
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 6.58 | 13.0284
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 7.33 | 14.5134
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 13.5 | 26.73
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*6) |  | 2 | 0.66 | 0.5 | 0.5 | 1.16
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 8.08 | 18.7456
| Reducer (8+6)/2 (8+4)/2 |  | 2 | 0.58 | 0.5 | 1 | 2.16
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 5.41 | 10.7118
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 1.33 | 2.6334
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 1.33 | 2.6334
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 3.16 | 6.2568
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (14*4) |  | 2 | 1.16 | 0.33 | 0.5 | 1.49
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 10.25 | 30.545
| End Cap (14*4) |  | 2 | 1.16 | 0.33 | 0 | 0.38
| Neck (14*4) |  | 2 | 1.16 | 0.33 | 0.5 | 1.49
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 0.33 | 0.9834
| Elbow (14*4) L (2.58+.75 /2) |  | 2 | 1.16 | 0.33 | 1.66 | 4.9468
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 4.58 | 13.6484
| End Cap (14*4) |  | 2 | 1.16 | 0.33 | 0 | 0.38
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 1.66 | 6.0424
| Elbow (14*4) L (2.58+.75 /2) |  | 2 | 1.16 | 0.33 | 1.66 | 4.9468
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 6.08 | 22.1312
| End Cap (14*8) |  | 2 | 1.16 | 0.66 | 0 | 0.78
| Duct (10*10) |  | 2 | 0.83 | 0.83 | 2.75 | 9.13
| Elbow (10*10) L (2.08+.75 /2) |  | 2 | 0.83 | 0.83 | 1.41 | 4.6812
| Duct (10*10) |  | 2 | 0.83 | 0.83 | 7.83 | 25.9956
| Elbow (10*10) L (2.08+.75 /2) |  | 2 | 0.83 | 0.83 | 1.41 | 4.6812
| Duct (10*10) |  | 2 | 0.83 | 0.83 | 2.58 | 8.5656
| Neck (14*8) |  | 2 | 1.16 | 0.66 | 0.5 | 1.82
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 12.41 | 45.1724
| Reducer (14+8)/2 (8+6)/2 |  | 2 | 0.91 | 0.58 | 1 | 2.98
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 3.16 | 7.3312
| Reducer (8+6)/2 (8+4)/2 |  | 2 | 0.58 | 0.5 | 1 | 2.16
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 8.83 | 17.4834
| Elbow (8*4) L (1.83+.75 /2) |  | 2 | 0.66 | 0.33 | 1.29 | 2.5542
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 2.5 | 4.95
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 2 | 3.96
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 2.58 | 5.1084
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 2.5 | 10
| End Cap (18*6) |  | 2 | 1.5 | 0.5 | 0 | 0.75
| Duct (14*10) |  | 2 | 1.16 | 0.83 | 9.41 | 37.4518
| Elbow (14*10) L (2.58+.75 /2) |  | 2 | 1.16 | 0.83 | 1.65 | 6.567
| Duct (14*10) |  | 2 | 1.16 | 0.83 | 8 | 31.84
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 1.33 | 3.9634
| Elbow (14*4) L (2.58+.75 /2) |  | 2 | 1.16 | 0.33 | 1.66 | 4.9468
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 6.5 | 19.37
| End Cap (14*4) |  | 2 | 1.16 | 0.33 | 0 | 0.38
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 2.83 | 8.4334
| Elbow (14*4) L (2.58+.75 /2) |  | 2 | 1.16 | 0.33 | 1.66 | 4.9468
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 7 | 20.86
| Elbow (14*4) L (2.58+.75 /2) |  | 2 | 1.16 | 0.33 | 1.66 | 4.9468
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 6.33 | 18.8634
| End Cap (14*4) |  | 2 | 1.16 | 0.33 | 0 | 0.38
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 5.41 | 17.9612
| Elbow (14*6) L (2.58+.75 /2) |  | 2 | 1.16 | 0.5 | 1.66 | 5.5112
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 3.58 | 11.8856
| Elbow (14*6) L (2.58+.75 /2) |  | 2 | 1.16 | 0.5 | 1.66 | 5.5112
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 6.91 | 22.9412
| Reducer (14+6)/2 (14+4)/2 |  | 2 | 0.83 | 0.75 | 1 | 3.16
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 7.66 | 22.8268
| End Cap (14*4) |  | 2 | 1.16 | 0.33 | 0 | 0.38
| This Bill Qty. | Sq.ft |  |  |  |  | 853.971
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-07-11
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
GROUND FLOOR
10 | Supply, fabrication and installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connection, access door, wooden frame, transformation, plenums chambers, anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
Exhaust & Fresh Air Duct (INSTALLATION)
| Neck (10*8) |  | 2 | 0.83 | 0.66 | 0.5 | 1.49
| Duct (10*8) |  | 2 | 0.83 | 0.66 | 2.75 | 8.195
| Reducer (10+8)/2 (8+8)/2 |  | 2 | 0.75 | 0.66 | 1.5 | 4.23
| Duct (8*8) |  | 2 | 0.66 | 0.66 | 4.58 | 12.0912
| Reducer (8+8)/2 (8+6)/2 |  | 2 | 0.66 | 0.58 | 1.5 | 3.72
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 3.5 | 8.12
| End Cap (8*6) |  | 2 | 0.66 | 0.5 | 0 | 0.33
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 10.08 | 19.9584
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*6) |  | 2 | 0.66 | 0.5 | 0.5 | 1.16
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 4 | 9.28
| Reducer (8+6)/2 (8+4)/2 |  | 2 | 0.58 | 0.5 | 1.5 | 3.24
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 5.5 | 10.89
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 2.25 | 4.455
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 0.91 | 1.8018
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 3.66 | 7.2468
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 10.08 | 19.9584
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 10.75 | 21.285
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 2.75 | 9.13
| Elbow (14*6) L (2.91+1.08 /2) |  | 2 | 1.16 | 0.5 | 1.99 | 6.6068
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 1.58 | 5.2456
| Elbow (14*6) L (2.91+1.08 /2) |  | 2 | 1.16 | 0.5 | 1.99 | 6.6068
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 9.33 | 30.9756
| End Cap (14*6) |  | 2 | 1.16 | 0.5 | 0 | 0.58
| This Bill Qty. | Sq.ft |  |  |  |  | 204.0764
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-04
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
FIRST FLOOR
10 | Supply, fabrication and installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connection, access door, wooden frame, transformation, plenums chambers, anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
Exhaust & Fresh Air Duct (DISMANTLING)
| Neck (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.33 | 1.3134
| Elbow (16*8) L (1.08+3.16 /2) |  | 2 | 1.33 | 0.66 | 2.12 | 8.4376
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 3.58 | 14.2484
| Reducer (16+8)/2 (14+8)/2 |  | 2 | 1 | 0.91 | 1.16 | 4.4312
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 11.08 | 40.3312
| End Cap (14*8) |  | 1 | 1.16 | 0.66 | 0 | 0.78
| Neck (16*6) |  | 2 | 1.33 | 0.5 | 0.5 | 1.83
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 6 | 21.96
| Reducer (16+6)/2 (14+6)/2 |  | 2 | 0.91 | 0.83 | 1.16 | 4.0368
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 27.58 | 91.5656
| Elbow (14*6) L (1.08+2.91 /2) |  | 2 | 1.16 | 0.5 | 1.99 | 6.6068
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 2 | 6.64
| End Cap (14*6) |  | 1 | 1.16 | 0.5 | 0 | 0.58
| Neck (8*6) |  | 2 | 0.66 | 0.5 | 0.5 | 1.16
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 3.83 | 8.8856
| Reducer (8+6)/2 (6+6)/2 |  | 2 | 0.58 | 0.5 | 1 | 2.16
| Duct (6*6) |  | 2 | 0.5 | 0.5 | 2 | 4
| Elbow (6*6) L (.25+.66 /2) |  | 2 | 0.5 | 0.5 | 0.45 | 0.9
| Duct (6*6) |  | 2 | 0.5 | 0.5 | 1 | 2
| Elbow (6*6) L (.25+.66 /2) |  | 2 | 0.5 | 0.5 | 0.45 | 0.9
| Duct (6*6) |  | 2 | 0.5 | 0.5 | 7.08 | 14.16
| End Cap (6*6) |  | 1 | 0.5 | 0.5 | 0 | 0.25
| Duct (22*4) |  | 2 | 1.83 | 0.33 | 5.75 | 24.84
| End Cap (22*4) |  | 1 | 1.83 | 0.33 | 0 | 0.61
| Neck (22*4) |  | 2 | 1.83 | 0.33 | 0.5 | 2.16
| Duct (22*4) |  | 2 | 1.83 | 0.33 | 6 | 25.92
| End Cap (22*4) |  | 1 | 1.83 | 0.33 | 0 | 0.61
| Duct (22*4) |  | 2 | 1.83 | 0.33 | 3.91 | 16.8912
| End Cap (22*4) |  | 1 | 1.83 | 0.33 | 0 | 0.61
| Duct (14*10) |  | 2 | 1.16 | 0.83 | 7.75 | 30.845
| Reducer (14+10)/2 (14+4)/2 |  | 2 | 1 | 0.75 | 1 | 3.5
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 13.91 | 41.4518
| End Cap (14*4) |  | 1 | 1.16 | 0.33 | 0 | 0.38
| Neck (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 7.5 | 39.9
| Reducer (22+10)/2 (22+6)/2 |  | 2 | 1.33 | 1.16 | 1.5 | 7.47
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 9.41 | 43.8506
| Elbow (22*6) L (1.08+3.91 /2) |  | 2 | 1.83 | 0.5 | 2.49 | 11.6034
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 3.25 | 15.145
| End Cap (22*6) |  | 1 | 1.83 | 0.5 | 0 | 0.91
| This Bill Qty. | Sq.ft |  |  |  |  | 508.5236
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-02
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
FIRST FLOOR
10 | Supply, fabrication and installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connection, access door, wooden frame, transformation, plenums chambers, anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
Exhaust Air Duct (Installation Works)
| Neck (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.33 | 1.3134
| Elbow (16*8) L (1.08+3.16 /2) |  | 2 | 1.33 | 0.66 | 2.12 | 8.4376
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 10.25 | 40.795
| Reducer (16+8)/2 (14+8)/2 |  | 2 | 1 | 0.91 | 1.16 | 4.4312
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 11.33 | 41.2412
| End Cap (14*8) |  | 1 | 1.16 | 0.66 | 0 | 0.78
| Neck (16*6) |  | 2 | 1.33 | 0.5 | 0.5 | 1.83
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 6 | 21.96
| Reducer (16+6)/2 (14+6)/2 |  | 2 | 0.91 | 0.83 | 1.16 | 4.0368
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 6.91 | 22.9412
| End Cap (14*6) |  | 1 | 1.16 | 0.5 | 0 | 0.58
| Neck (8*6) |  | 2 | 0.66 | 0.5 | 0.5 | 1.16
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 5.16 | 11.9712
| Reducer (8+6)/2 (6+6)/2 |  | 2 | 0.58 | 0.5 | 1 | 2.16
| Duct (6*6) |  | 2 | 0.5 | 0.5 | 9 | 18
| End Cap (6*6) |  | 1 | 0.5 | 0.5 | 0 | 0.25
| This Bill Qty. | Sq.ft |  |  |  |  | 183.8776

## Measurements Sheet FINAL BILL
SUMMARY OF HVAC
TRIFIT LIMITED-T1 GYM CLIFTON KARACHI
BOQ NO. | DESCRIPTION | Unit | No. | GROUND FLOOR | FIRST FLOOR | SECOND FLOOR | CURRANT TOTAL
2 | Unloading, installation, testing and commissioning of (OWNER SUPPLIED) single split units of different capacities including supply & installation of supports, brackets, rubber isolators, flashing, power wiring from isolation box to unit (10' to 15' radius), control wiring termination etc, complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
| FF-AC-01 |  |  | 1 | 2 |  | 3
| SF-AC-01 |  |  |  |  | 2 | 2
SF-AC-02
3 | Supply & installation of refrigerant pipes for VRF Units (all hard pipes except 1/4") (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping including additional gas charging if required and installation of branch distributor (supplied with VRF / VRV units), supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
3.2 | 3/8" Dia | Rft. |  | 15 |  |  | 15
3.3 | 1/2" Dia | Rft. |  | 40.14 | 31.58 |  | 71.72
3.4 | 5/8" Dia | Rft. |  | 15 |  |  | 15
3.5 | 3/4" Dia | Rft.
3.7 | 1-1/8" Dia | Rft. |  | 39.89 | 31.5 |  | 71.39
5 | Supply & installation of refrigerant pipes for Split Units (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping + control wiring for split units in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Soft Pipes for all Wall Mounted Units
5.1 | FF-AC-01 | Rft. |  | 33.41 | 35.4 |  | 68.81
5.2 | SF-AC-01 | Rft. |  |  |  | 93.05 | 93.05
Hard Pipes for all Cassette Type Units
5.4 | GF-CSU-01-E | Rft. |  | 256.09 | 84.72 |  | 340.81
5.6 | FF-CSU-02 | Rft. |  |  | 611.71 |  | 611.71
5.8 | SF-CSU-02 | Rft. |  |  |  | 531.52 | 531.52
6 | Supply & installation of 18 SWG powder quoted G.I. sheet metal tray with cover for refrigerant pipes and control wiring exposed to weather area and for main hall internal area complete in all respects including hangers, supports brackets complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
|  | Sq.ft |  | 66.5 | 441.1633 | 483.7467 | 991.41
7 | Supply & installation of uPVC make class D SCH-40 pipe with 3/8" thick expanded rubber foam insulation, PVC tape wrapping for condensate drain including support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
7.1 | 1" Dia | Rft. |  | 52.14 | 245.17 | 178.32 | 475.63
7.2 | 1.25" Dia | Rft. |  |  | 282.06 | 337.89 | 619.95
7.3 | 1.5" Dia | Rft. |  | 38.06 | 136.66 | 52 | 226.72
10 | Supply, fabrication and installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connection, access door, wooden frame, transformation, plenums chambers, anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
|  | Sq.ft |  | 551.3675 | 936.6098 | 1657.8842 | 3145.8615
11 | Supply and installation of rubber foam (XLPE) insulation adhesive with aluminum facing 12mm thick complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
|  | Sq.ft |  | 551.3675 | 1251.2848 | 2611.0016 | 4413.6539
13 | Supply & installation of aluminum fabricated powder coated exhaust & fresh Air louvers including wooden frame, rain protection sheet bird mesh etc complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
|  | Sq.in |  | 4322 |  |  | 4322
14 | Supply, installation of Aluminum fabricated, powder coated Grills, Diffusers and Registers for supply air, return air, exhaust air & fresh air of different sizes (Grade A ), wooden frame, supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
14.1 | Fresh & Exhaust Air Register / Diffuser with Damper | Sq.in |  | 3050 | 5634 | 4680 | 13364
14.2 | Exhaust Air Disc Valves 6" dia | Nos. |  | 16 | 2 | 16 | 34
15 | Supply & installation of Volume Control Damper in 16 SWG G.I sheet metal with gas kits, nut bolts, complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
|  | Sq.in |  | 200 | 481 | 570 | 1251
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-10-10
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
No.
GROUND FLOOR
2 | Unloading, installation, testing and commissioning of (OWNER SUPPLIED) single split units of different capacities including supply & installation of supports, brackets, rubber isolators, flashing, power wiring from isolation box to unit (10' to 15' radius), control wiring termination etc, complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
5.1 | G.F-AC-01 (LV Room Wall Mounted) | Nos | 1 |  |  |  | 1
| This Bill Qty. | Nos |  |  |  |  | 1
Pioneer Services | [7 empty] | 4493.8615
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-10-10
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
No.
FIRST FLOOR
2 | Unloading, installation, testing and commissioning of (OWNER SUPPLIED) single split units of different capacities including supply & installation of supports, brackets, rubber isolators, flashing, power wiring from isolation box to unit (10' to 15' radius), control wiring termination etc, complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
5.1 | F.F-AC-01 | Nos | 2 |  |  |  | 2
| This Bill Qty. | Nos |  |  |  |  | 2
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-10-10
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
No.
SECOND FLOOR
2 | Unloading, installation, testing and commissioning of (OWNER SUPPLIED) single split units of different capacities including supply & installation of supports, brackets, rubber isolators, flashing, power wiring from isolation box to unit (10' to 15' radius), control wiring termination etc, complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
5.1 | S.F-AC-01 | Nos | 2 |  |  |  | 2
| This Bill Qty. | Nos |  |  |  |  | 2
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-07
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | Size | Size
| GROUND FLOOR |  |  | 1/2" | 1-1/8"
3 | Supply & installation of refrigerant pipes for VRF Units (all hard pipes except 1/4") (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping including additional gas charging if required and installation of branch distributor (supplied with VRF / VRV units), supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Copper Pipe-12-TON
|  | Rft. | 1 | 0.83 | 0.33
|  |  | 1 | 2.41 | 2.16
|  |  | 1 | 8.08 | 8.41
| Vertical Pipe |  | 1 | 8 | 8
| This Bill Qty. | Rft. |  | 19.32 | 18.9
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-07
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | Size | Size
| FIRST FLOOR |  |  | 1/2" | 1-1/8"
3 | Supply & installation of refrigerant pipes for VRF Units (all hard pipes except 1/4") (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping including additional gas charging if required and installation of branch distributor (supplied with VRF / VRV units), supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Copper Pipe-12-TON
|  | Rft. | 1 | 8 | 8
| Vertical Pipe |  | 1 | 4 | 4
| This Bill Qty. | Rft. |  | 12 | 12
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-07
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | Size | Size
| GROUND FLOOR |  |  | 3/8" | 5/8"
3 | Supply & installation of refrigerant pipes for VRF Units (all hard pipes except 1/4") (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping including additional gas charging if required and installation of branch distributor (supplied with VRF / VRV units), supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Copper Pipe-24-TON
Rft.
|  |  | 1 | 15 | 15
| This Bill Qty. | Rft. |  | 15 | 15
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-07
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | Size | Size
| GROUND FLOOR |  |  | 1/2" | 1-1/8"
3 | Supply & installation of refrigerant pipes for VRF Units (all hard pipes except 1/4") (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping including additional gas charging if required and installation of branch distributor (supplied with VRF / VRV units), supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Copper Pipe-24-TON
Rft.
|  |  | 1 | 1.58 | 1.16
|  |  | 1 | 3.08 | 3.5
|  |  | 1 | 8.16 | 8.33
| Vertical Pipe |  | 1 | 8 | 8
| This Bill Qty. | Rft. |  | 20.82 | 20.99
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-07
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | Size | Size
| FIRST FLOOR |  |  | 1/2" | 1-1/8"
3 | Supply & installation of refrigerant pipes for VRF Units (all hard pipes except 1/4") (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping including additional gas charging if required and installation of branch distributor (supplied with VRF / VRV units), supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Copper Pipe-24-TON
|  | Rft. | 1 | 15.58 | 15.5
| Vertical Pipe |  | 1 | 4 | 4
| This Bill Qty. | Rft. |  | 19.58 | 19.5
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-10-10
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | Size | Size
| GROUND FLOOR |  |  | 1/4" | 3/8"
Copper Pipe
5 | Supply & installation of refrigerant pipes for Split Units (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping + control wiring for split units in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Soft Pipes for all Wall Mounted Units
5.1 | G.F-AC-01 | Rft. | 1 | 0.91 | 1
|  |  | 1 | 24.75 | 25.41
| Vertical Pipe |  | 1 | 7 | 7
| This Bill Qty. | Rft. |  | 32.66 | 33.41
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-08
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | Size | Size
| FIRST FLOOR |  |  | 1/4" | 3/8"
Copper Pipe
5 | Supply & installation of refrigerant pipes for Split Units (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping + control wiring for split units in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Soft Pipes for all Wall Mounted Units
5.1 | FF-AC-01 | Rft. | 1 | 1.08 | 1
| FF-AC-01 |  | 1 | 9.16 | 9.25
|  |  | 1 | 4.16 | 4.08
|  |  | 1 | 10 | 10
|  |  | 1 | 11 | 11
| This Bill Qty. | Rft. |  | 35.4 | 35.33
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-09
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | Size | Size
| SECOND FLOOR |  |  | 1/4" | 3/8"
Copper Pipe
5 | Supply & installation of refrigerant pipes for Split Units (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping + control wiring for split units in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Soft Pipes for all Wall Mounted Units
5.2 | SF-AC-01 | Rft. | 1 | 0.66 | 0.5
| SF-AC-01 |  | 1 | 14.33 | 14.75
|  |  | 1 | 22.58 | 22.25
|  |  | 1 | 3.83 | 4.08
|  |  | 1 | 0.83 | 0.91
|  |  | 1 | 0.41 | 0.25
|  |  | 1 | 4.91 | 4.5
|  |  | 1 | 22.5 | 22.25
|  |  | 1 | 15 | 15
|  |  | 1 | 8 | 8
| This Bill Qty. | Rft. |  | 93.05 | 92.49
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-08-26
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | Size | Size
| GROUND FLOOR |  |  | 5/8" | 3/8"
5 | Supply & installation of refrigerant pipes for Split Units (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping + control wiring for split units in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Copper Pipe-2-TON
5.4 | GF-CSU-01-E | Rft. | 1 | 0.66 | 0.5
|  |  | 1 | 25.33 | 24.83
|  |  | 1 | 22.83 | 22.66
|  |  | 1 | 27.08 | 27.33
|  |  | 1 | 21.58 | 21.25
|  |  | 1 | 0.66 | 0.33
|  |  | 1 | 56.58 | 57.41
|  |  | 1 | 23.91 | 23.58
|  |  | 1 | 8.91 | 8.91
|  |  | 1 | 8.91 | 8.91
|  |  | 1 | 8.91 | 8.91
|  |  | 1 | 8.91 | 8.91
|  |  | 1 | 8.91 | 8.91
|  |  | 1 | 8.91 | 8.91
| Vertical Pipe |  | 1 | 24 | 24
| This Bill Qty. | Rft. |  | 256.09 | 255.35
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-07
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | Size | Size
| GROUND FLOOR |  |  | 3/4" | 3/8"
5 | Supply & installation of refrigerant pipes for Split Units (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping + control wiring for split units in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Copper Pipe-4-TON
5.4 | GF-CSU-02 | Rft. | 1 | 8.08 | 8.08
| GF-CSU-02 |  | 1 | 18.5 | 18.5
|  |  | 1 | 0.41 | 0.33
|  |  | 1 | 8.08 | 8.08
|  |  | 1 | 0.25 | 0.5
|  |  | 1 | 11.58 | 11.66
| This Bill Qty. | Rft. |  | 46.9 | 47.15
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-08
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | Size | Size
| FIRST FLOOR |  |  | 5/8" | 3/8"
5 | Supply & installation of refrigerant pipes for Split Units (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping + control wiring for split units in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Copper Pipe-2-TON
5.4 | GF-CSU-01-E | Rft. | 1 | 17.33 | 17.16
|  |  | 1 | 3.16 | 3.16
|  |  | 1 | 24.41 | 24.25
|  |  | 1 | 3.33 | 3.33
|  |  | 1 | 30.5 | 30.33
|  |  | 1 | 2.08 | 2.16
|  |  | 1 | 2.91 | 3.08
|  |  | 1 | 1 | 0.75
| This Bill Qty. | Rft. |  | 84.72 | 84.22
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-08
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | Size | Size
| FIRST FLOOR |  |  | 3/4" | 3/8"
5 | Supply & installation of refrigerant pipes for Split Units (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping + control wiring for split units in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Copper Pipe-4-TON
5.6 | FF-CSU-02 | Rft. | 1 | 0.75 | 1
|  |  | 1 | 20.83 | 21.5
|  |  | 1 | 0.75 | 0.75
|  |  | 1 | 15.75 | 16.08
|  |  | 1 | 0.5 | 0.5
|  |  | 1 | 10.16 | 10.5
|  |  | 1 | 0.5 | 0.5
|  |  | 1 | 6.58 | 6.58
|  |  | 1 | 2.25 | 2.41
|  |  | 1 | 1 | 1
|  |  | 1 | 1.75 | 1.66
|  |  | 1 | 6.08 | 5.83
|  |  | 1 | 1.33 | 1.25
|  |  | 1 | 9.16 | 9.25
|  |  | 1 | 1.16 | 1.08
|  |  | 1 | 13.33 | 13.5
|  |  | 1 | 0.5 | 0.75
|  |  | 1 | 1.33 | 1
|  |  | 1 | 16.5 | 16.58
|  |  | 1 | 0.75 | 0.75
|  |  | 1 | 1 | 1
|  |  | 1 | 19.83 | 19.75
|  |  | 1 | 0.91 | 1
|  |  | 1 | 1 | 0.91
|  |  | 1 | 5.66 | 5.5
|  |  | 1 | 0.75 | 0.66
|  |  | 1 | 1.41 | 1.25
|  |  | 1 | 1.5 | 1.5
|  |  | 1 | 13 | 13.16
|  |  | 1 | 5.41 | 5.66
|  |  | 1 | 6.5 | 6.25
|  |  | 1 | 1.33 | 1.33
|  |  | 1 | 12.91 | 13
|  |  | 1 | 5.33 | 5.66
|  |  | 1 | 3.33 | 3.16
|  |  | 1 | 1.08 | 0.91
|  |  | 1 | 12.33 | 12.16
|  |  | 1 | 6.16 | 6.33
|  |  | 1 | 6.83 | 6.91
|  |  | 1 | 3.41 | 3.5
|  |  | 1 | 0.83 | 0.83
|  |  | 1 | 1.25 | 1.33
|  |  | 1 | 0.75 | 0.58
| Vertical Pipe |  | 20 | 240 | 240
| Vertical Pipe |  | 20 | 40 | 40
| This Bill Qty. | Rft. |  | 503.47 | 504.81
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-08-27
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | Size | Size
| FIRST FLOOR |  |  | 3/4" | 3/8"
Copper Pipe
5 | Supply & installation of refrigerant pipes for Split Units (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping + control wiring for split units in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Hard Pipes for all Cassette Type Units
5.6 | FF-CSU-02 | Rft. | 1 | 3 | 3
| FF-CSU-02 |  | 2 | 3 | 3
| FF-CSU-02 |  | 3 | 3 | 3
| FF-CSU-02 |  | 4 | 3 | 3
| FF-CSU-02 |  | 5 | 3 | 3
| FF-CSU-02 |  | 6 | 3 | 3
| FF-CSU-02 |  | 7 | 3 | 3
| FF-CSU-02 |  | 8 | 3 | 3
| FF-CSU-02 |  | 9 | 3 | 3
| FF-CSU-02 |  | 10 | 3 | 3
| FF-CSU-02 |  | 11 | 3 | 3
| FF-CSU-02 |  | 12 | 3 | 3
| FF-CSU-02 |  | 13 | 3 | 3
| FF-CSU-02 |  | 14 | 3 | 3
| FF-CSU-02 |  | 15 | 3 | 3
| FF-CSU-02 |  | 16 | 3 | 3
| FF-CSU-02 |  | 17 | 3 | 3
| FF-CSU-02 |  | 18 | 3 | 3
| FF-CSU-02 |  | 19 | 3 | 3
| FF-CSU-02 |  | 20 | 3 | 3
| This Bill Qty. | Rft. |  | 60 | 60
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-09
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | Size | Size
| SECOND FLOOR |  |  | 3/4" | 3/8"
5 | Supply & installation of refrigerant pipes for Split Units (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping + control wiring for split units in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Copper Pipe-4-TON
5.8 | SF-CSU-02 | Rft. | 1 | 0.66 | 0.58
|  |  | 1 | 2.25 | 2.33
|  |  | 1 | 0.41 | 0.5
|  |  | 1 | 1.33 | 1.25
|  |  | 1 | 1.33 | 1.16
|  |  | 1 | 0.66 | 0.5
|  |  | 1 | 5.58 | 5.58
|  |  | 1 | 0.41 | 0.58
|  |  | 1 | 9.58 | 9.66
|  |  | 1 | 0.66 | 0.91
|  |  | 1 | 13.58 | 13.66
|  |  | 1 | 1 | 1.16
|  |  | 1 | 1.33 | 1.25
|  |  | 1 | 0.83 | 0.75
|  |  | 1 | 3.75 | 3.66
|  |  | 1 | 0.58 | 0.5
|  |  | 1 | 7.66 | 7.66
|  |  | 1 | 0.5 | 0.66
|  |  | 1 | 14.91 | 14.66
|  |  | 1 | 0.83 | 0.75
|  |  | 1 | 19.25 | 19
|  |  | 1 | 1.08 | 1
|  |  | 1 | 0.91 | 1.08
|  |  | 1 | 10.25 | 10.33
|  |  | 1 | 4.33 | 4.08
|  |  | 1 | 20.66 | 21
|  |  | 1 | 0.66 | 0.83
|  |  | 1 | 6.66 | 6.66
|  |  | 1 | 4.25 | 4
|  |  | 1 | 20.58 | 21
|  |  | 1 | 0.5 | 0.41
|  |  | 1 | 3.16 | 3.33
|  |  | 1 | 4 | 4
|  |  | 1 | 20.41 | 20.58
|  |  | 1 | 4.08 | 3.91
|  |  | 1 | 20.58 | 20.83
|  |  | 1 | 1.83 | 1.66
|  |  | 1 | 13.91 | 14.16
|  |  | 1 | 1.33 | 1
|  |  | 1 | 9.91 | 10.16
|  |  | 1 | 0.83 | 0.66
|  |  | 1 | 4.83 | 5.08
| Vertical Pipe |  | 17 | 204 | 204
| Vertical Pipe |  | 17 | 34 | 34
| This Bill Qty. | Rft. |  | 479.84 | 480.52
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-08-27
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | Size | Size
| SECOND FLOOR |  |  | 3/4" | 3/8"
Copper Pipe
5 | Supply & installation of refrigerant pipes for Split Units (liquid + gas) with 1/2" thick expended rubber foam insulation, PVC tape wrapping + control wiring for split units in G.I. for external / PVC for internal from outdoor unit to indoor unit, including additional gas charging if required, supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Hard Pipes for all Cassette Type Units
5.8 | SF-CSU-02 | Rft. | 1 | 3 | 3
| SF-CSU-02 |  | 2 | 3 | 3
| SF-CSU-02 |  | 3 | 3 | 3
| SF-CSU-02 |  | 4 | 3 | 3
| SF-CSU-02 |  | 5 | 3 | 3
| SF-CSU-02 |  | 6 | 3 | 3
| SF-CSU-02 |  | 7 | 3 | 3
| SF-CSU-02 |  | 8 | 3 | 3
| SF-CSU-02 |  | 9 | 3 | 3
| SF-CSU-02 |  | 10 | 3 | 3
| SF-CSU-02 |  | 11 | 3 | 3
| SF-CSU-02 |  | 12 | 3 | 3
| SF-CSU-02 |  | 13 | 3 | 3
| SF-CSU-02 |  | 14 | 3 | 3
| SF-CSU-02 |  | 15 | 3 | 3
| SF-CSU-02 |  | 16 | 3 | 3
| SF-CSU-02 |  | 17 | 3 | 3
| This Bill Qty. | Rft. |  | 51 | 51
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-07
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H
GROUND FLOOR
6 | Supply & installation of 18 SWG powder quoted G.I. sheet metal tray with cover for refrigerant pipes and control wiring exposed to weather area and for main hall internal area complete in all respects including hangers, supports brackets complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
G.I CABLE TRAY
| Cable Tray (10"x4") | Sqft. | 2 | 10.5 | 10 | 4 | 24.5
|  |  | 2 | 10 | 10 | 4 | 23.3333
| Vertical Cable Tray |  | 2 | 8 | 10 | 4 | 18.6667
| This Bill Qty. | Sqft. |  |  |  |  | 66.5
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-04
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H
FIRST FLOOR
6 | Supply & installation of 18 SWG powder quoted G.I. sheet metal tray with cover for refrigerant pipes and control wiring exposed to weather area and for main hall internal area complete in all respects including hangers, supports brackets complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
G.I CABLE TRAY
| Cable Tray (10"x4") | Sqft. | 2 | 26.25 | 10 | 4 | 61.25
|  |  | 2 | 69.33 | 10 | 4 | 161.77
|  |  | 2 | 13.58 | 10 | 4 | 31.6867
|  |  | 2 | 2.66 | 10 | 4 | 6.2067
|  |  | 2 | 17.25 | 10 | 4 | 40.25
| Vertical Cable Tray |  | 2 | 60 | 10 | 4 | 140
| This Bill Qty. | Sqft. |  |  |  |  | 441.1633
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-04
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H
SECOND FLOOR
6 | Supply & installation of 18 SWG powder quoted G.I. sheet metal tray with cover for refrigerant pipes and control wiring exposed to weather area and for main hall internal area complete in all respects including hangers, supports brackets complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
G.I CABLE TRAY
| Cable Tray (10"x4") | Sqft. | 2 | 69.33 | 10 | 4 | 161.77
|  |  | 2 | 21.75 | 10 | 4 | 50.75
|  |  | 2 | 2.66 | 10 | 4 | 6.2067
|  |  | 2 | 17.25 | 10 | 4 | 40.25
|  |  | 2 | 13.58 | 10 | 4 | 31.6867
|  |  | 2 | 22.75 | 10 | 4 | 53.0833
| Vertical Cable Tray |  | 2 | 60 | 10 | 4 | 140
| This Bill Qty. | Sqft. |  |  |  |  | 483.7467
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-08-30
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H
GROUND FLOOR
7 | Supply & installation of uPVC make class D SCH-40 pipe with 3/8" thick expanded rubber foam insulation, PVC tape wrapping for condensate drain including support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
Drain Pipe
GF-CSU-01-E
7.1 | 1" Dia | Rft. | 1 | 1.33 |  |  | 1.33
|  |  | 1 | 2.58 |  |  | 2.58
|  |  | 1 | 1.33 |  |  | 1.33
|  |  | 1 | 1.16 |  |  | 1.16
|  |  | 1 | 1.33 |  |  | 1.33
|  |  | 1 | 0.83 |  |  | 0.83
| Vertical Pipe |  | 6 | 0.5 |  |  | 3
| This Bill Qty. | Rft. |  |  |  |  | 11.56
7.3 | 1.5" Dia | Rft. | 1 | 7.5 |  |  | 7.5
|  |  | 1 | 5.75 |  |  | 5.75
| This Bill Qty. | Rft. |  |  |  |  | 24.81
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-09
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H
GROUND FLOOR
7 | Supply & installation of uPVC make class D SCH-40 pipe with 3/8" thick expanded rubber foam insulation, PVC tape wrapping for condensate drain including support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
Drain Pipe
7.1 | 1" Dia | Rft. | 1 | 1.25 |  |  | 1.25
|  |  | 1 | 10.33 |  |  | 10.33
|  |  | 1 | 19 |  |  | 19
| Vertical Pipe |  | 1 | 10 |  |  | 10
| This Bill Qty. | Rft. |  |  |  |  | 40.58
7.3 | 1.5" Dia | Rft. | 1 | 7.5 |  |  | 7.5
|  |  | 1 | 5.75 |  |  | 5.75
| This Bill Qty. | Rft. |  |  |  |  | 13.25
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-09
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H
FIRST FLOOR
7 | Supply & installation of uPVC make class D SCH-40 pipe with 3/8" thick expanded rubber foam insulation, PVC tape wrapping for condensate drain including support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
Drain Pipe
7.1 | 1" Dia | Rft. | 1 | 5.5 |  |  | 5.5
|  |  | 1 | 2.5 |  |  | 2.5
| Vertical Pipe |  | 1 | 12 |  |  | 12
| Vertical Pipe |  | 1 | 20 |  |  | 20
| This Bill Qty. | Rft. |  |  |  |  | 40
7.2 | 1.25" Dia
|  |  | 1 | 17.08 |  |  | 17.08
| Vertical Pipe |  | 1 | 20 |  |  | 20
| Vertical Pipe |  | 1 | 20 |  |  | 20
| Vertical Pipe |  | 1 | 14 |  |  | 14
| This Bill Qty. | Rft. |  |  |  |  | 71.08
7.3 | 1.5" Dia
|  |  | 1 | 69.83 |  |  | 69.83
|  |  | 1 | 23.83 |  |  | 23.83
| Vertical Pipe |  | 1 | 20 |  |  | 20
| Vertical Pipe |  | 1 | 20 |  |  | 20
| Vertical Pipe |  | 1 | 3 |  |  | 3
| This Bill Qty. | Rft. |  |  |  |  | 136.66
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-08-26
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H
FIRST FLOOR
7 | Supply & installation of uPVC make class D SCH-40 pipe with 3/8" thick expanded rubber foam insulation, PVC tape wrapping for condensate drain including support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
Drain Pipe
7.1 | 1" Dia | Rft. | 1 | 3.75 |  |  | 3.75
|  |  | 1 | 11 |  |  | 11
|  |  | 1 | 8.33 |  |  | 8.33
|  |  | 1 | 8.33 |  |  | 8.33
|  |  | 1 | 4.91 |  |  | 4.91
|  |  | 1 | 5.83 |  |  | 5.83
|  |  | 1 | 18.75 |  |  | 18.75
|  |  | 1 | 1.58 |  |  | 1.58
|  |  | 1 | 17.25 |  |  | 17.25
|  |  | 1 | 8.25 |  |  | 8.25
|  |  | 1 | 16.5 |  |  | 16.5
|  |  | 1 | 1.08 |  |  | 1.08
|  |  | 1 | 4 |  |  | 4
|  |  | 1 | 12.08 |  |  | 12.08
|  |  | 1 | 13.33 |  |  | 13.33
|  |  | 1 | 7.16 |  |  | 7.16
|  |  | 1 | 4.33 |  |  | 4.33
|  |  | 1 | 8.75 |  |  | 8.75
|  |  | 1 | 4.33 |  |  | 4.33
|  |  | 1 | 4.33 |  |  | 4.33
|  |  | 1 | 2.58 |  |  | 2.58
|  |  | 1 | 10 |  |  | 10
|  |  | 1 | 2.33 |  |  | 2.33
|  |  | 1 | 1.41 |  |  | 1.41
|  |  | 1 | 1.41 |  |  | 1.41
|  |  | 1 | 10.58 |  |  | 10.58
|  |  | 1 | 1.41 |  |  | 1.41
|  |  | 1 | 1.33 |  |  | 1.33
|  |  | 1 | 10.25 |  |  | 10.25
| This Bill Qty. | Rft. |  |  |  |  | 205.17
7.2 | 1.25" Dia
|  |  | 1 | 38.5 |  |  | 38.5
|  |  | 1 | 38.66 |  |  | 38.66
|  |  | 1 | 40.75 |  |  | 40.75
|  |  | 1 | 36.83 |  |  | 36.83
|  |  | 1 | 13 |  |  | 13
|  |  | 1 | 3.08 |  |  | 3.08
|  |  | 1 | 40.16 |  |  | 40.16
| This Bill Qty. | Rft. |  |  |  |  | 210.98
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-08-26
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H
SECOND FLOOR
7 | Supply & installation of uPVC make class D SCH-40 pipe with 3/8" thick expanded rubber foam insulation, PVC tape wrapping for condensate drain including support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
Drain Pipe
7.1 | 1" Dia | Rft. | 1 | 9.08 |  |  | 9.08
|  |  | 1 | 13.91 |  |  | 13.91
|  |  | 1 | 9.08 |  |  | 9.08
|  |  | 1 | 9.08 |  |  | 9.08
|  |  | 1 | 5.16 |  |  | 5.16
|  |  | 1 | 20.41 |  |  | 20.41
|  |  | 1 | 5.16 |  |  | 5.16
|  |  | 1 | 12.83 |  |  | 12.83
|  |  | 1 | 12.83 |  |  | 12.83
|  |  | 1 | 1.91 |  |  | 1.91
|  |  | 1 | 8.58 |  |  | 8.58
|  |  | 1 | 2.33 |  |  | 2.33
|  |  | 1 | 8.58 |  |  | 8.58
|  |  | 1 | 9.41 |  |  | 9.41
|  |  | 1 | 7.91 |  |  | 7.91
|  |  | 1 | 7.08 |  |  | 7.08
|  |  | 1 | 1.83 |  |  | 1.83
|  |  | 1 | 6.58 |  |  | 6.58
|  |  | 1 | 1.83 |  |  | 1.83
|  |  | 1 | 4.83 |  |  | 4.83
|  |  | 1 | 14.08 |  |  | 14.08
|  |  | 1 | 4.83 |  |  | 4.83
|  |  | 1 | 1 |  |  | 1
| This Bill Qty. | Rft. |  |  |  |  | 178.32
7.2 | 1.25" Dia
|  |  | 1 | 21.66 |  |  | 21.66
|  |  | 1 | 37 |  |  | 37
|  |  | 1 | 34.33 |  |  | 34.33
|  |  | 1 | 55.33 |  |  | 55.33
|  |  | 1 | 33 |  |  | 33
|  |  | 1 | 47.25 |  |  | 47.25
|  |  | 1 | 39.58 |  |  | 39.58
| This Bill Qty. | Rft. |  |  |  |  | 268.15
7.3 | 1.5" Dia
| Vertical Pipe |  | 4 | 3 |  |  | 12
| Vertical Pipe |  | 1 | 14 |  |  | 14
| This Bill Qty. | Rft. |  |  |  |  | 26
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-10-10
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H
SECOND FLOOR
7 | Supply & installation of uPVC make class D SCH-40 pipe with 3/8" thick expanded rubber foam insulation, PVC tape wrapping for condensate drain including support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
Drain Pipe
7.2 | 1.25" Dia | Rft. | 1 | 20.91 |  |  | 20.91
|  |  | 1 | 6.83 |  |  | 6.83
| Vertical Pipe |  | 3 | 14 |  |  | 42
| This Bill Qty. | Rft. |  |  |  |  | 69.74
7.3 | 1.5" Dia
| Vertical Pipe |  | 4 | 3 |  |  | 12
| Vertical Pipe |  | 1 | 14 |  |  | 14
| This Bill Qty. | Rft. |  |  |  |  | 26
GROUND FLOOR
10 | Supply, fabrication and installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connection, access door, wooden frame, transformation, plenums chambers, anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
Exhaust & Fresh Air Duct
| Elbow (26*9) L (1.33+4.75 /2) |  | 2 | 2.16 | 0.75 | 3.04 | 17.6928
| Round Duct (13") Dia |  | 1 | 2.16 | 1.08 | 2.33 | 7.9141
| Elbow (13*14) L (.41+1.58 /2) |  | 2 | 1.08 | 1.16 | 0.99 | 4.4352
| Duct (13*14) |  | 2 | 1.08 | 1.16 | 0.5 | 2.24
| Reducer (13+14)/2 (16+14)/2 |  | 2 | 1.125 | 1.25 | 0.5 | 2.375
| Duct (16*14) |  | 2 | 1.33 | 1.16 | 1 | 4.98
| Round Duct (13") Dia |  | 1 | 1.5 | 1.08 | 2.33 | 7.9141
| Plenum Box (36*36) |  | 2 | 3 | 3 | 3 | 36
| Neck (18*12) |  | 2 | 1.5 | 1 | 0.58 | 2.9
| Elbow (18*12) L (.75+3.16 /2) |  | 2 | 1.5 | 1 | 1.95 | 9.75
| Duct (18*12) |  | 2 | 1.5 | 1 | 6.75 | 33.75
| Round Drop Neck (8") Dia |  | 3 | 0.66 | 0.66 | 2.16 | 13.4505
| Drop Neck (20*5) |  | 2 | 1.66 | 0.41 | 3.33 | 13.7862
| Drop Neck (20*5) |  | 2 | 1.66 | 0.41 | 3.33 | 13.7862
| This Bill Qty. | Sq.ft |  |  |  |  | 170.9741
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-08-28
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H | L
GROUND FLOOR
10 | Supply, fabrication and installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connection, access door, wooden frame, transformation, plenums chambers, anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
(Drop Neck) Exhaust & Fresh Air Duct
| Round Drop Neck (6") Dia |  | 16 | 0.5 | 0.5 | 0.83 | 20.8828
| Neck (9*9) |  | 2 | 0.75 | 0.75 | 1 | 3
| Neck (9*9) |  | 2 | 0.75 | 0.75 | 1 | 3
| Neck (9*9) |  | 2 | 0.75 | 0.75 | 1 | 3
| Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Neck (9*9) |  | 2 | 0.75 | 0.75 | 1 | 3
| Neck (12*12) |  | 2 | 1 | 1 | 1 | 4
| Neck (12*12) |  | 2 | 1 | 1 | 1 | 4
| Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Neck (12*12) |  | 2 | 1 | 1 | 1 | 4
| Neck (12*12) |  | 2 | 1 | 1 | 1 | 4
| Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Neck (6*6) |  | 2 | 0.5 | 0.5 | 1 | 2
| Neck (6*6) |  | 2 | 0.5 | 0.5 | 1 | 2
| Neck (6*6) |  | 2 | 0.5 | 0.5 | 1 | 2
| Neck (6*6) |  | 2 | 0.5 | 0.5 | 1 | 2
| Neck (12*12) |  | 2 | 1 | 1 | 1 | 4
| Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| This Bill Qty. | Sq.ft |  |  |  |  | 90.8828
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-08-11
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H | L
GROUND FLOOR
10 | Supply, fabrication and installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connection, access door, wooden frame, transformation, plenums chambers, anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
Exhaust & Fresh Air Duct (Cafeterea)
| End Cap (16*14) |  | 2 | 1.33 | 1.16 | 0 | 1.56
| Duct (16*14) |  | 2 | 1.33 | 1.16 | 8 | 39.84
| Elbow (16*14) L (3.16+1.08 /2) |  | 2 | 1.33 | 1.16 | 2.12 | 10.5576
| Duct (16*14) |  | 2 | 1.33 | 1.16 | 1.91 | 9.5118
| Elbow (16*14) L (1.41+.41 /2) |  | 2 | 1.33 | 1.16 | 0.91 | 4.5318
| Offset (16*14) |  | 2 | 1.33 | 1.16 | 1.33 | 6.6234
| Elbow (16*14) L (1.41+.41 /2) |  | 2 | 1.33 | 1.16 | 0.91 | 4.5318
| Duct (16*14) |  | 2 | 1.33 | 1.16 | 2.75 | 13.695
| Elbow (26*8) L (4.41+1.16 /2) |  | 2 | 2.16 | 0.66 | 2.78 | 15.6792
| Offset (16*14) |  | 2 | 1.33 | 1.16 | 1 | 4.98
| Offset (26*8) |  | 2 | 2.16 | 0.66 | 2.5 | 14.1
| Duct (18*12) |  | 2 | 1.5 | 1 | 19.33 | 96.65
| Elbow (18*12) L (3.41+1.08 /2) |  | 2 | 1.5 | 1 | 2.24 | 11.2
| Duct (18*12) |  | 2 | 1.5 | 1 | 10.91 | 54.55
| End Cap (18*12) |  | 2 | 1.5 | 1 | 0 | 1.5
| This Bill Qty. | Sq.ft |  |  |  |  | 289.5106
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-09
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H | L
FIRST FLOOR
10 | Supply, fabrication and installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connection, access door, wooden frame, transformation, plenums chambers, anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
Drop Neck Fresh & Exhaust Air
EAD | Drop Neck (15*15) | 1 | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (6*6) |  | 1 | 0.5 | 0.5 | 0.33 | 0.33
| Drop Neck (6*6) |  | 1 | 0.5 | 0.5 | 0.33 | 0.33
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 0.33 | 1.98
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 0.33 | 1.98
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 0.33 | 1.98
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 0.33 | 1.98
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 1 | 6
FAD | Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Drop Neck (6*6) |  | 1 | 0.5 | 0.5 | 0.33 | 0.33
| Drop Neck (6*6) |  | 1 | 0.5 | 0.5 | 0.33 | 0.33
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 0.33 | 1.98
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 0.33 | 1.98
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 0.33 | 1.98
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 0.33 | 1.98
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 0.33 | 1.98
| This Bill Qty. | Sq.ft |  |  |  |  | 55.04
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-09
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H | L
(Round Drop Neck Disc Valves) Exhaust Air Duct
10 | Supply, fabrication and installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connection, access door, wooden frame, transformation, plenums chambers, anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
FIRST FLOOR
| Round Drop Neck (6") Dia |  | 2 | 0.5 | 0.5 | 1 | 3.145
SECOND FLOOR
| Round Drop Neck (6") Dia |  | 16 | 0.5 | 0.5 | 1 | 25.16
| This Bill Qty. | Sq.ft |  |  |  |  | 28.305
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-08-26
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H | L
FIRST FLOOR
10 | Supply, fabrication and installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connection, access door, wooden frame, transformation, plenums chambers, anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
Exhaust & Fresh Air Duct
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 2.58 | 13.7256
| Elbow (22*10) L (1.16+4 /2) |  | 2 | 1.83 | 0.83 | 2.58 | 13.7256
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 2.91 | 15.4812
| Elbow (22*10) L (1.16+4 /2) |  | 2 | 1.83 | 0.83 | 2.58 | 13.7256
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 2.25 | 11.97
| Reducer (22+10)/2 (36+14)/2 |  | 2 | 1.33 | 2.08 | 1 | 6.82
| Neck (36*14) |  | 2 | 3 | 1.16 | 0.5 | 4.16
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 8.91 | 47.4012
| Duct (26*14) |  | 2 | 2.16 | 1.16 | 4.08 | 27.0912
| Elbow (26*14) L (.5+2.25 /2) |  | 2 | 2.16 | 1.16 | 1.37 | 9.0968
| Duct (26*14) |  | 2 | 2.16 | 1.16 | 1.16 | 7.7024
| Elbow (26*14) L (.5+2.25 /2) |  | 2 | 2.16 | 1.16 | 1.37 | 9.0968
| Duct (26*14) |  | 2 | 2.16 | 1.16 | 0.58 | 3.8512
| Reducer (26+14)/2 (28+14)/2 |  | 2 | 1.66 | 1.75 | 1 | 6.82
| Neck (28*14) |  | 2 | 2.33 | 1.16 | 0.5 | 3.49
| Duct (26*12) |  | 2 | 2.16 | 1 | 2.33 | 14.7256
| Elbow (26*12) L (1.08+4.41 /2) |  | 2 | 2.16 | 1 | 2.75 | 17.38
| Duct (26*12) |  | 2 | 2.16 | 1 | 7.83 | 49.4856
| Elbow (26*12) L (1.08+4.41 /2) |  | 2 | 2.16 | 1 | 2.75 | 17.38
| Duct (26*12) |  | 2 | 2.16 | 1 | 2.16 | 13.6512
| Reducer (26+12)/2 (38+14)/2 |  | 2 | 1.58 | 2.16 | 1 | 7.48
| Neck (38*14) |  | 2 | 3.16 | 1.16 | 0.5 | 4.32
| Duct (26*12) |  | 2 | 2.16 | 1 | 5.33 | 33.6856
| Elbow (26*12) L (.41+2.08 /2) |  | 2 | 2.16 | 1 | 1.24 | 7.8368
| Duct (26*12) |  | 2 | 2.16 | 1 | 1.75 | 11.06
| Elbow (26*12) L (.41+2.08 /2) |  | 2 | 2.16 | 1 | 1.24 | 7.8368
| Duct (26*12) |  | 2 | 2.16 | 1 | 13.5 | 85.32
| End Cap (26*12) |  | 1 | 2.16 | 1 | 0 | 2.16
| Neck (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 8 | 37.28
| End Cap (22*6) |  | 1 | 1.83 | 0.5 | 0 | 0.91
| Neck (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 8.16 | 38.0256
| End Cap (22*6) |  | 1 | 1.83 | 0.5 | 0 | 0.91
| Neck (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 9.66 | 45.0156
| End Cap (22*6) |  | 1 | 1.83 | 0.5 | 0 | 0.91
| Duct (30*14) |  | 2 | 2.5 | 1.16 | 2.66 | 19.4712
| Elbow (30*14) L (1.08+5 /2) |  | 2 | 2.5 | 1.16 | 3.04 | 22.2528
| Duct (30*14) |  | 2 | 2.5 | 1.16 | 12.16 | 89.0112
| Elbow (30*14) L (1.08+5 /2) |  | 2 | 2.5 | 1.16 | 3.04 | 22.2528
| Duct (30*14) |  | 2 | 2.5 | 1.16 | 1.41 | 10.3212
| Reducer (30+14)/2 (38+14)/2 |  | 2 | 1.83 | 2.16 | 1 | 7.98
| Neck (38*14) |  | 2 | 3.16 | 1.16 | 0.5 | 4.32
| Elbow (22*12) L (1.08+3.91 /2) |  | 2 | 1.83 | 1 | 2.49 | 14.0934
| Duct (22*12) |  | 2 | 1.83 | 1 | 2.25 | 12.735
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 4 | 21.28
| Reducer (22+10)/2 (22+8)/2 |  | 2 | 1.33 | 1.25 | 1.5 | 7.74
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 12.16 | 24.0768
| End Cap (8*4) |  | 1 | 0.66 | 0.33 | 0 | 0.22
| This Bill Qty. | Sq.ft |  |  |  |  | 853.2648
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-09
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H | L
SECOND FLOOR
10 | Supply, fabrication and installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connection, access door, wooden frame, transformation, plenums chambers, anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
Drop Neck Fresh & Exhaust Air
EAD | Drop Neck (18*18) | 1 | 2 | 1.5 | 1.5 | 0.33 | 1.98
| Drop Neck (18*18) | 2 | 2 | 1.5 | 1.5 | 0.33 | 1.98
| Drop Neck (15*15) | 3 | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (15*15) | 4 | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (12*12) | 5 | 2 | 1 | 1 | 1 | 4
| Drop Neck (12*12) | 6 | 2 | 1 | 1 | 1 | 4
| Drop Neck (12*12) | 7 | 2 | 1 | 1 | 0.33 | 1.32
| Drop Neck (12*12) | 8 | 2 | 1 | 1 | 0.33 | 1.32
| Drop Neck (12*12) | 9 | 2 | 1 | 1 | 0.33 | 1.32
| Drop Neck (12*12) | 10 | 2 | 1 | 1 | 0.33 | 1.32
| Drop Neck (12*12) | 11 | 2 | 1 | 1 | 0.33 | 1.32
| Drop Neck (9*9) | 12 | 2 | 0.75 | 0.75 | 0.33 | 0.99
| Drop Neck (9*9) | 13 | 2 | 0.75 | 0.75 | 0.33 | 0.99
| Drop Neck (9*9) | 14 | 2 | 0.75 | 0.75 | 0.33 | 0.99
| Drop Neck (9*9) | 15 | 2 | 0.75 | 0.75 | 0.33 | 0.99
FAD | Drop Neck (15*15) | 16 | 2 | 1.25 | 1.25 | 1 | 5
| Drop Neck (15*15) | 17 | 2 | 1.25 | 1.25 | 1 | 5
| Drop Neck (9*9) | 18 | 2 | 0.75 | 0.75 | 1 | 3
| Drop Neck (9*9) | 19 | 2 | 0.75 | 0.75 | 1 | 3
| Drop Neck (15*15) | 20 | 2 | 1.25 | 1.25 | 1 | 5
| Drop Neck (15*15) | 21 | 2 | 1.25 | 1.25 | 1 | 5
| Drop Neck (15*15) | 22 | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (15*15) | 23 | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (15*15) | 24 | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (15*15) | 25 | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (12*12) | 26 | 2 | 1 | 1 | 0.33 | 1.32
| Drop Neck (12*12) | 27 | 2 | 1 | 1 | 0.33 | 1.32
| This Bill Qty. | Sq.ft |  |  |  |  | 61.06
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-08-26
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H | L
SECOND FLOOR
10 | Supply, fabrication and installation of machine made G.I sheet metal duct work of different sections of supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connection, access door, wooden frame, transformation, plenums chambers, anchors supports & hangers, complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant.
Exhaust & Fresh Air Duct
| Duct (26*12) |  | 2 | 2.16 | 1 | 13.5 | 85.32
| Reducer (26+12)/2 (34+14)/2 |  | 2 | 1.58 | 2 | 1 | 7.16
| Neck (34*14) |  | 2 | 2.83 | 1.16 | 0.5 | 3.99
| Duct (26*12) |  | 2 | 2.16 | 1 | 3.41 | 21.5512
| Elbow (26*12) L (.5+2.25 /2) |  | 2 | 2.16 | 1 | 1.37 | 8.6584
| Duct (26*12) |  | 2 | 2.16 | 1 | 2.91 | 18.3912
| Elbow (26*12) L (.5+2.25 /2) |  | 2 | 2.16 | 1 | 1.37 | 8.6584
| Reducer (26+12)/2 (26+10)/2 |  | 2 | 1.58 | 1.5 | 1.5 | 9.24
| Duct (26*10) |  | 2 | 2.16 | 0.83 | 26.16 | 156.4368
| End Cap (26*10) |  | 1 | 2.16 | 0.83 | 0 | 1.8
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 4 | 17.28
| Neck (14*4) |  | 2 | 1.16 | 0.33 | 0.5 | 1.49
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 2.83 | 8.4334
| End Cap (14*4) |  | 1 | 1.16 | 0.33 | 0 | 0.38
| Duct (12*6) |  | 2 | 1 | 0.5 | 29.25 | 87.75
| End Cap (12*6) |  | 1 | 1 | 0.5 | 0 | 0.5
| Neck (12*4) |  | 2 | 1 | 0.33 | 0.5 | 1.33
| Duct (12*4) |  | 2 | 1 | 0.33 | 18.75 | 49.875
| End Cap (12*4) |  | 1 | 1 | 0.33 | 0 | 0.33
| Neck (12*4) |  | 2 | 1 | 0.33 | 0.5 | 1.33
| Duct (12*4) |  | 2 | 1 | 0.33 | 2.16 | 5.7456
| End Cap (12*4) |  | 1 | 1 | 0.33 | 0 | 0.33
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 9.75 | 19.305
| Elbow (8*4) L (.5+1.58 /2) |  | 2 | 0.66 | 0.33 | 1.04 | 2.0592
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 3.16 | 6.2568
| End Cap (8*4) |  | 1 | 0.66 | 0.33 | 0 | 0.22
| Duct (22*12) |  | 2 | 1.83 | 1 | 1.33 | 7.5278
| Elbow (22*12) L (1.08+3.91 /2) |  | 2 | 1.83 | 1 | 2.49 | 14.0934
| Duct (22*12) |  | 2 | 1.83 | 1 | 3.08 | 17.4328
| Elbow (22*12) L (1.08+3.91 /2) |  | 2 | 1.83 | 1 | 2.49 | 14.0934
| Duct (22*12) |  | 2 | 1.83 | 1 | 1 | 5.66
| Reducer (22+12)/2 (28+14)/2 |  | 2 | 1.41 | 1.75 | 1 | 6.32
| Neck (28*14) |  | 2 | 2.33 | 1.16 | 0.5 | 3.49
| Duct (22*12) |  | 2 | 1.83 | 1 | 1.5 | 8.49
| Neck (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 20.75 | 103.335
| Reducer (22+8)/2 (18+8)/2 |  | 2 | 1.25 | 1.08 | 2.5 | 11.65
| Duct (28*12) |  | 2 | 2.33 | 1 | 5.75 | 38.295
| Elbow (28*12) L (1.08+4.75 /2) |  | 2 | 2.33 | 1 | 2.91 | 19.3806
| Duct (28*12) |  | 2 | 2.33 | 1 | 4.58 | 30.5028
| Elbow (28*12) L (1.08+4.75 /2) |  | 2 | 2.33 | 1 | 2.91 | 19.3806
| Duct (28*12) |  | 2 | 2.33 | 1 | 4.08 | 27.1728
| Reducer (28+12)/2 (42+14)/2 |  | 2 | 1.66 | 2.33 | 1 | 7.98
| Neck (42*14) |  | 2 | 3.5 | 1.16 | 0.5 | 4.66
| Duct (28*12) |  | 2 | 2.33 | 1 | 7.08 | 47.1528
| Elbow (28*12) L (1.08+4.75 /2) |  | 2 | 2.33 | 1 | 2.91 | 19.3806
| Duct (28*12) |  | 2 | 2.33 | 1 | 0.5 | 3.33
| Reducer (28+12)/2 (18+12)/2 |  | 2 | 1.66 | 1.25 | 1 | 5.82
| Offset (18*12) |  | 2 | 1.5 | 1 | 1 | 5
| Duct (18*12) |  | 2 | 1.5 | 1 | 2.83 | 14.15
| Offset (18*12) |  | 2 | 1.5 | 1 | 1 | 5
| Duct (18*12) |  | 2 | 1.5 | 1 | 8.5 | 42.5
| Reducer (18+12)/2 (18+8)/2 |  | 2 | 1.25 | 1.08 | 1 | 4.66
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 1 | 4.32
| Reducer (26+8)/2 (18+8)/2 |  | 2 | 1.41 | 1.08 | 0.83 | 4.1334
| Neck (20*10) |  | 2 | 1.66 | 0.83 | 0.5 | 2.49
| Duct (20*10) |  | 2 | 1.66 | 0.83 | 8.58 | 42.7284
| Reducer (20+10)/2 (14+10)/2 |  | 2 | 1.25 | 1 | 1.5 | 6.75
| Duct (14*10) |  | 2 | 1.16 | 0.83 | 4.75 | 18.905
| Reducer (14+10)/2 (14+8)/2 |  | 2 | 1 | 0.91 | 1.16 | 4.4312
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 4.33 | 15.7612
| Elbow (14*8) L (1.08+2.91 /2) |  | 2 | 1.16 | 0.66 | 1.99 | 7.2436
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 11.25 | 40.95
| End Cap (14*8) |  | 1 | 1.16 | 0.66 | 0 | 0.78
| Neck (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 8.5 | 22.61
| End Cap (10*6) |  | 1 | 0.83 | 0.5 | 0 | 0.41
| Neck (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 4.91 | 13.0606
| End Cap (10*6) |  | 1 | 0.83 | 0.5 | 0 | 0.41
| Neck (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 3.91 | 15.64
| End Cap (18*6) |  | 1 | 1.5 | 0.5 | 0 | 0.75
| Neck (10*8) |  | 2 | 0.83 | 0.66 | 0.5 | 1.49
| Duct (10*8) |  | 2 | 0.83 | 0.66 | 0.58 | 1.7284
| Duct (26*12) |  | 2 | 2.16 | 1 | 1.16 | 7.3312
| Elbow (26*12) L (1.08+4.41 /2) |  | 2 | 2.16 | 1 | 2.75 | 17.38
| Duct (26*12) |  | 2 | 2.16 | 1 | 7.75 | 48.98
| Elbow (26*12) L (1.08+4.41 /2) |  | 2 | 2.16 | 1 | 2.75 | 17.38
| Duct (26*12) |  | 2 | 2.16 | 1 | 1 | 6.32
| Reducer (26+12)/2 (38+14)/2 |  | 2 | 1.58 | 2.16 | 1 | 7.48
| Neck (38*14) |  | 2 | 3.16 | 1.16 | 0.5 | 4.32
| Offset (18*8) |  | 2 | 1.5 | 0.66 | 1 | 4.32
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 1 | 4.32
| Offset (18*8) |  | 2 | 1.5 | 0.66 | 1 | 4.32
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 7.41 | 32.0112
| Reducer (18+8)/2 (18+6)/2 |  | 2 | 1.08 | 1 | 1.33 | 5.5328
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 8.16 | 32.64
| End Cap (18*6) |  | 1 | 1.5 | 0.5 | 0 | 0.75
| Neck (24*10) |  | 2 | 2 | 0.83 | 0.5 | 2.83
| Duct (24*10) |  | 2 | 2 | 0.83 | 10.91 | 61.7506
| Offset (24*10) |  | 2 | 2 | 0.83 | 1.5 | 8.49
| Reducer (24+10)/2 (18+10)/2 |  | 2 | 1.41 | 1.16 | 1.5 | 7.71
| Duct (18*10) |  | 2 | 1.5 | 0.83 | 4.41 | 20.5506
| Elbow (18*10) L (.41+1.58 /2) |  | 2 | 1.5 | 0.83 | 0.99 | 4.6134
| Duct (18*10) |  | 2 | 1.5 | 0.83 | 4.41 | 20.5506
| Elbow (18*10) L (.41+1.58 /2) |  | 2 | 1.5 | 0.83 | 0.99 | 4.6134
| Duct (18*10) |  | 2 | 1.5 | 0.83 | 1 | 4.66
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 4 | 17.28
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 4 | 17.28
| Reducer (18+8)/2 (18+6)/2 |  | 2 | 1.08 | 1 | 2.5 | 10.4
| This Bill Qty. | Sq.ft |  |  |  |  | 1596.8242
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-09
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H | L
GROUND FLOOR
11 | Supply and installation of rubber foam (XLPE) insulation adhesive with aluminum facing 12mm thick complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Exhaust & Fresh Air Duct (Insulation)
| Elbow (26*9) L (1.33+4.75 /2) |  | 2 | 2.16 | 0.75 | 3.04 | 17.6928
| Round Duct (13") Dia |  | 1 | 2.16 | 1.08 | 2.33 | 7.9141
| Elbow (13*14) L (.41+1.58 /2) |  | 2 | 1.08 | 1.16 | 0.99 | 4.4352
| Duct (13*14) |  | 2 | 1.08 | 1.16 | 0.5 | 2.24
| Reducer (13+14)/2 (16+14)/2 |  | 2 | 1.125 | 1.25 | 0.5 | 2.375
| Duct (16*14) |  | 2 | 1.33 | 1.16 | 1 | 4.98
| Round Duct (13") Dia |  | 1 | 1.5 | 1.08 | 2.33 | 7.9141
| Plenum Box (36*36) |  | 2 | 3 | 3 | 3 | 36
| Neck (18*12) |  | 2 | 1.5 | 1 | 0.58 | 2.9
| Elbow (18*12) L (.75+3.16 /2) |  | 2 | 1.5 | 1 | 1.95 | 9.75
| Duct (18*12) |  | 2 | 1.5 | 1 | 6.75 | 33.75
| Round Drop Neck (8") Dia |  | 3 | 0.66 | 0.66 | 2.16 | 13.4505
| Drop Neck (20*5) |  | 2 | 1.66 | 0.41 | 3.33 | 13.7862
| Drop Neck (20*5) |  | 2 | 1.66 | 0.41 | 3.33 | 13.7862
| This Bill Qty. | Sq.ft |  |  |  |  | 170.9741
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-08-28
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H | L
GROUND FLOOR
11 | Supply and installation of rubber foam (XLPE) insulation adhesive with aluminum facing 12mm thick complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
(Drop Neck) Exhaust & Fresh Air Duct
| Round Drop Neck (6") Dia |  | 16 | 0.5 | 0.5 | 0.83 | 20.8828
| Neck (9*9) |  | 2 | 0.75 | 0.75 | 1 | 3
| Neck (9*9) |  | 2 | 0.75 | 0.75 | 1 | 3
| Neck (9*9) |  | 2 | 0.75 | 0.75 | 1 | 3
| Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Neck (9*9) |  | 2 | 0.75 | 0.75 | 1 | 3
| Neck (12*12) |  | 2 | 1 | 1 | 1 | 4
| Neck (12*12) |  | 2 | 1 | 1 | 1 | 4
| Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Neck (12*12) |  | 2 | 1 | 1 | 1 | 4
| Neck (12*12) |  | 2 | 1 | 1 | 1 | 4
| Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Neck (6*6) |  | 2 | 0.5 | 0.5 | 1 | 2
| Neck (6*6) |  | 2 | 0.5 | 0.5 | 1 | 2
| Neck (6*6) |  | 2 | 0.5 | 0.5 | 1 | 2
| Neck (6*6) |  | 2 | 0.5 | 0.5 | 1 | 2
| Neck (12*12) |  | 2 | 1 | 1 | 1 | 4
| Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| This Bill Qty. | Sq.ft |  |  |  |  | 90.8828
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-08-11
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H | L
GROUND FLOOR
11 | Supply and installation of rubber foam (XLPE) insulation adhesive with aluminum facing 12mm thick complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Exhaust & Fresh Air Duct (Cafeterea)
| End Cap (16*14) |  | 2 | 1.33 | 1.16 | 0 | 1.56
| Duct (16*14) |  | 2 | 1.33 | 1.16 | 8 | 39.84
| Elbow (16*14) L (3.16+1.08 /2) |  | 2 | 1.33 | 1.16 | 2.12 | 10.5576
| Duct (16*14) |  | 2 | 1.33 | 1.16 | 1.91 | 9.5118
| Elbow (16*14) L (1.41+.41 /2) |  | 2 | 1.33 | 1.16 | 0.91 | 4.5318
| Offset (16*14) |  | 2 | 1.33 | 1.16 | 1.33 | 6.6234
| Elbow (16*14) L (1.41+.41 /2) |  | 2 | 1.33 | 1.16 | 0.91 | 4.5318
| Duct (16*14) |  | 2 | 1.33 | 1.16 | 2.75 | 13.695
| Elbow (26*8) L (4.41+1.16 /2) |  | 2 | 2.16 | 0.66 | 2.78 | 15.6792
| Offset (16*14) |  | 2 | 1.33 | 1.16 | 1 | 4.98
| Offset (26*8) |  | 2 | 2.16 | 0.66 | 2.5 | 14.1
| Duct (18*12) |  | 2 | 1.5 | 1 | 19.33 | 96.65
| Elbow (18*12) L (3.41+1.08 /2) |  | 2 | 1.5 | 1 | 2.24 | 11.2
| Duct (18*12) |  | 2 | 1.5 | 1 | 10.91 | 54.55
| End Cap (18*12) |  | 2 | 1.5 | 1 | 0 | 1.5
| This Bill Qty. | Sq.ft |  |  |  |  | 289.5106
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-09
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H | L
FIRST FLOOR
11 | Supply and installation of rubber foam (XLPE) insulation adhesive with aluminum facing 12mm thick complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Drop Neck Fresh & Exhaust Air (Insulation)
EAD | Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (6*6) |  | 1 | 0.5 | 0.5 | 0.33 | 0.33
| Drop Neck (6*6) |  | 1 | 0.5 | 0.5 | 0.33 | 0.33
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 0.33 | 1.98
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 0.33 | 1.98
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 0.33 | 1.98
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 0.33 | 1.98
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 1 | 6
FAD | Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Drop Neck (6*6) |  | 1 | 0.5 | 0.5 | 0.33 | 0.33
| Drop Neck (6*6) |  | 1 | 0.5 | 0.5 | 0.33 | 0.33
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 0.33 | 1.98
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 0.33 | 1.98
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 0.33 | 1.98
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 0.33 | 1.98
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 0.33 | 1.98
| This Bill Qty. | Sq.ft |  |  |  |  | 55.04
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-08-26
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H | L
FIRST FLOOR
11 | Supply and installation of rubber foam (XLPE) insulation adhesive with aluminum facing 12mm thick complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Exhaust & Fresh Air Duct
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 2.58 | 13.7256
| Elbow (22*10) L (1.16+4 /2) |  | 2 | 1.83 | 0.83 | 2.58 | 13.7256
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 2.91 | 15.4812
| Elbow (22*10) L (1.16+4 /2) |  | 2 | 1.83 | 0.83 | 2.58 | 13.7256
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 2.25 | 11.97
| Reducer (22+10)/2 (36+14)/2 |  | 2 | 1.33 | 2.08 | 1 | 6.82
| Neck (36*14) |  | 2 | 3 | 1.16 | 0.5 | 4.16
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 8.91 | 47.4012
| Duct (26*14) |  | 2 | 2.16 | 1.16 | 4.08 | 27.0912
| Elbow (26*14) L (.5+2.25 /2) |  | 2 | 2.16 | 1.16 | 1.37 | 9.0968
| Duct (26*14) |  | 2 | 2.16 | 1.16 | 1.16 | 7.7024
| Elbow (26*14) L (.5+2.25 /2) |  | 2 | 2.16 | 1.16 | 1.37 | 9.0968
| Duct (26*14) |  | 2 | 2.16 | 1.16 | 0.58 | 3.8512
| Reducer (26+14)/2 (28+14)/2 |  | 2 | 1.66 | 1.75 | 1 | 6.82
| Neck (28*14) |  | 2 | 2.33 | 1.16 | 0.5 | 3.49
| Duct (26*12) |  | 2 | 2.16 | 1 | 2.33 | 14.7256
| Elbow (26*12) L (1.08+4.41 /2) |  | 2 | 2.16 | 1 | 2.75 | 17.38
| Duct (26*12) |  | 2 | 2.16 | 1 | 7.83 | 49.4856
| Elbow (26*12) L (1.08+4.41 /2) |  | 2 | 2.16 | 1 | 2.75 | 17.38
| Duct (26*12) |  | 2 | 2.16 | 1 | 2.16 | 13.6512
| Reducer (26+12)/2 (38+14)/2 |  | 2 | 1.58 | 2.16 | 1 | 7.48
| Neck (38*14) |  | 2 | 3.16 | 1.16 | 0.5 | 4.32
| Duct (26*12) |  | 2 | 2.16 | 1 | 5.33 | 33.6856
| Elbow (26*12) L (.41+2.08 /2) |  | 2 | 2.16 | 1 | 1.24 | 7.8368
| Duct (26*12) |  | 2 | 2.16 | 1 | 1.75 | 11.06
| Elbow (26*12) L (.41+2.08 /2) |  | 2 | 2.16 | 1 | 1.24 | 7.8368
| Duct (26*12) |  | 2 | 2.16 | 1 | 13.5 | 85.32
| End Cap (26*12) |  | 1 | 2.16 | 1 | 0 | 2.16
| Neck (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 8 | 37.28
| End Cap (22*6) |  | 1 | 1.83 | 0.5 | 0 | 0.91
| Neck (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 8.16 | 38.0256
| End Cap (22*6) |  | 1 | 1.83 | 0.5 | 0 | 0.91
| Neck (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 9.66 | 45.0156
| End Cap (22*6) |  | 1 | 1.83 | 0.5 | 0 | 0.91
| Duct (30*14) |  | 2 | 2.5 | 1.16 | 2.66 | 19.4712
| Elbow (30*14) L (1.08+5 /2) |  | 2 | 2.5 | 1.16 | 3.04 | 22.2528
| Duct (30*14) |  | 2 | 2.5 | 1.16 | 12.16 | 89.0112
| Elbow (30*14) L (1.08+5 /2) |  | 2 | 2.5 | 1.16 | 3.04 | 22.2528
| Duct (30*14) |  | 2 | 2.5 | 1.16 | 1.41 | 10.3212
| Reducer (30+14)/2 (38+14)/2 |  | 2 | 1.83 | 2.16 | 1 | 7.98
| Neck (38*14) |  | 2 | 3.16 | 1.16 | 0.5 | 4.32
| Elbow (22*12) L (1.08+3.91 /2) |  | 2 | 1.83 | 1 | 2.49 | 14.0934
| Duct (22*12) |  | 2 | 1.83 | 1 | 2.25 | 12.735
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 4 | 21.28
| Reducer (22+10)/2 (22+8)/2 |  | 2 | 1.33 | 1.25 | 1.5 | 7.74
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 12.16 | 24.0768
| End Cap (8*4) |  | 1 | 0.66 | 0.33 | 0 | 0.22
| This Bill Qty. | Sq.ft |  |  |  |  | 853.2648
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-25
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H | L
FIRST FLOOR
11 | Supply and installation of rubber foam (XLPE) insulation adhesive with aluminum facing 12mm thick complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Exhaust & Fresh Air Duct (Insulation Pocket)
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*4) |  | 2 | 1.83 | 0.33 | 0.5 | 2.16
| Duct (22*4) |  | 2 | 1.83 | 0.33 | 0.5 | 2.16
| Duct (22*4) |  | 2 | 1.83 | 0.33 | 0.5 | 2.16
| Duct (22*4) |  | 2 | 1.83 | 0.33 | 0.5 | 2.16
| Duct (22*4) |  | 2 | 1.83 | 0.33 | 0.5 | 2.16
| Duct (22*4) |  | 2 | 1.83 | 0.33 | 0.5 | 2.16
| Duct (22*4) |  | 2 | 1.83 | 0.33 | 0.5 | 2.16
| Duct (22*4) |  | 2 | 1.83 | 0.33 | 0.5 | 2.16
| Duct (22*4) |  | 2 | 1.83 | 0.33 | 0.5 | 2.16
| Duct (22*4) |  | 2 | 1.83 | 0.33 | 0.5 | 2.16
| Duct (22*4) |  | 2 | 1.83 | 0.33 | 0.5 | 2.16
| Duct (22*4) |  | 2 | 1.83 | 0.33 | 0.5 | 2.16
| Duct (22*4) |  | 2 | 1.83 | 0.33 | 0.5 | 2.16
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 0.5 | 1.82
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 0.5 | 1.82
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 0.5 | 1.82
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 0.5 | 1.83
| Duct (16*6) |  | 2 | 1.33 | 0.5 | 0.5 | 1.83
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 0.5 | 1.66
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 0.5 | 1.66
| Duct (22*4) |  | 2 | 1.83 | 0.33 | 0.5 | 2.16
| Duct (14*6) |  | 2 | 1.16 | 0.5 | 0.5 | 1.66
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 0.5 | 1.16
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 0.5 | 1.16
| Duct (6*6) |  | 2 | 0.5 | 0.5 | 0.5 | 1
| Duct (6*6) |  | 2 | 0.5 | 0.5 | 0.5 | 1
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (26*12) |  | 2 | 2.16 | 1 | 0.5 | 3.16
| Duct (26*12) |  | 2 | 2.16 | 1 | 0.5 | 3.16
| Duct (26*12) |  | 2 | 2.16 | 1 | 0.5 | 3.16
| Duct (26*12) |  | 2 | 2.16 | 1 | 0.5 | 3.16
| Duct (26*12) |  | 2 | 2.16 | 1 | 0.5 | 3.16
| Duct (26*12) |  | 2 | 2.16 | 1 | 0.5 | 3.16
| Duct (26*12) |  | 2 | 2.16 | 1 | 0.5 | 3.16
| Duct (26*12) |  | 2 | 2.16 | 1 | 0.5 | 3.16
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (26*10) |  | 2 | 2.16 | 0.83 | 0.5 | 2.99
| Duct (26*10) |  | 2 | 2.16 | 0.83 | 0.5 | 2.99
| Duct (26*10) |  | 2 | 2.16 | 0.83 | 0.5 | 2.99
| Duct (26*10) |  | 2 | 2.16 | 0.83 | 0.5 | 2.99
| Duct (26*10) |  | 2 | 2.16 | 0.83 | 0.5 | 2.99
| Duct (26*10) |  | 2 | 2.16 | 0.83 | 0.5 | 2.99
| Duct (26*10) |  | 2 | 2.16 | 0.83 | 0.5 | 2.99
| Duct (26*14) |  | 2 | 2.16 | 1.16 | 0.5 | 3.32
| Duct (26*14) |  | 2 | 2.16 | 1.16 | 0.5 | 3.32
| Duct (26*14) |  | 2 | 2.16 | 1.16 | 0.5 | 3.32
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (22*12) |  | 2 | 1.83 | 1 | 0.5 | 2.83
| Duct (22*12) |  | 2 | 1.83 | 1 | 0.5 | 2.83
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*10) |  | 2 | 1.83 | 0.83 | 0.5 | 2.66
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*6) |  | 2 | 1.83 | 0.5 | 0.5 | 2.33
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| This Bill Qty. | Sq.ft |  |  |  |  | 342.98
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-09
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H | L
SECOND FLOOR
11 | Supply and installation of rubber foam (XLPE) insulation adhesive with aluminum facing 12mm thick complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Drop Neck Fresh & Exhaust Air (Insulation)
EAD | Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 0.33 | 1.98
| Drop Neck (18*18) |  | 2 | 1.5 | 1.5 | 0.33 | 1.98
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (12*12) |  | 2 | 1 | 1 | 1 | 4
| Drop Neck (12*12) |  | 2 | 1 | 1 | 1 | 4
| Drop Neck (12*12) |  | 2 | 1 | 1 | 0.33 | 1.32
| Drop Neck (12*12) |  | 2 | 1 | 1 | 0.33 | 1.32
| Drop Neck (12*12) |  | 2 | 1 | 1 | 0.33 | 1.32
| Drop Neck (12*12) |  | 2 | 1 | 1 | 0.33 | 1.32
| Drop Neck (12*12) |  | 2 | 1 | 1 | 0.33 | 1.32
| Drop Neck (9*9) |  | 2 | 0.75 | 0.75 | 0.33 | 0.99
| Drop Neck (9*9) |  | 2 | 0.75 | 0.75 | 0.33 | 0.99
| Drop Neck (9*9) |  | 2 | 0.75 | 0.75 | 0.33 | 0.99
| Drop Neck (9*9) |  | 2 | 0.75 | 0.75 | 0.33 | 0.99
FAD | Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Drop Neck (9*9) |  | 2 | 0.75 | 0.75 | 1 | 3
| Drop Neck (9*9) |  | 2 | 0.75 | 0.75 | 1 | 3
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 1 | 5
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (15*15) |  | 2 | 1.25 | 1.25 | 0.33 | 1.65
| Drop Neck (12*12) |  | 2 | 1 | 1 | 0.33 | 1.32
| Drop Neck (12*12) |  | 2 | 1 | 1 | 0.33 | 1.32
| This Bill Qty. | Sq.ft |  |  |  |  | 61.06
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-09
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H | L
(Round Drop Neck Disc Valves) Exhaust Air Duct
11 | Supply and installation of rubber foam (XLPE) insulation adhesive with aluminum facing 12mm thick complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
FIRST FLOOR
| Round Drop Neck (6") Dia |  | 2 | 0.5 | 0.5 | 1 | 3.145
SECOND FLOOR
| Round Drop Neck (6") Dia |  | 16 | 0.5 | 0.5 | 1 | 25.16
| This Bill Qty. | Sq.ft |  |  |  |  | 28.305
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-08-26
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H | L
SECOND FLOOR
11 | Supply and installation of rubber foam (XLPE) insulation adhesive with aluminum facing 12mm thick complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Exhaust & Fresh Air Duct
| Duct (26*12) |  | 2 | 2.16 | 1 | 13.5 | 85.32
| Reducer (26+12)/2 (34+14)/2 |  | 2 | 1.58 | 2 | 1 | 7.16
| Neck (34*14) |  | 2 | 2.83 | 1.16 | 0.5 | 3.99
| Duct (26*12) |  | 2 | 2.16 | 1 | 3.41 | 21.5512
| Elbow (26*12) L (.5+2.25 /2) |  | 2 | 2.16 | 1 | 1.37 | 8.6584
| Duct (26*12) |  | 2 | 2.16 | 1 | 2.91 | 18.3912
| Elbow (26*12) L (.5+2.25 /2) |  | 2 | 2.16 | 1 | 1.37 | 8.6584
| Reducer (26+12)/2 (26+10)/2 |  | 2 | 1.58 | 1.5 | 1.5 | 9.24
| Duct (26*10) |  | 2 | 2.16 | 0.83 | 26.16 | 156.4368
| End Cap (26*10) |  | 1 | 2.16 | 0.83 | 0 | 1.8
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 4 | 17.28
| Neck (14*4) |  | 2 | 1.16 | 0.33 | 0.5 | 1.49
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 2.83 | 8.4334
| End Cap (14*4) |  | 1 | 1.16 | 0.33 | 0 | 0.38
| Duct (12*6) |  | 2 | 1 | 0.5 | 29.25 | 87.75
| End Cap (12*6) |  | 1 | 1 | 0.5 | 0 | 0.5
| Neck (12*4) |  | 2 | 1 | 0.33 | 0.5 | 1.33
| Duct (12*4) |  | 2 | 1 | 0.33 | 18.75 | 49.875
| End Cap (12*4) |  | 1 | 1 | 0.33 | 0 | 0.33
| Neck (12*4) |  | 2 | 1 | 0.33 | 0.5 | 1.33
| Duct (12*4) |  | 2 | 1 | 0.33 | 2.16 | 5.7456
| End Cap (12*4) |  | 1 | 1 | 0.33 | 0 | 0.33
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 9.75 | 19.305
| Elbow (8*4) L (.5+1.58 /2) |  | 2 | 0.66 | 0.33 | 1.04 | 2.0592
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 3.16 | 6.2568
| End Cap (8*4) |  | 1 | 0.66 | 0.33 | 0 | 0.22
| Duct (22*12) |  | 2 | 1.83 | 1 | 1.33 | 7.5278
| Elbow (22*12) L (1.08+3.91 /2) |  | 2 | 1.83 | 1 | 2.49 | 14.0934
| Duct (22*12) |  | 2 | 1.83 | 1 | 3.08 | 17.4328
| Elbow (22*12) L (1.08+3.91 /2) |  | 2 | 1.83 | 1 | 2.49 | 14.0934
| Duct (22*12) |  | 2 | 1.83 | 1 | 1 | 5.66
| Reducer (22+12)/2 (28+14)/2 |  | 2 | 1.41 | 1.75 | 1 | 6.32
| Neck (28*14) |  | 2 | 2.33 | 1.16 | 0.5 | 3.49
| Duct (22*12) |  | 2 | 1.83 | 1 | 1.5 | 8.49
| Neck (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 20.75 | 103.335
| Reducer (22+8)/2 (18+8)/2 |  | 2 | 1.25 | 1.08 | 2.5 | 11.65
| Duct (28*12) |  | 2 | 2.33 | 1 | 5.75 | 38.295
| Elbow (28*12) L (1.08+4.75 /2) |  | 2 | 2.33 | 1 | 2.91 | 19.3806
| Duct (28*12) |  | 2 | 2.33 | 1 | 4.58 | 30.5028
| Elbow (28*12) L (1.08+4.75 /2) |  | 2 | 2.33 | 1 | 2.91 | 19.3806
| Duct (28*12) |  | 2 | 2.33 | 1 | 4.08 | 27.1728
| Reducer (28+12)/2 (42+14)/2 |  | 2 | 1.66 | 2.33 | 1 | 7.98
| Neck (42*14) |  | 2 | 3.5 | 1.16 | 0.5 | 4.66
| Duct (28*12) |  | 2 | 2.33 | 1 | 7.08 | 47.1528
| Elbow (28*12) L (1.08+4.75 /2) |  | 2 | 2.33 | 1 | 2.91 | 19.3806
| Duct (28*12) |  | 2 | 2.33 | 1 | 0.5 | 3.33
| Reducer (28+12)/2 (18+12)/2 |  | 2 | 1.66 | 1.25 | 1 | 5.82
| Offset (18*12) |  | 2 | 1.5 | 1 | 1 | 5
| Duct (18*12) |  | 2 | 1.5 | 1 | 2.83 | 14.15
| Offset (18*12) |  | 2 | 1.5 | 1 | 1 | 5
| Duct (18*12) |  | 2 | 1.5 | 1 | 8.5 | 42.5
| Reducer (18+12)/2 (18+8)/2 |  | 2 | 1.25 | 1.08 | 1 | 4.66
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 1 | 4.32
| Reducer (26+8)/2 (18+8)/2 |  | 2 | 1.41 | 1.08 | 0.83 | 4.1334
| Neck (20*10) |  | 2 | 1.66 | 0.83 | 0.5 | 2.49
| Duct (20*10) |  | 2 | 1.66 | 0.83 | 8.58 | 42.7284
| Reducer (20+10)/2 (14+10)/2 |  | 2 | 1.25 | 1 | 1.5 | 6.75
| Duct (14*10) |  | 2 | 1.16 | 0.83 | 4.75 | 18.905
| Reducer (14+10)/2 (14+8)/2 |  | 2 | 1 | 0.91 | 1.16 | 4.4312
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 4.33 | 15.7612
| Elbow (14*8) L (1.08+2.91 /2) |  | 2 | 1.16 | 0.66 | 1.99 | 7.2436
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 11.25 | 40.95
| End Cap (14*8) |  | 1 | 1.16 | 0.66 | 0 | 0.78
| Neck (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 8.5 | 22.61
| End Cap (10*6) |  | 1 | 0.83 | 0.5 | 0 | 0.41
| Neck (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 4.91 | 13.0606
| End Cap (10*6) |  | 1 | 0.83 | 0.5 | 0 | 0.41
| Neck (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 3.91 | 15.64
| End Cap (18*6) |  | 1 | 1.5 | 0.5 | 0 | 0.75
| Neck (10*8) |  | 2 | 0.83 | 0.66 | 0.5 | 1.49
| Duct (10*8) |  | 2 | 0.83 | 0.66 | 0.58 | 1.7284
| Duct (26*12) |  | 2 | 2.16 | 1 | 1.16 | 7.3312
| Elbow (26*12) L (1.08+4.41 /2) |  | 2 | 2.16 | 1 | 2.75 | 17.38
| Duct (26*12) |  | 2 | 2.16 | 1 | 7.75 | 48.98
| Elbow (26*12) L (1.08+4.41 /2) |  | 2 | 2.16 | 1 | 2.75 | 17.38
| Duct (26*12) |  | 2 | 2.16 | 1 | 1 | 6.32
| Reducer (26+12)/2 (38+14)/2 |  | 2 | 1.58 | 2.16 | 1 | 7.48
| Neck (38*14) |  | 2 | 3.16 | 1.16 | 0.5 | 4.32
| Offset (18*8) |  | 2 | 1.5 | 0.66 | 1 | 4.32
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 1 | 4.32
| Offset (18*8) |  | 2 | 1.5 | 0.66 | 1 | 4.32
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 7.41 | 32.0112
| Reducer (18+8)/2 (18+6)/2 |  | 2 | 1.08 | 1 | 1.33 | 5.5328
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 8.16 | 32.64
| End Cap (18*6) |  | 1 | 1.5 | 0.5 | 0 | 0.75
| Neck (24*10) |  | 2 | 2 | 0.83 | 0.5 | 2.83
| Duct (24*10) |  | 2 | 2 | 0.83 | 10.91 | 61.7506
| Offset (24*10) |  | 2 | 2 | 0.83 | 1.5 | 8.49
| Reducer (24+10)/2 (18+10)/2 |  | 2 | 1.41 | 1.16 | 1.5 | 7.71
| Duct (18*10) |  | 2 | 1.5 | 0.83 | 4.41 | 20.5506
| Elbow (18*10) L (.41+1.58 /2) |  | 2 | 1.5 | 0.83 | 0.99 | 4.6134
| Duct (18*10) |  | 2 | 1.5 | 0.83 | 4.41 | 20.5506
| Elbow (18*10) L (.41+1.58 /2) |  | 2 | 1.5 | 0.83 | 0.99 | 4.6134
| Duct (18*10) |  | 2 | 1.5 | 0.83 | 1 | 4.66
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 4 | 17.28
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 4 | 17.28
| Reducer (18+8)/2 (18+6)/2 |  | 2 | 1.08 | 1 | 2.5 | 10.4
| This Bill Qty. | Sq.ft |  |  |  |  | 1596.8242
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-01
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H | L
SECOND FLOOR
11 | Supply and installation of rubber foam (XLPE) insulation adhesive with aluminum facing 12mm thick complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Exhaust & Fresh Air Duct
| Duct (14*10) |  | 2 | 1.16 | 0.83 | 20 | 79.6
| End Cap (14*10) |  | 2 | 1.16 | 0.83 | 0 | 0.97
| Neck (12*4) |  | 2 | 1 | 0.33 | 0.5 | 1.33
| Duct (12*4) |  | 2 | 1 | 0.33 | 0.33 | 0.8778
| Elbow (12*4) L (2.33+.75 /2) |  | 2 | 1 | 0.33 | 1.54 | 4.0964
| Duct (12*4) |  | 2 | 1 | 0.33 | 3.83 | 10.1878
| Elbow (12*4) L (2.33+.75 /2) |  | 2 | 1 | 0.33 | 1.54 | 4.0964
| Duct (12*4) |  | 2 | 1 | 0.33 | 2.33 | 6.1978
| End Cap (12*4) |  | 2 | 1 | 0.33 | 0 | 0.33
| Neck (8*6) |  | 2 | 0.66 | 0.5 | 0.5 | 1.16
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 5.91 | 13.7112
| End Cap (8*6) |  | 2 | 0.66 | 0.5 | 0 | 0.33
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 7.83 | 15.5034
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 4.58 | 9.0684
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (12*10) |  | 2 | 1 | 0.83 | 0.5 | 1.83
| Duct (12*10) |  | 2 | 1 | 0.83 | 8.58 | 31.4028
| Reducer (12+10)/2 (10+10)/2 |  | 2 | 0.91 | 0.83 | 1 | 3.48
| Duct (10*10) |  | 2 | 0.83 | 0.83 | 9 | 29.88
| Elbow (10*10) L (2.08+.75 /2) |  | 2 | 0.83 | 0.83 | 1.41 | 4.6812
| Duct (10*10) |  | 2 | 0.83 | 0.83 | 34.91 | 115.9012
| Elbow (10*10) L (2.08+.75 /2) |  | 2 | 0.83 | 0.83 | 1.41 | 4.6812
| Duct (10*10) |  | 2 | 0.83 | 0.83 | 7.58 | 25.1656
| Reducer (10+10)/2 (8+8)/2 |  | 2 | 0.83 | 0.66 | 1 | 2.98
| Duct (8*8) |  | 2 | 0.66 | 0.66 | 8.16 | 21.5424
| Reducer (8+8)/2 (8+4)/2 |  | 2 | 0.66 | 0.5 | 1 | 2.32
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 5.5 | 10.89
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*6) |  | 2 | 0.66 | 0.5 | 0.5 | 1.16
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 4.66 | 10.8112
| Reducer (8+6)/2 (8+4)/2 |  | 2 | 0.58 | 0.5 | 1 | 2.16
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 8.91 | 17.6418
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*6) |  | 2 | 0.66 | 0.5 | 0.5 | 1.16
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 6.33 | 14.6856
| Reducer (8+6)/2 (8+4)/2 |  | 2 | 0.58 | 0.5 | 1 | 2.16
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 6.66 | 13.1868
| End Cap (8*4) |  | 2 | 0.66 | 0.33 | 0 | 0.22
| Neck (8*6) |  | 2 | 0.66 | 0.5 | 0.5 | 1.16
| Duct (8*6) |  | 2 | 0.66 | 0.5 | 0.83 | 1.9256
| End Cap (8*6) |  | 2 | 0.66 | 0.5 | 0 | 0.33
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 19.33 | 70.3612
| Elbow (14*8) L (1.41+.5 /2) |  | 2 | 1.16 | 0.66 | 0.95 | 3.458
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 1 | 3.64
| Elbow (14*8) L (1.41+.5 /2) |  | 2 | 1.16 | 0.66 | 0.95 | 3.458
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 3.08 | 11.2112
| Elbow (14*8) L (1.41+.5 /2) |  | 2 | 1.16 | 0.66 | 0.95 | 3.458
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 1 | 3.64
| Elbow (14*8) L (1.41+.5 /2) |  | 2 | 1.16 | 0.66 | 0.95 | 3.458
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 6.5 | 23.66
| Reducer (14+8)/2 (14+4)/2 |  | 2 | 0.91 | 0.75 | 1 | 3.32
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 9.33 | 27.8034
| End Cap (14*4) |  | 2 | 1.16 | 0.33 | 0 | 0.89
| This Bill Qty. | Sq.ft |  |  |  |  | 630.0324
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-25
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H | L
SECOND FLOOR
11 | Supply and installation of rubber foam (XLPE) insulation adhesive with aluminum facing 12mm thick complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Exhaust & Fresh Air Duct (Insulation Pocket)
| Duct (24*8) |  | 2 | 2 | 0.66 | 0.5 | 2.66
| Duct (24*8) |  | 2 | 2 | 0.66 | 0.5 | 2.66
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 0.5 | 2.16
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 0.5 | 2.16
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (18*4) |  | 2 | 1.5 | 0.33 | 0.5 | 1.83
| Duct (26*10) |  | 2 | 2.16 | 0.83 | 0.5 | 2.99
| Duct (26*10) |  | 2 | 2.16 | 0.83 | 0.5 | 2.99
| Duct (26*10) |  | 2 | 2.16 | 0.83 | 0.5 | 2.99
| Duct (26*10) |  | 2 | 2.16 | 0.83 | 0.5 | 2.99
| Duct (26*10) |  | 2 | 2.16 | 0.83 | 0.5 | 2.99
| Duct (26*10) |  | 2 | 2.16 | 0.83 | 0.5 | 2.99
| Duct (26*10) |  | 2 | 2.16 | 0.83 | 0.5 | 2.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (16*8) |  | 2 | 1.33 | 0.66 | 0.5 | 1.99
| Duct (10*8) |  | 2 | 0.83 | 0.66 | 0.5 | 1.49
| Duct (10*8) |  | 2 | 0.83 | 0.66 | 0.5 | 1.49
| Duct (10*8) |  | 2 | 0.83 | 0.66 | 0.5 | 1.49
| Duct (10*8) |  | 2 | 0.83 | 0.66 | 0.5 | 1.49
| Duct (10*8) |  | 2 | 0.83 | 0.66 | 0.5 | 1.49
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 0.5 | 1.49
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 0.5 | 1.49
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 0.5 | 1.49
| Duct (14*4) |  | 2 | 1.16 | 0.33 | 0.5 | 1.49
| Duct (18*4) |  | 2 | 1.5 | 0.33 | 0.5 | 1.83
| Duct (12*6) |  | 2 | 1 | 0.5 | 0.5 | 1.5
| Duct (12*6) |  | 2 | 1 | 0.5 | 0.5 | 1.5
| Duct (12*6) |  | 2 | 1 | 0.5 | 0.5 | 1.5
| Duct (12*6) |  | 2 | 1 | 0.5 | 0.5 | 1.5
| Duct (12*6) |  | 2 | 1 | 0.5 | 0.5 | 1.5
| Duct (12*6) |  | 2 | 1 | 0.5 | 0.5 | 1.5
| Duct (12*6) |  | 2 | 1 | 0.5 | 0.5 | 1.5
| Duct (12*6) |  | 2 | 1 | 0.5 | 0.5 | 1.5
| Duct (12*6) |  | 2 | 1 | 0.5 | 0.5 | 1.5
| Duct (12*6) |  | 2 | 1 | 0.5 | 0.5 | 1.5
| Duct (12*6) |  | 2 | 1 | 0.5 | 0.5 | 1.5
| Duct (12*6) |  | 2 | 1 | 0.5 | 0.5 | 1.5
| Duct (12*6) |  | 2 | 1 | 0.5 | 0.5 | 1.5
| Duct (12*6) |  | 2 | 1 | 0.5 | 0.5 | 1.5
| Duct (12*4) |  | 2 | 1 | 0.33 | 0.5 | 1.33
| Duct (12*4) |  | 2 | 1 | 0.33 | 0.5 | 1.33
| Duct (12*4) |  | 2 | 1 | 0.33 | 0.5 | 1.33
| Duct (12*4) |  | 2 | 1 | 0.33 | 0.5 | 1.33
| Duct (12*4) |  | 2 | 1 | 0.33 | 0.5 | 1.33
| Duct (12*4) |  | 2 | 1 | 0.33 | 0.5 | 1.33
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (8*4) |  | 2 | 0.66 | 0.33 | 0.5 | 0.99
| Duct (18*12) |  | 2 | 1.5 | 1 | 0.5 | 2.5
| Duct (18*12) |  | 2 | 1.5 | 1 | 0.5 | 2.5
| Duct (18*12) |  | 2 | 1.5 | 1 | 0.5 | 2.5
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 0.5 | 2.16
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (20*10) |  | 2 | 1.66 | 0.83 | 0.5 | 2.49
| Duct (20*10) |  | 2 | 1.66 | 0.83 | 0.5 | 2.49
| Duct (20*10) |  | 2 | 1.66 | 0.83 | 0.5 | 2.49
| Duct (10*8) |  | 2 | 0.83 | 0.66 | 0.5 | 1.49
| Duct (14*10) |  | 2 | 1.16 | 0.83 | 0.5 | 1.99
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 0.5 | 1.82
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 0.5 | 1.82
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 0.5 | 1.82
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 0.5 | 1.82
| Duct (14*8) |  | 2 | 1.16 | 0.66 | 0.5 | 1.82
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (10*6) |  | 2 | 0.83 | 0.5 | 0.5 | 1.33
| Duct (22*12) |  | 2 | 1.83 | 1 | 0.5 | 2.83
| Duct (22*12) |  | 2 | 1.83 | 1 | 0.5 | 2.83
| Duct (22*12) |  | 2 | 1.83 | 1 | 0.5 | 2.83
| Duct (22*12) |  | 2 | 1.83 | 1 | 0.5 | 2.83
| Duct (22*12) |  | 2 | 1.83 | 1 | 0.5 | 2.83
| Duct (22*12) |  | 2 | 1.83 | 1 | 0.5 | 2.83
| Duct (22*12) |  | 2 | 1.83 | 1 | 0.5 | 2.83
| Duct (22*12) |  | 2 | 1.83 | 1 | 0.5 | 2.83
| Duct (22*12) |  | 2 | 1.83 | 1 | 0.5 | 2.83
| Duct (22*12) |  | 2 | 1.83 | 1 | 0.5 | 2.83
| Duct (22*12) |  | 2 | 1.83 | 1 | 0.5 | 2.83
| Duct (22*12) |  | 2 | 1.83 | 1 | 0.5 | 2.83
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 0.5 | 2.16
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 0.5 | 2.16
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 0.5 | 2.16
| Duct (18*4) |  | 2 | 1.5 | 0.33 | 0.5 | 1.83
| Duct (18*4) |  | 2 | 1.5 | 0.33 | 0.5 | 1.83
| Duct (18*4) |  | 2 | 1.5 | 0.33 | 0.5 | 1.83
| Duct (18*4) |  | 2 | 1.5 | 0.33 | 0.5 | 1.83
| Duct (18*4) |  | 2 | 1.5 | 0.33 | 0.5 | 1.83
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (22*8) |  | 2 | 1.83 | 0.66 | 0.5 | 2.49
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 0.5 | 2.16
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 0.5 | 2.16
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 0.5 | 2.16
| Duct (18*4) |  | 2 | 1.5 | 0.33 | 0.5 | 1.83
| Duct (18*4) |  | 2 | 1.5 | 0.33 | 0.5 | 1.83
| Duct (18*4) |  | 2 | 1.5 | 0.33 | 0.5 | 1.83
| Duct (18*4) |  | 2 | 1.5 | 0.33 | 0.5 | 1.83
| Duct (18*4) |  | 2 | 1.5 | 0.33 | 0.5 | 1.83
| Duct (18*4) |  | 2 | 1.5 | 0.33 | 0.5 | 1.83
| Duct (18*4) |  | 2 | 1.5 | 0.33 | 0.5 | 1.83
| Duct (26*12) |  | 2 | 2.16 | 1 | 0.5 | 3.16
| Duct (26*12) |  | 2 | 2.16 | 1 | 0.5 | 3.16
| Duct (26*12) |  | 2 | 2.16 | 1 | 0.5 | 3.16
| Duct (26*12) |  | 2 | 2.16 | 1 | 0.5 | 3.16
| Duct (26*12) |  | 2 | 2.16 | 1 | 0.5 | 3.16
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 0.5 | 2.16
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 0.5 | 2.16
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 0.5 | 2.16
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (24*10) |  | 2 | 2 | 0.83 | 0.5 | 2.83
| Duct (24*10) |  | 2 | 2 | 0.83 | 0.5 | 2.83
| Duct (24*10) |  | 2 | 2 | 0.83 | 0.5 | 2.83
| Duct (24*10) |  | 2 | 2 | 0.83 | 0.5 | 2.83
| Duct (18*10) |  | 2 | 1.5 | 0.83 | 0.5 | 2.33
| Duct (18*10) |  | 2 | 1.5 | 0.83 | 0.5 | 2.33
| Duct (18*10) |  | 2 | 1.5 | 0.83 | 0.5 | 2.33
| Duct (18*10) |  | 2 | 1.5 | 0.83 | 0.5 | 2.33
| Duct (18*10) |  | 2 | 1.5 | 0.83 | 0.5 | 2.33
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 0.5 | 2.16
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 0.5 | 2.16
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 0.5 | 2.16
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 0.5 | 2.16
| Duct (18*8) |  | 2 | 1.5 | 0.66 | 0.5 | 2.16
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| Duct (18*6) |  | 2 | 1.5 | 0.5 | 0.5 | 2
| This Bill Qty. | Sq.ft |  |  |  |  | 294.78
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-10-05
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H | L
EXTERNAL
13 | Supply & installation of aluminum fabricated powder coated exhaust & fresh Air louvers including wooden frame, rain protection sheet bird mesh etc complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Exhaust & Fresh Air Louvers
| (32*8) |  | 1 | 32 | 8 |  | 256
| (30*13) |  | 1 | 30 | 13 |  | 390
| (34*14) |  | 2 | 34 | 14 |  | 952
| (42*14) |  | 1 | 42 | 14 |  | 588
| (38*14) |  | 2 | 38 | 14 |  | 1064
| (28*14) |  | 1 | 28 | 14 |  | 392
| (20*7) |  | 1 | 20 | 7 |  | 140
| (10*10) |  | 1 | 10 | 10 |  | 100
| (16*14) |  | 1 | 16 | 14 |  | 224
| (18*12) |  | 1 | 18 | 12 |  | 216
| This Bill Qty. | Sq.in |  |  |  |  | 4322
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-10-04
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H
GROUND FLOOR
14 | Supply, installation of Aluminum fabricated, powder coated Grills, Diffusers and Registers for supply air, return air, exhaust air & fresh air of different sizes (Grade A ), wooden frame, supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
14.1 | Fresh & Exhaust Air Register / Diffuser with Damper
EAD | (9*9) |  | 1 | 9 | 9 |  | 81
| (9*9) |  | 1 | 9 | 9 |  | 81
| (9*9) |  | 1 | 9 | 9 |  | 81
| (15*15) |  | 1 | 15 | 15 |  | 225
| (15*15) |  | 1 | 15 | 15 |  | 225
| (9*9) |  | 1 | 9 | 9 |  | 81
| (12*12) |  | 1 | 12 | 12 |  | 144
| (12*12) |  | 1 | 12 | 12 |  | 144
| (15*15) |  | 1 | 15 | 15 |  | 225
FAD | (12*12) |  | 1 | 12 | 12 |  | 144
| (12*12) |  | 1 | 12 | 12 |  | 144
| (6*6) |  | 1 | 6 | 6 |  | 36
| (6*6) |  | 1 | 6 | 6 |  | 36
| (15*15) |  | 1 | 15 | 15 |  | 225
| (15*15) |  | 1 | 15 | 15 |  | 225
| (6*6) |  | 1 | 6 | 6 |  | 36
| (6*6) |  | 1 | 6 | 6 |  | 36
| (12*12) |  | 1 | 12 | 12 |  | 144
| (15*15) |  | 1 | 15 | 15 |  | 225
| This Bill Qty. | Sq.in |  |  |  |  | 2538
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-10-04
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H
GROUND & SECOND FLOOR
14 | Supply, installation of Aluminum fabricated, powder coated Grills, Diffusers and Registers for supply air, return air, exhaust air & fresh air of different sizes (Grade A ), wooden frame, supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
14.1 | Fresh & Exhaust Air Register / Diffuser with Damper
Fresh Air Grills
| (10*8) |  | 1 | 10 | 8 |  | 80
| (26*8) |  | 1 | 26 | 8 |  | 208
| (14*8) |  | 1 | 14 | 8 |  | 112
| (14*8) |  | 1 | 14 | 8 |  | 112
| This Bill Qty. | Sq.in |  |  |  |  | 512
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-10-04
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H
FIRST FLOOR
14 | Supply, installation of Aluminum fabricated, powder coated Grills, Diffusers and Registers for supply air, return air, exhaust air & fresh air of different sizes (Grade A ), wooden frame, supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
14.1 | Fresh & Exhaust Air Register / Diffuser with Damper
EAD | (15*15) |  | 1 | 15 | 15 |  | 225
| (15*15) |  | 1 | 15 | 15 |  | 225
| (15*15) |  | 1 | 15 | 15 |  | 225
| (15*15) |  | 1 | 15 | 15 |  | 225
| (6*6) |  | 1 | 6 | 6 |  | 36
| (6*6) |  | 1 | 6 | 6 |  | 36
| (15*15) |  | 1 | 15 | 15 |  | 225
| (18*18) |  | 1 | 18 | 18 |  | 324
| (18*18) |  | 1 | 18 | 18 |  | 324
| (18*18) |  | 1 | 18 | 18 |  | 324
| (18*18) |  | 1 | 18 | 18 |  | 324
| (18*18) |  | 1 | 18 | 18 |  | 324
FAD | (15*15) |  | 1 | 15 | 15 |  | 225
| (15*15) |  | 1 | 15 | 15 |  | 225
| (15*15) |  | 1 | 15 | 15 |  | 225
| (15*15) |  | 1 | 15 | 15 |  | 225
| (15*15) |  | 1 | 15 | 15 |  | 225
| (6*6) |  | 1 | 6 | 6 |  | 36
| (6*6) |  | 1 | 6 | 6 |  | 36
| (18*18) |  | 1 | 18 | 18 |  | 324
| (18*18) |  | 1 | 18 | 18 |  | 324
| (18*18) |  | 1 | 18 | 18 |  | 324
| (18*18) |  | 1 | 18 | 18 |  | 324
| (18*18) |  | 1 | 18 | 18 |  | 324
| This Bill Qty. | Sq.in |  |  |  |  | 5634
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-10-04
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H
SECOND FLOOR
14 | Supply, installation of Aluminum fabricated, powder coated Grills, Diffusers and Registers for supply air, return air, exhaust air & fresh air of different sizes (Grade A ), wooden frame, supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
14.1 | Fresh & Exhaust Air Register / Diffuser with Damper
EAD | (18*18) |  | 1 | 18 | 18 |  | 324
| (18*18) |  | 1 | 18 | 18 |  | 324
| (15*15) |  | 1 | 15 | 15 |  | 225
| (15*15) |  | 1 | 15 | 15 |  | 225
| (12*12) |  | 1 | 12 | 12 |  | 144
| (12*12) |  | 1 | 12 | 12 |  | 144
| (12*12) |  | 1 | 12 | 12 |  | 144
| (12*12) |  | 1 | 12 | 12 |  | 144
| (12*12) |  | 1 | 12 | 12 |  | 144
| (12*12) |  | 1 | 12 | 12 |  | 144
| (12*12) |  | 1 | 12 | 12 |  | 144
| (9*9) |  | 1 | 9 | 9 |  | 81
| (9*9) |  | 1 | 9 | 9 |  | 81
| (9*9) |  | 1 | 9 | 9 |  | 81
| (9*9) |  | 1 | 9 | 9 |  | 81
FAD | (15*15) |  | 1 | 15 | 15 |  | 225
| (15*15) |  | 1 | 15 | 15 |  | 225
| (9*9) |  | 1 | 9 | 9 |  | 81
| (9*9) |  | 1 | 9 | 9 |  | 81
| (15*15) |  | 1 | 15 | 15 |  | 225
| (15*15) |  | 1 | 15 | 15 |  | 225
| (15*15) |  | 1 | 15 | 15 |  | 225
| (15*15) |  | 1 | 15 | 15 |  | 225
| (15*15) |  | 1 | 15 | 15 |  | 225
| (15*15) |  | 1 | 15 | 15 |  | 225
| (12*12) |  | 1 | 12 | 12 |  | 144
| (12*12) |  | 1 | 12 | 12 |  | 144
| This Bill Qty. | Sq.in |  |  |  |  | 4680
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-10-04
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H
GROUND FLOOR
14 | Supply, installation of Aluminum fabricated, powder coated Grills, Diffusers and Registers for supply air, return air, exhaust air & fresh air of different sizes (Grade A ), wooden frame, supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
14.2 | Exhaust Air Disc Valves 6" dia
|  |  | 12 |  |  |  | 12
|  |  | 4 |  |  |  | 4
| This Bill Qty. | Nos. |  |  |  |  | 16
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-10-04
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H
FIRST FLOOR
14 | Supply, installation of Aluminum fabricated, powder coated Grills, Diffusers and Registers for supply air, return air, exhaust air & fresh air of different sizes (Grade A ), wooden frame, supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
14.2 | Exhaust Air Disc Valves 6" dia
|  |  | 2 |  |  |  | 2
| This Bill Qty. | Nos. |  |  |  |  | 2
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-10-04
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H
SECOND FLOOR
14 | Supply, installation of Aluminum fabricated, powder coated Grills, Diffusers and Registers for supply air, return air, exhaust air & fresh air of different sizes (Grade A ), wooden frame, supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
14.2 | Exhaust Air Disc Valves 6" dia
|  |  | 16 |  |  |  | 16
| This Bill Qty. | Nos. |  |  |  |  | 16
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-09
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | W | H
Volume Control Damper
15 | Supply & installation of Volume Control Damper in 16 SWG G.I sheet metal with gas kits, nut bolts, complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
GROUND FLOOR
| (20*5) |  | 1 | 20 | 5 |  | 100
| (20*5) |  | 1 | 20 | 5 |  | 100
200
FIRST FLOOR
| (21.5*13) |  | 1 | 21.5 | 13 |  | 279.5
| (15.5*13) |  | 1 | 15.5 | 13 |  | 201.5
481
SECOND FLOOR
| (22*15) |  | 1 | 22 | 15 |  | 330
| (16*15) |  | 1 | 16 | 15 |  | 240
570
| This Bill Qty. | Sq.in |  |  |  |  | 1251
SUMMARY OF FIRE FIGHTING
TRIFIT LIMITED-T1 GYM CLIFTON KARACHI
BOQ NO. | DESCRIPTION | Unit | No. | GROUND FLOOR | FIRST FLOOR | SECOND FLOOR | CURRANT TOTAL
3 | Fire department breeching connection 2 ways as per BSS 5041-3 including cabinet with breakable glass, SS frame & drain plug.
|  | Nos. |  |  | 1 |  | 1
4 | MS Sch-40 seamless pipes including all specials fittings UL listed FM approved, threaded, welded joints, flexible pipe, flanges, coupling, masking plates, bends, tees, clamps, supports and hangers, sleeves, masking plates chiseling, cutting holes, making good where required, painting and protection treatment etc. Complete in all respects.
4.5 | Dia 4" | Rft. |  | 128.73 | 18 |  | 146.73
5 | Fire extinguishers with fixing accessories.
5.1 | Type Class B&C FX-3 (5 Kg. CO2 Carbon Dioxide Gas) | Nos. |  | 4 | 2 | 2 | 8
5.2 | Type Class A,B&C FX-4 (6 Kg. Dry Chemical Powder) | Nos. |  | 5 | 2 | 2 | 9
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-05
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
No.
GROUND FLOOR
Fire Extinguishers
5 | Fire Extinguishers with fixing accessories.
5.1 | Type Class B&C FX-3 (5 Kg. CO2 Carbon Dioxide Gas) | Nos. | 4 |  |  |  | 4
5.2 | Type Class A,B&C FX-4 (6 Kg. Dry Chemical Powder) | Nos. | 5 |  |  |  | 5
| This Bill Qty. | Nos. |  |  |  |  | 9
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-05
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
No.
FIRST FLOOR
Fire Extinguishers
5 | Fire Extinguishers with fixing accessories.
5.1 | Type Class B&C FX-3 (5 Kg. CO2 Carbon Dioxide Gas) | Nos. | 2 |  |  |  | 2
5.2 | Type Class A,B&C FX-4 (6 Kg. Dry Chemical Powder) | Nos. | 2 |  |  |  | 2
| This Bill Qty. | Nos. |  |  |  |  | 4
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-09-05
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
No.
SECOND FLOOR
Fire Extinguishers
5 | Fire Extinguishers with fixing accessories.
5.1 | Type Class B&C FX-3 (5 Kg. CO2 Carbon Dioxide Gas) | Nos. | 2 |  |  |  | 2
5.2 | Type Class A,B&C FX-4 (6 Kg. Dry Chemical Powder) | Nos. | 2 |  |  |  | 2
| This Bill Qty. | Nos. |  |  |  |  | 4
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-10-11
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
3 | Fire department breeching connection 2 ways as per BSS 5041-3 including cabinet with breakable glass, SS frame & drain plug.
| GROUND FLOOR | Nos. | 1 |  |  |  | 1
| This Bill Qty. | Nos. |  |  |  |  | 1
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-10-10
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
BASEMENT
Fire Pipe
4 | MS Sch-40 seamless pipes including all specials fittings UL listed FM approved, threaded, welded joints, flexible pipe, flanges, coupling, masking plates, bends, tees, clamps, supports and hangers, sleeves, masking plates chiseling, cutting holes, making good where required, painting and protection treatment etc. Complete in all respects.
4.5 | Dia 4" | Rft. | 1 | 6.66 |  |  | 6.66
|  |  | 1 | 18.66 |  |  | 18.66
|  |  | 1 | 79.91 |  |  | 79.91
|  |  | 1 | 3.5 |  |  | 3.5
| Riser No-02 Vertical Pipe |  | 1 | 20 |  |  | 20
| This Bill Qty. | Rft. |  |  |  |  | 128.73
Pioneer Services
Measurement Sheet For Running Bill.
Project :- ASPL/1189-TRIFIT LIMITED-T1 |  | TRIFIT LIMITED-T1 GYM CLIFTON KARACHI |  |  | Date: |  | 2023-10-10
Client :- TRIFIT LIMITED-T1 GYM |  |  |  |  | Drawing No.
Contractor:- NEC |  |  |  |  | Prepared by
B.O.Q Item | Description | Unit | Measurement |  |  |  | Total Quantity
|  |  | No. | L | W | H/D
GROUND FLOOR
Fire Pipe
4 | MS Sch-40 seamless pipes including all specials fittings UL listed FM approved, threaded, welded joints, flexible pipe, flanges, coupling, masking plates, bends, tees, clamps, supports and hangers, sleeves, masking plates chiseling, cutting holes, making good where required, painting and protection treatment etc. Complete in all respects.
4.5 | Dia 4" | Rft. | 1 | 6.75 |  |  | 6.75
|  |  | 1 | 4.25 |  |  | 4.25
| Riser No-02 Vertical Pipe |  | 1 | 7 |  |  | 7
| This Bill Qty. | Rft. |  |  |  |  | 18