## VO Sheet 1
VISA FIT OUT PROJECT
10th FLOOR UNIT # 4, DOLMEN SKY TOWER - A, CLIFTON KARACHI.
MECHANICAL WORKS
Non Boq Work
S.# | Description | Unit | As Per Site Qty | Rate | Amount | Verified Qty | Approved Rate | Amount | Remarks
MECH-VO-01 | G.I Ducting & Fire Piping
| Dismantling existing G.I Ducting & supply and Installation Fire Piping etc | Job | 1 | 101239 | 101239 | 1 | 90688 | 90688 | Approved with comments
MECH-VO-02 | DFCU & WCPU
| Supply of fan coil unit including interconnecting power & control wiring. Make TRANE, China | No | 1 | 258115.2 | 258115.2
| Supplyof of fan coil unit including interconnecting power & control wiring. Make SABRO | No | 1 | 1344695 | 1344695
MECH-VO-03 | Wall Mounted Fans with Auto Shutter
| Supply & installation of following Decorative Wall Mounted Fan with Auto Shutter etc. Complete in all respect. | Job | 1 | 592497 | 592497 | 1 | 478977 | 478977 | Approved with comments
MECH-VO-04 | Test & Drain valves
| Supply & installation of test & drain valves 1" dia etc. Complete in all respect. | Job | 1 | 119325 | 119325 | 1 | 109650 | 109650 | Approved with comments
MECH-VO-05 | Gasket & Related fitting
| Supply & installation of Gasket & Related fittings etc. Complete in all respect. | Job | 1 | 30960 | 30960 | 1 |  | 0 | Rejected. Already part of BOQ / Specs
Mech-VO-06 | Return air fan L Pieces
| Supply & installation of L- duct pieces for the installation of Return air Fans | SFT | 280 | 597.915 | 167416.2 | 1 |  | 0 | Not Approved. S.No 1, 2 & 4 are BOQ Items. & S.No 3 should be submitted in sqinch or mentioned sizes.
| Supply & installation of acoustical duct sound liner in duct pieces. | SFT | 280 | 478.3965 | 133951.02
| Supply & installation of S.S wire mesh. | Sqin | 2880 | 12.255 | 35294.4
HVAC-VO-08 | Temperature meter & pressure guage
| Temperature Meter & Pressure Guage | Job | 1 | 167803 | 167803 | 1 | 162643 | 162643 | Approved with comments
| Total Amount |  |  |  | 2951295.82 | TOTAL VERIFIED |  | 841958
Note: Same VO No. use in different items

## VO Sheet 2
VISA FIT OUT PROJECT
10th FLOOR UNIT # 4, DOLMEN SKY TOWER - A, CLIFTON KARACHI.
MECHANICAL WORKS
S.# | Description | Unit | As Per Site Qty | Rate | Amount | Verified Qty | Approved Rate | Amount | Remarks
MECH-VO-06 | VFD for Fans
| Supply and Installation VFD for Fan | Job | 0 | 1045793 | 1045793 |  |  |  | Rejected, Because of Doubling Already claimed by IKA (Mentioned Below)
MECH-VO-06 | VFD
| Supply and Installation VFD | Job | 1 | 928916 | 928916 | 1 | 928916 | 928916 | Technically Approved by Consultant, Commercials already with PM/Client (VFD for 2 Nos. AHU & 1 No. RAF)
MECH-VO-06 | BMS Controls
| Supply and Installation BMS controls etc | Job | 1 | 2598048 | 2598048 | 1 | 2598048 | 2598048 | Technically Approved by Consultant, Commercials already with PM/Client (VFD for 2 Nos. AHU & 1 No. RAF)
VFD 4 kW
| Supply and Installation 4 kW VFD | Job | 1 | 240000 | 240000 | 1 | 240000 | 240000 | Technically Approved by Consultant, Commercials already with PM/Client. (Temporary VFD for RAF). Should be handed over to Visa once the permanent one gets installed.
MECH-VO-09 | VFD Accessories
| Supply and Installation VFD accessories | Job | 1 | 114101 | 114101 |  |  |  | Rejected. The above item was quoted as all inclusive.
MECH-VO-08 | BMS Controls
| Supply and Installation BMS controls etc | Job | 1 | 1470527 | 1470527 | 1 | 1470527 | 1470527 | Technically Approved by Consultant, Commercials already with PM/Client. (Siemens Scope of Work)
MECH-VO-08 | Pressure Switches for Water Cooled Package Unit
| Supply and Installation Pressure Switches | Job | 1 | 38636 | 38636 | 1 | 38636 | 38636 | Approved
MECH-VO-01 | Fans
| Supply and Installation Fans | Job | 0 | 723432 | 723432 |  |  |  | Rejected, Because of Doubling Already claimed by IKA (Mentioned in VO Sheet-1, MECH-VO-03)
| Total Amount |  |  |  | 7159453 | TOTAL VERIFIED |  | 5276127
Note: Same VO No. use in different items