## Table 1
SH-2021-22 | [8 empty] | March 20, 2024.
Running Bill
SAIFEE HOSPITAL
FROM 08TH FLOOR TO 11TH FLOOR
S. No. | DESCRIPTION | QTY |  | UNIT RATE (RS) |  | Billed Qty | AMOUNT(RS)
|  |  |  | COST OF SUPPLY | COST OF INSTALLATION |  | COST OF SUPPLY | COST OF INSTALLATION | TOTAL COST
PART-A FIRE FIGHTING SYSTEM
1 | Supply, installation, testing & commissioning of Fire Pump Skid Mounted Package set complete with Electric, Diesel & Jockey pump including Control panel, fuel tank all special fitting, Painting and hangers complete in all respects as per drawing & specifications. (250GPM & 10BAR) | 0 | Set | 0 | 0 |  | 0 | 0 | 0
2 | Supply, installation, testing & commissioning of Fire Hose Cabinets including automatic 1" diameter Hose reel, Nozzle, CO2, Dry Powder Extinguishers, 25mm Lock shield Valve, 1" pressure reducing Valve, 2 1/2" diameter landing Valve with pressure regulator complete in all respectss as shown on drawings & specifications | 2 | Nos | 0 | 10000 |  | 0 | 0 | 0
3 | Supply, installation, testing & commissioning of 2-way Fire Department Connection Including all accessories complete in all respects as shown on Drawings / Specifications. | 0 | Nos | 0 | 0 |  | 0 | 0 | 0
4 | Supply, Installation, testing & commissioning of OS&Y Gate valve Including all accessories complete in all respects as shown on Drawings / Specifications. | [5 empty] | 0 | 0 | 0
i. | 2-1/2" dia | 2 | Nos | 0 | 7000 |  | 0 | 0 | 0
5 | Supply & Installation of puddle connection in water tank complete with all repect. 5" dia | 0 | Nos | 0 | 0 |  | 0 | 0 | 0
6 | Supply, Installation, testing & commissioning of Water proof MCC for fire System with circuit Breakers, Disconnect switches, fuses, phase reversal, starters etc. for all equipment as per specification & drawing. (Isolation breakers shall be finalized as per manufacturer specifications.) | 0 | Nos | 0 | 0 |  | 0 | 0 | 0
7 | Supply, Installation, testing & commissioning of seamless M.S schedule-40 Fire piping including all special fitting, Painting and hangers complete in all respects show on drawing & specifications. | [5 empty] | 0 | 0 | 0
i. | 5" dia | 80 | Rft. | 5305 | 750 | 339.57 | 1801418.85 | 254677.5 | 2056096.35
ii | 2-1/2" dia | 100 | Rft. | 2340 | 400 |  | 0 | 0 | 0
8 | Supply, Installation, testing & commissioning of Complete Electric power & control wiring complete with PVC conduit and power wiring will be in G.I.Cable tray & hanger supports etc. for Equipment as per Specification and drawings. | 0 | Lot. | 0 | 0 |  | 0 | 0 | 0
9 | Supply & Installation of Wall Mounted Fire Extinguisher with hangers as per drawing and specification. | [5 empty] | 0 | 0 | 0
i. | Fire Extinguisher 6 Kg Dry Powder | 11 | Nos | 0 | 1700 |  | 0 | 0 | 0
ii | Fire Extinguisher 6 Kg CO2 | 11 | Nos | 0 | 1700 |  | 0 | 0 | 0
TOTAL COST PART -A (RS.)
PART-B WATER SUPPLY AND DRAINAGE SYSTEM.
1 | Supply, Installation, testing & commissioning of Submersible O.H Water Transfer pumps complete with accessories as per drawings and specifications. (100gpm, 240 ft. Head) | 0 | Nos. | 0 | 0 |  | 0 | 0 | 0
2 | Supply & Installation of Hot Water Electric operated Geyser 50 Gallons Capacity Storage Type. Inner Tank made with G.I Sheet 8 SWG/3.8mm Outer Shell made With Stainless Steel Sheet, With Imported Thermostat, Upto 60 Psi. | 2 | Nos. | 165000 | 10000 |  | 0 | 0 | 0
3 | Supply, Installation, testing & commissioning of Circulation Hot water pumps complete with accessories as per drawings and specifications. (25gpm, 20ft Head) | 2 | Nos. | 0 | 15000 |  | 0 | 0 | 0
4 | Water closets European style with close coupled cistern, cistern fittings, acrylic seat cover, complete with accessories. | 57 | Nos. | 66700 | 8000 |  | 0 | 0 | 0
5 | Water closets European style with close coupled cistern, cistern fittings, acrylic seat cover, for handi cap toilet complete with accessories. | 1 | Nos. | 83475 | 8000 |  | 0 | 0 | 0
6 | Wash basins, single center hole, suitable for counter top fittings for below, complete with accessories. | 58 | Nos. | 34565 | 7000 |  | 0 | 0 | 0
7 | Wash basins, single center hole, suitable for counter top fittings for below, for dirty utility complete with accessories. | 0 | Nos. | 0 | 0 |  | 0 | 0 | 0
8 | C.P Tee valves, for cistern water inlet CP connectors with nuts and fittings, complete with accessories. | 112 | Nos. | 2150 | 500 |  | 0 | 0 | 0
9 | Muslim Shower with flexible hose, valve nozzle angle valve spont, complete with accessories. | 26 | Nos. | 7500 | 1000 |  | 0 | 0 | 0
10 | CP Tee valves for wash basins, CP connections with nutes, fittings and complete with all accessories. | 70 | Nos. | 1975 | 1000 |  | 0 | 0 | 0
11 | CP bottle trap 1-1/4" with pipe for wash basin waste connection and water strainer, complete with all accessories. | 56 | Nos. | 4375 | 1000 |  | 0 | 0 | 0
12 | CP Toilet paper roll holder Asia or approved equal complete with accessories. | 56 | Nos. | 6180 | 500 |  | 0 | 0 | 0
13 | Soap bottles, decorative type complete with accessories. | 56 | Nos. | 10625 | 500 |  | 0 | 0 | 0
14 | Supply and installation of basins mixture complete with all accessories. | 56 | Nos. | 14250 | 2000 |  | 0 | 0 | 0
15 | Supply & Installation of Sanitizer -Automatic. | 52 | Nos. | 21250 | 1000 |  | 0 | 0 | 0
16 | Supply & Installation of hand Dryer. | 88 | Nos. | 23000 | 2000 |  | 0 | 0 | 0
17 | WATER DISTRIBUTION SYSTEM | [5 empty] | 0 | 0 | 0
a. | Supply and installation of PPR PN 20 piping for cold & Hot water system, with fittings, specialties, including all cutting, fitting, fixing and cleaning, wall and slab sleeves/Core Cutting, CP clamps, hangers and supports, making connection with fixtures, valves and specialties, chiseling, making wall an floor openings and making good, pressure testing at a pressure of 250 psig, painting of exposed piping in occupied areas with primer and coats of approved paint in approved color complete in all respect. | [5 empty] | 0 | 0 | 0
i. | 2" dia | 200 | Rft. | 1580 | 250 | 120 | 189600 | 30000 | 219600
ii. | 1-1/2" dia | 0 | Rft. | 1062 | 200 | 60 | 63720 | 12000 | 75720
iii. | 1-1/4" dia | 300 | Rft. | 780 | 180 | 361.65 | 282087 | 65097 | 347184
iv. | 1" dia | 150 | Rft. | 530 | 180 | 431.38 | 228631.4 | 77648.4 | 306279.8
v. | 3/4" dia | 200 | Rft. | 392 | 170 | 711.5 | 278908 | 120955 | 399863
vi | 1/2" dia | 0 | Rft. | 295 | 100 | 724.51 | 213730.45 | 72451 | 286181.45
b. | Gate Valve | [5 empty] | 0 | 0 | 0
i. | 2" dia | 6 | Nos | 32000 | 2500 |  | 0 | 0 | 0
ii. | 1-1/2" dia | 6 | Nos | 18864 | 2000 |  | 0 | 0 | 0
iii. | 1-1/4" dia | 6 | Nos | 17244 | 1500 | 8 | 137952 | 12000 | 149952
iv. | 1" dia | 6 | Nos | 11600 | 1500 | 4 | 46400 | 6000 | 52400
v | 3/4" dia | 6 | Nos | 8850 | 1000 |  | 0 | 0 | 0
c. | Ball Valve | [5 empty] | 0 | 0 | 0
i. | 1/2" dia | 3 | Nos | 5750 | 1000 | 4 | 23000 | 4000 | 27000
ii. | 2" dia | 3 | Nos | 38960 | 3000 |  | 0 | 0 | 0
d. | Float valve | 2 | Nos | 32000 | 3000 |  | 0 | 0 | 0
e. | Foot valve 2" dia | 2 | Nos | 24500 | 3000 |  | 0 | 0 | 0
f. | Strainer 2" dia | 0 | Nos | 0 | 0 |  | 0 | 0 | 0
g. | Check valve 2" dia | 0 | Nos | 0 | 0 |  | 0 | 0 | 0
18 | SOIL, WASTE AND VENT SYSTEM | [5 empty] | 0 | 0 | 0
a. | Supply and installation of UPVC Class D piping including all fittings, sockets, hangers and specials for soil, waste,rain& vent stacks and horizontal runs buried in ground or above false ceiling, in shafts exposed or concealed in floors and walls and connecting to manholes, including cutting, fitting, chiseling, wall and slab sleeves/Core Cutting, making good, fixing and cleaning, wall and slab openings complete in all respect. | [5 empty] | 0 | 0 | 0
i. | 8" dia | 69 | Rft. | 2750 | 300 |  | 0 | 0 | 0
ii. | 6" dia | 100 | Rft. | 2150 | 280 | 192.07 | 412950.5 | 53779.6 | 466730.1
iii. | 4" dia | 800 | Rft. | 1335 | 250 | 666.23 | 889417.05 | 166557.5 | 1055974.55
iv. | 3" dia | 900 | Rft. | 890 | 225 | 675.44 | 601141.6 | 151974 | 753115.6
v. | 2" dia | 800 | Rft. | 515 | 200 | 660.92 | 340373.8 | 132184 | 472557.8
19 | Supply and installation of Roof Drain with Trap complete in all respect. | [5 empty] | 0 | 0 | 0
i | 6" dia | 2 | Nos. | 19000 | 2000 | 68 | 1292000 | 136000 | 1428000
20 | Supply and installation of Floor Drain with Trap complete in all respect. | [5 empty] | 0 | 0 | 0
i. | 4" dia | 90 | Nos. | 7500 | 1000 |  | 0 | 0 | 0
21 | Supply & installation of Vent cowl complete with all respect as per drawing & specificaiton. | [5 empty] | 0 | 0 | 0
i. | 6" dia | 1 | Nos. | 2000 | 700 |  | 0 | 0 | 0
ii | 4" dia | 1 | Nos. | 1800 | 700 | 17 | 30600 | 11900 | 42500
iii. | 3" dia | 1 | Nos. | 1700 | 700 | 8 | 13600 | 5600 | 19200
22 | Supply and installation of Clean Out complete in all respect. | [5 empty] | 0 | 0 | 0
i. | 4" dia | 7 | Nos. | 8160 | 1000 |  | 0 | 0 | 0
ii. | 3" dia | 30 | Nos. | 6970 | 1000 |  | 0 | 0 | 0
23 | Supply & Installation of Weatherproof MCC for Plumbing System with circuit Breakers, Disconnect switches, fuses, starters etc. for all equipment as per specification & drawing.(Isolation breakers shall be finalized as per manufacturer specifications. ) | 0 | Nos. | 0 | 0 |  | 0 | 0 | 0
24 | Supply & installation of R.C.C M.H with Heavy duty cover complete with all respect as per drawing & specification. | 0 | Nos. | 0 | 0 |  | 0 | 0 | 0
25 | Supply & installation of G.T with Heavy duty cover complete with all respect as per drawing & specification. | 0 | Nos. | 0 | 0 |  | 0 | 0 | 0
26 | Supply & Installation of Complete Electric power & control wiring complete with PVC conduit and power wiring will be in G.I.Cable tray & hanger supports etc. for Equipment as per Specification and drawings. | 0 | Lot. | 0 | 0 |  | 0 | 0 | 0
27 | City sewerage and water supply connection from city connection point to building connection location. | 0 | Lot. | 0 | 0 |  | 0 | 0 | 0
TOTAL COST PART -B (RS.)
PART-C RO WATER SYSTEM SYSTEM
1 | Installation, testing & commissioning of OFM RO water system complete in all respectss as shown on drawings & specifications | 1 | Set | 0 | 100000 |  | 0 | 0 | 0
2 | Supply, Installation, testing & commissioning of PE(1000 USG) tank complete in all respectss as shown on drawings & specifications | 3 | Nos. | 345000 | 15000 |  | 0 | 0 | 0
3 | Supply, Installation, Testing & Commissioning of Multistage (2+1 No's) Boosting Pumping system 2nos running and 1no standby with speed controller, control pannel,integrated dry running detection and low water cut out switch complete with valve fitting with all respect as per drawings and specification.(60 Gpm and 8 bar) | 1 | Set | 0 | 35000 |  | 0 | 0 | 0
4 | RO WATER DISTRIBUTION SYSTEM | [5 empty] | 0 | 0 | 0
a. | PPR PN 20 piping for RO water system, with fittings, specialties, including all cutting, fitting, fixing and cleaning, wall and slab sleeves, CP clamps, hangers and supports, making connection with fixtures, valves and specialties, chiseling, making wall an floor openings and making good, pressure testing at a pressure of 250 psig, painting of exposed piping in occupied areas with primer and coats of approved paint in approved color complete in all respect. | [5 empty] | 0 | 0 | 0
i. | 2" dia | 60 | Rft. | 1600 | 200 | 60 | 96000 | 12000 | 108000
ii. | 1-1/2" dia | 40 | Rft. | 960 | 180 | 8.25 | 7920 | 1485 | 9405
iii. | 1-1/4" dia | 50 | Rft. | 680 | 150 | 275.23 | 187156.4 | 41284.5 | 228440.9
iv. | 1" dia | 60 | Rft. | 500 | 125 | 139.98 | 69990 | 17497.5 | 87487.5
v. | 3/4" dia | 40 | Rft. | 390 | 100 | 217.26 | 84731.4 | 21726 | 106457.4
vi | 1/2" dia | 270 | Rft. | 295 | 100 | 613.24 | 180905.8 | 61324 | 242229.8
5 | Gate Valve | [5 empty] | 0 | 0 | 0
i. | 2" dia | 0 | Nos | 0 | 0 |  | 0 | 0 | 0
ii | 1 1/4" dia | 5 | Nos | 0 | 0 |  | 0 | 0 | 0
6 | Strainer 2" dia | 0 | Nos | 0 | 0 |  | 0 | 0 | 0
TOTAL COST PART -C RO WATER SYSTEM (RS.)
PART-D GERNAL WORKS
1 | Equipment foundation and equipment shifting charges from Ground floor to foundation pads as per specification and drawings. | 1 | Job | 200000 | 100000 |  | 0 | 0 | 0
2 | Supply, installation, testing & commissioning of level sensor for Fire Fighting & Plumbing system complete with all respect as per drawings & specification. | 1 | Job | 380000 | 8000 |  | 0 | 0 | 0
3 | M&P Services Shop drawings & As Built Drawings Color Copies. (Minimum scale 1- 1/8”) Hard Copy and Soft Copy in Autocad format in CD | 4 | Set | 12000 | 3000 |  | 0 | 0 | 0
4 | Cost of testing, Starting up, commissioning, balancing, adjusting and handling over of the complete Plant. | 1 | Job | 0 | 200000 |  | 0 | 0 | 0
5 | Cost of System operation for 3 months (2 Operators ). | 1 | Job |  | 500000 |  | 0 | 0 | 0
TATAL COST PART -D (RS.)
GRAND TOTAL | [8 empty] | 8940375.25
Special Discount | [8 empty] | 1000000
NET TOTAL | [8 empty] | 7940375.25
NOTES:
1 | The Contractor shall be responsible for the supply, procurement and delivery of all the material and shifting of the equipment to their respective location, installation, testing, commissioning of the systems in all respects.
2 | The quoted cost should include all overheads, profits, income tax and all other Taxes which are applicable, import duty (if any), insurance, packing, unpacking, transportation charges etc.
3 | The work at site shall be executed in accordance with the approved shop drawings which will be prepared by the Contractor.
4 | The work at site shall be executed in accordance with the approved shop drawings which will be prepared by the Contractor within 1 week after award of works and Manufacturers drawings, Contract Specifications
5 | The work shall be awarded on item Rate cost basis.
6 | The complete system complete replacement warranty should be minimum 1years.
7 | The contractor will provide Equipment Operation & Maintenance Manuals (2 sets Hard copy & Soft Copy.)
8 | The contractor will provide Operation & Maintenance Instructions to Clients Representatives
9 | The Owner reserves the right to delete any item before award of works. The cost of such items shall be reduced.
10 | Abbreviation used in the BOQ are as follows: a) Sq. ft....... Square feet, (b) R. ft. ....... Running feet, (c) Ton ....... Ton weight, (d) TR ........ Ton of refrigeration, (e) No. ........ Number, (f) Lot /Job Complete package/lump sum.