## DPR
DAILY SITE PROGRESS REPORT
PRELIMINARY DETAILS
Client: | Patient Aid Foundation (PAF) |  |  | Contractor: | Pioneer Services |  |  | Project Manager: |  | Imran Ali
Project: | NICVD |  |  | Works/Contract: |  |  |  | Week #:
Submission Date: | 2025-03-17 | Weather: |  | Temperature: |  | Humidity: |  | Total. Working Day:
DAILY WORK PROGRESS
S. NO | Activity Description | Location/Grid | Units | Qty | Completed |  |  |  |  | Target Completion Date Of the Activity
[5 empty] | Progress Up Till Yesterday | Today's Progress | Commulative Progress | % Completion | Next work day plan (Qty/%)
1 | GROUND FLOOR
1 | Installation Of AC Control Wire | Zone C G.F | Rft | 2100 | 1500 | 100 | 1600 | 76.19% | 14% | Unit Connection Work remaining (OFM)
FIRST FLOOR
BASEMENT
1 | Refrigerant pipe Pressure hold 600 psi | Zone A,B,C & basement
a | Installation of Refrigerant pipe dia 1 3/8'' |  | Rft | 33.5 | 24 | 9.5 | 33.5 | 100%
b | Installation of Refrigerant pipe dia 1 1/8'' |  | Rft | 970 | 290 | 147 | 437 | 45.05% | 15% | Unit Connection Work remaining (OFM)
c | Installation of Refrigerant pipe dia 7/8'' |  | Rft | 163 | 110 | 53 | 163 | 100%
d | Installation of Refrigerant pipe dia 3/4'' |  | Rft | 430 | 286 | 114 | 400 | 93.02% | 7% | Unit Connection Work remaining (OFM)
e | Installation of Refrigerant pipe dia 5/8'' |  | Rft | 1395 | 1128 | 33 | 1161 | 83.23% | 17% | Unit Connection Work remaining (OFM)
f | Installation of Refrigerant pipe dia 1/2'' |  | Rft | 1593 | 1452 | 141 | 1593 | 100%
g | Installation of G.I ducting |  | SQFT | 7050 |  |  | 6316 | 89.59% | 10% | Unit Connection Work remaining (OFM)
h | Installation of duct insulation |  | SQFT | 4900 |  |  | 4243 | 87% | 13% | Unit Connection Work remaining (OFM)
Completed Activities
1 | Installation of Upvc condensate drain pipe dia 1" |  | Rft | 1768 |  |  | 1768 | 100%
2 | Installation of Refrigerant pipe dia 1 1/8'' |  | Rft | 970 |  |  | 1768 | 100%
3 | Installation of Refrigerant pipe dia 1 3/8'' |  | Rft | 33.5 |  |  | 33.5 | 100%
4 | Installation of Refrigerant pipe dia 1/2'' |  | Rft | 1593 |  |  | 1593 | 100%
5 | Installation of Refrigerant pipe dia 3/8'' |  | Rft | 2443 |  |  | 2443 | 100%