## HVAC
M/S Dawat-e-Hadiyah Burhani Mahal |  |  |  | Date | 2024-12-05
Mciver Road, Karachi |  |  |  | Invoice # | 320
|  |  |  | NTN # | 4312149-7
Invoice
Installation of HVAC Material for Food Court - The North Walk Shopping Mall
S. # | Description | Unit | Qty | Rate | Amount
1 | Regging, lifting & shifting of packaged unit at over head tank roof including installation of vibration isolator by rigger. | Nos | 2 | 25000 | 50000
2 | Installation of G.I. sheet metal duct machine made (22 / 24 SWG) with flange, nut bolts, gasket, duct sealant etc. complete in all respect. | Sqft | 4560 | 60 | 273600
3 | Installation of aluminum faced XLPE insulation 20mm thick for supply & return air ducts. (internal duct area) | Sqft | 1041 | 60 | 62460
4 | Installation of Glass wool insulation of 25mm thick for supply & return air ducts including canvas cloth & antifungus paint complete in all respect. (internal duct area) | Sqft | 262 | 30 | 7860
5 | Installation of PU insulation 50mm thick for supply & return air ducts including canvas cloth & antifungus paint complete in all respect. (internal duct area) | Sqft | 2880 | 75 | 216000
6 | Installation of G.I Cladding on exposed area duct (26 SWG) for protection of insulation. | Sqft | 3626 | 60 | 217560
7 | Installation of folding for installation of ducts and cladding. (after completion of job remove the folding from Site) | Job | 1 | 150000 | 150000
8 | Installation of double deflection return air grill including rectagular M.S pipe frame. |  |  |  | 0
| i) 18 x 24 | Nos | 4 | 2000 | 8000
| ii) 10 x 30 | Nos | 5 | 2000 | 10000
8 | Installation of owner supplied 06" dia jet diffuser | Nos | 20 | 1000 | 20000
9 | Installation of fresh air in take louver 12 x 20 | Nos | 2 | 1000 | 2000
10 | Installation of aluminium filter 1" thick 12 x 20 | Nos | 2 | 700 | 1400
11 | Installation of Flexible duct connector for return / supply air duct connection. | Rft | 36 | 100 | 3600
12 | Installation of volume control damper 12 x 20 | Nos | 2 | 1000 | 2000
13 | Installation of volume control damper 32 x 20 | Nos | 2 | 1500 | 3000
14 | Installation of Fire damper 32 x 20 | Nos | 2 | 1500 | 3000
15 | Installation of hangers / supports for G.I sheet metal ducts. | Job | 1 | 15000 | 15000
16 | Making of Shop drawings & As built on Auto CAD 2018. | Set | 1 | 10000 | 10000
17 | Installation of control wiring including installation of thermostat complete in all respect. | Job | 0 | 5000 | 0
18 | Painting & Identification. | Job | 1 | 20000 | 20000
19 | Testing & commissioning cordination with supplier | Job | 2 | 5000 | 10000
Total Amount Rs |  |  |  |  | 1085480
SST 15% |  |  |  |  | 162822
Grand Total |  |  |  |  | 1248302
For PIONEER SERVICES.
4122651
0
0
0
0
0
0
0
PIONEER SERVICES

## working
|  |  | Discount | 4.811%
Sub Total Amount | 3661200 | 756600
Claimed 50% | 1830600 | 378300
Discount | 88065.0403 | 18198.9538
Sub Total Amount | 1742534.9597 | 360101.0462
SRB 13% on Labour | 0 | 46813.136
Total Amount | 1742534.9597 | 406914.1823
Grand Total Amount |  | 2149449.1419
Sub Total Amount | 3661200 | 756600
Claimed 50% | 1830600 | 378300
SRB 13% on Labour | 0 | 49179
Total Amount | 1830600 | 427479
Discount | 88065.0403 | 20564.8177
Grand Total Amount | 1742534.9597 | 406914.1823
Grand Total Amount |  | 2149449.1419