## Summary
SANA SAFINAZ DOLMEN MALL, LAHORE |  |  |  | BILL OF QUANTITIES
HVAC & FIRE SUPPRESSION SYSTEM WORKS
M/S IK Associates
SUMMARY OF BILL OF QUANTITIES
ITEM NO. | DESCRIPTION | MATERIAL AMOUNT (RS.) | INSTALLATION AMOUNT (RS.) | TOTAL AMOUNT (RS.)
1 | HVAC |  |  | 5875840
2 | FIRE |  |  | 3116102
(C) | GRAND TOTAL (A3+B3) = |  |  | 8991942

## HVAC
S # | Description | Bill of Quantities |  |  |  | Running Bill No 1
[6 empty] | Material |  | Labour |  | Total Amount
|  | Unit | Qty | Material Rate | Labour Rate | Bill Qty | Amount | Bill Qty | Amount
Section 01: Supply, Installation, Testing & Commissioning of HVAC Equipment
1 | Lifting, Installation, Testing, Balancing & Commissioning of Air Handling Units of different capacities to the locations as per the new layout including hangers, supports, steel base, vibration isolators,interconnecting power & control wiring, Thermostats with inlet & outlet cooling water connections, valves assemblies, drain connection, flexible rubber duct connection / connector etc. complete in all respects, ready to operate as per schedule, specification, drawings and as per instruction of consultant.
a | CSU-1F-07 (7.0 Tons) | 2 | Nos. | 15000 | 15000 | 2 | 30000 | 2 | 30000 | 60000
SUB-TOTAL FOR SECTION 01 (Rs.)
Section 02:Supply, Installation & Testing of Piping Works
1 | Supply, Installation & Testing of uPVC Drain Pipe with 3/8" Thick Rubber Foam Insulation including clamps, bends, tees, drain plugs, sockets, protection treatment, PVC tape etc. complete in all respects and as per instructions of Consultant.
a | Ø 1-1/4" | 80 | Rft | 600 | 100 | 58 | 34800 | 58 | 5800 | 40600
2 | Supply, Installation, Testing & Balancing of MS Sch. 40 Seamless Pipes (for Chilled Water Supply/Return) with threaded fittings including sockets, tees, elbows, bends, reducers, unions, clamps, hangers & supports etc. making core cuts/holes (if required), painting and protection treatments on pipe. complete in all respect ready to operate as per specifications, drawings and as per instruction of Consultant.
b | Ø 1-1/2" Supply / Return | 90 | Rft | 1150 | 200 | 290 | 333500 | 290 | 58000 | 391500
3 | Supply & Installation of Pre Formed Thermopore insulation (32 kg/m3 density) for chilled water M.S. pipes, bends, tees, unions, sockets, valves and on specials protected with Kraft paper, wrapped with 8oz Canvas cloth than paint with Anti fungus paint, GI Cladding etc, complete in all respects ready to operate.
3.1 | 25 mm Thick Insulation
a | Ø 1-1/2" | 99 | Rft. | 500 | 100 | 290 | 145000 | 290 | 29000 | 174000
4 | Supply, Installation, Testing & Balancing of Valves of different types complete in all respect ready to operate as per specifications, drawings and as per instruction of Consultant. (Contractor to check the health of existing Valves before reuse)
4.1 | Gate / Isolation Valve
a | Ø 1-1/2" | 4 | Nos. | 18000 | 2000 | 4 | 72000 | 4 | 8000 | 80000
4.2 | Balancing Valve
a | Ø 1-1/2" | 2 | Nos. | 23000 | 2000 | 0 | 0 | 0 | 0 | 0
4.3 | Strainer
a | Ø 1-1/2" | 2 | Nos. | 17500 | 2000 | 2 | 35000 | 2 | 4000 | 39000
4.4 | 2-Way / 3-Way Motorized Valve with Actuator (0-100% modulating) | [5 empty] | 0 | 0 | 0 | 0
a | Ø 1-1/2" | 2 | Nos. | 180000 | 3000 | 2 | 360000 | 2 | 6000 | 366000
4.5 | Accessories for AHU(s) Assembly
a | Thermometer 150 mm Height Scale Type (with Thermo well) with range 0˚C to 60˚C | 4 | Nos. | 12000 | 1000 | 4 | 48000 | 4 | 4000 | 52000
b | Pressure Gauge with with Ball Valve & Siphon, Liquid filled Dial type range -ve 5 psi to 100 psi. (100mm dial Size) | 4 | Nos. | 12000 | 1000 | 4 | 48000 | 4 | 4000 | 52000
c | Digital Decorative Thermostat Controller with Duct Sensor (BMS Interfacable) | 2 | Nos. | 25000 | 2000 | 2 | 50000 | 2 | 4000 | 54000
d | Control wiring from controller to sensors, motorized valve and Power wiring from FCP to fan, up to 5 meter radius | 2 | Nos. | 27500 | 5000 | 2 | 55000 | 2 | 10000 | 65000
SUB-TOTAL FOR SECTION 02 (Rs.)
Section 03: Supply, Installation & Testing of Ducting & Air Devices
1 | Supply, fabrication, Installation & Testing of Machine Made G.I Sheet Metal Duct Work (galvanized G- 22 for internal & G-26 for external) for supply, return, fresh & exhaust air complete in all respects including plenums, splitter dampers, guide vanes, flexible duct connector, access door, transformation, plenums chambers, wooden frame, anchors as per SMACNA Standards along with supports & hangers complete in all respects ready to operate as per drawings, instruction and approval of Consultant.
1.1 | For AC Supply | 3888 | Sq.ft. | 490 | 80 | 3344 | 1638560 | 3344 | 267520 | 1906080
1.2 | For Fresh | 180 | Sq.ft. | 490 | 80 | 0 | 0 | 0 | 0 | 0
1.3 | Flexiable Connector
a | FC - 26"x14" | 1 | No. | 7000 | 1000 | 1 | 7000 | 1 | 1000 | 8000
b | FC - 28"x14" | 1 | No. | 7000 | 1000 | 1 | 7000 | 1 | 1000 | 8000
2 | Supply and Installation of Aluminum Faced XLPE insulation 1" thick for Internal ducts of different sections compete in all respect as per specifications, drawings and as per instructions of Consultant. | 4882 | Sq.ft. | 580 | 60 | 3344 | 1939520 | 3344 | 200640 | 2140160
3 | Supply, Installation & Commissioning of Aluminum Fabricated, Powder Coated Air Devices for supply, return, exhaust & fresh air. including framing, hangers & supports and other accessories etc. complete in all respects ready to operate as per instruction of Consultant.
Diffusers/Grilles/Registers (with Dampers)
3.1 | For AC - Supply Air
a | Round Diffusers - 6" Dia. | 6 | Nos. | 4500 | 750 | 6 | 27000 | 6 | 4500 | 31500
b | Swirl Diffusers - 12" Dia. | 29 | Nos. | 7500 | 750 | 26 | 195000 | 26 | 19500 | 214500
3.2 | Exhaust & Fresh Air Grills
a | FAG - 32"x14" | 1 | No. | 13500 | 2000 | 6 | 81000 | 6 | 12000 | 93000
b | EAG - 32"x14" | 1 | No. | 9250 | 1000 | 2 | 18500 | 2 | 2000 | 20500
3.3 | Fire Damper
a | FD - 32"x14" | 1 | No. | 9800 | 1000 | 0 | 0 | 0 | 0 | 0
SUB-TOTAL FOR SECTION 03 (Rs.)
Section 04: Miscellaneous Works
1 | Supply & Installation of Thermostats for AHUs along with control cables complete in all respect and ready to operate. | 2 | Nos. | 27000 | 3000 | 0 | 0 | 0 | 0 | 0
2 | Providing Material Submittals and Samples for Consultant's Approval. | 1 | Job. | 10000 | 10000 | 1 | 10000 | 1 | 10000 | 20000
3 | Supply & Installation of Brass Tags for Equipment and System. | 1 | Job. | 10000 | 5000 | 1 | 10000 | 1 | 5000 | 15000
4 | Supply, Installation and Commissioning of Fire Stopping Material as per specifications and drawings complete in all respect. | 1 | Job. | 10000 | 10000 | 1 | 10000 | 1 | 10000 | 20000
5 | Making of Shop Drawings and As-Built Drawings on Auto CAD with sectional details, equipment details and their foundation details, Technical submittals and sample boards complete in all respect as per instruction of Consultant. | 1 | Job. | 10000 | 15000 | 1 | 10000 | 1 | 15000 | 25000
6 | Supply, Installation and Commissioning of items not listed in BOQ but required for complition of work to ensure satisfactory performance. (Contractor to provide list) | 1 | Job. | 0 | 0 |  | 0 | 0 | 0 | 0
SUB-TOTAL FOR SECTION 04 (Rs.)
TOTAL COST OF WORKS (SECTION 01 TO SECTION 04) (Rs.) | [9 empty] | 5875840

## FIRE
S # | Description | Bill of Quantities |  |  |  | Running Bill No 1
[6 empty] | Material |  | Labour |  | Total Amount
|  | Unit | Qty | Material Rate | Labour Rate | Bill Qty | Amount | Bill Qty | Amount
SECTION 01: SUPPLY AND INSTALLATION OF FIRE EXTINGUISHERS
1 | 5 Kg. CO2 | 2 | Nos. | 27000 | 500 | 2 | 54000 | 2 | 1000 | 55000
2 | ABC Extinguishers | 4 | Nos. | 16250 | 500 | 4 | 65000 | 4 | 2000 | 67000
SUB-TOTAL FOR SECTION 01 (Rs.)
SECTION 02: SUPPLY AND INSTALLATION OF FIRE SPRINKLERS
1 | Sprinkler Pendent type with cover plate quick response K = 5.6 (Opening Temperature 57ºC) UL/FM | 10 | Nos. | 4250 | 600 | 13 | 55250 | 13 | 7800 | 63050
2 | Sprinkler Upright type standard response K = 5.6 (Opening Temperature 57ºC) UL/FM | 72 | Nos. | 3150 | 500 | 101 | 318150 | 101 | 50500 | 368650
SUB-TOTAL FOR SECTION 02 (Rs.)
SECTION 03: SUPPLY AND INSTALLATION OF MS PIPE WORK & VALVES
1 | Supply & installation of MS SCH 40 pipes (seamless) with threaded & welded fittings (UL/FM) including sockets, tees, elbows, bends, reducers, unions, clamps, hangers & supports etc. making core cuts/holes (if required), painting and protection treatments on pipe. complete in all respect ready to opearte.
a | Dia. 1" (Threaded fitting) | 420 | Rft. | 650 | 150 | 900 | 585000 | 900 | 135000 | 720000
b | Dia. 1-1/4" (Threaded fitting) | 160 | Rft. | 875 | 200 | 35 | 30625 | 35 | 7000 | 37625
c | Dia. 1-1/2" (Threaded fitting) | 253 | Rft. | 990 | 250 | 195 | 193050 | 195 | 48750 | 241800
d | Dia. 2" (Threaded fitting) | 131 | Rft. | 1275 | 300 | 40 | 51000 | 40 | 12000 | 63000
e | Dia. 2-1/2" (Welded Joint fitting) | 29 | Rft. | 1815 | 350 | 87 | 157905 | 87 | 30450 | 188355
f | Dia. 3" (Welded Joint fitting) | 127 | Rft. | 2370 | 400 | 260 | 616200 | 260 | 104000 | 720200 | 4" Valve variation | 119
2 | Test & Drain Assembly with sight glass & sectional drain valve. UL/FM
a | Dia. 1" | 1 | No. | 58000 | 2000 | 0 | 0 | 0 | 0 | 0
3 | Supply & installation of Seismic Supports (Bracing) of steel cable to restrict horizontal shaking of pipe from earth quake with Strut Fittings · Strut beam clamps · Strut pipe clamps · Strut mounted pipe .clamping pipe attachments complete in all respect.
3.1 | Lateral
a | Dia. 2" | 1 | No. | 16300 | 1000 | 1 | 16300 | 1 | 1000 | 17300
b | Dia. 2-1/2" | 1 | No. | 16500 | 1000 | 1 | 16500 | 1 | 1000 | 17500
c | Dia. 3" | 1 | No. | 17500 | 1000 | 1 | 17500 | 1 | 1000 | 18500
d | Dia. 4" | 3 | Nos. | 17650 | 1000 | 3 | 52950 | 3 | 3000 | 55950
3.2 | Longitudnal
a | Dia. 2" | 1 | No. | 20500 | 1000 | 1 | 20500 | 1 | 1000 | 21500
c | Dia. 3" | 1 | No. | 21250 | 1000 | 1 | 21250 | 1 | 1000 | 22250
a | Dia. 4" | 1 | No. | 22222 | 1000 | 1 | 22222 | 1 | 1000 | 23222
3.3 | Restraint
a | Dia. 1" | 13 | Nos. | 6000 | 1500 | 13 | 78000 | 13 | 19500 | 97500
b | Dia. 1-1/4" | 12 | Nos. | 6250 | 500 | 12 | 75000 | 12 | 6000 | 81000
c | Dia. 1-1/2" | 3 | Nos. | 6500 | 500 | 3 | 19500 | 3 | 1500 | 21000
d | Dia. 2" | 1 | No. | 7200 | 500 | 1 | 7200 | 1 | 500 | 7700
SUB-TOTAL FOR SECTION 03 (Rs.)
SECTION 04: SUPPLY AND INSTALLATION OF PASSIVE FIRE PROTECTION
1 | Supply and Installation of Fire Stop Material (for passive fire fighting / smoke barrier) in all MEP openings and penetrations, either in slab or wall, complete in all respects, ready to operate as per fire stopper recommended material, and as per instruction of Consultant. | 1 | Job. | 20000 | 8000 | 1 | 20000 | 1 | 8000 | 28000
SUB-TOTAL FOR SECTION 04 (Rs.)
SECTION 05: MISCELLANEOUS ITEMS
1 | Providing Material Submittals and Samples for Consultant's Approval. | 1 | Job. | 10000 | 10000 | 1 | 10000 | 1 | 10000 | 20000
2 | Making of Shop Drawings & As-Built Drawings for Consultant's Approval. | 1 | Job. | 10000 | 15000 | 1 | 10000 | 1 | 15000 | 25000
3 | Painting, Identification and Tagging as per standards. | 1 | Job. | 45000 | 55000 | 1 | 45000 | 1 | 55000 | 100000
4 | Testing, Balancing and Commissioning of entire fire fighting system as per approval of consultant. | 1 | Job. | 15000 | 20000 | 1 | 15000 | 1 | 20000 | 35000
5 | Supply, Installation and Commissioning of items not listed in BOQ but required to complete the system for satisfacotry performance. (Contractor to provide the list of item if required) | 1 | Job. |  |  |  | 0 | 0 | 0 | 0
SUB-TOTAL FOR SECTION 05 (Rs.)
TOTAL COST OF WORKS (SECTION 01 TO SECTION 05) (Rs.) | [9 empty] | 3116102