## Sheet1
M/S IK Associates | [7 empty] | 2024-09-18
Project: DHL Office, Fortune Center, Karachi
Attn: Mr. Taha Ghaznavi
Variation order No 2
Variation order for Extra Work for VRF & Split Units.
S. # | Description | Material Rate | Labour Rate | Over Head profit 28% | Total Rates | Unit | Qty | Amount
1 | Unloading of VRF units from container by regger, lifted and shifted with lifter to the 3rd floor parking and 12th floor. | 0 | 45000 | 12600 | 57600 | Job | 1 | 57600
2 | Unloading of split units from container by regger and lifted shifted with lifter to the 12th floor and roof. | 0 | 45000 | 12600 | 57600 | Job | 1 | 57600
3 | VRf condencing units lifted to the roof top by rgger including cuttings and reinstallation of grills' supports etc complete in all respect. | 0 | 90000 | 25200 | 115200 | Job | 1 | 115200
4 | Providing and making RCC plateform for VRF and split units condencing units. (as required by Building) | 0 | 160000 | 44800 | 204800 | Job | 1 | 204800
5 | Intallation of fresh air unit with related fittings. | 0 | 15000 | 4200 | 19200 | Job | 1 | 19200
6 | Core cuttings for split units and VRF copper pipes as roof given by building owner. | 0 | 1800 | 504 | 2304 | Nos | 42 | 96768
7 | Providing and installation of 1 HP pressure pump set with related fittings such as valve, non return valve, pressure cut out etc complete in all respect. | 85000 | 10000 | 26600 | 121600 | Job | 1 | 121600
8 | Supply of Freon of split AC and VRF system. | 56640 | 0 | 15859.2 | 72499.2 | Set | 3 | 217497.6
9 | Providing and installation of UPVC pipe 06" Dia with related fittings such as Reducing-Tee, elbow & Reducing Socket | 1450 | 300 | 490 | 2240 | Rft | 48 | 107520
10 | Providing and installation of UPVC pipe 04" Dia with related fittings such as Reducing-Tee, elbow & Reducing Socket | 2200 | 200 | 672 | 3072 | Rft | 54 | 165888
11 | Supply and installation of Disc valve. | 4500 | 500 | 1400 | 6400 | Nos | 9 | 57600
Total Amount Rs. | [7 empty] | 1221273.6
Note: Vendor quotation attached
Thanking you,
For PIONEER ENGINEERING SERVICES.
Bilal Habib