## Sheet1
Current Work Status for the Project Saifee Hospital Karachi
S No | Floor | Water Supply | Sewage | Fire Fighting | Remark
1 | Ground Floor | Hold By Client | Hold By Client | Awaiting For Civil Work
2 | First Floor | Piping Done 100%, Fixtures Remaining, Riser Not Install, Testing in Progress. | Piping Done 100%, Fixtures Remaining, Riser, Soil, Rain, Waste & Rain, Testing in Progress. | Awaiting For Civil Work | Riser To Install
3 | Second Floor | Piping Done 100%, Fixtures Remaining, Riser Not Install, Testing in Progress. | Piping Done 100%, Fixtures Remaining, Riser, Soil, Rain, Waste & Rain, Testing in Progress. | 50%
4 | Third Floor | Piping Done 100%, Fixtures Remaining, Riser Not Install, Testing in Progress. | Piping Done 100%, Fixtures Remaining, Riser, Soil, Rain, Waste & Rain, Testing in Progress. | 50%
5 | Forth Floor | Piping Done 100%, Fixtures Remaining, Riser Not Install, Testing in Progress. | Piping Done 100%, Fixtures Remaining, Riser, Soil, Rain, Waste & Rain, Testing in Progress. | 50%
6 | Fifth Floor | Piping Done 100%, Fixtures Remaining, Riser Not Install, Testing in Progress. | Piping Done 100%, Fixtures Remaining, Riser, Soil, Rain, Waste & Rain, Testing in Progress. | 50%
7 | Sixth Floor | Piping Done 100%, Fixtures Remaining, Riser Not Install, Testing in Progress. | Piping Done 100%, Fixtures Remaining, Riser, Soil, Rain, Waste & Rain, Testing in Progress. | 50%
8 | Seventh Floor | Piping Done 100%, Fixtures Remaining, Riser Not Install, Testing in Progress. | Piping Done 100%, Fixtures Remaining, Riser, Soil, Rain, Waste & Rain, Testing in Progress. | 50%
9 | Eight Floor | Piping Done 100%, Fixtures Remaining, Riser Not Install, Testing in Progress. | Piping Done 100%, Fixtures Remaining, Riser, Soil, Rain, Waste & Rain, Testing in Progress. | 50%
10 | Ninth Floor | Piping Done 100%, Fixtures Remaining, Riser Not Install, Testing in Progress. | Piping Done 100%, Fixtures Remaining, Riser, Soil, Rain, Waste & Rain, Testing in Progress. | 50%
11 | Ten Floor | Hold By Client | Hold By Client | 50%
12 | Eleven Floor | Hold By Client | Hold By Client | 50%
13 | Roof | Awaiting For Client
Note:
Awaiting for 10th & 11th Floor Final Drawings and awaiting for OFM Fire Equipment.