## Table 1
HVAC & Fire Fighting Work Schedule
Description | Duration | Start Date | End Date | Remarks | 2024-06-01 |  |  |  | 2024-07-01 |  |  |  | 2024-08-01 |  |  |  | 2024-09-01
[5 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
12th FLOOR
Shop Drawings | 07 Days | 2023-03-22 | 2023-04-02
Installation of Ducted Units (OFM) | 60 Days | 2023-04-08 | 2023-05-15 | OFM
Installation of VAVs | 30 Days | 2023-04-08 | 2023-05-15 | OFM
Water & air balancing | 21 Days
Installation of Ventilation Fan | 30 Days | 2023-04-08 | 2023-05-15 | OFM
Installation of Hanger & Support | 90 Days | 2023-03-22 | 2023-04-08
Installation of Chilled water Pipe | 45 Days | 2023-04-08 | 2023-05-15
Insulation Of Chilled water Pipe | 45 Days | 2023-05-15 | 2023-05-25
Installation of ducting | 60 Days | 2023-04-08 | 2023-05-15
Duct Insulation work | 60 Days | 2023-05-15 | 2023-05-25
Installation of MS Fire Pipe | 60 Days | 2023-04-08 | 2023-05-15
Condensate Drain Piping with insulation | 30 Days | 2023-04-01 | 2023-04-25
Installation of air devices | 60 Days | 2023-05-25 | 2023-05-30
Painting / Identification | 60 Days | 2023-05-25 | 2023-05-30
Fire Sprinkler & Fire Extinguishers | 45 Days | 2023-05-20 | 2023-05-30
FCU Assembly Testing | 7 Days | 2023-05-30 | 2023-06-02
FCU Commissioning | 7 Days | 2023-05-30 | 2023-06-02
AHU Testing & Commissioning | 7 Days
Fire Testing | 14 Days | 2023-05-30 | 2023-06-02
Fire Commissioning | 14 Days | 2023-05-30 | 2023-06-02