## Summary
Bank Al-Habib Limited
HVAC & Fire Fighting Work |  |  |  | 2023-10-06
22nd & 23rd Floor Centerpoint Karachi
SUMMARY OF RUNNING BILL NO 1
S.No | Description | Material | Labour | Amount
1 | HVAC 22nd Floor | 13125993.5 | 1004056.5 | 14130050
2 | HVAC 23rd Floor | 12293464.5 | 844753.5 | 13138218
| Total Amount HVAC |  |  | 27268268
3 | Fire Fighting 22nd Floor | 2234704.19 | 494449.01 | 2729153.2
4 | Fire Fighting 23rd Floor | 1223172.24 | 275927.98 | 1499100.22
| Total Amount Fire Fighting |  |  | 4228253.42
| Grand Total Amount | 28877334.43 | 2619186.99 | 31496521.42
31455571
-40950.42

## HVAC 22nd Floor
Bill of Quantities ACMV Works Bank Al Habib (22nd Floor) Centrepoint, Karachi
Bill of Quantities | [6 empty] | RUNNING BILL NO 1
Sr. | No. | DESCRIPTION | UNIT | QTY | MATERIAL RATE | LABOUR RATE | BILL QTY | MATERIAL AMOUNT | BILL QTY | LABOUR AMOUNT | TOTAL AMOUNT
AMOUNT
All works shall be completed, tested and commissioned as per drawings, specifications and as per instruction of Consultant
Cutting dismantling and shifting of the existing ACMV works as per instruction of consuttant, including cleaning the site and shifting the dismantled parts / mater al to suitable place given by client complete in ali respects ready to operate as per drawings and as per instruction of consu!tant.
1 |  | ACMV WorKs i.e; FCU, Pipe, Vlaves, accessories, duct, inulation etc complete job as reguired | Job. | 1 | 0 | 105000 |  | 0 | 0.8 | 84000 | 84000
2 |  | Unloading, installation, testing and commissioning of (Owner Supplled) of fan coil units of different capacities complete in all respects, ready to operate including suppIy and insatallation of all accessories, supports. hanger steel base, vibration isolators, including interconnecting power & control wiring (terminal connection) with inlet & outlet chilled water connections, drain connection, flexible rubber duct connect on / connector etc. complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant. DFCU-01 | Nos | 2 | 0 | 5250 |  | 0 | 2 | 10500 | 10500
3 |  | Supply & installation of valves & accessories for FCU with supports, hangers, flanges, gas kits, nut & bolts where it required, etc. complete in all respects as per specifications, drawings and as per instructions of consultant. |  |  | 0 | 0 |  |  | 0
|  | Gate Valve |  |  | 0 | 0 |  |  | 0
| 3.1 | 25mm dia | Nos | 8 | 8768 | 1050 | 4 | 35072 | 4 | 4200 | 39272
|  | Strainers | [6 empty] | 0 |  | ”
| 3.1 | 25mm dia | Nos | 2 | 7613 | 1050 | 2 | 15226 | 2 | 2100 | 17326
| 3.3 | Balancing Valve (with self sealing measuring nipples) | [6 empty] | 0
|  | 25mm dia | Nos. | 2 | 19425 | 1050 | 2 | 38850 | 2 | 2100 | 40950
| 3.4 | Thermometer 150mm Height Scale Type (w th Thermo well) 0 °C to 60 °C | Nos. | 4 | 11550 | 1050 | 0 | 0 | 0 | 0 | 0
| 3.5 | Pressure Gauge with Ball Valve & Siphon, Liquid filled Dial type range 0 psi to 100 psi. (100mm dial Size) | Nos. | 4 | 9975 | 1050 | 0 | 0 | 0 | 0 | 0
| 3.6 | 2-Way Motorized Valve with Actuator (0-100% modulating) | [6 empty] | 0
|  | 25mm dia | Nos. | 2 | 92400 | 1050 | 1 | 92400 | 1 | 1050 | 93450
| 3.7 | Digital Decora1ive Thermostat Controller (BMS Interfacable with Ouct Mounted Sensor | Nos. | 2 | 57750 | 1050 | 0 | 0 | 0 | 0 | 0
| 3.8 | Control wiring from controller to sensors, motorized valve and Power wiring up to 15’ radius | Job. | 2 | 21000 | 3150 | 0 | 0 | 0 | 0 | 0
4 |  | Supply & installation of SCH-40 M.S.(As per ASME & API standard, Heavy Quality with standard SCH 40 wall thickness) pipes & fitting for chilled & cooling water circulation system complete with bends, tees, unions, sockets, specials, support, hangers & anchors, M.S. angle, U channel, roller support, bolts, rods, clamps, concrete fasteners etc as requireo to complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. |  |  | 0 | 0 |  |  | 0
| 4.1 | 25mm dia | Rm | 30 | 3045 | 735 | 0 | 0 | 0 | 0 | 0
| 4.2 | 32mm dia | Rm | 15 | 3675 | 840 | 0 | 0 | 0 | 0 | 0
5 |  | Supply & installation of aluminum foil facing fiber glass (24 kg/m3 density) insulation with aluminum threaded tape, protected with 8oz canvas cloth than painted anti fungus paint, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. |  |  | 0 | 0 |  |  | 0
| 5.1 | 25mm dia | Rm | 30 | 2835 | 210 | 0 | 0 | 0 | 0 | 0
| 5.2 | 32mm dia | Rm | 15 | 3990 | 315 | 0 | 0 | 0 | 0 | 0
6 | 6.1 | Supply & istallation of uPVC (Sch 40.) drain pipe insula1ed with 3/8" thick rubber foam insulation including clamps, bends, tees, drain plugs, sockets, protection treatment, PVC tape wrapping. supports & hangers complete in all respects as per specifications, drawings & as per instructions of Consultant. 25mm dia | Rm | 20 | 1680 | 315 | 0 | 0 | 0 | 0 | 0
7 |  | Supply & installation of VAV Boxes as per mentioned in schedule with digital thermostat controller, pressure sensor, control wiring, including supply & installation of flexible duct connection / connector, electrical connection, lindaptor support & hangers complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. |  |  | 0 | 0 |  |  | 0
|  | VAV-01 | No. | 1 | 295470 | 3150 | 1 | 295470 | 1 | 3150 | 298620
|  | VAV-02 | No. | 1 | 308700 | 3150 | 1 | 308700 | 1 | 3150 | 311850
|  | VAV-03 | Nos. | 1 | 285180 | 3150 | 2 | 570360 | 2 | 6300 | 576660
|  | VAV-04 | No. | 1 | 296205 | 3150 | 1 | 296205 | 1 | 3150 | 299355
|  | VAV-05 | Nos. | 3 | 308700 | 3150 | 3 | 926100 | 3 | 9450 | 935550
|  | VAV-06 | Nos. | 1 | 308700 | 3150 | 1 | 308700 | 1 | 3150 | 311850
|  | VAV-07 | No. | 1 | 285180 | 3150 | 1 | 285180 | 1 | 3150 | 288330
|  | VAV-08 | No. | 1 | 295470 | 3150 | 1 | 295470 | 1 | 3150 | 298620
|  | VAV-09 | No. | 2 | 295470 | 3150 | 2 | 590940 | 2 | 6300 | 597240
|  | VAV-10 | No. | 1 | 277463 | 3150 | 1 | 277463 | 1 | 3150 | 280613
|  | VAV-11 | No. | 2 | 295470 | 3150 | 2 | 590940 | 2 | 6300 | 597240
|  | VAV-12 | No. | 1 | 277463 | 3150 | 1 | 277463 | 1 | 3150 | 280613
8 |  | Supply, rigging, lifting, placement, installation, testing and commissioning of Ventilation Fans as per mentioned in schedule, including supply & installation of vibration isolator, electrical connection, flexible duct connection / connector, support & hangers compiete in all respects ready to operate as per drawings, specification and as per instruction of consultant. |  |  | 0 | 0 |  |  | 0
8.1 | 8.1 | TAF-01 | Nos. | 1 | 25200 | 3150 | 1 | 25200 | 1 | 3150 | 28350
8.2 | 8.2 | TAF-02 | Nos. | 2 | 65625 | 3150 | 2 | 131250 | 2 | 6300 | 137550
| 8.3 | TAF-03 | Nos. | 1 | 72450 | 3150 | 1 | 72450 | 1 | 3150 | 75600
| 8.4 | TAF-04 | Nos. | 2 | 72450 | 3150 | 2 | 144900 | 2 | 6300 | 151200
| 8.5 | TAF-05 | Nos. | 1 | 82950 | 3150 | 1 | 82950 | 1 | 3150 | 86100
9 |  | Supply, fabrication and installation of machine made G.I sheet metal duct different sections supply, return, fresh & exhaust air including plenums, splitter dampers, guide vanes, flexbile duct connector / connections, access doors, transformation, plenem chambers, wooden frames, anchors, supports & hangers complete in all respect ready to operate as per drawings, specification, instruction and approval of consultant. | Sqm | 1000 | 5775 | 693 | 586.5 | 3387037.5 | 586.5 | 406444.5 | 3793482
10 |  | Supply & installation of adhesive 20mm thick rubber foam (XLPE) insulation with aluminum foil over supply & return duct and plenums (except toilet exhaust duct), complete in al respects ready to operate as per specification, drawings and aser instruction, of consultant | Sqm | 1000 | 6038 | 578 | 586.5 | 3541287 | 586.5 | 338997 | 3880284
11 |  | Supply & installation of acoustcal duct sound liner adhesive with 12mm thick in supply air duct complete in all respects ready to operate as per specification, drawings and as per istruction of consultant. | Sqm | 60 | 5723 | 578 | 0 | 0 | 0 | 0 | 0
12 |  | Supply, installation of Aluminum fabricated, powder coated Grills, Diffusers and Registers for supply air. return air, exhaust air & fresh air of different sizes (Grade A ), wooden frame, supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. |  |  | 0 | 0 |  |  | 0
|  | Supply & Return Air Registers / Diffuser with Damper |  |  | 0 | 0 |  |  | 0
| 12.1 | 300mm x 300mm Square Diffuser | Nos. | 6 | 4200 | 735 | 0 | 0 | 0 | 0 | 0
|  | 375mm x 375mm Square Diffuser | Nos. | 2 | 6038 | 735 | 0 | 0 | 0 | 0 | 0
| 12.2 | 300mm dia Jet Diffuser | Nos. | 4 | 9450 | 1050 | 0 | 0 | 0 | 0 | 0
|  | Supply & Return Air Grills |  |  | 0 | 0 |  |  | 0
| 12.3 | 450mm x 250mm | Nos. | 2 | 4725 | 735 | 0 | 0 | 0 | 0 | 0
| 12.4 | S S. wire Mesh with G.I Frame | Sqm | 3 | 3150 | 525 | 0 | 0 | 0 | 0 | 0
|  | Linear Slots 6,000 Series |  |  | 0 | 0 |  |  | 0
| 12.5 | 2 Slots of 20mm | Rm | 110 | 4725 | 735 | 0 | 0 | 0 | 0 | 0
13 |  | Supply & installation of flexible duct including hangers, jubilee clamp complete in all respects as per specification, drawings & as per instruction of consultant. |  |  | 0 | 0 |  |  | 0
| 13.1 | 150mm dia | Rm | 110 | 1523 | 315 | 80 | 121840 | 80 | 25200 | 147040
14 |  | Supply & installation of butterfly damper for above flexible duct with gas bits, nut bolts, complete in all respects, ready to erLal te s per specification, drawings & as per instruction of the consultant |  |  | 0 | 0 |  |  | 0
| 14.1 | 150mm dia | Nos. | 105 | 2888 | 263 | 105 | 303240 | 105 | 27615 | 330855
15 |  | Supply, Installation of Volume Control Damper in 16 SWG G.I sheet metal with gaskets, nut bolts, etc, complete in all respects ready to operate as per specification, drawings and as ger instruction of consultant | Sqm | 6 | 47775 | 5250 | 2 | 95550 | 2 | 10500 | 106050
16 |  | Painting & Identification work on supports, hangers platfom of condensing units etc complete in all respects witn one coat of ICI make Red lead oxide primer & two coats of ICI make enamel paint complete in all respects ready to operate as per drawings, specification, instruction and approval of Consuttant. | Lot | 1 | 21000 | 15750 | 50% | 10500 | 50% | 7875 | 18375
17 |  | Testing & commissioning of the system (from independent agency) complete in all respects inc!ud ng air measurement & balancing, temp, pressure & electrical data of related equipment etc. complete in all respects ready to operate as per specification, drawings and as get instruction of Consultant. | Job. | 1 |  | 52500 |  | 0 | 0 | 0 | 0
18 |  | Making of Shop drawings on Auto CAD (latest version) with section details, equipment foundation details and Making of as built drawings, documentatin technical / operational manual & LOG book for each equipment complete in all respect as per specification, drawings and as per instruction of Consultant. | Job. | 1 | 10500 | 15750 | 50% | 5250 | 50% | 7875 | 13125
|  | Total Cost of Works Rs. | [5 empty] | 13125993.5 |  | 1004056.5 | 14130050

## HVAC 23rd Floor
Bill of Quantities ACMV Works Bank Al Habib (23rd Floor) Centrepoint, Karachi
Bill of Quantities | [6 empty] | RUNNING BILL NO 1
Sr. | No. | DESCRIPTION | UNIT | QTY | MATERIAL RATE | LABOUR RATE | BILL QTY | MATERIAL AMOUNT | BILL QTY | LABOUR AMOUNT | TOTAL AMOUNT
All works shall be completed, tested and commissioned as per drawings, specifications and as per instruction of Consultant
Cutting dismantling and shifting of the existing ACMV works as per instruction of consuttant, including cleaning the site and shifting the dismantled parts / mater al to suitable place given by client complete in ali respects ready to operate as per drawings and as per instruction of consu!tant.
1 |  | ACMV WorKs i.e; FCU, Pipe, Vlaves, accessories, duct, inulation etc complete job as reguired | Job. | 1 | 0 | 105000 |  | 0 | 80% | 84000 | 84000
2 |  | Unloading, installation, testing and commissioning of (Owner Supplled) of fan coil units of different capacities complete in all respects, ready to operate including suppIy and insatallation of all accessories, supports. hanger steel base, vibration isolators, including interconnecting power & control wiring (terminal connection) with inlet & outlet chilled water connections, drain connection, flexible rubber duct connect on / connector etc. complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant. DFCU-01 | Nos | 2 | 0 | 5250 |  | 0 | 2 | 10500 | 10500
3 |  | Supply & installation of valves & accessories for FCU with supports, hangers, flanges, gas kits, nut & bolts where it required, etc. complete in all respects as per specifications, drawings and as per instructions of consultant. | [6 empty] | 0
|  | Gate Valve | [6 empty] | 0
| 3.1 | 25mm dia | Nos | 8 | 8768 | 1050 | 4 | 35072 | 4 | 4200 | 39272
|  | Strainers | [6 empty] | 0 |  | ”
| 3.1 | 25mm dia | Nos | 2 | 7613 | 1050 | 2 | 15226 | 2 | 2100 | 17326
| 3.3 | Balancing Valve (with self sealing measuring nipples) | [6 empty] | 0
|  | 25mm dia | Nos. | 2 | 19425 | 1050 | 2 | 38850 | 2 | 2100 | 40950
| 3.4 | Thermometer 150mm Height Scale Type (w th Thermo well) 0 °C to 60 °C | Nos. | 4 | 11550 | 1050 | 0 | 0 | 0 | 0 | 0
| 3.5 | Pressure Gauge with Ball Valve & Siphon, Liquid filled Dial type range 0 psi to 100 psi. (100mm dial Size) | Nos. | 4 | 9975 | 1050 | 0 | 0 | 0 | 0 | 0
| 3.6 | 2-Way Motorized Valve with Actuator (0-100% modulating) | [6 empty] | 0
|  | 25mm dia | Nos. | 2 | 92400 | 1050 | 1 | 92400 | 1 | 1050 | 93450
| 3.7 | Digital Decora1ive Thermostat Controller (BMS Interfacable with Ouct Mounted Sensor | Nos. | 2 | 57750 | 1050 |  | 0 | 0 | 0 | 0
| 3.8 | Control wiring from controller to sensors, motorized valve and Power wiring up to 15’ radius | Job. | 2 | 21000 | 1050 |  | 0 | 0 | 0 | 0
4 |  | Supply & installation of SCH-40 M.S.(As per ASME & API standard, Heavy Quality with standard SCH 40 wall thickness) pipes & fitting for chilled & cooling water circulation system complete with bends, tees, unions, sockets, specials, support, hangers & anchors, M.S. angle, U channel, roller support, bolts, rods, clamps, concrete fasteners etc as requireo to complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | [6 empty] | 0
| 4.1 | 25mm dia | Rm | 25 | 3045 | 735 | 0 | 0 | 0 | 0 | 0
| 4.2 | 32mm dia | Rm | 15 | 3675 | 840 | 0 | 0 | 0 | 0 | 0
5 |  | Supply & installation of aluminum foil facing fiber glass (24 kg/m3 density) insulation with aluminum threaded tape, protected with 8oz canvas cloth than painted anti fungus paint, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | [6 empty] | 0
| 5.1 | 25mm dia | Rm | 25 | 2835 | 210 | 0 | 0 | 0 | 0 | 0
| 5.2 | 32mm dia | Rm | 15 | 3990 | 315 | 0 | 0 | 0 | 0 | 0
6 | 6.1 | Supply & istallation of uPVC (Sch 40.) drain pipe insula1ed with 3/8" thick rubber foam insulation including clamps, bends, tees, drain plugs, sockets, protection treatment, PVC tape wrapping. supports & hangers complete in all respects as per specifications, drawings & as per instructions of Consultant. 25mm dia | Rm | 20 | 1680 | 315 | 0 | 0 | 0 | 0 | 0
7 |  | Supply & installation of VAV Boxes as per mentioned in schedule with digital thermostat controller, pressure sensor, control wiring, including supply & installation of flexible duct connection / connector, electrical connection, lindaptor support & hangers complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. |  |  | 0 | 0 |  |  | 0
|  | VAV-01 | No. | 1 | 270480 | 3150 | 1 | 270480 | 1 | 3150 | 273630
|  | VAV-02 | No. | 1 | 277463 | 3150 | 1 | 277463 | 1 | 3150 | 280613
|  | VAV-03 | Nos. | 2 | 310170 | 3150 | 2 | 620340 | 2 | 6300 | 626640
|  | VAV-04 | No. | 1 | 295470 | 3150 | 1 | 295470 | 1 | 3150 | 298620
|  | VAV-05 | Nos. | 2 | 285180 | 3150 | 2 | 570360 | 2 | 6300 | 576660
|  | VAV-06 | Nos. | 2 | 295470 | 3150 | 2 | 590940 | 2 | 6300 | 597240
|  | VAV-07 | No. | 1 | 308700 | 3150 | 1 | 308700 | 1 | 3150 | 311850
|  | VAV-08 | No. | 1 | 295470 | 3150 | 1 | 295470 | 1 | 3150 | 298620
|  | VAV-09 | No. | 1 | 285180 | 3150 | 1 | 285180 | 1 | 3150 | 288330
|  | VAV-10 | No. | 1 | 295470 | 3150 | 1 | 295470 | 1 | 3150 | 298620
|  | VAV-11 | No. | 1 | 285180 | 3150 | 1 | 285180 | 1 | 3150 | 288330
|  | VAV-12 | No. | 1 | 285180 | 3150 | 1 | 285180 | 1 | 3150 | 288330
|  | VAV-13 | No. | 1 | 285170 | 3150 | 1 | 285170 | 1 | 3150 | 288320
|  | VAV-14 | No. | 1 | 296205 | 3150 | 1 | 296205 | 1 | 3150 | 299355
|  | VAV-15 | No. | 1 | 285180 | 3150 | 1 | 285180 | 1 | 3150 | 288330
|  | VAV-16 | No. | 1 | 277463 | 3150 | 1 | 277463 | 1 | 3150 | 280613
|  | VAV-17 | No. | 1 | 285180 | 3150 | 1 | 285180 | 1 | 3150 | 288330 | 20
8 |  | Supply, rigging, lifting, placement, installation, testing and commissioning of Ventilation Fans as per mentioned in schedule, including supply & installation of vibration isolator, electrical connection, flexible duct connection / connector, support & hangers compiete in all respects ready to operate as per drawings, specification and as per instruction of consultant. | [6 empty] | 0
8.1 | 8.1 | TAF-01 | Nos. | 1 | 24675 | 3150 | 1 | 24675 | 1 | 3150 | 27825
8.2 | 8.2 | TAF-02 | Nos. | 2 | 59850 | 3150 | 2 | 119700 | 2 | 6300 | 126000 |  |  |  | #REF!
| 8.3 | TAF-03 | Nos. | 2 | 67725 | 3150 | 2 | 135450 | 2 | 6300 | 141750
9 |  | Supply, fabrication and installation of machine made G.I sheet metal duct different sections supply, return, fresh & exhaust air including plenums, splitter dampers, guide vanes, flexbile duct connector / connections, access doors, transformation, plenem chambers, wooden frames, anchors, supports & hangers complete in all respect ready to operate as per drawings, specification, instruction and approval of consultant. | Sqm | 900 | 5775 | 693 | 508.5 | 2936587.5 | 508.5 | 352390.5 | 3288978
10 |  | Supply & installation of adhesive 20mm thick rubber foam (XLPE) insulation with aluminum foil over supply & return duct and plenums (except toilet exhaust duct), complete in al respects ready to operate as per specification, drawings and aser instruction, of consultant | Sqm | 900 | 6038 | 578 | 508.5 | 3070323 | 508.5 | 293913 | 3364236
11 |  | Supply & installation of acoustcal duct sound liner adhesive with 12mm thick in supply air duct complete in all respects ready to operate as per specification, drawings and as per istruction of consultant. | Sqm | 60 | 5723 | 578 | 0 | 0 | 0 | 0 | 0
12 |  | Supply, installation of Aluminum fabricated, powder coated Grills, Diffusers and Registers for supply air. return air, exhaust air & fresh air of different sizes (Grade A ), wooden frame, supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | [6 empty] | 0
|  | Supply & Return Air Registers / Diffuser with Damper | [6 empty] | 0
| 12.1 | 300mm x 300mm Square Diffuser | Nos. | 15 | 4200 | 735 | 0 | 0 | 0 | 0 | 0
| 12.2 | 300mm dia Jet Diffuser | Nos. | 4 | 9450 | 1050 | 0 | 0 | 0 | 0 | 0
|  | Supply & Return Air Grills | [6 empty] | 0
| 12.3 | 450mm x 250mm | Nos. | 2 | 4725 | 735 | 0 | 0 | 0 | 0 | 0
| 12.4 | S S. wire Mesh with G.I Frame | Sqm | 2 | 3150 | 525 | 0 | 0 | 0 | 0 | 0
|  | Linear Slots 6,000 Series | [6 empty] | 0
| 12.5 | 2 Slots of 20mm | Rm | 110 | 4725 | 735 | 0 | 0 | 0 | 0 | 0
13 |  | Supply & installation of flexible duct including hangers, jubilee clamp complete in all respects as per specification, drawings & as per instruction of consultant. | [6 empty] | 0
| 13.1 | 150mm dia | Rm | 120 | 1523 | 315 |  | 0 | 0 | 0 | 0
14 |  | Supply & installation of butterfly damper for above flexible duct with gas bits, nut bolts, complete in all respects, ready to erLal te s per specification, drawings & as per instruction of the consultant | [6 empty] | 0
| 14.1 | 150mm dia | Nos. | 120 | 2888 | 263 |  | 0 | 0 | 0 | 0
15 |  | Supply, Installation of Volume Control Damper in 16 SWG G.I sheet metal with gaskets, nut bolts, etc, complete in all respects ready to operate as per specification, drawings and as ger instruction of consultant | Sqm | 6 | 47775 | 5250 |  | 0 | 0 | 0 | 0
16 |  | Painting & Identification work on supports, hangers platfom of condensing units etc complete in all respects witn one coat of ICI make Red lead oxide primer & two coats of ICI make enamel paint complete in all respects ready to operate as per drawings, specification, instruction and approval of Consuttant. | Lot | 1 | 21000 | 15750 | 50% | 10500 | 50% | 7875 | 18375
17 |  | Testing & commissioning of the system (from independent agency) complete in all respects inc!ud ng air measurement & balancing, temp, pressure & electrical data of related equipment etc. complete in all respects ready to operate as per specification, drawings and as get instruction of Consultant. | Job. | 1 | 0 | 52500 |  | 0 | 0 | 0 | 0
18 |  | Making of Shop drawings on Auto CAD (latest version) with section details, equipment foundation details and Making of as built drawings, documentatin technical / operational manual & LOG book for each equipment complete in all respect as per specification, drawings and as per instruction of Consultant. | Job. | 1 | 10500 | 15750 | 50% | 5250 | 50% | 7875 | 13125
|  | Total Coat of Works Rs. | [5 empty] | 12293464.5 |  | 844753.5 | 13138218 | 13829703.1579 | 691485.1579 | 13138218

## Fire 22nd
Bill of Quantities Fire Suppression Services Bank AI Habib Limited (22nd Floor) Center Point Tower, Karachi.
Bill of Quantities | [5 empty] | RUNNING BILL NO 1
S.No. | Description | UnN | Qty | Material Rate | Labour Rate | BILL QTY | MATERIAL AMOUNT | BILL QTY | LABOUR AMOUNT | TOTAL AMOUNT
1 1.1 2 2.1 2.2 2.3 2.4 2.5 2.6 2.7 3 3.1 3.2 | FIRE FIGHTING SERVICES Supply, installation, testing & commissioning of fire suppression system including all equipment, pipe works and accessories ready to operate as per specifications, drawings and instructions of consultants. Cutting dismantling and shifting of the existing fire fighting works as per instruction of consultant, including cleaning the site and shifting the dismantled parts / material to suitable place given by client complete in all respects ready to operate as per drawings and as per instruction of consultant. | Job. | 1 |  | 273000 |  | 0 |  | 0 | 0
Fire Fighting Works i.e; Pipe, Valves, accessories, sprinklers etc complete job as required, (except risers)
MS Sch-40 seamless pipes including all specials fittings UL listed & FM approved, threaded. welded joints, flexible pipe. flanges, coupling, masking plates, bends, tees, clamps, supports and hangers, sleeves, masking plates chiseling, cutting holes, making good where required, painting and protection treatment etc.
| Dia 25 mm (Threaded fitting) | Rm | 250 | 2636 | 727 | 215.92 | 569165.12 | 215.92 | 156973.84 | 726138.96
| Dia 32 mm (Threaded fitting) | Rm | 25 | 3668 | 882 | 23.45 | 86014.6 | 23.45 | 20682.9 | 106697.5
| Dia 40 mm (Threaded fitting | Rm | 30 | 3906 | 1113 | 10.66 | 41637.96 | 10.66 | 11864.58 | 53502.54
| Dia 50 mm (Threaded fitting) | Rm | 30 | 7067 | 1297 | 23.93 | 169113.31 | 23.93 | 31037.21 | 200150.52
| Dia 65 mm (Welded joints fitting) | Rm | 30 | 9406 | 1565 | 49.72 | 467666.32 | 49.72 | 77811.8 | 545478.12
| Dia 75 mm (Welded joints fitting) | Rm | 35 | 10332 | 1638 | 6.2 | 64058.4 | 6.2 | 10155.6 | 74214
| Dia 100 mm (Welded joints fitting) | Rm | 2 | 13466 | 1911 | 8.28 | 111498.48 | 8.28 | 15823.08 | 127321.56
| Sprinkler Heads Sprinkler Pendent type (concealed with face / cover plate) K=5.6 (Opening Temperature 57°C) | No | 87 | 8400 | 1575 | 70 | 588000 | 70 | 110250 | 698250
| Fire extinguishers with fixing accessories. Automatic fire extinguisher (10 Kg. Dry Chemical Powder). | No | 1 | 36750 | 2100 |  | 0 | 0 | 0 | 0
| Isolation Gate valve with matching flanges. Size. 100 mm | No | 1 | 88200 | 3675 |  | 0 |  | 0 | 0
| Supply and installation of Fire Stop material (for passive fire fighting / smoke barrier) in all openings and penetrations, either in slab or wall complete in all respect ready as per fire stopper recommended material and as per instructiuon of consultant. | Job. | 1 | 47250 | 15750 |  | 0 |  | 0 | 0
| Making of As-Built & Shop Drawings on AutoCAD 2018 or latest version with sectional details complete in all respects as per instructions of consultant. | Job. | 1 | 42000 | 10500 | 50% | 21000 | 50% | 5250 | 26250
| Painting, identification and tagging to the installations and equipments. | Job. | 1 | 63000 | 21000 | 80% | 50400 | 80% | 16800 | 67200
| Flushing of entire fire pipe work according to (NFPA-13). | Job. | 1 | 36750 | 21000 | 1 | 36750 | 1 | 21000 | 57750
| Testing, and commissioning of entire fire fighting installation as per Consultant’s approval. | Job. | 1 | 36750 | 21000 | 80% | 29400 | 80% | 16800 | 46200
| Total Cost of FSS Rs. | [5 empty] | 2234704.19 |  | 494449.01 | 2729153.2

## Fire 23rd
Bill of Quantities Fire Suppression Services Bank AI Habib Limited (23rd Floor) Center Point Tower, Karachi.
Bill of Quantities | [5 empty] | RUNNING BILL NO 1
S.No. | Description | UnN | Qty | Material Rate | Labour Rate | BILL QTY | MATERIAL AMOUNT | BILL QTY | LABOUR AMOUNT | TOTAL AMOUNT
1 1.1 2 2.1 2.2 2.3 2.4 2.5 2.6 2.7 3 3.1 3.2 | FIRE FIGHTING SERVICES Supply, installation, testing & commissioning of fire suppression system including all equipment, pipe works and accessories ready to operate as per specifications, drawings and instructions of consultants. Cutting dismantling and shifting of the existing fire fighting works as per instruction of consultant, including cleaning the site and shifting the dismantled parts / material to suitable place given by client complete in all respects ready to operate as per drawings and as per instruction of consultant. | Job. | 1 |  | 273000 |  | 0 |  | 0 | 0
Fire Fighting Works i.e; Pipe, Valves, accessories, sprinklers etc complete job as required, (except risers)
MS Sch-40 seamless pipes including all specials fittings UL listed & FM approved, threaded. welded joints, flexible pipe. flanges, coupling, masking plates, bends, tees, clamps, supports and hangers, sleeves, masking plates chiseling, cutting holes, making good where required, painting and protection treatment etc.
| Dia 25 mm (Threaded fitting) | Rm | 230 | 2636 | 727 | 147 | 387492 | 147 | 106869 | 494361
| Dia 32 mm (Threaded fitting) | Rm | 15 | 3668 | 882 | 20.34 | 74607.12 | 20.34 | 17939.88 | 92547
| Dia 40 mm (Threaded fitting | Rm | 20 | 3906 | 1113 | 3.63 | 14178.78 | 3.63 | 4040.19 | 18218.97
| Dia 50 mm (Threaded fitting) | Rm | 25 | 7067 | 1297 | 25.2 | 178088.4 | 25.2 | 32684.4 | 210772.8
| Dia 65 mm (Welded joints fitting) | Rm | 25 | 9406 | 1565 | 25.94 | 243991.64 | 25.94 | 40596.1 | 284587.74
| Dia 75 mm (Welded joints fitting) | Rm | 30 | 10332 | 1638 | 8.46 | 87408.72 | 8.46 | 13857.48 | 101266.2
| Dia 100 mm (Welded joints fitting) | Rm | 2 | 13466 | 1911 | 17.63 | 237405.58 | 17.63 | 33690.93 | 271096.51
| Sprinkler Heads Sprinkler Upright type standard response K = 5.6 (Opening Temperature 68°C) | No | 1 | 6510 | 1575 |  | 0 | 0 | 0 | 0
| Sprinkler Pendent type (concealed with face / cover plate) K=5.6 (Opening Temperature 57°C) | Nos | 75 | 8400 | 1575 |  | 0 | 0 | 0 | 0
| Fire extinguishers with fixing accessories. Automatic fire extinguisher (10 Kg. Dry Chemical Powder). | No | 1 | 36750 | 2100 |  | 0 | 0 | 0 | 0
| Isolation Gate valve with matching flanges. Size. 100 mm | No | 1 | 88200 | 3675 | 0 | 0 | 0 | 0 | 0
| Supply and installation of Fire Stop material (for passive fire fighting / smoke barrier) in all openings and penetrations, either in slab or wall complete in all respect ready as per fire stopper recommended material and as per instructiuon of consultant. | Job. | 1 | 47250 | 15750 | 0 | 0 | 0 | 0 | 0
| Making of As-Built & Shop Drawings on AutoCAD 2018 or latest version with sectional details complete in all respects as per instructions of consultant. | Job. | 1 | 42000 | 10500 |  | 0 | 50% | 5250 | 5250
| Painting, identification and tagging to the installations and equipments. | Job. | 1 | 63000 | 21000 |  | 0 | 50% | 10500 | 10500
| Flushing of entire fire pipe work according to (NFPA-13). | Job. | 1 | 36750 | 21000 |  | 0 | 50% | 10500 | 10500
| Testing, and commissioning of entire fire fighting installation as per Consultant’s approval. | Job. | 1 | 36750 | 21000 |  | 0 |  | 0 | 0
| Total Cost of FSS Rs. | [5 empty] | 1223172.24 |  | 275927.98 | 1499100.22

## Sheet1
HVAC Work at Bank Al-Habib (Cente Point)
| 22nd Floor |  | 23rd Floor
Description | Unit | Qty | Unit | Qty
Gate Valve
25mm dia | Nos | 8 | Nos | 8
Strainers
25mm dia | Nos | 2 | Nos | 2
Balancing Valve (with self sealing measuring nipples)
25mm dia | Nos | 2 | Nos | 2
Thermometer 150mm Height Scale Type (w th Thermo well) 0 °C to 60 °C | Nos | 4 | Nos | 4
Pressure Gauge with Ball Valve & Siphon, Liquid filled Dial t'/peran e 0 psi to 100 psi. (l00mm dial Size) | Nos | 4 | Nos | 4
2-Way Motorized Valve with Actuator (0-100% modulating)
25mm dia | Nos | 2 | Nos | 2
SCH-40 M.S.(As per ASME & API standard
25mm dia | RM | 30 | RM | 25
32mm dia | RM | 15 | RM | 15
Aluminum foil facing fiber glass (24 kg/m3 density) insulation
25mm dia | RM | 30 | RM | 25
32mm dia | RM | 15 | RM | 15
FLEXIBLE DUCT 6" | RM | 110 | RM | 120
Fire Work at Bank Al-Habib (Cente Point)
| 22nd Floor |  | 23rd Floor
Description | Unit | Qty | Unit | Qty
MS Sch-40 seamless pipes
Dia 25 mm (Threaded fitting) | RM | 250 | RM | 230
Dia 32 mm (Threaded fitting) | RM | 25 | RM | 15
Dia 40 mm (Threaded fitting | RM | 30 | RM | 20
Dia 50 mm (Threaded fitting) | RM | 30 | RM | 25
Dia 65 mm (Welded joints fitting) | RM | 30 | RM | 25
Dia 75 mm (Welded joints fitting) | RM | 35 | RM | 30
Dia 100 mm (Welded joints fitting) | RM | 2 | RM | 2
Sprlnlder Heade Sprinkler Upright type standard response K = 5.6 (Opening Temperature 68°C) | Nos | 87 | Nos | 1
Sprinkler Pendent type (concealed with face / cover plate) K=5.6 (Opening Temperature 57°C) | Nos | NIL | NOS | 75
Fire extinguishers with fixing acceeaorles. Automatic fire extinguisher (10 Kg. Dry Chemical Powder). | Nos | 1 | Nos | 1
Isolation Gate valve with matching flanges. Size. 100 mm | Nos | 1 | Nos | 1
HVAC Work at Bank Al-Habib (Cente Point)
| 22nd Floor |  | 23rd Floor
Description | Unit | Qty | Unit | Qty
Supply & Return Air Registers / Diffuser with Damper
300mm x 300mm Square Diffuser | Nos. | 6 | Nos. | 15
375mm x 375mm Square Diffuser | Nos | 2 | Nos | NIL
300mm dia Jet Diffuser | Nos. | 4 | Nos. | 4
Supply & Return Air Grills
450mm x 250mm | Nos. | 2 | Nos. | 2
S S. wire Mesh with G.I Frame | Sqm | 3 | Sqm | 2
Lineer Slots 6,000 Series
2 Slots of 20mm | Rm | 110 | Rm | 110
Butter Fly Dampers 6" | Nos. | 105 | Nos. | 120
Volume Control Damper in 16 SWG sheet metal. | Sqm | 3 | Nos. | 6