## HVAC
Bill of Quantities
ACMV Works
SPAR SUPERMARKET | [11 empty] | Rev.00
DHA, Karachi | [11 empty] | Date: 12-08-2024
S. No. |  | DESCRIPTION | Bill of Quantities |  |  |  | Running Bill No 2
|  |  | UNIT | QTY | MATERIAL | LABOUR | Prv Qty | Current Qty | Total Qty | Material Amount | Labour Amount | Total Amount
[5 empty] | RATE | RATE
All works shall be completed, tested and commissioned as per drawings, specifications and as per instruction of Consultant
1 |  | Unloading, rigging, lifting, placement, installation, testing and commissioning of (OWNER SUPPLIED) VRF / VRV air conditioning units with multiple indoor evaporative units of different capacities with central controller complete in all respects, ready to operate including supply & installation of supports, brackets, flexible duct connector / connection, rubber isolators, flashing, power wiring from isolation box to unit (10' to 15' radius), control wiring termination etc, complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
| 1.1 | GF-FACU-01 (03 Indoors + 1 Outdoor Condensing Unit Consisted of Different Modules) | Set | 1 | 25200 | 25200 | 2 |  | 2 | 0 | 0 | 0
| 1.2 | CU-01 (1-2) (07 Indoors + 1 Outdoor Condensing Unit Consisted of Different Modules) | Set | 1 | 25200 | 25200 | 2 |  | 2 | 0 | 0 | 0
| 1.3 | CU-01 (2-2) (08 Indoors + 1 Outdoor Condensing Unit Consisted of Different Modules) | Set | 1 | 25200 | 25200 | 1 |  | 1 | 0 | 0 | 0
| 1.4 | CU-02 (1-2) (08 Indoors + 1 Outdoor Condensing Unit Consisted of Different Modules) | Set | 1 | 25200 | 25200 | 2 |  | 2 | 0 | 0 | 0
| 1.5 | CU-02 (2-2) (08 Indoors + 1 Outdoor Condensing Unit Consisted of Different Modules) | Set | 1 | 25200 | 25200 | 2 |  | 2 | 0 | 0 | 0
| 1.6 | CU-03 (1-2) (13 Indoors + 1 Outdoor Condensing Unit Consisted of Different Modules) | Set | 1 | 25200 | 25200 | 3 |  | 3 | 0 | 0 | 0
| 1.7 | CU-03 (2-2) (12 Indoors + 1 Outdoor Condensing Unit Consisted of Different Modules) | Set | 1 | 25200 | 25200 | 3 |  | 3 | 0 | 0 | 0
2 |  | Unloading, installation, testing and commissioning of (OWNER SUPPLIED) single split units of different capacities including supply & installation of supports, brackets, rubber isolators, flashing, power wiring from isolation box to unit (10' to 15' radius), control wiring termination etc, complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant. | [6 empty] | 0 | 0 | 0
| 2.1 | AC-01 | Nos. | 5 | 6720 | 5040 | 3 |  | 3 | 0 | 0 | 0
| 2.2 | FS-01 | Nos. | 4 | 6720 | 5040 | 0 |  | 0 | 0 | 0 | 0
3 |  | Supply & installation of refrigerant pipes for all units (liquid + gas) with 1/2" thick expended close cell rubber foam insulation, PVC tape wrapping including additional gas charging if required and installation of branch distributor (supplied with VRF / VRV units) complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. (VRF / VRV Units copper pipes sizes & quantities shall be vary according to the equipment brand / selection) | [6 empty] | 0 | 0 | 0
| A | All hard pipes except 1/4" | [6 empty] | 0 | 0 | 0
| 3.1 | 1/4" dia | Rft | 65 | 348.6 | 126 | 369 |  | 369 | 0 | 0 | 0
| 3.2 | 3/8" dia | Rft | 1730 | 403.2 | 126 | 2916 | 30 | 2946 | 12096 | 3780 | 15876
| 3.3 | 1/2" dia | Rft | 670 | 882 | 126 | 515 |  | 515 | 0 | 0 | 0
| 3.4 | 5/8" dia | Rft | 1565 | 1008 | 168 | 1871 | 82 | 1953 | 82656 | 13776 | 96432
| 3.5 | 3/4" dia | Rft | 605 | 1139.88 | 168 | 2039 |  | 2039 | 0 | 0 | 0
| 3.6 | 7/8" dia | Rft | 205 | 1470 | 168 | 595 |  | 595 | 0 | 0 | 0
| 3.7 | 1 1/8" dia (also for 1") | Rft | 945 | 1764 | 168 | 665 | 52 | 717 | 91728 | 8736 | 100464
| 3.8 | 1 3/8" dia (also for 1-1/4") | Rft | 215 | 2604 | 168 | 0 |  | 0 | 0 | 0 | 0
| 3.9 | 1 5/8" dia (also for 1-1/2") | Rft | 85 | 4032 | 168 | 874 |  | 874 | 0 | 0 | 0
| 3.1 | 2 1/8" dia (also for 1-3/4") | Rft | 5 | 7770 | 210 | 0 |  | 0 | 0 | 0 | 0
| B | Soft pipes for wall mounted single split unit only | [6 empty] | 0 | 0 | 0
| 3.11 | 1/4" dia | Rft | 250 | 378 | 126 | 248 |  | 248 | 0 | 0 | 0
| 3.12 | 1/2" dia | Rft | 250 | 693 | 126 | 248 |  | 248 | 0 | 0 | 0
4 |  | Supply & installation of control wiring in G.I. conduit for external / PVC conduit for internal area from outdoor unit to indoor unit including microprocessor & central controller wiring & fixing / installation of central controller supplied with units complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Lot | 1 | 504000 | 210000 | 1 |  | 1 | 0 | 0 | 0
5 |  | Supply & installation of 18 SWG powder quoted G.I. sheet metal tray with cover for refrigerant pipes and control wiring exposed to weather area and for main hall internal area complete in all respects including hangers, supports brackets complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqft | 500 | 483 | 84 | 1000 |  | 1000 | 0 | 0 | 0
6 |  | Supply & installation of uPVC make class D SCH-40 pipe for internal area with 3/8" thick expanded closed cell rubber foam insulation, PVC tape wrapping for condensate drain including support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | [6 empty] | 0 | 0 | 0
| 6.1 | 1" dia | Rft | 900 | 336 | 50.4 | 672 | 110 | 782 | 36960 | 5544 | 42504
| 6.2 | 1.25" dia | Rft | 450 | 378 | 58.8 | 824 |  | 824 | 0 | 0 | 0
| 6.3 | 1.5" dia | Rft | 10 | 655.2 | 67.2 | 10 |  | 10 | 0 | 0 | 0
| 6.4 | 2" dia | Rft | 10 | 882 | 84 | 10 |  | 10 | 0 | 0 | 0
7 |  | Supply & installation of air curtains including, supports, electrical connection etc, complete in all respects ready to operate as per drawings, specification & as per instruction of consultant. | [6 empty] | 0 | 0 | 0
| 7.1 | 5 Feet length | Nos. | 3 | 71400 | 2520 | 0 |  | 0 | 0 | 0 | 0
8 |  | Supply, installation, testing and commissioning of ventilation fans as per mentioned in schedule, including supply & installation of vibration isolator, flexible duct connection / connector, support & hangers, power wiring from isolation box to unit (10' to 15' radius) etc, complete in all respects ready to operate as per drawings, specification and as per instruction of consultant. | [6 empty] | 0 | 0 | 0
| 8.1 | EAF-01 | No. | 1 | 43612.8 | 1680 | 1 |  | 1 | 0 | 0 | 0
| 8.2 | EAF-02 | No. | 1 | 50551.2 | 4200 | 1 |  | 1 | 0 | 0 | 0
| 8.3 | EAF-03 | No. | 1 | 231000 | 5040 | 1 |  | 1 | 0 | 0 | 0
| 8.4 | EAF-04 | No. | 1 | 315000 | 6720 | 1 |  | 1 | 0 | 0 | 0
| 8.5 | SEF-01 | No. | 1 | 365400 | 8400 | 1 |  | 1 | 0 | 0 | 0
| 8.6 | FAF-01 | No. | 1 | 407400 | 8400 | 1 |  | 1 | 0 | 0 | 0
| 8.7 | FAF-02 | No. | 1 | 415800 | 8400 | 1 |  | 1 | 0 | 0 | 0
9 |  | Supply, fabrication and installation of epoxy painted M.S sheet metal welded duct of (18 Gauge) for condensing units exhaust air, complete in all respects including all changes in direction, transformation, plenums chambers, connection pecs of hood round to square, supports & hangers etc. complete in all respects ready to operate as per drawings, specification, instruction and approval of consultant. | Sqft | 700 | 474.6 | 105 | 0 |  | 0 | 0 | 0 | 0
10 |  | Supply, fabrication and installation of M.S sheet metal welded duct of 2.0 mm (16 Gauge) thickness for kitchen exhasut duct, complete in all respects including 300x150mm access doors at all changes in direction, transformation, plenums chambers, connection pecs of hood round to square, supports & hangers etc. complete in all respects ready to operate as per drawings, specification, instruction of consultant.. | Sqft | 650 | 462 | 84 | 356 |  | 356 | 0 | 0 | 0
11 |  | Supply, fabrication and installation of 2" thick rockwool (double layar) insulation of 50kg/m3 density with wire mesh reinforcement over M.S sheet metal ducts of kitchen exhaust air duct, complete in all respects ready to operate as per drawings, specification, instruction of consultant. | Sqft | 700 | 92.4 | 42 | 484 |  | 484 | 0 | 0 | 0
12 |  | Supply, fabrication and installation of 26 SWG gauge G.I. cladding for over rockwool insulation etc. complete in all respects ready to operate as per drawings, specification, instruction of consultant. | Sqft | 700 | 294 | 58.8 | 484 |  | 484 | 0 | 0 | 0
13 |  | Supply, fabrication and installation of machine made G.I sheet metal duct different sections supply, return, fresh & exhaust air including plenums, splitter dampers, guide vanes, flexible duct connector/connection, access door, transformation, plenums chambers, wooden frame, anchors supports & hangers complete in all respects ready to operate as per drawings, specification, instruction of consultant. | Sqft | 6200 | 348.6 | 50.4 | 6620 | 166 | 6786 | 57867.6 | 8366.4 | 66234
14 |  | Supply & installation of 3/4" thick 25kg/m3 density rubber foam (XLPE) adhesive insulation with aluminum foil for condition area fresh air ducts only, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqft | 2250 | 357 | 42 | 3229 |  | 3229 | 0 | 0 | 0
15 |  | Supply & installation of acoustical duct sound liner adhesive with aluminum facing 1/2" thick in supply air duct complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Sqft | Rate only | 462 | 42 | 0 |  | 0 | 0 | 0 | 0
16 |  | Supply & installation of aluminum fabricated powder coated exhaust & fresh Air louvers including wooden frame, rain protection sheet bird mesh etc complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqin | 11500 | 21 | 2.52 | 3212 |  | 3212 | 0 | 0 | 0
17 |  | Supply, installation of Aluminum fabricated, powder coated Grills, Diffusers and Registers for supply air, return air, exhaust air & fresh air of different sizes (Grade A ), wooden frame, supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. |  |  | 0 | 0 |  |  | 0 | 0 | 0
| 17.1 | Registers / Diffuser with Damper | Sqin | 5400 | 23.52 | 2.52 | 4640 |  | 4640 | 0 | 0 | 0
| 17.2 | Grills | Sqin | 3000 | 19.32 | 2.52 | 2848 |  | 2848 | 0 | 0 | 0
| 17.3 | S.S Mesh with G.I Frame | Sqin | 15500 | 15.12 | 1.68 | 15500 |  | 15500 | 0 | 0 | 0
| 17.4 | Exhaust Air Disc Valves 6" dia | Nos. | 3 | 2520 | 588 | 3 |  | 3 | 0 | 0 | 0
18 |  | Supply & installation of 6" dia flexible duct including hangers, jubilee clamp complete in all respects as per specification, drawings & as per instruction of consultant. | Rft | 5 | 378 | 126 | 5 |  | 5 | 0 | 0 | 0
19 |  | Supply & installation of 6" dia butterfly damper for above flexible duct with gas kits, nut bolts, complete in all respects, ready to operate as per specification, drawings & as per instruction of consultant. | Nos. | 1 | 3360 | 420 | 1 |  | 1 | 0 | 0 | 0
20 |  | Supply & installation of Volume Control Damper in 16 SWG G.I sheet metal with gas kits, nut bolts, complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Sqin | 5900 | 21 | 2.52 |  |  | 0 | 0 | 0 | 0
21 |  | Supply, fabrication & installation of pre-insulated Volume Control Damper, blades to be constructed with extruded aluminum in airfoil shape with thermal isolation gape & shall have seals, pvc / aluminum profiles duct connection at both end etc. complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | Sqin | 1000 | 42 | 4.2 | 0 |  | 0 | 0 | 0 | 0
22 |  | Supply and installation of fire damper with linkage & fuse complete in all respects ready to operate as per specification, drawings & as per instruction of Consultant. | Sqin | 2000 | 25.2 | 2.52 | 0 |  | 0 | 0 | 0 | 0
23 |  | Supply and installation of back draft damper in MS Sheet with gas kits, nut botls. complete in all respects ready to operate as per specification, drawings & as per instruction of Consultant. | Sqin | 2500 | 20.16 | 2.52 | 0 |  | 0 | 0 | 0 | 0
24 |  | Supply, installation of motorized damper with gas kits, nut bolts, including pressure transmeter, controller & control wiring, complete in all respects, ready to operate as per specification, drawings & as per instruction of consultant. | [6 empty] | 0 | 0 | 0
| 24.1 | 20" x 22" | No. | 1 | 71400 | 4200 | 1 |  | 1 | 0 | 0 | 0
| 24.2 | 50" x 10" | No. | 1 | 74760 | 4200 | 1 |  | 1 | 0 | 0 | 0
25 |  | Integration of smoke control system using I/O modules with the fire alarm control panel of building with fire resistant wiring & fixing accessories, complete in all respects, ready to operate as per drawings, specification and instruction of consultant. | Lot | 1 | 294000 | 42000 | 1 |  | 1 | 0 | 0 | 0
26 |  | Painting & Identification work on supports, hangers, platform of condensing units etc complete in all respects with one coat of ICI make Red lead oxide primer & two coats of ICI make enamel paint complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | Lot | 1 | 50400 | 8400 | 1 |  | 1 | 0 | 0 | 0
27 |  | Testing, balancing and commissioning of air side of the system (from independent agency) complete in all respects including air measurement & balancing, temp, pressure & electrical data of related equipment etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Job. | 1 | 0 | 105000 | 1 |  | 1 | 0 | 0 | 0
28 |  | Making of Shop drawings on Auto CAD (latest version) with section details, equipment foundation details and Making of As Built drawings, Documentation Technical / Operational Manual & LOG Book for each equipment complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Job. | 1 | 12600 | 12600 | 1 |  | 1 | 0 | 0 | 0
|  | Total Cost of Works with I. Tax Rs. | [7 empty] | 281307.6 | 40202.4 | 321510

## Sheet1
Ducting
1 | Copper Tube | 1/4" | 9 |  | 9 | Coil |  | 130.53 | 166.49
2 | Copper Tube | 3/8" | 1 |  | 1 | Coil |  | 11.25 | 85.96
3 | Copper Tube | 1/2" | 7 |  | 7 | Coil |  | 189.81 | 32.75
| Copper pipe L type | 1/4" | 120 |  | 120 |  |  | 152.11 | 28.69
| Copper pipe L type | 3/8" | 740 |  | 740 |  |  | 46.25 | 3.13
| Copper pipe L type | 1/2" | 120 |  | 120 |  |  | 385.29 | 12
4 | Copper pipe L type | 3/8" | 1680 |  | 1680 | Rft |  | 42 | 220.06
5 | Copper pipe L type | 1/2" | 152 |  | 152 | Rft |  | 396.98 | 6.67
6 | Copper pipe L type | 5/8" | 1363 | 280 | 1643 | Rft |  | 311.02 | 406.74
7 | Copper pipe L type | 3/4" | 1494 | 440 | 1934 | Rft |  | 169.43 | 28.19
8 | Copper pipe L type | 1-1/8" | 642 | 200 | 842 | Rft |  | 32.28 | 990.68
9 | Copper pipe L type | 1-3/8" | 95 | 160 | 255 | Rft |  | 20.28
10 | Copper pipe L type | 1-5/8" | 635 | 280 | 915 | Rft |  | 7.13
|  | 7/8" | 285 |  | 285 |  |  | 30.06
119.72
32.69
[5 empty] | 8686 |  |  | 88.85
[5 empty] | 350 |  |  | 133.28
[5 empty] | 50 |  |  | 98.38
[5 empty] | 450 |  |  | 705.1
[5 empty] | 9536 |  |  | 550.13
311.5
111.39
42.33
736.67
105
310.74
448.6
246.67
7.46
25.92
621
6619.85