## sum
Deutche Bank |  | 2023-05-23
HVAC & Fire Work
SUMMARY OF WORK DONE
Deutsche Bank
S.No | Activity. | AMOUNT
A | Total work done upto final bill | 26121172
| TOTAL Work Done RS. | 26121172
LESS REBATE ____% RS.
TOTAL ESTIMATED COST OF PROJECT RS. |  | 26121172
| COVERED AREA | 10000
RATE PER SFT.
| Add Variations amount | 3571369.0625
| Grand Total Amount | 29692541.0625
| Add 4.5% Tax amount as discussed | 1336164.3478
| Grand Total Amount after Tax amount | 31028705.4103 | 835500
| Total Received | 27744816
| Receivable amount | 3283889.4103

## Summary
Deutsche Bank, DMC Karachi
HVAC & Fire Fighting Work |  | 2023-03-22
15th & 16th Floor Deutsche Bank Karachi.
SUMMARY OF FINAL BILL
S.No | Description | Amount
1 | HVAC 15th Floor | 13301241.4
2 | HVAC 16th Floor | 9975455.9
| Total Amount | 23276697.3
NO discount
1 | Fire Suppression Services 15th Floor | 1631714.9
2 | Fire Suppression Services 16th Floor | 1212759.8
| Total Amount | 2844474.7
| Grand Total Amount | 26121172
Note: Above prices are without taxes.
| Variations | 3185218
| Total | 29306390
| rec | 15289715
| rem | 14016675

## HVAC 15
Deutsche Bank AG, Karachi Branch
Karachi Branch Relocation
S # | Description | Bill of Quantities |  |  |  | Final Bill
[6 empty] | Material |  | Labour |  | Total Amount
|  | Unit | Qty | Material Rate | Labout Rate | Bill Qty | Amount | Bill Qty | Amount
1 | ACMV WORKS
1.1 | VAV & CAV BOXES
Supply & installation of VAV / CAV Boxes as per mentioned in schedule with digital thermostat controller, pressure sensor, control wiring, including supply & installation of flexible duct connection, power wiring upto 10' to 15' radius, lindapter support & hangers etc, complete in all respects ready to operate as per schedule, drawings, specification, instruction of consultant.
a | VAV Boxes | Nos. | 20 | 285000 | 3000 | 20 | 5700000 | 20 | 60000 | 5760000
b | CAV Boxes | Nos. | 5 | 125000 | 3000 | 5 | 625000 | 5 | 15000 | 640000
c | Control Wiring | Lot | 1 | 300000 | 35000 | 1 | 300000 | 1 | 35000 | 335000
1.2 | WATER LEAK DETECTING SYSTEM WITH CONTROL PANEL
| Supply & installation of water leak detecting ropes with control panel including fixing accessories, control & power wiring, complete system (integrated with BMS) inside technology equipment room (TER), complete in all respects as per specifications, drawings and instructions of consultant. | Lot | 1 | Scope Deleted |  |  |  | 0 | 0 | 0
1.3 | DUCTED FAN COIL UNITS
Supply & installation of ducted fan coil units of different capacities complete in all respects, ready to operate with supply and fixing of all accessories, including hanger steel base, vibration isolators, including interconnecting & control wiring, power wiring upto 10' to 15' radius, with inlet & outlet chilled water connections, drain connection, flexible rubber duct connection / connector, lindapter hangers & supports etc. complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
a | DFCU-01 | No. | 1 | 229000 | 30000 | 1 | 229000 | 1 | 30000 | 259000
1.4 | VALVES & ACCESSORIES
Supply & installation of valves & accessories for DFCUs with fixing accessories, lindapter supports, hangers, etc. complete in all respects as per specifications, drawings and as per instructions of consultant.
a | Ball Valve
i. | 25mm dia | Nos. | 4 | 4500 | 1000 | 2 | 9000 | 2 | 2000 | 11000
b | Strainers
i. | 25mm dia | No. | 1 | 4500 | 1000 | 1 | 4500 | 1 | 1000 | 5500
c | Balancing Valve (with self sealing measuring nipples)
i. | 25mm dia | No. | 1 | 9000 | 1500 | 1 | 9000 | 1 | 1500 | 10500
d | 2-Way Motorized Valve with Actuator (0-100% modulating)
i. | 25mm dia | No. | 1 | 42000 | 3000 | 1 | 42000 | 1 | 3000 | 45000
e | Digital Decorative Thermostat Controller (BMS Interfacable) with Duct Mounted Sensor | No. | 1 | 20000 | 2000 | 1 | 20000 | 1 | 2000 | 22000
f | Control wiring from controller to sensors, motorized valve and Power wiring up to 15' radius | Lot | 1 | 15000 | 5000 | 1 | 15000 | 1 | 5000 | 20000
1.5 | M.S PIPES
Supply & installation of SCH-40 M.S. (As per ASME & API standard, heavy quality with standard SCH 40 wall thickness) pipes & fitting for chilled & cooling water circulation system complete with bends, tees, unions, sockets, specials, MS Pipe lindapter support, hangers & anchors, M.S. angle, U channel, roller support, bolts, rods, clamps, concrete fasteners etc as required to complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Chilled Water
a | 25mm dia | Rm | 25 | 1580 | 500 | 23.3 | 36814 | 23.3 | 11650 | 48464
b | 38mm dia | Rm | 50 | 2562 | 580 | 55.3 | 141678.6 | 55.3 | 32074 | 173752.6
Cooling Water
b | 38mm dia | Rm | 50 | 2562 | 580 | 55.3 | 141678.6 | 55.3 | 32074 | 173752.6
1.6 | PIPES INSULATION
Supply & installation of Pre Formed Polystyrene (Thermopore) insulation (32 kg/m3 density) for chilled water pipes, bends, tees, unions, sockets, valves and on specials protected with Kraft paper, wrapped with 8oz canvas cloth than paint with anti fungus paint complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Chilled Water
a | 25mm dia | Rm | 25 | 1100 | 200 | 23.3 | 25630 | 23.3 | 4660 | 30290
b | 38mm dia | Rm | 50 | 1250 | 250 | 55.3 | 69125 | 55.3 | 13825 | 82950
1.7 | DRAIN PIPES
Supply & installation of uPVC make class D SCH-40 pipe with 10mm thick expanded rubber foam insulation, PVC tape wrapping for condensate drain including support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
a | 25mm dia | Rm | 12 | 500 | 200 | 9.1 | 4550 | 9.1 | 1820 | 6370
b | 50mm dia | Rm | 15 | 780 | 250 | 8.8 | 6864 | 8.8 | 2200 | 9064
1.8 | FANS
Supply & installation of ventilation fans including flexible duct connection / connector, lindapter support & hangers, power wiring upto 10' to 15' radius etc, complete in all respects ready to operate as per schedule, drawings, specification, instruction of consultant.
a | TAF-01 | Nos. | 2 | 19500 | 2000 | 2 | 39000 | 2 | 4000 | 43000
1.9 | DUCT
| Supply, fabrication and installation of machine made G.I sheet metal duct different sections supply, return, fresh & exhaust air including plenums, splitter dampers, guide vanes, flexible duct connector / connection, access door, transformation, plenums chambers, wooden frame, anchors supports & hangers complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | Sqm | 610 | 3100 | 650 | 680 | 2108000 | 680 | 442000 | 2550000
1.1 | DUCT INSULATION
| Supply & installation of adhesive 20mm thick rubber foam (XLPE) insulation with aluminum foil over supply & return duct, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqm | 610 | 2650 | 400 | 680 | 1802000 | 680 | 272000 | 2074000
1.11 | SOUND LINER
| Supply & installation of acoustical duct sound liner (adhesive 12mm thick) in supply air duct etc, complete in all respects ready to operate as per drawings, specification and as per instruction of consultant. | Sqm | 60 | 2000 | 400 | 51.97 | 103940 | 51.97 | 20788 | 124728
1.12 | AIR DEVICES
Supply & installation of aluminum fabricated, powder coated grills, diffusers and registers etc for supply, return, exhaust & fresh air of different sizes (Grade A) wooden frame, lindaptor supports and other accessories etc, complete in all respects ready to operate as per drawings, specification and as per instruction of consultant.
a | Supply & Return Air Diffuser with Damper
i. | 225mm x 225mm | Nos. | 3 | 3055 | 500 | 3 | 9165 | 3 | 1500 | 10665
ii. | 300mm x 300mm | Nos. | 15 | 3705 | 500 | 11 | 40755 | 11 | 5500 | 46255
iii. | 450mm x 450mm | Nos. | 20 | 8214 | 500 | 21 | 172494 | 21 | 10500 | 182994
iv. | 300mm dia | Nos. | 6 | 4680 | 500 | 3 | 14040 | 3 | 1500 | 15540
b | Transfer Air Grill
i. | 300mm x 150mm | No. | 1 | 1625 | 500 | 1 | 1625 | 1 | 500 | 2125
ii. | 400mm x 150mm | No. | 1 | 2340 | 500 | 1 | 2340 | 1 | 500 | 2840
iii. | 600mm x 250mm | No. | 1 | 4680 | 500 | 1 | 4680 | 1 | 500 | 5180
b | S.S Mesh with G.I Frame
i. | 200mm x 200mm | No. | 1 | 2000 | 400 | 1 | 2000 | 1 | 400 | 2400
ii. | 250mm x 250mm | No. | 1 | 2400 | 400 | 3 | 7200 | 3 | 1200 | 8400
iii. | 300mm x 150mm | No. | 1 | 2800 | 400 | 1 | 2800 | 1 | 400 | 3200
iv. | 400mm x 250mm | No. | 1 | 3500 | 400 | 1 | 3500 | 1 | 400 | 3900
v. | 450mm x 200mm | No. | 1 | 3800 | 400 | 1 | 3800 | 1 | 400 | 4200
vi. | 500mm x 250mm | No. | 1 | 4500 | 400 | 1 | 4500 | 1 | 400 | 4900
vii. | 550mm x 350mm | No. | 1 | 5500 | 400 | 1 | 5500 | 1 | 400 | 5900
viii. | 1800mm x 600mm | No. | 1 | 8000 | 400 | 1 | 8000 | 1 | 400 | 8400
c | Linear Slot 6,000 Series
i. | 1 slot of 20mm | Rm | 4 | 3198 | 1000 | 3.6 | 11512.8 | 3.6 | 3600 | 15112.8
ii. | 2 slots of 20mm | Rm | 40 | 3731 | 1000 | 36.4 | 135808.4 | 36.4 | 36400 | 172208.4
d | Exhaust Air Disc Valves
i. | 150mm dia | Nos. | 12 | 1625 | 500 | 12 | 19500 | 12 | 6000 | 25500
1.13 | FLEXIBLE DUCT
Supply & installation of flexible duct including hangers, jubilee clamp complete in all respects as per specification, drawings & as per instruction of consultant.
a | 150mm dia | Rm | 40 | 1200 | 300 | 41 | 49200 | 41 | 12300 | 61500
1.14 | BUTTERFLY DAMPER
Supply & installation of butterfly damper for above flexible duct with gas kits, nut bolts, complete in all respects, ready to operate as per specification, drawings & as per instruction of consultant.
a | 150mm dia | Nos. | 34 | 1950 | 500 | 34 | 66300 | 34 | 17000 | 83300
1.15 | VOLUME CONTROL DAMPER
Supply, fabrication & installation of pre-insulated Volume Control Damper, blades to be constructed with extruded aluminum in airfoil shape with thermal isolation gape & shall have seals, pvc / aluminum profiles duct connection at both end, lindapter supports & hangers, etc, complete in all respects ready to operate as per drawings, specification and as per instruction of consultant.
a | 200mm x 200mm | No. | 1 | 3250 | 500 | 1 | 3250 | 1 | 500 | 3750
b | 300mm x 150mm | No. | 1 | 3250 | 500 | 1 | 3250 | 1 | 500 | 3750
c | 350mm x 100mm | No. | 1 | 3250 | 500 | 1 | 3250 | 1 | 500 | 3750
d | 350mm x 350mm | No. | 1 | 5614 | 500 | 1 | 5614 | 1 | 500 | 6114
e | 400mm x 150mm | Nos. | 5 | 3250 | 500 | 2 | 6500 | 2 | 1000 | 7500
f | 400mm x 250mm | No. | 1 | 4576 | 500 | 1 | 4576 | 1 | 500 | 5076
g | 450mm x 200mm | No. | 1 | 4119 | 500 | 1 | 4119 | 1 | 500 | 4619
h | 550mm x 150mm | No. | 1 | 4030 | 500 | 1 | 4030 | 1 | 500 | 4530
i | 1150mm x 300mm | No. | 1 | 15787 | 500 | 1 | 15787 | 1 | 500 | 16287
j | 1200mm x 300mm | No. | 1 | 16474 | 500 | 1 | 16474 | 1 | 500 | 16974
2 | MISCELLANEOUS WORKS
2.1 | PAINTING & IDENDTIFICATION
| Painting & Identification work on chilled water pipes & exhaust duct, supports, hangers etc, complete in all respects with one coat of ICI make Red lead oxide primer & two coats of ICI make enamel paint etc, complete in all respects as per instruction of consultant. | Job | 1 | 15000 | 10000 | 1 | 15000 | 1 | 10000 | 25000
2.2 | TESTING & COMMISSIONING OF SYSTEM
| Testing, balancing and commissioning of air side of the system (from independent agency) complete in all respects including flow measurement & balancing, temp, pressure, electrical data of related equipment etc, complete in all respects as per instruction of consultant. Moreover, testing and commissioning to be carried out as per the Testing and Commissioning document shared within the RFP. | Job | 1 | 0 | 90000 | 1 | 0 | 1 | 90000 | 90000
2.2 | SHOP & AS BUILT DRWAINGS
| Making of Shop drawings on Auto CAD 2018 with section details, equipment foundation details and Making of As Built drawings, Documentation Technical / Operational Manual & LOG Book for each equipment complete in all respects as per instruction of consultant. | Job | 1 | 10000 | 15000 | 1 | 10000 | 1 | 15000 | 25000
| TOTAL COST OF ACMV WORKS | [8 empty] | 13301241.4

## HVAC 16
Deutsche Bank AG, Karachi Branch | [9 empty] | 2023-03-22
Karachi Branch Relocation
S # | Description | Bill of Quantities |  |  |  | Final Bill
[6 empty] | Material |  | Labour |  | Total Amount
|  | Unit | Qty | Material Rate | Labout Rate | Bill Qty | Amount | Bill Qty | Amount
1 | ACMV WORKS
1.1 | VAV & CAV BOXES
Supply & installation of VAV / CAV Boxes as per mentioned in schedule with digital thermostat controller, pressure sensor, control wiring, including supply & installation of flexible duct connection, power wiring upto 10' to 15' radius, lindapter support & hangers etc, complete in all respects ready to operate as per schedule, drawings, specification, instruction of consultant.
a | VAV Boxes | Nos. | 9 | 285000 | 3000 | 9 | 2565000 | 9 | 27000 | 2592000
b | CAV Boxes | Nos. | 3 | 175000 | 3000 | 3 | 525000 | 3 | 9000 | 534000
c | Control Wiring | Lot | 1 | 160000 | 30000 | 1 | 160000 | 1 | 30000 | 190000
1.2 | WATER LEAK DETECTING SYSTEM WITH CONTROL PANEL
| Supply & installation of water leak detecting ropes with control panel including fixing accessories, control & power wiring, complete system (integrated with BMS) inside technology room (TR), complete in all respects as per specifications, drawings and instructions of consultant. | Lot | 1 | Scope Deleted |  |  |  | 0 | 0
1.3 | DUCTED FAN COIL UNITS
Supply & installation of ducted fan coil units of different capacities complete in all respects, ready to operate with supply and fixing of all accessories, including hanger steel base, vibration isolators, including interconnecting & control wiring, power wiring upto 10' to 15' radius, with inlet & outlet chilled water connections, drain connection, flexible rubber duct connection / connector, lindapter hangers & supports etc. complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
a | DFCU-01 | No. | 1 | 229000 | 30000 | 1 | 229000 | 1 | 30000 | 259000
b | DFCU-02 | Nos. | 2 | 229000 | 30000 | 2 | 458000 | 2 | 60000 | 518000
c | DFCU-03 | No. | 1 | 229000 | 30000 | 1 | 229000 | 1 | 30000 | 259000
1.4 | VALVES & ACCESSORIES
Supply & installation of valves & accessories for DFCUs with fixing accessories, lindapter supports, hangers, etc. complete in all respects as per specifications, drawings and as per instructions of consultant.
a | Ball Valve
i. | 25mm dia | Nos. | 16 | 4500 | 1000 | 8 | 36000 | 8 | 8000 | 44000
b | Strainers
i. | 25mm dia | Nos. | 4 | 4500 | 1000 | 4 | 18000 | 4 | 4000 | 22000
c | Balancing Valve (with self sealing measuring nipples)
i. | 25mm dia | Nos. | 4 | 9000 | 1500 | 4 | 36000 | 4 | 6000 | 42000
d | 2-Way Motorized Valve with Actuator (0-100% modulating)
i. | 25mm dia | Nos. | 4 | 42000 | 3000 | 4 | 168000 | 4 | 12000 | 180000
e | Digital Decorative Thermostat Controller (BMS Interfacable) with Duct Mounted Sensor | Nos. | 4 | 20000 | 2000 | 4 | 80000 | 4 | 8000 | 88000
f | Control wiring from controller to sensors, motorized valve and Power wiring up to 15' radius | Lot | 4 | 15000 | 5000 | 4 | 60000 | 4 | 20000 | 80000
1.5 | M.S PIPES
Supply & installation of SCH-40 M.S. (As per ASME & API standard, heavy quality with standard SCH 40 wall thickness) pipes & fitting for chilled & cooling water circulation system complete with bends, tees, unions, sockets, specials, MS Pipe lindapter support, hangers & anchors, M.S. angle, U channel, roller support, bolts, rods, clamps, concrete fasteners etc as required to complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Chilled Water
a | 25mm dia | Rm | 75 | 1580 | 500 | 71 | 112180 | 71 | 35500 | 147680
b | 32mm dia | Rm | 20 | 2141 | 500 | 2.3 | 4924.3 | 2.3 | 1150 | 6074.3
c | 38mm dia | Rm | 40 | 2562 | 580 | 28 | 71736 | 28 | 16240 | 87976
Cooling Water
d | 38mm dia | Rm | 30 | 2562 | 580 | 15.1 | 38686.2 | 15.1 | 8758 | 47444.2
1.6 | PIPES INSULATION
Supply & installation of Pre Formed Polystyrene (Thermopore) insulation (32 kg/m3 density) for chilled water pipes, bends, tees, unions, sockets, valves and on specials protected with Kraft paper, wrapped with 8oz canvas cloth than paint with anti fungus paint complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
Chilled Water
a | 25mm dia | Rm | 75 | 1100 | 200 | 71 | 78100 | 71 | 14200 | 92300
b | 32mm dia | Rm | 20 | 1150 | 210 | 2.3 | 2645 |  | 0 | 2645
c | 38mm dia | Rm | 40 | 1250 | 250 | 28 | 35000 | 28 | 7000 | 42000
1.7 | DRAIN PIPES
Supply & installation of uPVC make class D SCH-40 pipe with 10mm thick expanded rubber foam insulation, PVC tape wrapping for condensate drain including support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
a | 25mm dia | Rm | 6 | 500 | 200 | 58.6 | 29300 | 58.6 | 11720 | 41020
b | 32mm dia | Rm | 20 | 700 | 250 | 7.8 | 5460 | 7.8 | 1950 | 7410
1.8 | FANS
Supply & installation of ventilation fans including flexible duct connection / connector, lindapter support & hangers, power wiring upto 10' to 15' radius etc, complete in all respects ready to operate as per schedule, drawings, specification, instruction of consultant.
a | TAF-01 | No. | 1 | 19500 | 2000 | 1 | 19500 | 1 | 2000 | 21500
b | TAF-02 | No. | 1 | 40000 | 5000 | 1 | 40000 | 1 | 5000 | 45000
1.9 | DUCT
| Supply, fabrication and installation of machine made G.I sheet metal duct different sections supply, return, fresh & exhaust air including plenums, splitter dampers, guide vanes, flexible duct connector / connection, access door, transformation, plenums chambers, wooden frame, anchors supports & hangers complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | Sqm | 375 | 3100 | 650 | 551.32 | 1709092 | 551.32 | 358358 | 2067450
1.1 | DUCT INSULATION
| Supply & installation of adhesive 20mm thick rubber foam (XLPE) insulation with aluminum foil over supply & return duct, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqm | 375 | 2650 | 400 | 533 | 1412450 | 533 | 213200 | 1625650
1.11 | SOUND LINER
| Supply & installation of acoustical duct sound liner (adhesive 12mm thick) in supply air & return air duct etc, complete in all respects ready to operate as per drawings, specification and as per instruction of consultant. | Sqm | 60 | 2000 | 400 | 28.6 | 57200 | 28.6 | 11440 | 68640
1.12 | AIR DEVICES
Supply & installation of aluminum fabricated, powder coated grills, diffusers and registers etc for supply, return, exhaust & fresh air of different sizes (Grade A) wooden frame, lindaptor supports and other accessories etc, complete in all respects ready to operate as per drawings, specification and as per instruction of consultant.
a | Supply & Return Air Diffuser with Damper
i. | 300mm x 300mm | Nos. | 18 | 3705 | 500 | 13 | 48165 | 13 | 6500 | 54665
ii. | 375mm x 375mm | Nos. | 2
iii. | 450mm x 450mm | Nos. | 4 | 8214 | 500 | 4 | 32856 | 4 | 2000 | 34856
b | Exhaust Air Disc Valves
i. | 150mm dia | Nos. | 10 | 1625 | 500 | 10 | 16250 | 10 | 5000 | 21250
c | Supply, Transfer & Return Air Grill
i. | 450mm x 150mm | No. | 1 | 2470 | 500 |  | 0 | 0 | 0 | 0
ii. | 450mm x 250mm | Nos. | 4 | 2210 | 500 |  | 0 | 0 | 0 | 0
d | Return & Exhaust Air Register
i. | 150mm x 150mm | No. | 1 | 1650 | 500 |  | 0 | 0 | 0 | 0
ii. | 225mm x 225mm | No. | 1 | 2210 | 500 |  | 0 | 0 | 0 | 0
iii. | 350mm x 350mm | No. | 1 | 4587 | 500 |  | 0 | 0 | 0 | 0
iv. | 900mm x 650mm | No. | 1 | 21902 | 500 |  | 0 | 0 | 0 | 0
e | Linear Slot 6,000 Series
i. | 1 slot of 20mm | Rm | 8 | 3199 | 500 | 10.8 | 34549.2 | 10.8 | 5400 | 39949.2
ii. | 2 slots of 20mm | Rm | 51 | 3732 | 500 | 48.6 | 181375.2 | 48.6 | 24300 | 205675.2
f | S.S Mesh with G.I Frame
i. | 350mm x 150mm | Nos. | 3 | 3500 | 400 | 3 | 10500 | 3 | 1200 | 11700
ii. | 400mm x 200mm | Nos. | 3 | 3500 | 400 | 3 | 10500 | 3 | 1200 | 11700
iii. | 450mm x 200mm | Nos. | 3 | 3800 | 400 | 3 | 11400 | 3 | 1200 | 12600
iv. | 900mm x 250mm | No. | 1 | 6500 | 400 | 1 | 6500 | 1 | 400 | 6900
v. | 1100mm x 200mm | No. | 1 | 8000 | 400 | 1 | 8000 | 1 | 400 | 8400
1.13 | FLEXIBLE DUCT
Supply & installation of flexible duct including hangers, jubilee clamp complete in all respects as per specification, drawings & as per instruction of consultant.
a | 150mm dia | Rm | 25 | 1200 | 300 | 72 | 86400 | 72 | 21600 | 108000
1.14 | BUTTERFLY DAMPER
Supply & installation of butterfly damper for above flexible duct with gas kits, nut bolts, complete in all respects, ready to operate as per specification, drawings & as per instruction of consultant.
a | 150mm dia | Nos. | 22 | 1950 | 500 | 54 | 105300 | 54 | 27000 | 132300
1.15 | VOLUME CONTROL DAMPER
Supply, fabrication & installation of pre-insulated Volume Control Damper, blades to be constructed with extruded aluminum in airfoil shape with thermal isolation gape & shall have seals, pvc / aluminum profiles duct connection at both end, lindapter supports & hangers, etc, complete in all respects ready to operate as per drawings, specification and as per instruction of consultant.
a | 300mm x 150mm | No. | 1 | 3250 | 500 | 6 | 19500 | 6 | 3000 | 22500
b | 350mm x 100mm | Nos. | 2 | 3250 | 500 | 1 | 3250 | 1 | 500 | 3750
c | 400mm x 200mm | Nos. | 3 | 3575 | 500 | 3 | 10725 | 3 | 1500 | 12225
d | 450mm x 200mm | Nos. | 2 | 3276 | 500 | 2 | 6552 | 2 | 1000 | 7552
e | 500mm x 250mm | No. | 1 | 5720 | 500 | 3 | 17160 | 3 | 1500 | 18660
f | 550mm x 200mm | Nos. | 2 | 5033 | 500 | 0 | 0 | 0 | 0 | 0
g | 600mm x 200mm | No. | 1 | 5492 | 500 | 2 | 10984 | 2 | 1000 | 11984
2 | MISCELLANEOUS WORKS
2.1 | PAINTING & IDENDTIFICATION
| Painting & Identification work on chilled water pipes & exhaust duct, supports, hangers etc, complete in all respects with one coat of ICI make Red lead oxide primer & two coats of ICI make enamel paint etc, complete in all respects as per instruction of consultant. | Job | 1 | 15000 | 10000 | 1 | 15000 | 1 | 10000 | 25000
2.2 | TESTING & COMMISSIONING OF SYSTEM
| Testing, balancing and commissioning of air side of the system (from independent agency) complete in all respects including flow measurement & balancing, temp, pressure, electrical data of related equipment etc, complete in all respects as per instruction of consultant. Moreover, testing and commissioning to be carried out as per the Testing and Commissioning document shared within the RFP. | Job | 1 | 0 | 90000 | 1 | 0 | 1 | 90000 | 90000
2.2 | SHOP & AS BUILT DRWAINGS
| Making of Shop drawings on Auto CAD 2018 with section details, equipment foundation details and Making of As Built drawings, Documentation Technical / Operational Manual & LOG Book for each equipment complete in all respects as per instruction of consultant. | Job | 1 | 10000 | 15000 | 1 | 10000 | 1 | 15000 | 25000
| TOTAL COST OF ACMV WORKS | [8 empty] | 9975455.9

## Fire 15
Deutsche Bank AG, Karachi branch | [9 empty] | 2023-03-22
Karachi branch Relocation
S # | Description | Bill of Quantities |  |  |  | Final Bill
[6 empty] | Material |  | Labour |  | Total Amount
|  | Unit | Qty | Material Rate | Labout Rate | Bill Qty | Amount | Bill Qty | Amount
1 | FIRE SUPPRESSION SERVICES
1.1 | MS SCH-40 PIPES
Supply & installation of MS Sch-40 seamless pipes including all specials M.I & D.I threaded & welded joint fittings UL listed FM approved, flexible pipe, flanges, coupling, masking plates, bends, tees, clamps, lindapter supports hangers and sleeves, masking plates chiseling, cutting holes, making good where required, painting and protection treatment etc. complete in all respects ready to operate as per drawings, specification, instruction of consultant.
a | 25mm dia | Rm | 180 | 1580 | 500 | 203.9 | 322162 | 203.9 | 101950 | 424112
b | 32mm dia | Rm | 20 | 2141 | 580 | 21.1 | 45175.1 | 21.1 | 12238 | 57413.1
c | 40mm dia | Rm | 8 | 2555 | 750 | 21.2 | 54166 | 21.2 | 15900 | 70066
d | 50mm dia | Rm | 25 | 3436 | 850 | 16.7 | 57381.2 | 16.7 | 14195 | 71576.2
e | 65mm dia | Rm | 10 | 5452 | 1150 | 43.8 | 238797.6 | 43.8 | 50370 | 289167.6
f | 75mm dia | Rm | 8 | 7404 | 1500 | 20 | 148080 | 20 | 30000 | 178080
1.2 | SPRINKLERS
Supply & installation of sprinkler with fixing accessories, complete in all respects ready to operate as per drawings, specification, instruction of consultant.
a | Sprinkler Upright type quick response K = 5.6 (Opening Temperature 57ºC) | No | 51 | 2500 | 300 | 37 | 92500 | 37 | 11100 | 103600
b | Sprinkler Pendent type with escutcheon plate quick response K = 5.6 (Opening Temperature 57ºC) | No | 25 | 3200 | 400 | 56 | 179200 | 56 | 22400 | 201600
1.3 | FIRE EXTINGUISHERS
Supply & installation of fire extinguishers with fixing accessories, complete in all respects ready to operate as per drawings, specification, instruction of consultant.
a | Type Class B&C FX-3 (5 Kg. CO2 Carbon Dioxide Gas) | No | 3 | 15600 | 300 | 3 | 46800 | 3 | 900 | 47700
b | Type Class A,B&C FX-4 (6 Kg. Dry Chemical Powder) | No | 3 | 8000 | 300 | 3 | 24000 | 3 | 900 | 24900
c | Automatic fire extinguisher (6 Kg. Dry Chemical Powder) | No | 2 | 13000 | 500 | 1 | 13000 | 1 | 500 | 13500
1.4 | INPUT & OUTPUT DEVICES
Supply & installation of input and output devices for the clean agent suppression system (integrated with BMS) with wiring, controls & fixing accessories, complete in all respects ready to operate as per drawings, specification, instruction of consultant
a | Very Early Smoke Detection Apparatus Panel | No. | 1 | 390000 | 50000 |  | 0 | 0 | 0 | 0
b | Air sampling smoke detectors with early warning detection capabilities | No | 2 | 390000 | 50000 |  | 0 | 0 | 0 | 0
2 | MISCELLANEOUS WORKS
2.1 | FLUSHING, TESTING & COMMISSIONING
a | Flushing of entire fire pipe work according to (NFPA-13), complete in all respects as per instruction of consultant. | Job | 1 | 20000 | 20000 | 1 | 20000 | 1 | 20000 | 40000
b | Testing and commissioning of entire clean agent fire suppression system complete in all respects as per instruction of consultant. Moreover, Testing and Commissioning to be carried out as per the testing and commissioning annexure shared in the RFP. | Job | 1 | 0 | 40000 | 1 | 0 | 1 | 40000 | 40000
2.2 | PAINTING & IDENDTIFICATION
| Painting, identification and tagging to the installations and equipments, complete in all respects as per instruction of consultant. | Job | 1 | 30000 | 20000 | 1 | 30000 | 1 | 20000 | 50000
2.3 | MAKING SHOP DRAWINGS
| Making of Shop drawings on Auto CAD 2018 with section details, equipment foundation details and Making of As Built drawings, Documentation Technical / Operational Manual & LOG Book for each equipment complete in all respects as per instruction of consultant. | Job | 1 | 10000 | 10000 | 1 | 10000 | 1 | 10000 | 20000
| TOTAL COST OF FIRE SUPPRESSION SERVICES | [8 empty] | 1631714.9

## Fire 16
Deutsche Bank AG, Karachi branch | [9 empty] | 2023-03-22
Karachi branch Relocation
S # | Description | Bill of Quantities |  |  |  | Final Bill
[6 empty] | Material |  | Labour |  | Total Amount
|  | Unit | Qty | Material Rate | Labout Rate | Bill Qty | Amount | Bill Qty | Amount
1 | FIRE SUPPRESSION SERVICES
1.1 | MS SCH-40 PIPES
Supply & installation of MS Sch-40 seamless pipes including all specials M.I & D.I threaded & welded joint fittings UL listed FM approved, flexible pipe, flanges, coupling, masking plates, bends, tees, clamps, lindapter supports hangers and sleeves, masking plates chiseling, cutting holes, making good where required, painting and protection treatment etc. complete in all respects ready to operate as per drawings, specification, instruction of consultant.
a | 25mm dia | Rm | 160 | 1580 | 500 | 150.7 | 238106 | 150.7 | 75350 | 313456
b | 32mm dia | Rm | 20 | 2141 | 580 | 10.6 | 22694.6 | 10.6 | 6148 | 28842.6
c | 40mm dia | Rm | 4 | 2555 | 750 | 36.6 | 93513 | 36.6 | 27450 | 120963
d | 50mm dia | Rm | 20 | 3436 | 850 | 14.6 | 50165.6 | 14.6 | 12410 | 62575.6
e | 65mm dia | Rm | 30 | 5452 | 1150 | 19.3 | 105223.6 | 19.3 | 22195 | 127418.6
f | 75mm dia | Rm | 20 | 7404 | 1500 | 13.5 | 99954 | 13.5 | 20250 | 120204
1.2 | SPRINKLERS
Supply & installation of sprinkler with fixing accessories, complete in all respects ready to operate as per drawings, specification, instruction of consultant.
a | Sprinkler Upright type quick response K = 5.6 (Opening Temperature 57ºC) | No | 23 | 2500 | 300 | 16 | 40000 | 16 | 4800 | 44800
b | Sprinkler Pendent type with escutcheon plate quick response K = 5.6 (Opening Temperature 57ºC) | No | 35 | 3200 | 400 | 44 | 140800 | 44 | 17600 | 158400
1.3 | FIRE EXTINGUISHERS
Supply & installation of fire extinguishers with fixing accessories, complete in all respects ready to operate as per drawings, specification, instruction of consultant.
a | Type Class B&C FX-3 (5 Kg. CO2 Carbon Dioxide Gas) | No | 3 | 15600 | 300 | 3 | 46800 | 3 | 900 | 47700
b | Type Class A,B&C FX-4 (6 Kg. Dry Chemical Powder) | No | 3 | 8000 | 300 | 3 | 24000 | 3 | 900 | 24900
c | Automatic fire extinguisher (10 Kg. Dry Chemical Powder) | No | 1 | 13000 | 500 | 1 | 13000 | 1 | 500 | 13500
2 | MISCELLANEOUS WORKS
2.1 | FLUSHING, TESTING & COMMISSIONING
a | Flushing of entire fire pipe work according to (NFPA-13), complete in all respects as per instruction of consultant. | Job | 1 | 20000 | 20000 | 1 | 20000 | 1 | 20000 | 40000
b | Testing and commissioning of entire clean agent fire suppression system complete in all respects as per instruction of consultant. Moreover, Testing and Commissioning to be carried out as per the testing and commissioning annexure shared in the RFP. | Job | 1 | 0 | 40000 | 1 | 0 | 1 | 40000 | 40000
2.2 | PAINTING & IDENDTIFICATION
| Painting, identification and tagging to the installations and equipments, complete in all respects as per instruction of consultant. | Job | 1 | 30000 | 20000 | 1 | 30000 | 1 | 20000 | 50000
2.3 | MAKING SHOP DRAWINGS
| Making of Shop drawings on Auto CAD 2018 with section details, equipment foundation details and Making of As Built drawings, Documentation Technical / Operational Manual & LOG Book for each equipment complete in all respects as per instruction of consultant. | Job | 1 | 10000 | 10000 | 1 | 10000 | 1 | 10000 | 20000
| TOTAL COST OF FIRE SUPPRESSION SERVICES | [8 empty] | 1212759.8

## BLANK BOQ (hidden)
UNILEVER PAKISTAN LTD
3RD FLOOR
Ser # | Description | Unit | Qty | Rate | Amount
1 | CIVIL WORK
1.1 | BLOCK MASONRY
Cement concrete block masonry set in 1:4 cement
mortar with 1:4:5 or 1:3:6 machine made block minimum 800 psi
(approved by the Architect) including racking out joints curing, etc.,
complete as per specifications and relevant drawings
| 6" thick (External) | Sft | 5665
| 4" thick (Internal) | Sft | 500
| 3" Thick brick cladding ( Lobby Feature Wall) | Sft | 200
1.2 | PLASTER
Plaster 0.75" thick 1:4 cement plaster to internal
walls, columns, beams, slabs, lintels, steps, etc., including making
chamfered shape edges or rounding off corners at junctions including
curing, etc., complete as per specifications and relevant drawings.
a | Internal Walls | Sft | 8000
b | External periphery walls | Sft | 6700
1.3 | DRY WALL PARTITION WALL
a | 100 mm MDF partition on 75 mm x 75mm partal wood framing @600 mm x 600mm c.c (approx),in ducco finish,treated with approved antitermite slagnum & zahbia primer on both ends of MDF , shall ensure the sample to be approved before purchase of material. The approved sample shall always be at site as detailed in the General Condition of Contract. | Sft | 7000
b | GLASS WALL PARTITION (Translucent Glass film)
| 12 mm thick imported tempared glass fixed, Champaign color aluminium U- channel along with the wall at top and bottom and polishing of exposed edges,with 3M Electro cut 314 Brand frosted film complete in all respects and as directed by the Architect. | Sft | 3100
1.4 | PAINT
Low VOC acrylic emulsion by JOTUN paint on walls of approved quality and shade including rubbing, filling and primer coat., complete in all respects.
a | Internal Fair Faced Textured paint (includes walls and ceiling) | Sft | 5000
b | Internal Walls | Sft | 18500
External Weathred shield
c | 3 coats, external weathered shield by JOTUN, ICI, Nelson paint complete in all respects of approved quality and shade including rubbing, filling and primer coat. | Sft | 6700
1.5 | FLOORING & SPECIAL FINISHES
1.5.1 | PORCELAIN TILES IN OFFICE SPACES
Porcelain tile of 12"x24" full body approved quality.Shade pattern set in 1:4 cement mortar including preparing proper base of 1:2:4 concrete mortar all as per specification and drawing complete in all respect. (MML Product supplied by Benitoz or Equivalent; color & size to be approved by the Architect, price will be Rs. 3000 / sqm)
a | Flooring | Sft | 1000
1.5.2 | PORCELAIN TILES IN WET AREA TILES
Porcelain tile of 12"x24" full body approved quality.Shade pattern set in 1:4 cement mortar including preparing proper base of 1:2:4 concrete mortar all as per specification and drawing complete in all respect. (MML Product supplied by Benitoz or Equivalent; color & size to be approved by the Architect, price will be Rs. 3000 / sqm)
a | Floor | Sft | 1350
b | Wall | Sft | 4500
1.5.3 | CORRIDOR TILES
Porcelain tile of Fiandre Marmi MaximumTravertino size 5'x10' full body approved quality.Shade pattern set in 1:4 cement mortar including preparing proper base of 1:2:4 concrete mortar all as per specification and drawing complete in all respect. (Fiandre Product supplied by Benitoz or Equivalent; color & size to be approved by the Architect, price will be Rs. 13000 / sqm)
a | Floor | Sft | 15750
1.5.4 | GRANITE COUNTER TOP
Granite counter top , including all beds and anchoring, finished as below: (with basin hole cutting and special finishes complete as per drawing ) The Granite will be installed on a GI frame with red oxide coating and the finished with black spray paint. Rs. 800 / sqft
b | Polished finish on Counter Tops | Sft | 260
1.5.5 | GRANITE STEPS
i | Granite to be installed on the Steps using dry bond methodology . Dry bond to be used is Ressichem T210 or Millwala's Tifix
ii | Grouting. Water proof grouting color to be specified by the Architect.
Included in the laying of the Granite will be preparation of floor using cement mix to achieve perfect alignment a required of the floor for the application of tiles. Rs. 800 / sqft
iii | 3" Flame torch finish on Staircase Tread 5'-0" | No | 17
iv | Polish finish on Staircase Riser | No | 21
1.6 | SPECIAL FINISHES
a | Branding and Display (refer to attachment) | Sft | 765
b | Green wall (refer to attachment) baseprice Rs. 2500 SQFT | Sft | 350
c | Ceramic wall cladding (refer to attachment) | Sft | 265
b | Internal Ceiling | Sft | 26000
1.7 | ALUMINUM WINDOW
EXTERNAL WINDOWS
Aluminum Windows using imported section and high quality hardware; that must be airtight with minimum infiltration and exfiltration properties. The Aluminum section will be powder coated, color to be approved by Architect.
(Double-Glazed assembly with U-value of 1.4 W/Sqm.K in 6mm Low-E Exterior Glass + 12mm Air Gap (with or without Argon filling) + 6mm local clear Internal Glass)
| Imported Aluminum windows of W1 size 6'-0" x 4'-6" on front façade. | No. | 7
| Imported Aluminum windows of W2 size 14'-0" x 4'-6" on front façade (Board Room) . | No. | 1
TOTAL COST OF CIVIL WORK
2 | INTERIOR FINISHES WORK
2.1 | CARPET FLOOR
| Carpet as specified by Architect (For spec find the attachment) SQFT Rs. 325 | Sft | 20000
2.2 | VINYL FLOORING
Seamless vinyl flooring by Tarkett or equivalent. Thinkness 4.5mm. (50 mm x 50 mm tile) Inteface level set collection availabe from pak carpets or equivalent. SQFT Rs .265
| Color and size as approved by the Architect. | Sft | 550
2.3 | RUBBER FLOORING
| (Gym Area) 8.2 MM Thickness (For spec find the attachment) | Sft | 150
2.3 | FALSE CEILING
a | CEMENT BOARD CEILING
| Cement Board false ceiling at edges allaround the rooms and corridors to as make-up space to ensure metal pan ceilings are not cut and are used as full tiles. (Rs:110) | Sft | 27500
b | STEEL MESH CEILING IN VITALITY ZONE (Hexazonal MS frame rapped with steel mesh) | Sft | 1600
c | ALUMINUM CEILING ( High-grade pre-coated aluminum alloy ) 0.5mm~1.0mm thinckness | Sft | 1250
2.4 | MDF CLADDING (2" thick partal wood frame rapped around 1/2" thick one side MDF sheet).
| Providing MDF cladding on all exposed columns. | Sft | 7000
2.8 | JOINERY
1.5" thick solid core commercial ply veneer flush door shutters (Formite 7195 - Baluchistan Laminates) SWG G.I 16 gauage door frames 2" x 7" so lignum painted 2"x5/8", approved quality of oxidized brass hinges, brass screw, tower bolts, imported locks top of the line quick set hydraulic door closer (brand-New Star Japanese) Wherever needed aluminum push plates on both sides door stopper and other hardware of brass including iron hold fasts, complete in all respects as per drawings and as directed by the Architect.
| Size 3'-0" X 7'-0" | No | 6
| Size 2'-6" X 7'-0" | No | 9
2.9 | METAL SCREEN
| Laser cut perforated ( High Strength Low Alloy HSLA steel ) corten metal sheet. | Sft | 950
2.7 | Metal framing joinery work for the perforated partition and S.S pipes feature. | Sft | 300
2.9 | SKIRTING
a | PVC skirting of 2" thick in dark grey color. | Rft | 3500
TOTAL COST OF INTERIOR FINISHES WORK
3 | IMPORTED PARTITION WALLS & DOOR
3.1 | WOODEN PARTITION | Sft | 5500
3.2 | 6 plus 6mm LAMINATED TEMPERED GLASS PARTITION | Sft | 2500
3.3 | 10mm TEMPERED GLASS DOOR IN PARTITION | No | 30
3.4 | WOODEN DOOR IN PARTITION | No | 2
TOTAL COST OF PARTITION WALL & DOORS
SUMMARY
1 | CIVIL WORK
2 | INTERIOR FINISHES WORK
3 | PARTITION WALLS & DOORS
TOTAL COST