## summary
Ernst & Young
HVAC & Fire Fighting Work |  |  |  | 2023-11-24
SUMMARY OF BILL OF QUANTITIES
S.No | Description | Material | Labour | Amount
1 | HVAC Work 21st Floor | 24798489.16 | 3356510.44 | 28154999.6
2 | Fire Fighting 21st Floor | 7401145 | 1587140 | 8988285
1 | HVAC Work 22nd Floor | 26528890 | 3478710 | 30007600
2 | Fire Fighting 22nd Floor | 7502745 | 1593460 | 9096205
| Grand Total Amount | 66231269.16 | 10015820.44 | 76247089.6
| Discount 12% |  |  | 9149650.752
| Net Amount |  |  | 67097438.848
| Add 4.5% |  |  | 3019384.7482
| Gross Amount |  |  | 70116823.5962
| 50% |  |  | 35058411.7981
| Total Received |  |  | 35337381
| Receivable Amount |  |  | -278969.2019

## 21HVAC
EY Karachi - 21st Floor - M&P
ITEM NO. | DESCRIPTION |  |  | ESTIMATED QUANTITY | UNIT | MATERIAL |  | INSTALLATION |  | AMOUNT | Lead Time | Brands | Remarks
[6 empty] | RATE | AMOUNT | RATE | AMOUNT
1 | FAN COIL UNITS (SECTION 23 73 20 & DS/1831-23 73 20)
1.1 | Supply & Installation of Fan Coil Units FCU-21-01 Ceiling Hung Type with Wall Mounted Room Thermostat (3.0 TR) with scheduling feature |  |  | 1 | No. | 585000 | 585000 | 20000 | 20000 | 605000 | 5 Weeks | SABRO
1.2 | Supply & Installation of Automatic Air Vents |  |  | 2 | Nos. | 8500 | 17000 | 1000 | 2000 | 19000 | Ready Stock | SCON
1.3 | Ø ½" (Ø 15mm) Shredder Fitting for Air Vent/Pressure Testing |  |  | 2 | Nos. | 13000 | 26000 | 2000 | 4000 | 30000
1.4 | Engineered Supports System with Lindapter Type/TR60 complete in all respect. |  |  | 1 | Lot | 15000 | 15000 | 3000 | 3000 | 18000 | - | -
1.5 | Commissioning & Testing |  |  | 1 | Lot |  | 0 | 20000 | 20000 | 20000 | - | -
Sub-total Carried to Summary
2 | VAV TERMINALS (SECTION 23 36 10 & 23 36 15 & DS/1831-23 36 10 & 23 36 15)
2.1 | Supply & installation of Variable Air Volume (VAV) Terminals with Wall Mounted Thermostat having temperature (Inc./dec.) (Section 23 36 10 & DS/1676-23 36 10) |  |  | 11 | Nos. | 192000 | 2112000 | 7000 | 77000 | 2189000 | 8 to 10 Weeks | JES
2.2 | Engineered Supports System with Lindapter Type/TR60 complete in all respect. |  |  | 1 | Lot | 100000 | 100000 | 15000 | 15000 | 115000 | - | -
2.3 | Commissioning & Testing of VAV Terminals |  |  | 1 | Lot | 0 | 0 | 100000 | 100000 | 100000
Sub-total Carried to Summary
3 | DUCT WORK (MACHINE MADE) (SECTION 23 31 13)
3.1 | Sheet Metal Duct Work (Air Conditioning) (Supply Air), Machine made Ducts (Section 23 31 13) |  |  | 958 | m² | 4950 | 4742100 | 900 | 862200 | 5604300 | Ready Stock | ISL
3.2 | Sheet Metal Duct Work (Air Conditioning) (Return Air), Machine made Ducts (Section 23 31 13) |  |  | 2 | m² | 4700 | 9400 | 900 | 1800 | 11200 | Ready Stock | ISL
3.3 | Sheet Metal Duct Work (Exhaust Air) Machine made Ducts (Section 23 31 13) |  |  | 57 | m² | 4950 | 282150 | 900 | 51300 | 333450 | Ready Stock | ISL
3.4 | Quadrant Volume Damper |  |  | 17 | m² | 42500 | 722500 | 7000 | 119000 | 841500 | 8 Weeks | Steel Craft/ Air guide
3.5 | Flexible Ducts (Section 23 33 46) with Supports, Complete in all respect
3.5.1 | Ø 10" (Ø 250mm) |  |  | - | Rm | 2500 | Rate Only | 400 | Rate Only | Rate Only | Ready Stock | FLEXIVA / Thermoflex
3.5.2 | Ø 8" (Ø 200mm) |  |  | - | Rm | 2200 | Rate Only | 400 | Rate Only | Rate Only | Ready Stock | FLEXIVA / Thermoflex
3.5.3 | Ø 6" (Ø 150mm) |  |  | 16 | Rm | 1200 | 19200 | 400 | 6400 | 25600 | Ready Stock | FLEXIVA / Thermoflex
3.6 | Butterfly Dampers
3.6.1 | Ø 10" (Ø 250mm) |  |  | - | No. | 5000 | Rate Only | 1000 | Rate Only | Rate Only | 3 to 4 weeks | Steel Craft/ Air guide
3.6.2 | Ø 8" (Ø 200mm) |  |  | - | No. | 4000 | Rate Only | 1000 | Rate Only | Rate Only | 3 to 4 weeks | Steel Craft/ Air guide
3.6.3 | Ø 6" (Ø 150mm) |  |  | 16 | Nos. | 3500 | 56000 | 1000 | 16000 | 72000 | 3 to 4 weeks | Steel Craft/ Air guide
3.7 | Fire Damper - Motorized (UL - Listed)
3.7.1 | 42" x 6" (1050mm x 150mm) |  |  | 2 | No. | 185000 | 370000 | 15000 | 30000 | 400000 | 7 Weeks | LOCAL
3.8 | Damper - Motorized
3.8.1 | 14" x 12" (500mm x 300mm) |  |  | 1 | Nos. | 115000 | 115000 | 5000 | 5000 | 120000 | 13 Weeks | LOCAL
3.8.2 | 20" x 12" (500mm x 300mm) |  |  | 1 | Nos. | 125000 | 125000 | 5000 | 5000 | 130000 | 13 Weeks | LOCAL
3.9 | Engineered Support system for Ducts with Lindapter Type/TR60 Complete in all Respect |  |  | 1 | Lot | 600000 | 600000 | 75000 | 75000 | 675000
3.1 | Sound Trap Air Duct Z-Piece for Return Air Intake Size 450mm x 200mm - Refer FND Detail FND/D/35 |  |  | 8 | Nos. | 11000 | 88000 | 3000 | 24000 | 112000
3.11 | G.I Frame as Duct Sleeves - As per FND Detail |  |  | 1 | Lot | 50000 | 50000 | 25000 | 25000 | 75000 | As per required | LOCAL
3.12 | Wire Mesh on all Duct Openings |  |  | 1 | Lot | 25000 | 25000 | 15000 | 15000 | 40000 | As per required | LOCAL
3.13 | Light Testing for Ducting |  |  | 1 | Lot | 0 | 0 | 75000 | 75000 | 75000
Sub-total Carried to Summary
4 | PIPING (SECTION 23 21 13 & DS/1831-23 21 13)
4.1 | Supply & Installation Chilled Water Piping
4.1.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 4300 | Rate Only | 800 | Rate Only | Rate Only | Ready Stock | PROTEK - China
4.1.2 | Ø 1 ½" (Ø 40mm) |  |  | - | Rm | 3300 | Rate Only | 750 | Rate Only | Rate Only | Ready Stock | PROTEK - China
4.1.3 | Ø 1 ¼" (Ø 32mm) |  |  | - | Rm | 2800 | Rate Only | 730 | Rate Only | Rate Only | Ready Stock | PROTEK - China
4.1.4 | Ø 1" (Ø 25mm) |  |  | 3 | Rm | 2300 | 6900 | 660 | 1980 | 8880 | Ready Stock | PROTEK - China
4.2 | Supply & Installation Cooling Water Piping
4.2.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 7300 | Rate Only | 800 | Rate Only | Rate Only | Ready Stock | Aquatherm
4.2.2 | Ø 1 ½" (Ø 40mm) |  |  | - | Rm | 5500 | Rate Only | 750 | Rate Only | Rate Only | Ready Stock | Aquatherm
4.2.3 | Ø 1 ¼" (Ø 32mm) |  |  | 3 | Rm | 3500 | 10500 | 730 | 2190 | 12690 | Ready Stock | Aquatherm
4.2.4 | Ø 1" (Ø 25mm) |  |  | - | Rm | 3000 | Rate Only | 660 | Rate Only | Rate Only | Ready Stock | Aquatherm
4.3 | Condensate Drain Piping
4.3.1 | Ø 1 ¼" (Ø 32mm) |  |  | - | Rm | 1200 | Rate Only | 300 | Rate Only | Rate Only
4.3.2 | Ø 1" (Ø 25mm) |  |  | 11 | Rm | 1150 | 12650 | 280 | 3080 | 15730 | Ready Stock | AGM
4.4 | Pipe Pressure Testing |  |  | 1 | Lot | 0 | 0 | 25000 | 25000 | 25000 | Ready Stock | AGM
4.5 | Engineered Support system with Lindapter Type/TR60 Complete in all Respect |  |  | 1 | Lot | 100000 | 100000 | 15000 | 15000 | 115000
Sub-total Carried to Summary
5 | VALVES & SPECIALITIES (SECTION 23 05 23, 23 86 20 & 23 86 35)
5.1 | Supply and Installation of Gate Valves for Cooling Water with Material/Flanges/Unions etc. (Section 23 05 23)
5.1.1 | Ø 2" (Ø 50mm) |  |  | - | No. | 25000 | Rate Only | 1500 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.1.2 | Ø 1 ½" (Ø 40mm) |  |  | - | No. | 18000 | Rate Only | 1500 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.1.3 | Ø 1 ¼" (Ø 32mm) |  |  | 2 | Nos. | 11500 | 23000 | 1500 | 3000 | 26000 | 4 to 6 weeks | SCON / WATTS
5.1.4 | Ø 1" (Ø 25mm) |  |  | 3 | Nos. | 9500 | 28500 | 1500 | 4500 | 33000 | 4 to 6 weeks | SCON / WATTS
5.1.5 | Ø ¾" (Ø 20mm) |  |  | - | No. | 6500 | Rate Only | 1500 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.2 | Supply and Installation of Ball Valve for Cooling Water with Material/Flanges/Unions etc. (Section 23 05 23)
5.2.1 | Ø 1" (Ø 25mm) |  |  | - | No. | 9000 | Rate Only | 1500 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.2.2 | Ø ¾" (Ø 20mm) |  |  | - | Nos. | 7000 | Rate Only | 1500 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.3 | Supply and Installation of Strainer Cooling Water with Material/Flanges/Unions etc.
5.3.1 | Ø 2" (Ø 50mm) |  |  | - | No. | 20500 | Rate Only | 1000 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.3.2 | Ø 1 ½" (Ø 40mm) |  |  | - | No. | 16000 | Rate Only | 1000 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.3.3 | Ø 1 ¼" (Ø 32mm) |  |  | 1 | No. | 12000 | 12000 | 1000 | 1000 | 13000 | 4 to 6 weeks | SCON / WATTS
5.3.4 | Ø 1" (Ø 25mm) |  |  | 1 | No. | 7500 | 7500 | 1000 | 1000 | 8500 | 4 to 6 weeks | SCON / WATTS
5.4 | Supply and Installation of Flow Balancing & Shut-off Valve for Cooling Water with Material/Flanges/Unions etc.
5.4.1 | Ø 1 ½" (Ø 40mm) |  |  | - | No. | 31500 | Rate Only | 1500 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.4.2 | Ø 1 ¼" (Ø 32mm) |  |  | 1 | No. | 23800 | 23800 | 1500 | 1500 | 25300 | 4 to 6 weeks | SCON / WATTS
5.4.3 | Ø 1" (Ø 25mm) |  |  | - | No. | 20000 | Rate Only | 1500 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.5 | Supply and Installation of Pressure Independent Control Valve (PICV) for Fan Coil Unit with Material/Flanges/Unions etc.
5.5.1 | Ø 1 ½" (Ø 40mm) |  |  | - | No. | 393000 | Rate Only | 8000 | Rate Only | Rate Only | 8 to 10 Weeks | SCON / WATTS
5.5.2 | Ø 1 ¼" (Ø 32mm) |  |  | - | No. | 185000 | Rate Only | 8000 | Rate Only | Rate Only | 8 to 10 Weeks | SCON / WATTS
5.5.3 | Ø 1" (Ø 25mm) |  |  | 1 | No. | 148500 | 148500 | 8000 | 8000 | 156500 | 8 to 10 Weeks | SCON / WATTS
Sub-total Carried to Summary
6 | THERMAL INSULATION (SECTION 23 07 13 & 23 07 19 & DS/1831-23 07 13 & 23 07 19)
6.1 | Insulation of Supply Air Duct-Air Conditioned Space/Air Conditioned Ceiling Cavity |  |  | 958 | m² | 5300 | 5077400 | 750 | 718500 | 5795900 | Ready Stock | AEROFOAM
6.2 | Insulation of Return Air Duct-Air Conditioned Space/Air Conditioned Ceiling Cavity |  |  | 2 | m² | 5200 | 10400 | 750 | 1500 | 11900 | Ready Stock | AEROFOAM
6.3 | Supply & Installation Chilled Water Piping (Section 23 07 19 & DS/1831-23 07 19)
6.3.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 3600 | Rate Only | 230 | Rate Only | Rate Only | Ready Stock | AEROFOAM
6.3.2 | Ø 1 ½" (Ø 40mm) |  |  | - | Rm | 3300 | Rate Only | 230 | Rate Only | Rate Only | Ready Stock | AEROFOAM
6.3.3 | Ø 1 ¼" (Ø 32mm) |  |  | - | Rm | 3000 | Rate Only | 230 | Rate Only | Rate Only | Ready Stock | AEROFOAM
6.3.4 | Ø 1" (Ø 25mm) |  |  | 3 | Rm | 2780 | 8340 | 230 | 690 | 9030 | Ready Stock | AEROFOAM
6.4 | Condensate Drain Piping Insulation (Section 23 07 19 & DS/1831-23 07 19)
6.4.1 | Ø 1 ¼" (Ø 32mm) |  |  | - | Rm | 1900 | Rate Only | 300 | Rate Only | Rate Only | Ready Stock | AEROFOAM
6.4.2 | Ø 1" (Ø 25mm) |  |  | 10.668 | Rm | 1870 | 19949.16 | 330 | 3520.44 | 23469.6 | Ready Stock | AEROFOAM
6.5 | Cladding of Valves & Specialities (Openable Boxes with Insulation)
6.5.1 | Ø 2" (Ø 50mm) |  |  | - | No. |  | Rate Only |  | Rate Only | Rate Only | - | -
6.5.2 | Ø 1 ½" (Ø 40mm) |  |  | - | No. |  | Rate Only |  | Rate Only | Rate Only | - | -
6.5.3 | Ø 1 ¼" (Ø 32mm) |  |  | - | No. |  | Rate Only |  | Rate Only | Rate Only | - | -
6.5.4 | Ø 1" (Ø 25mm) |  |  | 5 | Nos. | 7000 | 'Rate Only | 1500 | 'Rate Only | 'Rate Only | - | -
Sub-total Carried to Summary
7 | AIR DEVICES (SECTION 23 37 13)
7.1 | Supply Air Linear (Tuttle & Bailey) (Series 7000 1" - 25mm x 3 Slots) with Factory Supplied & Field Installed Plenum with Insulation |  |  | 13 | Rm | 5700 | 74100 | 700 | 9100 | 83200 | 8 to 10 weeks | Steel Craft/ Air guide
7.2 | Return Air Linear (Tuttle & Bailey) (Series 7000 1" - 25mm x 3 Slots) with Factory Supplied & Field Installed Plenum with Insulation |  |  | 13 | Rm | 5700 | 74100 | 700 | 9100 | 83200 | 8 to 10 weeks | Steel Craft/ Air guide
7.3 | Supply/Return Air Fixed Bar Grill & Register (Tuttle & Bailey - A50 Series) 21" x 6" (525mm x 150mm) with Damper |  |  | 4 | Nos. | 4500 | 18000 | 700 | 2800 | 20800 | 8 to 10 weeks | Steel Craft/ Air guide
7.4 | Supply Air Fixed Bar Grill & Register (Tuttle & Bailey - A50 Series) 42" x 6" (1050mm x 150mm) with Damper |  |  | 1 | No. | 12000 | 12000 | 5000 | 5000 | 17000 | 8 to 10 weeks | Steel Craft/ Air guide
7.5 | Supply/Return Air Fixed Bar Grill & Register (Tuttle & Bailey - A50 Series) 232" x 18" (5800mm x 450mm) with Damper |  |  | 1 | No. | 105000 | 105000 | 5000 | 5000 | 110000 | 8 to 10 weeks | Steel Craft/ Air guide
7.6 | Supply Air Round Diffusers Ø 12" (Tuttle & Bailey) (Series AVJR 3-Cone) with Dampers |  |  | 89 | Nos. | 24500 | 2180500 | 1500 | 133500 | 2314000 | 8 to 10 weeks | Steel Craft/ Air guide
7.7 | Supply Air Round Diffusers Ø 10" (Tuttle & Bailey) (Series AVJR 3-Cone) with Dampers |  |  | - | No. | 22000 | Rate Only | 1500 | Rate Only | Rate Only | 8 to 10 weeks | Steel Craft/ Air guide
7.8 | Exhaust Air Disc Valve for Toilet Exhaust (Ø 6") |  |  | 24 | Nos. | 3200 | 76800 | 1000 | 24000 | 100800 | 8 to 10 weeks | Steel Craft/ Air guide
Sub-total Carried to Summary
8 | WATER COOLED PACKAGED AIR CONDITIONER (SECTION 23 81 30 & DS/1831-23 81 30)
8.1 | Supply and Installation of Water Cooled Packaged Air Conditioner (CWPU-21-01) Ceiling Hung Type with Wall Mounted Room Thermostat (3.0 TR) with Scheduling feature |  |  | 1 | No. | 1070000 | 1070000 | 25000 | 25000 | 1095000 | 12 Weeks | SABRO / COOLMAX
8.2 | Supply and Installation of Automatic Air Vents |  |  | 2 | Nos. | 8500 | 17000 | 1000 | 2000 | 19000 | Ready Stock | SCON / WATTS
8.3 | Ø ½" (Ø 15mm) Shredder Fitting for Air Vent/Pressure Testing |  |  | 2 | Nos. | 10000 | 20000 | 2000 | 4000 | 24000
8.4 | Pressure Switch |  |  | 1 | No. | 24000 | 24000 | 3000 | 3000 | 27000 | 5 Weeks | Danfoss
8.5 | Control Wiring Between Indoor and Thermostat |  |  | 1 | Lot | 10000 | 10000 | 2500 | 2500 | 12500 | Ready Stock | INDUS / FAST
8.6 | Support System for Water Cooled Package Units with Lindapter Type/TR60 complete in all respect |  |  | 1 | Lot | 15000 | 15000 | 3000 | 3000 | 18000 | Ready Stock | INDEX
8.7 | Commissioning & Testing of Water Cooled Package Units |  |  | 1 | Lot | 0 | 0 | 20000 | 20000 | 20000
Sub-total Carried to Summary
9 | METER & GAUGES (SECTION 23 05 19)
9.1 | Thermometers with Wells for Pipe Thermometer |  |  | 4 | Nos. | 12500 | 50000 | 1000 | 4000 | 54000 | Ready Stock | WEISS / WEKSLER
9.2 | Pressure Gauges on Pipes |  |  | 4 | Nos. | 9500 | 38000 | 1000 | 4000 | 42000 | Ready Stock | WEISS / WEKSLER
9.3 | Gauge Outlets with Cock |  |  | 4 | Nos. | 2000 | 8000 | 1000 | 4000 | 12000 | Ready Stock | WEISS / WEKSLER
Sub-total Carried to Summary
10 | HVAC CONTROLS (SECTION 23 09 20)
10.1 | DDC Controller (BACnet/IP) for FCU-21-01 (Refer FND Drawing # FND-1831-XX-H-XX-XX-700-00) |  |  | 1 | No. | 175000 | Rate Only | 5000 | Rate Only | Rate Only | 10 Weeks | JES
10.2 | DDC Controller (BACnet/IP) for CWPU-21-01 (Refer FND Drawing # FND-1831-XX-H-XX-XX-700-00) |  |  | 1 | No. | 175000 | Rate Only | 5000 | Rate Only | Rate Only | 10 Weeks | JES
10.3 | Installation of Differential Pressure Switch (DPS) with pressure adjustment range of .5 to 4 mbar and switching difference of 0.2 mbar or less. |  |  | 2 | Nos. | 0 | Rate Only | 15000 | Rate Only | Rate Only | 10 Weeks | JES
10.4 | Wiring of PS from Duct Index Point to AHU DDC Panel (3 Core x 18AWG Shielded Wire-Belden Cable) |  |  | 1 | Lot | 175000 | Rate Only | 25000 | Rate Only | Rate Only | 10 Weeks | JES
10.5 | Master/Network Controller that will host the connected devices (VAV's Controllers and thermostat) and can work as a standalone server. (complete set along with Power Supply) |  |  | 1 | No. | 0 | Rate Only | 100000 | Rate Only | Rate Only | 10 Weeks | JES
10.6 | Integration & comissioning of Pressure Independent Control Valve with Modulating Proportional Valve Actuator with Reversible Synchronous Motor 0-10 VDC. (Chilled Water Application) |  |  | 1 | No. | 75000 | Rate Only | 15000 | Rate Only | Rate Only | 10 Weeks | JES
10.7 | Integration of Wall Mounted Room Thermostat for FCU-21-01 - Supplied with FCU |  |  | 1 | No. | 75000 | Rate Only | 10000 | Rate Only | Rate Only | 10 Weeks | JES
10.8 | Integration of Wall Mounted Room Thermostat for CWPU-21/01 - Supplied with CWPU |  |  | 1 | No. | 75000 | Rate Only | 10000 | Rate Only | Rate Only | 10 Weeks | JES
10.9 | Integration of Pressure Switch - Supplied with CWPU |  |  | 1 | No. | 75000 | Rate Only | 15000 | Rate Only | Rate Only | 10 Weeks | JES
10.1 | Integration of Motorized Fire Damper Actuator (2 Nos.) with power & control cable 1.5mm2 installed in (Ø 20mm) PVC Conduit, complete in all respect (Size of Damper 525 x 150mm & Airflow is 500 cfm) - Material Covered in BOQ item # 3.7 |  |  | 1 | Lot | 100000 | Rate Only | 45000 | Rate Only | Rate Only | 10 Weeks | JES
10.11 | Integration of Motorized Fire Damper Actuator (1 No.) with power & control cable 1.5mm2 installed in (Ø 20mm) PVC Conduit, complete in all respect (Size of Damper 1050mm x 150mm & Airflow is 1000 cfm) - Material Covered in BOQ item # 3.7 |  |  | 1 | Lot | 100000 | Rate Only | 45000 | Rate Only | Rate Only | 10 Weeks | JES
10.12 | Integration of Motorized Damper Actuator (2 Nos.) with power & control cable 1.5mm2 installed in (Ø 20mm) PVC Conduit, complete in all respect (Size of Damper 500mm x 200mm & Airflow is 1000cfm) - Material Covered in BOQ item # 3.8 |  |  | 1 | Lot | 100000 | Rate Only | 50000 | Rate Only | Rate Only | 10 Weeks | JES
10.13 | Networking, Cabling, Receway Support, Hanger, Sleeves, Core Drilling etc. |  |  | 1 | Lot | 275000 | Rate Only | 75000 | Rate Only | Rate Only | 10 Weeks | JES
Sub-total Carried to Summary
11 | HOT WATER SUPPLY SYSTEM
11.1 | Supply & Installation of Instant Electric Operated Hot Water Heaters (Section 22 33 30 & DS/1831-22 33 30)
11.1.1 | Supply, Installation and Comissioning of Electric Operated Hot Water Heater HWH/01-02, 30L heating capacity. Including all fittings and accessories required from installation till comissioning of Hot Water Heater (Refer DS/1831-22 33 30) | 2 | Nos. | 2 | Nos. | 78000 | 156000 | 5000 | 10000 | 166000 | Ready Stock | ARISTON
11.2 | Poly Propylene Pipe for Cold Water Supply (PPR Pipe PN-20 with PN-20 Fittings including all Fittings and Accessories Required for Piping Installation) (Section 22 11 16 & DS/1831-22 11 16)
11.2.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 4500 | Rate Only | 800 | Rate Only | Rate Only | Ready Stock | RECKTHERM
11.2.2 | Ø 1 ½" (Ø 40mm) |  |  | - | Rm | 3500 | Rate Only | 800 | Rate Only | Rate Only | Ready Stock | RECKTHERM
11.2.3 | Ø 1 ¼" (Ø 32mm) |  |  | - | Rm | 3000 | Rate Only | 800 | Rate Only | Rate Only | Ready Stock | RECKTHERM
11.2.4 | Ø 1" (Ø 25mm) |  |  | 6 | Rm | 2200 | 13200 | 800 | 4800 | 18000 | Ready Stock | RECKTHERM
11.3 | Poly Propylene Pipe for Hot Water Supply (PPR Pipe PN-20 with PN-20 Fittings including all Fittings and Accessories Required for Piping Installation) (Section 22 11 16 & DS/1831-22 11 16)
11.3.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 4500 | Rate Only | 800 | Rate Only | Rate Only | Ready Stock | RECKTHERM
11.3.2 | Ø 1 ½" (Ø 40mm) |  |  | 13 | Rm | 3500 | 45500 | 800 | 10400 | 55900 | Ready Stock | RECKTHERM
11.3.3 | Ø 1 ¼" (Ø 32mm) |  |  | 23 | Rm | 3000 | 69000 | 800 | 18400 | 87400 | Ready Stock | RECKTHERM
11.3.4 | Ø 1" (Ø 25mm) |  |  | 12 | Rm | 2200 | 26400 | 800 | 9600 | 36000 | Ready Stock | RECKTHERM
11.4 | Valve & Specialities (Section 22 05 23)
11.4.1 | Gate Valves - PPR PN-20 (Including all Fittings and Accessories Required for Valve Installation) (Section 22 05 23)
11.4.1.1 | Ø 2" (Ø 50mm) |  |  | - | No. | 25000 | Rate Only | 1000 | Rate Only | Rate Only | Ready Stock | RECKTHERM
11.4.1.2 | Ø 1 ½" (Ø 40mm) |  |  | 2 | Nos. | 18000 | 36000 | 1000 | 2000 | 38000 | Ready Stock | RECKTHERM
11.4.1.3 | Ø 1 ¼" (Ø 32mm) |  |  | 4 | Nos. | 10800 | 43200 | 1000 | 4000 | 47200 | Ready Stock | RECKTHERM
11.4.1.4 | Ø 1" (Ø 25mm) |  |  | 10 | Nos. | 8500 | 85000 | 1000 | 10000 | 95000 | Ready Stock | RECKTHERM
11.4.2 | Insulation of Hot Water Piping Including Vapor Barrier, Jacketing & Cladding (Section 22 07 19 & DS/1831-22 07 19)
11.4.2.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 2200 | Rate Only | 140 | Rate Only | Rate Only | 2 to 3 weeks | AEROFOAM
11.4.2.2 | Ø 1 ½" (Ø 40mm) |  |  | 13 | Rm | 1800 | 23400 | 130 | 1690 | 25090 | 2 to 3 weeks | AEROFOAM
11.4.2.3 | Ø 1 ¼" (Ø 32mm) |  |  | 23 | Rm | 1700 | 39100 | 120 | 2760 | 41860 | 2 to 3 weeks | AEROFOAM
11.4.2.4 | Ø 1" (Ø 25mm) |  |  | 12 | Rm | 1500 | 18000 | 100 | 1200 | 19200 | 2 to 3 weeks | AEROFOAM
11.5 | Cladding of Valves & Specialities (Openable Boxes with Insulation)
11.5.1 | Ø 2" (Ø 50mm) |  |  | - | No. | 5000 | Rate Only | 600 | Rate Only | Rate Only
11.5.2 | Ø 1 ½" (Ø 40mm) |  |  | 2 | Nos. | 4000 | Rate Only | 600 | Rate Only | Rate Only
11.5.3 | Ø 1 ¼" (Ø 32mm) |  |  | 4 | Nos. | 3000 | Rate Only | 600 | Rate Only | Rate Only
11.5.4 | Ø 1" (Ø 25mm) |  |  | 8 | Nos. | 2000 | Rate Only | 600 | Rate Only | Rate Only
11.6 | Pressure Testing of Water Supply Piping (1.5 times of operating pressure) (Including all arrangements required for Pressure Testing) |  |  | 1 | Lot | 0 | 0 | 25000 | 25000 | 25000
11.7 | Engineered Support system with Lindapter Type/TR60 Complete in all Respect |  |  | 1 | Lot | 75000 | 75000 | 15000 | 15000 | 90000
Sub-total Carried to Summary
12 | PLUMBING FIXTURES & FITTINGS
12.1 | Fixtures (Section 22 41 10 & DS/1831-22 41 10)
12.1.1 | Supply & Installation of Wall Hung Western WC, Concealed Flush Tank Operated (Section 22 41 10 & DS/1831-22 41 10) |  |  | 10 | Nos. | 153000 | 1530000 | 7500 | 75000 | 1605000 | 12 weeks | Porta & Grohe
12.1.2 | Supply & Installation of Vanity Wash Basin with, Waste, Bottle Trap & Tee Stop-Cock (Section 22 41 10 & DS/1831-22 41 10) |  |  | 10 | Nos. | 75000 | 750000 | 6500 | 65000 | 815000 | 12 weeks | Porta & Grohe
12.1.3 | Supply & Installation of Disabled Toilet Set (Basin, WC) (Section 22 41 10 & DS/1831-22 41 10) |  |  | 2 | Nos. | 75000 | 150000 | 6500 | 13000 | 163000 | 12 weeks | Porta & Grohe
12.1.4 | Supply & Installation of Wash Basin Single Lever Faucet with Flexible Hoses (For Cold & Hot Water). (Section 22 41 10 & DS/1831-22 41 10) |  |  | 12 | Nos. | 55000 | 660000 | 4500 | 54000 | 714000 | 12 weeks | Porta & Grohe
12.1.5 | Supply & Installation of Stainless Steel Kitchen Sink including stop cocks, P-trap / bottle trap, waste pipe etc. |  |  | 1 | Nos. | 95000 | 95000 | 6000 | 6000 | 101000 | 12 weeks | Porta & Grohe
12.1.6 | Supply & Installation of Hot and Cold Water Mixer for Stainless Steel Kitchen Sink |  |  | 1 | Nos. | 48000 | 48000 | 4500 | 4500 | 52500 | 12 weeks | Porta & Grohe
12.1.7 | Supply & Installation of WC Hand Operated Shower Spray With Angle Valve and Flexible Hose. (Section 22 41 10 & DS/1831-22 41 10) |  |  | 12 | Nos. | 14500 | 174000 | 1500 | 18000 | 192000 | 12 weeks | Porta & Grohe
12.1.8 | Supply & Installation of Bib Cocks for (Janitor, Cleaning Area) (Section 22 41 10 & DS/1831-22 41 10) |  |  | 2 | Nos. | 2500 | 5000 | 1000 | 2000 | 7000 | 12 weeks | Porta & Grohe
12.1.9 | Supply & Installation of Single Lever Faucet Wall Mounted for (Hot & Cold Water) (Ablution Area) (Section 22 41 10 & DS/1831-22 41 10) |  |  | 6 | Nos. | 48000 | 288000 | 4500 | 27000 | 315000 | 12 weeks | Porta & Grohe
12.1.10 | Supply & Installation of Toilet Roll Holder (Section 22 41 10 & DS/1831-22 41 10) |  |  | 12 | Nos. | 13700 | 164400 | 1000 | 12000 | 176400 | 12 weeks | Porta & Grohe
12.1.11 | Supply & Installation of Wall Mounted Soap Dispenser (Section 22 41 10 & DS/1831-22 41 10) |  |  | 10 | Nos. | 14500 | 145000 | 1000 | 10000 | 155000 | 12 weeks | Porta & Grohe
12.2 | Drainage & Vent Pipe (uPVC - Non Pressure Class; Solvent Welded) Including all Fittings and Accessories Required for Piping Installation e.g Elbows, Y, Double Y, Ceiling Cleanouts, Reducers, Sockets etc. (Section 22 13 20 & DS/1831-22 13 20)
12.2.1 | Ø 4" (Ø 100mm) |  |  | - | Rm | 3500 | Rate Only | 600 | Rate Only | Rate Only | Ready Stock | AGM
12.2.2 | Ø 3" (Ø 75mm) |  |  | - | Rm | 2200 | Rate Only | 600 | Rate Only | Rate Only | Ready Stock | AGM
12.2.3 | Ø 2" (Ø 50mm) |  |  | - | Rm | 1600 | Rate Only | 600 | Rate Only | Rate Only | Ready Stock | AGM
12.2.4 | Ø 1 ½" (Ø 40mm) |  |  | - | Rm | 1250 | Rate Only | 600 | Rate Only | Rate Only | Ready Stock | AGM
12.3 | Drain Accessories (Section 22 11 19)
12.3.1 | SS Floor Drain (Section 22 11 19)
12.3.1.1 | Ø 6" x 6" (Ø 150 x 150 mm) |  |  | 20 | Nos. | 8800 | 176000 | 1000 | 20000 | 196000 | Ready Stock | QABIL
12.3.2 | SS Floor Clean Out (Section 22 11 19)
12.3.2.1 | Ø 4" (Ø 100mm) |  |  | 12 | Nos. | 7500 | 90000 | 1000 | 12000 | 102000 | Ready Stock | QABIL
12.3.2.2 | Ø 3" (Ø 75mm) |  |  | - | No. | 7500 | Rate Only | 1000 | Rate Only | Rate Only | Ready Stock | QABIL
12.4 | 350mm Wide Drain Channel with SS Grating for Ablution Area (Refer FND Detail # FND/SDS/24) |  |  | 6 | Rm | 42000 | 252000 | 1000 | 6000 | 258000 | Ready Stock | QABIL
12.5 | Gravity Testing of Drainage Piping (Including all arrangements required for Gravity Testing) |  |  | 1 | Lot |  | 0 | 30000 | 30000 | 30000
12.6 | Engineered Support system Complete in all Respect |  |  | 1 | Lot | 50000 | 50000 | 15000 | 15000 | 65000 | Ready Stock | INDEX
Sub-total Carried to Summary
13 | CLEANING & BALANCING OF HVAC SYSTEM (SECTION 23 05 93)
13.1 | Cleaning & Balancing of HVAC System (Water + Air) |  |  | 1 | Lot |  | 0 | 150000 | 150000 | 150000
Sub-total Carried to Summary
14 | PAINTING & FINISHING AND MECHANICAL IDENTIFICATION (SECTION 23 05 50 & 23 05 53)
14.1 | Painting & Finishing, Stenciling of Pipes & Ducts, Identification Tags on Valves etc. and Equipment Data Plates (Section 23 05 50) |  |  | 1 | Lot | 100000 | 100000 | 15000 | 15000 | 115000 | Ready Stock | ICI / BERGER
Sub-total Carried to Summary
15 | MISCELLANEOUS
15.1 | Pipe Sleeves/Core Cutting Where Required |  |  | 1 | Lot | 25000 | 25000 | 15000 | 15000 | 40000
15.2 | Shop Drawings, As Built Drawings, Operation & Maintenance Manuals |  |  | 1 | Lot | 25000 | 25000 | 15000 | 15000 | 40000
15.3 | Fire Stopping Material for all HVAC & Plumbing Pipes, Duct, Trays etc. Crossing a Fire Barrier Wall/Floor/Partition as per Required Fire Rating (Refer Fire Strategy Drawings for Fire Barrier Wall/Floor) |  |  | 1 | Lot | 100000 | 100000 | 75000 | 75000 | 175000
Sub-total Carried to Summary | [6 empty] | 24798489.16 |  | 3356510.44 | 28154999.6
37143284.6
113657454.2

## 21FF
EY Karachi - 21st Floor - FF
ITEM NO. | DESCRIPTION | ESTIMATED QUANTITY | UNIT | MATERIAL |  | INSTALLATION |  | AMOUNT | Lead Time | Brands | Remarks
|  |  |  | RATE | AMOUNT | RATE | AMOUNT
1 | FIRE SPRINKLERS (SECTION 21 13 10 & DS/1831-21 13 10)
1.1 | Fire Sprinkler- Upright, Quick Response (SP-01) | 220 | Nos. | 2800 | 616000 | 1000 | 220000 | 836000 | 10 Weeks | SHIELD
1.2 | Fire Sprinkler- Pendent Concealed, Quick Response (SP-02) | 60 | Nos. | 7500 | 450000 | 1000 | 60000 | 510000 | 10 Weeks | SHIELD
1.3 | Fire Sprinkler- Pendent Sprinkler, Quick Response (SP-03) | 12 | Nos. | 4500 | 54000 | 1000 | 12000 | 66000 | 10 Weeks | SHIELD
1.4 | Cabinet Complete with 06 Spare Sprinklers (Upright) (SP-01) | 1 | Nos. | 35000 | 35000 | 3000 | 3000 | 38000 | 10 Weeks | SHIELD
1.5 | Cabinet Complete with 06 Spare Sprinklers (Concealed Pendent) (SP-02) | 1 | No. | 45000 | 45000 | 2000 | 2000 | 47000 | 10 Weeks | SHIELD
1.6 | Cabinet Complete with 06 Spare Sprinklers (Pendent) (SP-03) | 1 | No. | 40000 | 40000 | 2000 | 2000 | 42000 | 10 Weeks | SHIELD
Sub-total Carried to Summary
2 | CORRUGATED STAINLESS STEEL FLEXIBLE CONNECTOR
2.1 | Corrugated Stainless Steel Flexible Connector Ø 1" X 3 ft (UL/FM) (Braided) | 60 | Nos. | 11500 | 690000 | 1000 | 60000 | 750000 | 10 Weeks | SHIELD / SEUNG JIN IND
Sub-total Carried to Summary
3 | PORTABLE FIRE EXTINGUISHER FOR FIRE TYPES A, B, C & AFFF (SECTION 21 21 10 & DS/1831-21 21 10)
3.1 | Supply & Installation of 6 Kg Dry Powder Extinguisher (ABC) | 2 | Nos. | 14500 | 29000 | 700 | 1400 | 30400 | 10 Weeks | NAFCO
3.2 | Supply & Installation of 6 Kg CO2 Fire Extinguisher | 2 | Nos. | 25500 | 51000 | 700 | 1400 | 52400 | 10 Weeks | NAFCO
Sub-total Carried to Summary
4 | BLACK STEEL SCHEDULE-40 PIPING (SECTION 21 10 10)
4.1 | Welded Piping System
4.1.1 | Ø 4" (100mm) | - | Rm | 12500 | Rate Only | 1250 | Rate Only | Rate Only | ReadyStock | Protek
4.1.2 | Ø 3" (75mm) | 100 | Rm | 9800 | 980000 | 880 | 88000 | 1068000 | ReadyStock | Protek
4.1.3 | Ø 2½" (65mm) | - | Rm | 7800 | Rate Only | 800 | Rate Only | Rate Only | ReadyStock | Protek
4.2 | Threaded Piping System
4.2.1 | Ø 2" (50mm) | 170 | Rm | 4700 | 799000 | 710 | 120700 | 919700 | ReadyStock | Protek
4.2.2 | Ø 1½" (40mm) | 157 | Rm | 3390 | 532230 | 700 | 109900 | 642130 | ReadyStock | Protek
4.2.3 | Ø 1¼" (32mm) | 96 | Rm | 2900 | 278400 | 690 | 66240 | 344640 | ReadyStock | Protek
4.2.4 | Ø 1" (25mm) | 500 | Rm | 2100 | 1050000 | 680 | 340000 | 1390000 | ReadyStock | Protek
Sub-total Carried to Summary
5 | GATE VALVE (SECTION 21 05 23)
5.1 | Ø2 inch (50 mm) | 2 | Nos. | 95000 | 190000 | 5000 | 10000 | 200000 | 10 Weeks | SHILED
Sub-total Carried to Summary
6 | SIESMIC BRACING
6.1 | Transverse Seismic Bracing (As per FND Detail No. FND/SS/10)
6.1.1 | Ø 4" (100mm) | - | No. |  | Rate Only |  | Rate Only | Rate Only | 6 weeks | Index
6.1.2 | Ø 3" (75mm) | 11 | Nos. | 9875 | 108625 | 3000 | 33000 | 141625 | 6 weeks | Index
6.1.3 | Ø 2½" (65mm) | - | No. |  | Rate Only |  | Rate Only | Rate Only | 6 weeks | Index
6.2 | Longitudinal Seismic Bracing (As per FND Detail No. FND/SS/11)
6.2.1 | Ø 4" (100mm) | - | No. |  | Rate Only |  | Rate Only | Rate Only | 6 weeks | Index
6.2.2 | Ø 3" (75mm) | 7 | Nos. | 12250 | 85750 | 3000 | 21000 | 106750 | 6 weeks | Index
6.2.3 | Ø 2½" (65mm) | - | No. |  | Rate Only |  | Rate Only | Rate Only | 6 weeks | Index
6.3 | Seismic Restraint (As per FND Detail No. FND/ADD/08)
6.3.1 | Ø 2" (50mm) | 17 | Nos. | 5820 | 98940 | 1500 | 25500 | 124440 | 6 weeks | Index
6.3.2 | Ø 1½" (40mm) | 34 | Nos. | 5300 | 180200 | 1500 | 51000 | 231200 | 6 weeks | Index
6.3.3 | Ø 1¼" (32mm) | 10 | Nos. | 5200 | 52000 | 1500 | 15000 | 67000 | 6 weeks | Index
6.3.4 | Ø 1" (25mm) | 70 | Nos. | 4800 | 336000 | 1500 | 105000 | 441000 | 6 weeks | Index
Sub-total Carried to Summary
7 | FIRE SPRINKLER SYSTEM ACCEPTANCE TEST (SECTION 21 13 17)
7.1 | Fire Sprinkler System Acceptance Test | 1 | Lot | 0 | 0 | 25000 | 25000 | 25000
Sub-total Carried to Summary
8 | PAINTING COATING & STENCILING (SECTION 21 05 50)
8.1 | Painting, Coating, Stenciling & Identification of Fire Piping | 1 | Lot | 200000 | 200000 | 35000 | 35000 | 235000 | Ready Stock | ICI / BERGER
Sub-total Carried to Summary
9 | PIPE SUPPORT SYSTEM (SECTION 21 05 29)
9.1 | Engineered Support system with Lindapter Type/TR60 Complete in all Respect | 1 | Lot | 375000 | 375000 | 55000 | 55000 | 430000 | ReadyStock | Index
Sub-total Carried to Summary
10 | MISCELLANEOUS
10.1 | Hydrostatic Testing | 1 | Lot |  | 0 | 50000 | 50000 | 50000
10.2 | Shop Drawings, As Built Drawings, Operation & Maintenance Manuals | 1 | Lot |  | 0 | 25000 | 25000 | 25000
10.3 | Fire Stopping of Paritions, Walls & Structure Openings (For Small Openings - Hilti FS - ONE or Approved Equivalent) | 1 | Lot | 100000 | 100000 | 25000 | 25000 | 125000
10.4 | Pipe Sleeves / Core Cutting Wherever Required | 1 | Lot | 25000 | 25000 | 25000 | 25000 | 50000
Sub-total Carried to Summary |  |  |  |  | 7401145 |  | 1587140 | 8988285

## 22HVAC
EY Karachi - 22nd Floor - M&P
ITEM NO. | DESCRIPTION |  |  | ESTIMATED QUANTITY | UNIT | MATERIAL |  | INSTALLATION |  | AMOUNT | Lead Time | Brands
[6 empty] | RATE | AMOUNT | RATE | AMOUNT
1 | FAN COIL UNITS (SECTION 23 73 20 & DS/1831-23 73 20)
1.1 | Supply & Installation of Fan Coil Units FCU/22-01 Ceiling Hung Type with Wall Mounted Room Thermostat (3.0 TR) with Scheduling Feature |  |  | 1 | Nos. | 585000 | 585000 | 20000 | 20000 | 605000 | 5 Weeks | SABRO
1.2 | Supply & Installation of Automatic Air Vents |  |  | 2 | Nos. | 8500 | 17000 | 1000 | 2000 | 19000 | Ready Stock | SCON
1.3 | Ø ½" (Ø 15mm) Shredder Fitting for Air Vent/Pressure Testing |  |  | 2 | Nos. | 13000 | 26000 | 2000 | 4000 | 30000
1.4 | Lifting & Shifting of Equipments to the Location Designated for Installation as Specified in the Drawings |  |  | 1 | No. |  | 0 | 10000 | 10000 | 10000
1.5 | Engineered Supports as per Hitli/Sikla/Walraven/Fischer with Lindapter Type/TR60 complete in all respect |  |  | 1 | Lot | 15000 | 15000 | 3000 | 3000 | 18000 | - | -
1.6 | Commissioning & Testing |  |  | 1 | Lot |  | 0 | 20000 | 20000 | 20000 | - | -
Sub-total Carried to Summary
2 | VAV TERMINALS (SECTION 23 36 10 & 23 36 15 & DS/1831-23 36 10 & 23 36 15)
2.1 | Supply & installation of Variable Air Volume (VAV) Terminals with Wall Mounted Thermostat having temperature (Inc./dec.) (Section 23 36 10 & DS/1676-23 36 10) |  |  | 10 | Nos. | 192000 | 1920000 | 7000 | 70000 | 1990000 | 8 to 10 Weeks | JES
2.2 | Engineered Supports System with Lindapter Type/TR60 complete in all respect. |  |  | 1 | Lot | 100000 | 100000 | 15000 | 15000 | 115000 | - | -
2.3 | Commissioning & Testing of VAV Terminals |  |  | 1 | Lot | 0 | 0 | 100000 | 100000 | 100000
Sub-total Carried to Summary
3 | DUCT WORK (MACHINE MADE) (SECTION 23 31 13)
3.1 | Sheet Metal Duct Work (Air Conditioning) (Supply Air), Machine made Ducts (Section 23 31 13) |  |  | 970 | m² | 4950 | 4801500 | 900 | 873000 | 5674500 | Ready Stock | ISL
3.2 | Sheet Metal Duct Work (Air Conditioning) (Return Air), Machine made Ducts (Section 23 31 13) |  |  | 4 | m² | 4700 | 18800 | 900 | 3600 | 22400 | Ready Stock | ISL
3.3 | Sheet Metal Duct Work (Exhaust Air) Machine made Ducts (Section 23 31 13) |  |  | 57 | m² | 4950 | 282150 | 900 | 51300 | 333450 | Ready Stock | ISL
3.4 | Quadrant Volume Damper |  |  | 14 | m² | 42500 | 595000 | 7000 | 98000 | 693000 | 8 Weeks | Steel Craft/ Air guide
3.5 | Flexible Ducts (Section 23 33 46) with Supports, Complete in all respect
3.5.1 | Ø 10" (Ø 250mm) |  |  | - | Rm | 2500 | Rate Only | 400 | Rate Only | Rate Only | Ready Stock | FLEXIVA / Thermoflex
3.5.2 | Ø 8" (Ø 200mm) |  |  | - | Rm | 2200 | Rate Only | 400 | Rate Only | Rate Only | Ready Stock | FLEXIVA / Thermoflex
3.5.3 | Ø 6" (Ø 150mm) |  |  | 16 | Rm | 1200 | 19200 | 400 | 6400 | 25600 | Ready Stock | FLEXIVA / Thermoflex
3.6 | Butterfly Dampers
3.6.1 | Ø 10" (Ø 250mm) |  |  | - | No. | 5000 | Rate Only | 1000 | Rate Only | Rate Only | 3 to 4 weeks | Steel Craft/ Air guide
3.6.2 | Ø 8" (Ø 200mm) |  |  | - | No. | 4000 | Rate Only | 1000 | Rate Only | Rate Only | 3 to 4 weeks | Steel Craft/ Air guide
3.6.3 | Ø 6" (Ø 150mm) |  |  | 16 | Nos. | 3500 | 56000 | 1000 | 16000 | 72000 | 3 to 4 weeks | Steel Craft/ Air guide
3.7 | Fire Damper - Motorized (UL - Listed)
3.7.1 | 42" x 6" (1050mm x 150mm) |  |  | 4 | No. | 185000 | 740000 | 15000 | 60000 | 800000 | 7 Weeks | LOCAL
3.8 | Damper - Motorized
3.8.1 | 14" x 12" (350mm x 300mm) |  |  | 1 | Nos. | 115000 | 115000 | 5000 | 5000 | 120000 | 13 Weeks | LOCAL
3.8.2 | 20" x 8" (500mm x 200mm) |  |  | 1 | Nos. | 120000 | 120000 | 5000 | 5000 | 125000 | 13 Weeks | LOCAL
3.8.3 | 20" x 12" (500mm x 300mm) |  |  | 1 | Nos. | 125000 | 125000 | 5000 | 5000 | 130000 | 13 Weeks | LOCAL
3.9 | Engineered Support system for Ducts with Lindapter Type/TR60 Complete in all Respect. |  |  | 1 | Lot | 600000 | 600000 | 75000 | 75000 | 675000
3.1 | Sound Trap Air Duct Z-Piece for Return Air Intake Size 450mm x 200mm - Refer FND Detail FND/D/35 |  |  | 9 | Nos. | 11000 | 99000 | 3000 | 27000 | 126000
3.11 | G.I Frame as Duct Sleeves - As per FND Detail |  |  | 1 | Lot | 50000 | 50000 | 25000 | 25000 | 75000 | As per required | LOCAL
3.12 | Wire Mesh on all Duct Openings |  |  | 1 | Lot | 25000 | 25000 | 15000 | 15000 | 40000 | As per required | LOCAL
3.13 | Light Testing for Ducting |  |  | 1 | Lot | 0 | 0 | 75000 | 75000 | 75000
Sub-total Carried to Summary
4 | PIPING (SECTION 23 21 13 & DS/1831-23 21 13)
4.1 | Supply & Installation Chilled Water Piping
4.1.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 4300 | Rate Only | 800 | Rate Only | Rate Only | Ready Stock | PROTEK - China
4.1.2 | Ø 1 ½" (Ø 40mm) |  |  | - | Rm | 3300 | Rate Only | 750 | Rate Only | Rate Only | Ready Stock | PROTEK - China
4.1.3 | Ø 1 ¼" (Ø 32mm) |  |  | - | Rm | 2800 | Rate Only | 730 | Rate Only | Rate Only | Ready Stock | PROTEK - China
4.1.4 | Ø 1" (Ø 25mm) |  |  | 20 | Rm | 2300 | 46000 | 660 | 13200 | 59200 | Ready Stock | PROTEK - China
4.2 | Supply & Installation Cooling Water Piping
4.2.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 7300 | Rate Only | 800 | Rate Only | Rate Only | Ready Stock | Aquatherm
4.2.2 | Ø 1 ½" (Ø 40mm) |  |  | - | Rm | 5500 | Rate Only | 750 | Rate Only | Rate Only | Ready Stock | Aquatherm
4.2.3 | Ø 1 ¼" (Ø 32mm) |  |  | 8 | Rm | 3500 | 28000 | 730 | 5840 | 33840 | Ready Stock | Aquatherm
4.2.4 | Ø 1" (Ø 25mm) |  |  | - | Rm | 3000 | Rate Only | 660 | Rate Only | Rate Only | Ready Stock | Aquatherm
4.3 | Condensate Drain Piping
4.3.1 | Ø 1 ¼" (Ø 32mm) |  |  | - | Rm | 1200 | Rate Only | 300 | Rate Only | Rate Only
4.3.2 | Ø 1" (Ø 25mm) |  |  | 22 | Rm | 1150 | 25300 | 280 | 6160 | 31460 | Ready Stock | AGM
4.4 | Pipe Pressure Testing |  |  | 1 | Lot | 0 | 0 | 25000 | 25000 | 25000 | Ready Stock | AGM
4.5 | Engineered Support system with Lindapter Type/TR60 Complete in all Respect. |  |  | 1 | Lot | 100000 | 100000 | 15000 | 15000 | 115000
Sub-total Carried to Summary
5 | VALVES & SPECIALITIES (SECTION 23 05 23, 23 86 20 & 23 86 35)
5.1 | Supply and Installation of Gate Valves for Cooling Water with Material/Flanges/Unions etc. (Section 23 05 23)
5.1.1 | Ø 2" (Ø 50mm) |  |  | - | No. | 25000 | Rate Only | 1500 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.1.2 | Ø 1 ½" (Ø 40mm) |  |  | - | No. | 18000 | Rate Only | 1500 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.1.3 | Ø 1 ¼" (Ø 32mm) |  |  | 4 | No. | 11500 | 46000 | 1500 | 6000 | 52000 | 4 to 6 weeks | SCON / WATTS
5.1.4 | Ø 1" (Ø 25mm) |  |  | 3 | Nos. | 9500 | 28500 | 1500 | 4500 | 33000 | 4 to 6 weeks | SCON / WATTS
5.1.5 | Ø ¾" (Ø 20mm) |  |  | - | No. | 6500 | Rate Only | 1500 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.2 | Supply and Installation of Ball Valve for Cooling Water with Material/Flanges/Unions etc. (Section 23 05 23)
5.2.1 | Ø 1" (Ø 25mm) |  |  | - | No. | 9000 | Rate Only | 1500 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.2.2 | Ø ¾" (Ø 20mm) |  |  | - | Nos. | 7000 | Rate Only | 1500 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.3 | Supply and Installation of Strainer Cooling Water with Material/Flanges/Unions etc.
5.3.1 | Ø 2" (Ø 50mm) |  |  | - | No. | 20500 | Rate Only | 1000 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.3.2 | Ø 1 ½" (Ø 40mm) |  |  | - | No. | 16000 | Rate Only | 1000 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.3.3 | Ø 1 ¼" (Ø 32mm) |  |  | 1 | No. | 12000 | 12000 | 1000 | 1000 | 13000 | 4 to 6 weeks | SCON / WATTS
5.3.4 | Ø 1" (Ø 25mm) |  |  | 1 | No. | 7500 | 7500 | 1000 | 1000 | 8500 | 4 to 6 weeks | SCON / WATTS
5.4 | Supply and Installation of Flow Balancing & Shut-off Valve for Cooling Water with Material/Flanges/Unions etc.
5.4.1 | Ø 1 ½" (Ø 40mm) |  |  | - | No. | 31500 | Rate Only | 1500 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.4.2 | Ø 1 ¼" (Ø 32mm) |  |  | 2 | Nos. | 23800 | 47600 | 1500 | 3000 | 50600 | 4 to 6 weeks | SCON / WATTS
5.4.3 | Ø 1" (Ø 25mm) |  |  | - | No. | 20000 | Rate Only | 1500 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.5 | Supply and Installation of Pressure Independent Control Valve (PICV) for Fan Coil Unit with Material/Flanges/Unions etc.
5.5.1 | Ø 1 ½" (Ø 40mm) |  |  | - | No. | 393000 | Rate Only | 8000 | Rate Only | Rate Only | 8 to 10 Weeks | SCON / WATTS
5.5.2 | Ø 1 ¼" (Ø 32mm) |  |  | - | No. | 185000 | Rate Only | 8000 | Rate Only | Rate Only | 8 to 10 Weeks | SCON / WATTS
5.5.3 | Ø 1" (Ø 25mm) |  |  | 1 | No. | 148500 | 148500 | 8000 | 8000 | 156500 | 8 to 10 Weeks | SCON / WATTS
Sub-total Carried to Summary
6 | THERMAL INSULATION (SECTION 23 07 13 & 23 07 19 & DS/1831-23 07 13 & 23 07 19)
6.1 | Insulation of Supply Air Duct-Air Conditioned Space/Air Conditioned Ceiling Cavity |  |  | 970 | m² | 5300 | 5141000 | 750 | 727500 | 5868500 | Ready Stock | AEROFOAM
6.2 | Insulation of Return Air Duct-Air Conditioned Space/Air Conditioned Ceiling Cavity |  |  | 4 | m² | 5200 | 20800 | 750 | 3000 | 23800 | Ready Stock | AEROFOAM
6.3 | Supply & Installation Chilled Water Piping (Section 23 07 19 & DS/1831-23 07 19)
6.3.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 3600 | Rate Only | 230 | Rate Only | Rate Only | Ready Stock | AEROFOAM
6.3.2 | Ø 1 ½" (Ø 40mm) |  |  | - | Rm | 3300 | Rate Only | 230 | Rate Only | Rate Only | Ready Stock | AEROFOAM
6.3.3 | Ø 1 ¼" (Ø 32mm) |  |  | - | Rm | 3000 | Rate Only | 230 | Rate Only | Rate Only | Ready Stock | AEROFOAM
6.3.4 | Ø 1" (Ø 25mm) |  |  | 20 | Rm | 2780 | 55600 | 230 | 4600 | 60200 | Ready Stock | AEROFOAM
6.4 | Condensate Drain Piping Insulation (Section 23 07 19 & DS/1831-23 07 19)
6.4.1 | Ø 1 ¼" (Ø 32mm) |  |  | - | Rm | 1900 | Rate Only | 300 | Rate Only | Rate Only | Ready Stock | AEROFOAM
6.4.2 | Ø 1" (Ø 25mm) |  |  | 22 | Rm | 1870 | 41140 | 330 | 7260 | 48400 | Ready Stock | AEROFOAM
6.5 | Cladding of Valves & Specialities (Openable Boxes with Insulation)
6.5.1 | Ø 2" (Ø 50mm) |  |  | - | No. |  | Rate Only |  | Rate Only | Rate Only | - | -
6.5.2 | Ø 1 ½" (Ø 40mm) |  |  | - | No. |  | Rate Only |  | Rate Only | Rate Only | - | -
6.5.3 | Ø 1 ¼" (Ø 32mm) |  |  | - | No. |  | Rate Only |  | Rate Only | Rate Only | - | -
6.5.4 | Ø 1" (Ø 25mm) |  |  | 5 | Nos. | 7000 | 'Rate Only | 1500 | 'Rate Only | 'Rate Only | - | -
Sub-total Carried to Summary
7 | AIR DEVICES (SECTION 23 37 13)
7.1 | Supply Air Linear (Tuttle & Bailey) (Series 7000 1" - 25mm x 3 Slots) with Factory Supplied & Field Installed Plenum with Insulation |  |  | 17 | Rm | 5700 | 96900 | 700 | 11900 | 108800 | 8 to 10 weeks | Steel Craft/ Air guide
7.2 | Return Air Linear (Tuttle & Bailey) (Series 7000 1" - 25mm x 3 Slots) with Factory Supplied & Field Installed Plenum with Insulation |  |  | 17 | Rm | 5700 | 96900 | 700 | 11900 | 108800 | 8 to 10 weeks | Steel Craft/ Air guide
7.3 | Supply / Return Air Fixed Bar Grill & Register (Tuttle & Bailey - A50 Series) 21" x 6" (525mm x 150mm) with Damper |  |  | 6 | Nos. | 4500 | 27000 | 700 | 4200 | 31200 | 8 to 10 weeks | Steel Craft/ Air guide
7.4 | Supply Air Fixed Bar Grill & Register (Tuttle & Bailey - A50 Series) 42" x 6" (1050mm x 150mm) with Damper |  |  | 2 | Nos. | 12000 | 24000 | 5000 | 10000 | 34000 | 8 to 10 weeks | Steel Craft/ Air guide
7.5 | Supply / Return Air Fixed Bar Grill & Register (Tuttle & Bailey - A50 Series) 232" x 18" (5800mm x 450mm) with Damper |  |  | 1 | No. | 105000 | 105000 | 5000 | 5000 | 110000 | 8 to 10 weeks | Steel Craft/ Air guide
7.6 | Supply Air Round Diffusers Ø 12" (Tuttle & Bailey) (Series AVJR 3-Cone) with Dampers |  |  | 89 | Nos. | 24500 | 2180500 | 1500 | 133500 | 2314000 | 8 to 10 weeks | Steel Craft/ Air guide
7.7 | Supply Air Round Diffusers Ø 10" (Tuttle & Bailey) (Series AVJR 3-Cone) with Dampers |  |  | - | No. | 22000 | Rate Only | 1500 | Rate Only | Rate Only | 8 to 10 weeks | Steel Craft/ Air guide
7.8 | Exhaust Air Disc Valve for Toilet Exhaust (Ø 6") |  |  | 24 | Nos. | 3200 | 76800 | 1000 | 24000 | 100800 | 8 to 10 weeks | Steel Craft/ Air guide
Sub-total Carried to Summary
8 | WATER COOLED PACKAGED AIR CONDITIONER (SECTION 23 81 30 & DS/1831-23 81 30)
8.1 | Supply and Installation of Water Cooled Packaged Air Conditioner (CWPU-22/01-02) Ceiling Hung Type with Wall Mounted Room Thermostat (3.0 TR) with Scheduling feature |  |  | 2 | Nos. | 1070000 | 2140000 | 25000 | 50000 | 2190000 | 12 Weeks | SABRO / COOLMAX
8.2 | Supply and Installation of Automatic Air Vents |  |  | 4 | Nos. | 8500 | 34000 | 1000 | 4000 | 38000 | Ready Stock | SCON / WATTS
8.3 | Ø ½" (Ø 15mm) Shredder Fitting for Air Vent/Pressure Testing |  |  | 4 | Nos. | 10000 | 40000 | 2000 | 8000 | 48000
8.4 | Pressure Switch |  |  | 1 | No. | 24000 | 24000 | 3000 | 3000 | 27000 | 5 Weeks | Danfoss
8.5 | Control Wiring Between Indoor and Thermostat |  |  | 1 | Lot. | 10000 | 10000 | 2500 | 2500 | 12500 | Ready Stock | INDUS / FAST
8.6 | Support System with Lindapter Type/TR60 complete in all respect |  |  | 1 | Lot. | 15000 | 15000 | 3000 | 3000 | 18000 | Ready Stock | INDEX
8.7 | Commissioning & Testing of Water Cooled Package Units |  |  | 1 | Lot. | 0 | 0 | 20000 | 20000 | 20000
Sub-total Carried to Summary
9 | METER & GAUGES (SECTION 23 05 19)
9.1 | Thermometers with Wells for Pipe Thermometer |  |  | 6 | Nos. | 12500 | 75000 | 1000 | 6000 | 81000 | Ready Stock | WEISS / WEKSLER
9.2 | Pressure Gauges on Pipes |  |  | 6 | Nos. | 9500 | 57000 | 1000 | 6000 | 63000 | Ready Stock | WEISS / WEKSLER
9.3 | Gauge Outlets with Cock |  |  | 6 | Nos. | 2000 | 12000 | 1000 | 6000 | 18000 | Ready Stock | WEISS / WEKSLER
Sub-total Carried to Summary
10 | HVAC CONTROLS (SECTION 23 09 20)
10.1 | DDC Controller (BACnet/IP) for FCU-22-01 (Refer FND Drawing # FND-1831-XX-H-XX-XX-700-00) |  |  | 1 | No. | 175000 | Rate Only | 5000 | Rate Only | Rate Only | 10 Weeks | JES
10.2 | DDC Controller (BACnet/IP) for CWPU-22-01&02 (Refer FND Drawing # FND-1831-XX-H-XX-XX-700-00) |  |  | 2 | Nos. | 175000 | Rate Only | 5000 | Rate Only | Rate Only | 10 Weeks | JES
10.3 | Installation of Differential Pressure Switch (DPS) with pressure adjustment range of .5 to 4 mbar and switching difference of 0.2 mbar or less. |  |  | 2 | Nos. |  | Rate Only | 15000 | Rate Only | Rate Only | 10 Weeks | JES
10.4 | Wiring of PS from Duct Index Point to AHU DDC Panel (3 Core x 18AWG Shielded Wire-Belden Cable) |  |  | 1 | Lot | 175000 | Rate Only | 25000 | Rate Only | Rate Only | 10 Weeks | JES
10.5 | Master/Network Controller that will host the connected devices (VAV's Controllers and thermostat) and can work as a standalone server. (complete set along with Power Supply) |  |  | 1 | No. | 1450000 | Rate Only | 77000 | Rate Only | Rate Only | 10 Weeks | JES
10.6 | Server Platform that work as single point of administration through WebStation for BMS Centralized alarms and data management |  |  | 1 | No. | 450000 | Rate Only | 73000 | Rate Only | Rate Only | 10 Weeks | JES
10.7 | Server Machine - Intel Corei5- 3.0 GHz or better processor, 8 GB or better of memory, and a hard drive of 1 TB. Supported with Microsoft Windows Server 2016 and Microsoft .NET Framework 4.5 or 4.6 |  |  | 1 | No. | 395000 | Rate Only | 67000 | Rate Only | Rate Only | 10 Weeks | JES
10.8 | License for enabling its WebServices on Internet |  |  | 1 | No. | 977000 | Rate Only | 73000 | Rate Only | Rate Only | 10 Weeks | JES
10.9 | Deployement of Mobile Application with its all customised mimics along with the comissioning as per control matrix / scheme (Platform:Apple iOS 11, Android 5.0 (Lollipop) and later) |  |  | 1 | No. | 145000 | Rate Only | 22500 | Rate Only | Rate Only | 10 Weeks | JES
10.1 | Deployement of Cat-6 cable infrastructure with all accessories throughout the facility in a Daisy Chain Pattern |  |  | 1 | Job | 977000 | Rate Only | 135000 | Rate Only | Rate Only | 10 Weeks | JES
10.11 | Layer 2 Manageable Switch with dual power supply , high-performance, standalone, 10/100 autosensing Fast Ethernet that should have 24-10/100 ports plus 2 fixed 100BASE-FX port |  |  | 1 | Lot | 95000 | Rate Only | 25000 | Rate Only | Rate Only | 10 Weeks | JES
10.12 | Integration & comissioning of Pressure Independent Control Valve with Modulating Proportional Valve Actuator with Reversible Synchronous Motor 0-10 VDC. (Chilled Water Application) |  |  | 1 | No. | 75000 | Rate Only | 15000 | Rate Only | Rate Only | 10 Weeks | JES
10.13 | Integration of Wall Mounted Room Thermostat for FCU-22-01 - Supplied with FCU |  |  | 1 | No. | 75000 | Rate Only | 10000 | Rate Only | Rate Only | 10 Weeks | JES
10.14 | Integration of Wall Mounted Room Thermostat for CWPU-22/01-02 - Supplied with CWPU |  |  | 2 | Nos. | 75000 | Rate Only | 10000 | Rate Only | Rate Only | 10 Weeks | JES
10.15 | Integration of Pressure Switch - Supplied with CWPU |  |  | 1 | No. | 75000 | Rate Only | 15000 | Rate Only | Rate Only | 10 Weeks | JES
10.16 | Integration of VAV-01 |  |  | 1 | No. | 135000 | Rate Only | 18000 | Rate Only | Rate Only | 10 Weeks | JES
10.17 | Integration of Motorized Fire Damper Actuator (4 Nos.) with power & control cable 1.5mm2 installed in (Ø 20mm) PVC Conduit, complete in all respect (Size of Damper 525 x 150mm & Airflow is 500 cfm) - Material Covered in BOQ item # 3.7 |  |  | 1 | Lot | 145000 | Rate Only | 45000 | Rate Only | Rate Only | 10 Weeks | JES
10.18 | Integration of Motorized Fire Damper Actuator (2 Nos.) with power & control cable 1.5mm2 installed in (Ø 20mm) PVC Conduit, complete in all respect (Size of Damper 1050mm x 150mm & Airflow is 1000 cfm) - Material Covered in BOQ item # 3.7 |  |  | 1 | Lot | 145000 | Rate Only | 45000 | Rate Only | Rate Only | 10 Weeks | JES
10.19 | Integration of Motorized Damper Actuator (2 No.) with power & control cable 1.5mm2 installed in (Ø 20mm) PVC Conduit, complete in all respect (Size of Damper 500mm x 200mm & Airflow is 1000cfm) - Material Covered in BOQ item # 3.8 |  |  | 1 | Lot | 100000 | Rate Only | 50000 | Rate Only | Rate Only | 10 Weeks | JES
10.2 | Networking, Cabling, Receway Support, Hanger, Sleeves, Core Drilling etc. |  |  | 1 | Lot | 350000 | Rate Only | 75000 | Rate Only | Rate Only | 10 Weeks | JES
Sub-total Carried to Summary
11 | HOT WATER SUPPLY SYSTEM
11.1 | Supply & Installation of Instant Electric Operated Hot Water Heaters (Section 22 33 30 & DS/1831-22 33 30)
11.1.1 | Supply, Installation and Comissioning of Electric Operated Hot Water Heater HWH/01-02, 30L heating capacity. Including all fittings and accessories required from installation till comissioning of Hot Water Heater (Refer DS/1831-22 33 30) | 2 | Nos. | 2 | Nos. | 78000 | 156000 | 5000 | 10000 | 166000 | Ready Stock | ARISTON
11.2 | Poly Propylene Pipe for Cold Water Supply (PPR Pipe PN-20 with PN-20 Fittings including all Fittings and Accessories Required for Piping Installation) (Section 22 11 16 & DS/1831-22 11 16)
11.2.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 4500 | Rate Only | 800 | Rate Only | Rate Only | Ready Stock | RECKTHERM
11.2.2 | Ø 1 ½" (Ø 40mm) |  |  | - | Rm | 3500 | Rate Only | 800 | Rate Only | Rate Only | Ready Stock | RECKTHERM
11.2.3 | Ø 1 ¼" (Ø 32mm) |  |  | - | Rm | 3000 | Rate Only | 800 | Rate Only | Rate Only | Ready Stock | RECKTHERM
11.2.4 | Ø 1" (Ø 25mm) |  |  | 6 | Rm | 2200 | 13200 | 800 | 4800 | 18000 | Ready Stock | RECKTHERM
11.3 | Poly Propylene Pipe for Hot Water Supply (PPR Pipe PN-20 with PN-20 Fittings including all Fittings and Accessories Required for Piping Installation) (Section 22 11 16 & DS/1831-22 11 16)
11.3.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 4500 | Rate Only | 800 | Rate Only | Rate Only | Ready Stock | RECKTHERM
11.3.2 | Ø 1 ½" (Ø 40mm) |  |  | 13 | Rm | 3500 | 45500 | 800 | 10400 | 55900 | Ready Stock | RECKTHERM
11.3.3 | Ø 1 ¼" (Ø 32mm) |  |  | 23 | Rm | 3000 | 69000 | 800 | 18400 | 87400 | Ready Stock | RECKTHERM
11.3.4 | Ø 1" (Ø 25mm) |  |  | 12 | Rm | 2200 | 26400 | 800 | 9600 | 36000 | Ready Stock | RECKTHERM
11.4 | Valve & Specialities (Section 22 05 23)
11.4.1 | Gate Valves - PPR PN-20 (Including all Fittings and Accessories Required for Valve Installation) (Section 22 05 23)
11.4.1.1 | Ø 2" (Ø 50mm) |  |  | - | No. | 25000 | Rate Only | 1000 | Rate Only | Rate Only | Ready Stock | RECKTHERM
11.4.1.2 | Ø 1 ½" (Ø 40mm) |  |  | 2 | Nos. | 18000 | 36000 | 1000 | 2000 | 38000 | Ready Stock | RECKTHERM
11.4.1.3 | Ø 1 ¼" (Ø 32mm) |  |  | 4 | Nos. | 10800 | 43200 | 1000 | 4000 | 47200 | Ready Stock | RECKTHERM
11.4.1.4 | Ø 1" (Ø 25mm) |  |  | 10 | Nos. | 8500 | 85000 | 1000 | 10000 | 95000 | Ready Stock | RECKTHERM
11.4.2 | Insulation of Hot Water Piping Including Vapor Barrier, Jacketing & Cladding (Section 22 07 19 & DS/1831-22 07 19)
11.4.2.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 2200 | Rate Only | 140 | Rate Only | Rate Only | 2 to 3 weeks | AEROFOAM
11.4.2.2 | Ø 1 ½" (Ø 40mm) |  |  | 13 | Rm | 1800 | 23400 | 130 | 1690 | 25090 | 2 to 3 weeks | AEROFOAM
11.4.2.3 | Ø 1 ¼" (Ø 32mm) |  |  | 23 | Rm | 1700 | 39100 | 120 | 2760 | 41860 | 2 to 3 weeks | AEROFOAM
11.4.2.4 | Ø 1" (Ø 25mm) |  |  | 12 | Rm | 1500 | 18000 | 100 | 1200 | 19200 | 2 to 3 weeks | AEROFOAM
11.5 | Cladding of Valves & Specialities (Openable Boxes with Insulation)
11.5.1 | Ø 2" (Ø 50mm) |  |  | - | No. | 5000 | Rate Only | 600 | Rate Only | Rate Only
11.5.2 | Ø 1 ½" (Ø 40mm) |  |  | 2 | Nos. | 4000 | Rate Only | 600 | Rate Only | Rate Only
11.5.3 | Ø 1 ¼" (Ø 32mm) |  |  | 4 | Nos. | 3000 | Rate Only | 600 | Rate Only | Rate Only
11.5.4 | Ø 1" (Ø 25mm) |  |  | 8 | Nos. | 2000 | Rate Only | 600 | Rate Only | Rate Only
11.6 | Pressure Testing of Water Supply Piping (1.5 times of operating pressure) (Including all arrangements required for Pressure Testing) |  |  | 1 | Lot | 0 | 0 | 25000 | 25000 | 25000
11.7 | Engineered Support system with Lindapter Type/TR60 Complete in all Respect. |  |  | 1 | Lot | 75000 | 75000 | 15000 | 15000 | 90000
Sub-total Carried to Summary
12 | PLUMBING FIXTURES & FITTINGS
12.1 | Fixtures (Section 22 41 10 & DS/1831-22 41 10)
12.1.1 | Supply & Installation of Wall Hung Western WC, Concealed Flush Tank Operated (Section 22 41 10 & DS/1831-22 41 10) |  |  | 10 | Nos. | 153000 | 1530000 | 7500 | 75000 | 1605000 | 12 weeks | Porta & Grohe
12.1.2 | Supply & Installation of Vanity Wash Basin with, Waste, Bottle Trap & Tee Stop-Cock (Section 22 41 10 & DS/1831-22 41 10) |  |  | 10 | Nos. | 75000 | 750000 | 6500 | 65000 | 815000 | 12 weeks | Porta & Grohe
12.1.3 | Supply & Installation of Disabled Toilet Set (Basin, WC) (Section 22 41 10 & DS/1831-22 41 10) |  |  | 2 | Nos. | 75000 | 150000 | 6500 | 13000 | 163000 | 12 weeks | Porta & Grohe
12.1.4 | Supply & Installation of Wash Basin Single Lever Faucet with Flexible Hoses (For Cold & Hot Water). (Section 22 41 10 & DS/1831-22 41 10) |  |  | 12 | Nos. | 55000 | 660000 | 4500 | 54000 | 714000 | 12 weeks | Porta & Grohe
12.1.5 | Supply & Installation of Stainless Steel Kitchen Sink including stop cocks, P-trap / bottle trap, waste pipe etc. |  |  | 1 | Nos. | 95000 | 95000 | 6000 | 6000 | 101000 | 12 weeks | Porta & Grohe
12.1.6 | Supply & Installation of Hot and Cold Water Mixer for Stainless Steel Kitchen Sink |  |  | 1 | Nos. | 48000 | 48000 | 4500 | 4500 | 52500 | 12 weeks | Porta & Grohe
12.1.7 | Supply & Installation of WC Hand Operated Shower Spray With Angle Valve and Flexible Hose. (Section 22 41 10 & DS/1831-22 41 10) |  |  | 12 | Nos. | 14500 | 174000 | 1500 | 18000 | 192000 | 12 weeks | Porta & Grohe
12.1.8 | Supply & Installation of Bib Cocks for (Janitor, Cleaning Area) (Section 22 41 10 & DS/1831-22 41 10) |  |  | 2 | Nos. | 2500 | 5000 | 1000 | 2000 | 7000 | 12 weeks | Porta & Grohe
12.1.9 | Supply & Installation of Single Lever Faucet Wall Mounted for (Hot & Cold Water) (Ablution Area) (Section 22 41 10 & DS/1831-22 41 10) |  |  | 6 | Nos. | 48000 | 288000 | 4500 | 27000 | 315000 | 12 weeks | Porta & Grohe
12.1.10 | Supply & Installation of Toilet Roll Holder (Section 22 41 10 & DS/1831-22 41 10) |  |  | 12 | Nos. | 13700 | 164400 | 1000 | 12000 | 176400 | 12 weeks | Porta & Grohe
12.1.11 | Supply & Installation of Wall Mounted Soap Dispenser (Section 22 41 10 & DS/1831-22 41 10) |  |  | 10 | Nos. | 14500 | 145000 | 1000 | 10000 | 155000 | 12 weeks | Porta & Grohe
12.2 | Drainage & Vent Pipe (uPVC - Non Pressure Class; Solvent Welded) Including all Fittings and Accessories Required for Piping Installation e.g Elbows, Y, Double Y, Ceiling Cleanouts, Reducers, Sockets etc. (Section 22 13 20 & DS/1831-22 13 20)
12.2.1 | Ø 4" (Ø 100mm) |  |  | - | Rm | 3500 | Rate Only | 600 | Rate Only | Rate Only | Ready Stock | AGM
12.2.2 | Ø 3" (Ø 75mm) |  |  | - | Rm | 2200 | Rate Only | 600 | Rate Only | Rate Only | Ready Stock | AGM
12.2.3 | Ø 2" (Ø 50mm) |  |  | - | Rm | 1600 | Rate Only | 600 | Rate Only | Rate Only | Ready Stock | AGM
12.2.4 | Ø 1 ½" (Ø 40mm) |  |  | - | Rm | 1250 | Rate Only | 600 | Rate Only | Rate Only | Ready Stock | AGM
12.3 | Drain Accessories (Section 22 11 19)
12.3.1 | SS Floor Drain (Section 22 11 19)
12.3.1.1 | Ø 6" x 6" (Ø 150 x 150 mm) |  |  | 20 | Nos. | 8800 | 176000 | 1000 | 20000 | 196000 | Ready Stock | QABIL
12.3.2 | SS Floor Clean Out (Section 22 11 19)
12.3.2.1 | Ø 4" (Ø 100mm) |  |  | 12 | Nos. | 7500 | 90000 | 1000 | 12000 | 102000 | Ready Stock | QABIL
12.3.2.2 | Ø 3" (Ø 75mm) |  |  | - | No. | 7500 | Rate Only | 1000 | Rate Only | Rate Only | Ready Stock | QABIL
12.4 | 350mm Wide Drain Channel with SS Grating for Ablution Area (Refer FND Detail # FND/SDS/24) |  |  | 6 | Rm | 42000 | 252000 | 1000 | 6000 | 258000 | Ready Stock | QABIL
12.5 | Gravity Testing of Drainage Piping (Including all arrangements required for Gravity Testing) |  |  | 1 | Lot |  | 0 | 30000 | 30000 | 30000
12.6 | Engineered Support system Complete in all Respect. |  |  | 1 | Lot | 50000 | 50000 | 15000 | 15000 | 65000 | Ready Stock | INDEX
Sub-total Carried to Summary
13 | CLEANING & BALANCING OF HVAC SYSTEM (SECTION 23 05 93)
13.1 | Cleaning & Balancing of HVAC System |  |  | 1 | Lot |  | 0 | 150000 | 150000 | 150000
Sub-total Carried to Summary
14 | PAINTING & FINISHING AND MECHANICAL IDENTIFICATION (SECTION 23 05 50 & 23 05 53)
14.1 | Painting & Finishing, Stenciling of Pipes & Ducts, Identification Tags on Valves etc. and Equipment Data Plates (Section 23 05 50) |  |  | 1 | Lot | 100000 | 100000 | 15000 | 15000 | 115000 | Ready Stock | ICI / BERGER
Sub-total Carried to Summary
15 | MISCELLANEOUS
15.1 | Pipe Sleeves/Core Cutting Where Required |  |  | 1 | Lot | 25000 | 25000 | 15000 | 15000 | 40000
15.2 | Shop Drawings, As Built Drawings, Operation & Maintenance Manuals |  |  | 1 | Lot | 25000 | 25000 | 15000 | 15000 | 40000
15.3 | Fire Stopping Material for all HVAC & Plumbing Pipes, Duct, Trays etc. Crossing a Fire Barrier Wall/Floor/Partition as per Required Fire Rating (Refer Fire Strategy Drawings for Fire Barrier Wall/Floor) |  |  | 1 | Lot | 100000 | 100000 | 75000 | 75000 | 175000
Sub-total Carried to Summary | [6 empty] | 26528890 |  | 3478710 | 30007600
39103805

## 22F
EY Karachi - 22nd Floor - FF
ITEM NO. | DESCRIPTION | ESTIMATED QUANTITY | UNIT | MATERIAL |  | INSTALLATION |  | AMOUNT | Lead Time | Brands
|  |  |  | RATE | AMOUNT | RATE | AMOUNT
1 | FIRE SPRINKLERS (SECTION 21 13 10 & DS/1831-21 13 10)
1.1 | Fire Sprinkler- Upright, Quick Response (SP-01) | 215 | Nos. | 2800 | 602000 | 1000 | 215000 | 817000 | 10 Weeks | SHIELD
1.2 | Fire Sprinkler- Pendent Concealed, Quick Response (SP-02) | 65 | Nos. | 7500 | 487500 | 1000 | 65000 | 552500 | 10 Weeks | SHIELD
1.3 | Fire Sprinkler- Pendent Sprinkler, Quick Response (SP-03) | 12 | Nos. | 4500 | 54000 | 1000 | 12000 | 66000 | 10 Weeks | SHIELD
1.4 | Cabinet Complete with 06 Spare Sprinklers (Upright) (SP-01) | 1 | Nos. | 35000 | 35000 | 3000 | 3000 | 38000 | 10 Weeks | SHIELD
1.5 | Cabinet Complete with 06 Spare Sprinklers (Concealed Pendent) (SP-02) | 1 | No. | 45000 | 45000 | 2000 | 2000 | 47000 | 10 Weeks | SHIELD
1.6 | Cabinet Complete with 06 Spare Sprinklers (Pendent) (SP-03) | 1 | No. | 40000 | 40000 | 2000 | 2000 | 42000 | 10 Weeks | SHIELD
Sub-total Carried to Summary
2 | CORRUGATED STAINLESS STEEL FLEXIBLE CONNECTOR
2.1 | Corrugated Stainless Steel Flexible Connector Ø 1" X 3 ft (UL/FM) (Braided) | 65 | Nos. | 11500 | 747500 | 1000 | 65000 | 812500 | 10 Weeks | SHIELD / SEUNG JIN IND
Sub-total Carried to Summary
3 | PORTABLE FIRE EXTINGUISHER FOR FIRE TYPES A, B, C & AFFF (SECTION 21 21 10 & DS/1831-21 21 10)
3.1 | Supply & Installation of 6 Kg Dry Powder Extinguisher (ABC) | 2 | Nos. | 14500 | 29000 | 700 | 1400 | 30400 | 10 Weeks | NAFCO
3.2 | Supply & Installation of 6 Kg CO2 Fire Extinguisher | 2 | Nos. | 25500 | 51000 | 700 | 1400 | 52400 | 10 Weeks | NAFCO
Sub-total Carried to Summary
4 | BLACK STEEL SCHEDULE-40 PIPING (SECTION 21 10 10)
4.1 | Welded Piping System
4.1.1 | Ø 4" (100mm) | - | Rm | 12500 | Rate Only | 1250 | Rate Only | Rate Only | ReadyStock | Protek
4.1.2 | Ø 3" (75mm) | 100 | Rm | 9800 | 980000 | 880 | 88000 | 1068000 | ReadyStock | Protek
4.1.3 | Ø 2½" (65mm) | - | Rm | 7800 | Rate Only | 800 | Rate Only | Rate Only | ReadyStock | Protek
4.2 | Threaded Piping System
4.2.1 | Ø 2" (50mm) | 178 | Rm | 4700 | 836600 | 710 | 126380 | 962980 | ReadyStock | Protek
4.2.2 | Ø 1½" (40mm) | 143 | Rm | 3390 | 484770 | 700 | 100100 | 584870 | ReadyStock | Protek
4.2.3 | Ø 1¼" (32mm) | 110 | Rm | 2900 | 319000 | 690 | 75900 | 394900 | ReadyStock | Protek
4.2.4 | Ø 1" (25mm) | 496 | Rm | 2100 | 1041600 | 680 | 337280 | 1378880 | ReadyStock | Protek
Sub-total Carried to Summary
5 | GATE VALVE (SECTION 21 05 23)
5.1 | Ø2 inch (50 mm) | 2 | Nos. | 95000 | 190000 | 5000 | 10000 | 200000 | 10 Weeks | SHILED
Sub-total Carried to Summary
6 | SIESMIC BRACING
6.1 | Transverse Seismic Bracing (As per FND Detail No. FND/SS/10)
6.1.1 | Ø 4" (100mm) | - | No. |  | Rate Only |  | Rate Only | Rate Only | 6 weeks | Index
6.1.2 | Ø 3" (75mm) | 11 | Nos. | 9875 | 108625 | 3000 | 33000 | 141625 | 6 weeks | Index
6.1.3 | Ø 2½" (65mm) | - | No. |  | Rate Only |  | Rate Only | Rate Only | 6 weeks | Index
6.2 | Longitudinal Seismic Bracing (As per FND Detail No. FND/SS/11)
6.2.1 | Ø 4" (100mm) | - | No. |  | Rate Only |  | Rate Only | Rate Only | 6 weeks | Index
6.2.2 | Ø 3" (75mm) | 7 | Nos. | 12250 | 85750 | 3000 | 21000 | 106750 | 6 weeks | Index
6.2.3 | Ø 2½" (65mm) | - | No. |  | Rate Only |  | Rate Only | Rate Only | 6 weeks | Index
6.3 | Seismic Restraint (As per FND Detail No. FND/ADD/08)
6.3.1 | Ø 2" (50mm) | 20 | Nos. | 5820 | 116400 | 1500 | 30000 | 146400 | 6 weeks | Index
6.3.2 | Ø 1½" (40mm) | 34 | Nos. | 5300 | 180200 | 1500 | 51000 | 231200 | 6 weeks | Index
6.3.3 | Ø 1¼" (32mm) | 10 | Nos. | 5200 | 52000 | 1500 | 15000 | 67000 | 6 weeks | Index
6.3.4 | Ø 1" (25mm) | 66 | Nos. | 4800 | 316800 | 1500 | 99000 | 415800 | 6 weeks | Index
Sub-total Carried to Summary
7 | FIRE SPRINKLER SYSTEM ACCEPTANCE TEST (SECTION 21 13 17)
7.1 | Fire Sprinkler System Acceptance Test | 1 | Lot | 0 | 0 | 25000 | 25000 | 25000
Sub-total Carried to Summary
8 | PAINTING COATING & STENCILING (SECTION 21 05 50)
8.1 | Painting, Coating, Stenciling & Identification of Fire Piping | 1 | Lot | 200000 | 200000 | 35000 | 35000 | 235000 | Ready Stock | ICI / BERGER
Sub-total Carried to Summary
9 | PIPE SUPPORT SYSTEM (SECTION 21 05 29)
9.1 | Engineered Support system with Lindapter Type/TR60 Complete in all Respect | 1 | Lot | 375000 | 375000 | 55000 | 55000 | 430000 | ReadyStock | Index
Sub-total Carried to Summary
10 | MISCELLANEOUS
10.1 | Hydrostatic Testing | 1 | Lot |  | 0 | 50000 | 50000 | 50000
10.2 | Shop Drawings, As Built Drawings, Operation & Maintenance Manuals | 1 | Lot |  | 0 | 25000 | 25000 | 25000
10.3 | Fire Stopping of Paritions, Walls & Structure Openings (For Small Openings - Hilti FS - ONE or Approved Equivalent) | 1 | Lot | 100000 | 100000 | 25000 | 25000 | 125000
10.4 | Pipe Sleeves / Core Cutting Wherever Required | 1 | Lot | 25000 | 25000 | 25000 | 25000 | 50000
Sub-total Carried to Summary |  |  |  |  | 7502745 |  | 1593460 | 9096205