## summary
Ernst & Young
HVAC & Fire Fighting Work |  |  |  | 2023-11-24
SUMMARY OF BILL OF QUANTITIES
S.No | Description | Material | Labour | Amount
1 | HVAC Work 21st Floor | 21822670.4608 | 2953729.1872 | 24776399.648
2 | Fire Fighting 21st Floor | 6513007.6 | 1396683.2 | 7909690.8
1 | HVAC Work 22nd Floor | 23345423.2 | 3061264.8 | 26406688
2 | Fire Fighting 22nd Floor | 6602415.6 | 1402244.8 | 8004660.4
| Grand Total Amount | 58283516.8608 | 8813921.9872 | 67097438.848
| Add 4.5% |  |  | 3019384.7482
| Gross Amount |  |  | 70116823.5962
| 90% Payment |  |  | 63105141.2365
| Received Amount |  |  | 62447124
| Payable Amount |  |  | 658017.2365
76247090
13724476.2
62522613.8

## 21HVAC
EY Karachi - 21st Floor - M&P
ITEM NO. | DESCRIPTION |  |  | ESTIMATED QUANTITY | UNIT | MATERIAL |  | INSTALLATION |  | AMOUNT | Lead Time | Brands | Remarks
[6 empty] | RATE | AMOUNT | RATE | AMOUNT
1 | FAN COIL UNITS (SECTION 23 73 20 & DS/1831-23 73 20)
1.1 | Supply & Installation of Fan Coil Units FCU-21-01 Ceiling Hung Type with Wall Mounted Room Thermostat (3.0 TR) with scheduling feature |  |  | 1 | No. | 514800 | 514800 | 17600 | 17600 | 532400 | 5 Weeks | SABRO
1.2 | Supply & Installation of Automatic Air Vents |  |  | 2 | Nos. | 7480 | 14960 | 880 | 1760 | 16720 | Ready Stock | SCON |  | 585000 | 70200 | 514800 | 20000 | 2400 | 17600
1.3 | Ø ½" (Ø 15mm) Shredder Fitting for Air Vent/Pressure Testing |  |  | 2 | Nos. | 11440 | 22880 | 1760 | 3520 | 26400 |  |  |  | 8500 | 1020 | 7480 | 1000 | 120 | 880
1.4 | Engineered Supports System with Lindapter Type/TR60 complete in all respect. |  |  | 1 | Lot | 13200 | 13200 | 2640 | 2640 | 15840 | - | - |  | 13000 | 1560 | 11440 | 2000 | 240 | 1760
1.5 | Commissioning & Testing |  |  | 1 | Lot |  | 0 | 17600 | 17600 | 17600 | - | - |  | 15000 | 1800 | 13200 | 3000 | 360 | 2640
Sub-total Carried to Summary | [14 empty] | 0 | 0 | 20000 | 2400 | 17600
2 | VAV TERMINALS (SECTION 23 36 10 & 23 36 15 & DS/1831-23 36 10 & 23 36 15) | [13 empty] | 0 | 0 |  | 0 | 0
2.1 | Supply & installation of Variable Air Volume (VAV) Terminals with Wall Mounted Thermostat having temperature (Inc./dec.) (Section 23 36 10 & DS/1676-23 36 10) |  |  | 11 | Nos. | 168960 | 1858560 | 6160 | 67760 | 1926320 | 8 to 10 Weeks | JES |  | 192000 | 23040 | 168960 | 7000 | 840 | 6160
2.2 | Engineered Supports System with Lindapter Type/TR60 complete in all respect. |  |  | 1 | Lot | 88000 | 88000 | 13200 | 13200 | 101200 | - | - |  | 100000 | 12000 | 88000 | 15000 | 1800 | 13200
2.3 | Commissioning & Testing of VAV Terminals |  |  | 1 | Lot | 0 | 0 | 88000 | 88000 | 88000 |  |  |  | 0 | 0 | 0 | 100000 | 12000 | 88000
Sub-total Carried to Summary | [14 empty] | 0 | 0 |  | 0 | 0
3 | DUCT WORK (MACHINE MADE) (SECTION 23 31 13) | [13 empty] | 0 | 0 |  | 0 | 0
3.1 | Sheet Metal Duct Work (Air Conditioning) (Supply Air), Machine made Ducts (Section 23 31 13) |  |  | 958 | m² | 4356 | 4173048 | 792 | 758736 | 4931784 | Ready Stock | ISL |  | 4950 | 594 | 4356 | 900 | 108 | 792
3.2 | Sheet Metal Duct Work (Air Conditioning) (Return Air), Machine made Ducts (Section 23 31 13) |  |  | 2 | m² | 4136 | 8272 | 792 | 1584 | 9856 | Ready Stock | ISL |  | 4700 | 564 | 4136 | 900 | 108 | 792
3.3 | Sheet Metal Duct Work (Exhaust Air) Machine made Ducts (Section 23 31 13) |  |  | 57 | m² | 4356 | 248292 | 792 | 45144 | 293436 | Ready Stock | ISL |  | 4950 | 594 | 4356 | 900 | 108 | 792
3.4 | Quadrant Volume Damper |  |  | 17 | m² | 37400 | 635800 | 6160 | 104720 | 740520 | 8 Weeks | Steel Craft/ Air guide |  | 42500 | 5100 | 37400 | 7000 | 840 | 6160
3.5 | Flexible Ducts (Section 23 33 46) with Supports, Complete in all respect |  |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
3.5.1 | Ø 10" (Ø 250mm) |  |  | - | Rm | 2200 | Rate Only | 352 | Rate Only | Rate Only | Ready Stock | FLEXIVA / Thermoflex |  | 2500 | 300 | 2200 | 400 | 48 | 352
3.5.2 | Ø 8" (Ø 200mm) |  |  | - | Rm | 1936 | Rate Only | 352 | Rate Only | Rate Only | Ready Stock | FLEXIVA / Thermoflex |  | 2200 | 264 | 1936 | 400 | 48 | 352
3.5.3 | Ø 6" (Ø 150mm) |  |  | 16 | Rm | 1056 | 16896 | 352 | 5632 | 22528 | Ready Stock | FLEXIVA / Thermoflex |  | 1200 | 144 | 1056 | 400 | 48 | 352
3.6 | Butterfly Dampers |  |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
3.6.1 | Ø 10" (Ø 250mm) |  |  | - | No. | 4400 | Rate Only | 880 | Rate Only | Rate Only | 3 to 4 weeks | Steel Craft/ Air guide |  | 5000 | 600 | 4400 | 1000 | 120 | 880
3.6.2 | Ø 8" (Ø 200mm) |  |  | - | No. | 3520 | Rate Only | 880 | Rate Only | Rate Only | 3 to 4 weeks | Steel Craft/ Air guide |  | 4000 | 480 | 3520 | 1000 | 120 | 880
3.6.3 | Ø 6" (Ø 150mm) |  |  | 16 | Nos. | 3080 | 49280 | 880 | 14080 | 63360 | 3 to 4 weeks | Steel Craft/ Air guide |  | 3500 | 420 | 3080 | 1000 | 120 | 880
3.7 | Fire Damper - Motorized (UL - Listed) |  |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
3.7.1 | 42" x 6" (1050mm x 150mm) |  |  | 2 | No. | 162800 | 325600 | 13200 | 26400 | 352000 | 7 Weeks | LOCAL |  | 185000 | 22200 | 162800 | 15000 | 1800 | 13200
3.8 | Damper - Motorized |  |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
3.8.1 | 14" x 12" (500mm x 300mm) |  |  | 1 | Nos. | 101200 | 101200 | 4400 | 4400 | 105600 | 13 Weeks | LOCAL |  | 115000 | 13800 | 101200 | 5000 | 600 | 4400
3.8.2 | 20" x 12" (500mm x 300mm) |  |  | 1 | Nos. | 110000 | 110000 | 4400 | 4400 | 114400 | 13 Weeks | LOCAL |  | 125000 | 15000 | 110000 | 5000 | 600 | 4400
3.9 | Engineered Support system for Ducts with Lindapter Type/TR60 Complete in all Respect |  |  | 1 | Lot | 528000 | 528000 | 66000 | 66000 | 594000 |  |  |  | 600000 | 72000 | 528000 | 75000 | 9000 | 66000
3.1 | Sound Trap Air Duct Z-Piece for Return Air Intake Size 450mm x 200mm - Refer FND Detail FND/D/35 |  |  | 8 | Nos. | 9680 | 77440 | 2640 | 21120 | 98560 |  |  |  | 11000 | 1320 | 9680 | 3000 | 360 | 2640
3.11 | G.I Frame as Duct Sleeves - As per FND Detail |  |  | 1 | Lot | 44000 | 44000 | 22000 | 22000 | 66000 | As per required | LOCAL |  | 50000 | 6000 | 44000 | 25000 | 3000 | 22000
3.12 | Wire Mesh on all Duct Openings |  |  | 1 | Lot | 22000 | 22000 | 13200 | 13200 | 35200 | As per required | LOCAL |  | 25000 | 3000 | 22000 | 15000 | 1800 | 13200
3.13 | Light Testing for Ducting |  |  | 1 | Lot | 0 | 0 | 66000 | 66000 | 66000 |  |  |  | 0 | 0 | 0 | 75000 | 9000 | 66000
Sub-total Carried to Summary | [14 empty] | 0 | 0 |  | 0 | 0
4 | PIPING (SECTION 23 21 13 & DS/1831-23 21 13) | [13 empty] | 0 | 0 |  | 0 | 0
4.1 | Supply & Installation Chilled Water Piping | [13 empty] | 0 | 0 |  | 0 | 0
4.1.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 3784 | Rate Only | 704 | Rate Only | Rate Only | Ready Stock | PROTEK - China |  | 4300 | 516 | 3784 | 800 | 96 | 704
4.1.2 | Ø 1 ½" (Ø 40mm) |  |  | - | Rm | 2904 | Rate Only | 660 | Rate Only | Rate Only | Ready Stock | PROTEK - China |  | 3300 | 396 | 2904 | 750 | 90 | 660
4.1.3 | Ø 1 ¼" (Ø 32mm) |  |  | - | Rm | 2464 | Rate Only | 642.4 | Rate Only | Rate Only | Ready Stock | PROTEK - China |  | 2800 | 336 | 2464 | 730 | 87.6 | 642.4
4.1.4 | Ø 1" (Ø 25mm) |  |  | 3 | Rm | 2024 | 6072 | 580.8 | 1742.4 | 7814.4 | Ready Stock | PROTEK - China |  | 2300 | 276 | 2024 | 660 | 79.2 | 580.8
4.2 | Supply & Installation Cooling Water Piping |  |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
4.2.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 6424 | Rate Only | 704 | Rate Only | Rate Only | Ready Stock | Aquatherm |  | 7300 | 876 | 6424 | 800 | 96 | 704
4.2.2 | Ø 1 ½" (Ø 40mm) |  |  | - | Rm | 4840 | Rate Only | 660 | Rate Only | Rate Only | Ready Stock | Aquatherm |  | 5500 | 660 | 4840 | 750 | 90 | 660
4.2.3 | Ø 1 ¼" (Ø 32mm) |  |  | 3 | Rm | 3080 | 9240 | 642.4 | 1927.2 | 11167.2 | Ready Stock | Aquatherm |  | 3500 | 420 | 3080 | 730 | 87.6 | 642.4
4.2.4 | Ø 1" (Ø 25mm) |  |  | - | Rm | 2640 | Rate Only | 580.8 | Rate Only | Rate Only | Ready Stock | Aquatherm |  | 3000 | 360 | 2640 | 660 | 79.2 | 580.8
4.3 | Condensate Drain Piping |  |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
4.3.1 | Ø 1 ¼" (Ø 32mm) |  |  | - | Rm | 1056 | Rate Only | 264 | Rate Only | Rate Only |  |  |  | 1200 | 144 | 1056 | 300 | 36 | 264
4.3.2 | Ø 1" (Ø 25mm) |  |  | 11 | Rm | 1012 | 11132 | 246.4 | 2710.4 | 13842.4 | Ready Stock | AGM |  | 1150 | 138 | 1012 | 280 | 33.6 | 246.4
4.4 | Pipe Pressure Testing |  |  | 1 | Lot | 0 | 0 | 22000 | 22000 | 22000 | Ready Stock | AGM |  | 0 | 0 | 0 | 25000 | 3000 | 22000
4.5 | Engineered Support system with Lindapter Type/TR60 Complete in all Respect |  |  | 1 | Lot | 88000 | 88000 | 13200 | 13200 | 101200 |  |  |  | 100000 | 12000 | 88000 | 15000 | 1800 | 13200
Sub-total Carried to Summary | [14 empty] | 0 | 0 |  | 0 | 0
5 | VALVES & SPECIALITIES (SECTION 23 05 23, 23 86 20 & 23 86 35) | [13 empty] | 0 | 0 |  | 0 | 0
5.1 | Supply and Installation of Gate Valves for Cooling Water with Material/Flanges/Unions etc. (Section 23 05 23) | [13 empty] | 0 | 0 |  | 0 | 0
5.1.1 | Ø 2" (Ø 50mm) |  |  | - | No. | 22000 | Rate Only | 1320 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS |  | 25000 | 3000 | 22000 | 1500 | 180 | 1320
5.1.2 | Ø 1 ½" (Ø 40mm) |  |  | - | No. | 15840 | Rate Only | 1320 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS |  | 18000 | 2160 | 15840 | 1500 | 180 | 1320
5.1.3 | Ø 1 ¼" (Ø 32mm) |  |  | 2 | Nos. | 10120 | 20240 | 1320 | 2640 | 22880 | 4 to 6 weeks | SCON / WATTS |  | 11500 | 1380 | 10120 | 1500 | 180 | 1320
5.1.4 | Ø 1" (Ø 25mm) |  |  | 3 | Nos. | 8360 | 25080 | 1320 | 3960 | 29040 | 4 to 6 weeks | SCON / WATTS |  | 9500 | 1140 | 8360 | 1500 | 180 | 1320
5.1.5 | Ø ¾" (Ø 20mm) |  |  | - | No. | 5720 | Rate Only | 1320 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS |  | 6500 | 780 | 5720 | 1500 | 180 | 1320
5.2 | Supply and Installation of Ball Valve for Cooling Water with Material/Flanges/Unions etc. (Section 23 05 23) |  |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
5.2.1 | Ø 1" (Ø 25mm) |  |  | - | No. | 7920 | Rate Only | 1320 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS |  | 9000 | 1080 | 7920 | 1500 | 180 | 1320
5.2.2 | Ø ¾" (Ø 20mm) |  |  | - | Nos. | 6160 | Rate Only | 1320 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS |  | 7000 | 840 | 6160 | 1500 | 180 | 1320
5.3 | Supply and Installation of Strainer Cooling Water with Material/Flanges/Unions etc. |  |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
5.3.1 | Ø 2" (Ø 50mm) |  |  | - | No. | 18040 | Rate Only | 880 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS |  | 20500 | 2460 | 18040 | 1000 | 120 | 880
5.3.2 | Ø 1 ½" (Ø 40mm) |  |  | - | No. | 14080 | Rate Only | 880 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS |  | 16000 | 1920 | 14080 | 1000 | 120 | 880
5.3.3 | Ø 1 ¼" (Ø 32mm) |  |  | 1 | No. | 10560 | 10560 | 880 | 880 | 11440 | 4 to 6 weeks | SCON / WATTS |  | 12000 | 1440 | 10560 | 1000 | 120 | 880
5.3.4 | Ø 1" (Ø 25mm) |  |  | 1 | No. | 6600 | 6600 | 880 | 880 | 7480 | 4 to 6 weeks | SCON / WATTS |  | 7500 | 900 | 6600 | 1000 | 120 | 880
5.4 | Supply and Installation of Flow Balancing & Shut-off Valve for Cooling Water with Material/Flanges/Unions etc. |  |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
5.4.1 | Ø 1 ½" (Ø 40mm) |  |  | - | No. | 27720 | Rate Only | 1320 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS |  | 31500 | 3780 | 27720 | 1500 | 180 | 1320
5.4.2 | Ø 1 ¼" (Ø 32mm) |  |  | 1 | No. | 20944 | 20944 | 1320 | 1320 | 22264 | 4 to 6 weeks | SCON / WATTS |  | 23800 | 2856 | 20944 | 1500 | 180 | 1320
5.4.3 | Ø 1" (Ø 25mm) |  |  | - | No. | 17600 | Rate Only | 1320 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS |  | 20000 | 2400 | 17600 | 1500 | 180 | 1320
5.5 | Supply and Installation of Pressure Independent Control Valve (PICV) for Fan Coil Unit with Material/Flanges/Unions etc. |  |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
5.5.1 | Ø 1 ½" (Ø 40mm) |  |  | - | No. | 345840 | Rate Only | 7040 | Rate Only | Rate Only | 8 to 10 Weeks | SCON / WATTS |  | 393000 | 47160 | 345840 | 8000 | 960 | 7040
5.5.2 | Ø 1 ¼" (Ø 32mm) |  |  | - | No. | 162800 | Rate Only | 7040 | Rate Only | Rate Only | 8 to 10 Weeks | SCON / WATTS |  | 185000 | 22200 | 162800 | 8000 | 960 | 7040
5.5.3 | Ø 1" (Ø 25mm) |  |  | 1 | No. | 130680 | 130680 | 7040 | 7040 | 137720 | 8 to 10 Weeks | SCON / WATTS |  | 148500 | 17820 | 130680 | 8000 | 960 | 7040
Sub-total Carried to Summary | [14 empty] | 0 | 0 |  | 0 | 0
6 | THERMAL INSULATION (SECTION 23 07 13 & 23 07 19 & DS/1831-23 07 13 & 23 07 19) | [13 empty] | 0 | 0 |  | 0 | 0
6.1 | Insulation of Supply Air Duct-Air Conditioned Space/Air Conditioned Ceiling Cavity |  |  | 958 | m² | 4664 | 4468112 | 660 | 632280 | 5100392 | Ready Stock | AEROFOAM |  | 5300 | 636 | 4664 | 750 | 90 | 660
6.2 | Insulation of Return Air Duct-Air Conditioned Space/Air Conditioned Ceiling Cavity |  |  | 2 | m² | 4576 | 9152 | 660 | 1320 | 10472 | Ready Stock | AEROFOAM |  | 5200 | 624 | 4576 | 750 | 90 | 660
6.3 | Supply & Installation Chilled Water Piping (Section 23 07 19 & DS/1831-23 07 19) |  |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
6.3.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 3168 | Rate Only | 202.4 | Rate Only | Rate Only | Ready Stock | AEROFOAM |  | 3600 | 432 | 3168 | 230 | 27.6 | 202.4
6.3.2 | Ø 1 ½" (Ø 40mm) |  |  | - | Rm | 2904 | Rate Only | 202.4 | Rate Only | Rate Only | Ready Stock | AEROFOAM |  | 3300 | 396 | 2904 | 230 | 27.6 | 202.4
6.3.3 | Ø 1 ¼" (Ø 32mm) |  |  | - | Rm | 2640 | Rate Only | 202.4 | Rate Only | Rate Only | Ready Stock | AEROFOAM |  | 3000 | 360 | 2640 | 230 | 27.6 | 202.4
6.3.4 | Ø 1" (Ø 25mm) |  |  | 3 | Rm | 2446.4 | 7339.2 | 202.4 | 607.2 | 7946.4 | Ready Stock | AEROFOAM |  | 2780 | 333.6 | 2446.4 | 230 | 27.6 | 202.4
6.4 | Condensate Drain Piping Insulation (Section 23 07 19 & DS/1831-23 07 19) |  |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
6.4.1 | Ø 1 ¼" (Ø 32mm) |  |  | - | Rm | 1672 | Rate Only | 264 | Rate Only | Rate Only | Ready Stock | AEROFOAM |  | 1900 | 228 | 1672 | 300 | 36 | 264
6.4.2 | Ø 1" (Ø 25mm) |  |  | 10.668 | Rm | 1645.6 | 17555.2608 | 290.4 | 3097.9872 | 20653.248 | Ready Stock | AEROFOAM |  | 1870 | 224.4 | 1645.6 | 330 | 39.6 | 290.4
6.5 | Cladding of Valves & Specialities (Openable Boxes with Insulation) |  |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
6.5.1 | Ø 2" (Ø 50mm) |  |  | - | No. | 0 | Rate Only | 0 | Rate Only | Rate Only | - | - |  |  | 0 | 0 |  | 0 | 0
6.5.2 | Ø 1 ½" (Ø 40mm) |  |  | - | No. | 0 | Rate Only | 0 | Rate Only | Rate Only | - | - |  |  | 0 | 0 |  | 0 | 0
6.5.3 | Ø 1 ¼" (Ø 32mm) |  |  | - | No. | 0 | Rate Only | 0 | Rate Only | Rate Only | - | - |  |  | 0 | 0 |  | 0 | 0
6.5.4 | Ø 1" (Ø 25mm) |  |  | 5 | Nos. | 6160 | 'Rate Only | 1320 | 'Rate Only | 'Rate Only | - | - |  | 7000 | 840 | 6160 | 1500 | 180 | 1320
Sub-total Carried to Summary | [14 empty] | 0 | 0 |  | 0 | 0
7 | AIR DEVICES (SECTION 23 37 13) | [13 empty] | 0 | 0 |  | 0 | 0
7.1 | Supply Air Linear (Tuttle & Bailey) (Series 7000 1" - 25mm x 3 Slots) with Factory Supplied & Field Installed Plenum with Insulation |  |  | 13 | Rm | 5016 | 65208 | 616 | 8008 | 73216 | 8 to 10 weeks | Steel Craft/ Air guide |  | 5700 | 684 | 5016 | 700 | 84 | 616
7.2 | Return Air Linear (Tuttle & Bailey) (Series 7000 1" - 25mm x 3 Slots) with Factory Supplied & Field Installed Plenum with Insulation |  |  | 13 | Rm | 5016 | 65208 | 616 | 8008 | 73216 | 8 to 10 weeks | Steel Craft/ Air guide |  | 5700 | 684 | 5016 | 700 | 84 | 616
7.3 | Supply/Return Air Fixed Bar Grill & Register (Tuttle & Bailey - A50 Series) 21" x 6" (525mm x 150mm) with Damper |  |  | 4 | Nos. | 3960 | 15840 | 616 | 2464 | 18304 | 8 to 10 weeks | Steel Craft/ Air guide |  | 4500 | 540 | 3960 | 700 | 84 | 616
7.4 | Supply Air Fixed Bar Grill & Register (Tuttle & Bailey - A50 Series) 42" x 6" (1050mm x 150mm) with Damper |  |  | 1 | No. | 10560 | 10560 | 4400 | 4400 | 14960 | 8 to 10 weeks | Steel Craft/ Air guide |  | 12000 | 1440 | 10560 | 5000 | 600 | 4400
7.5 | Supply/Return Air Fixed Bar Grill & Register (Tuttle & Bailey - A50 Series) 232" x 18" (5800mm x 450mm) with Damper |  |  | 1 | No. | 92400 | 92400 | 4400 | 4400 | 96800 | 8 to 10 weeks | Steel Craft/ Air guide |  | 105000 | 12600 | 92400 | 5000 | 600 | 4400
7.6 | Supply Air Round Diffusers Ø 12" (Tuttle & Bailey) (Series AVJR 3-Cone) with Dampers |  |  | 89 | Nos. | 21560 | 1918840 | 1320 | 117480 | 2036320 | 8 to 10 weeks | Steel Craft/ Air guide |  | 24500 | 2940 | 21560 | 1500 | 180 | 1320
7.7 | Supply Air Round Diffusers Ø 10" (Tuttle & Bailey) (Series AVJR 3-Cone) with Dampers |  |  | - | No. | 19360 | Rate Only | 1320 | Rate Only | Rate Only | 8 to 10 weeks | Steel Craft/ Air guide |  | 22000 | 2640 | 19360 | 1500 | 180 | 1320
7.8 | Exhaust Air Disc Valve for Toilet Exhaust (Ø 6") |  |  | 24 | Nos. | 2816 | 67584 | 880 | 21120 | 88704 | 8 to 10 weeks | Steel Craft/ Air guide |  | 3200 | 384 | 2816 | 1000 | 120 | 880
Sub-total Carried to Summary | [14 empty] | 0 | 0 |  | 0 | 0
8 | WATER COOLED PACKAGED AIR CONDITIONER (SECTION 23 81 30 & DS/1831-23 81 30) | [13 empty] | 0 | 0 |  | 0 | 0
8.1 | Supply and Installation of Water Cooled Packaged Air Conditioner (CWPU-21-01) Ceiling Hung Type with Wall Mounted Room Thermostat (3.0 TR) with Scheduling feature |  |  | 1 | No. | 941600 | 941600 | 22000 | 22000 | 963600 | 12 Weeks | SABRO / COOLMAX |  | 1070000 | 128400 | 941600 | 25000 | 3000 | 22000
8.2 | Supply and Installation of Automatic Air Vents |  |  | 2 | Nos. | 7480 | 14960 | 880 | 1760 | 16720 | Ready Stock | SCON / WATTS |  | 8500 | 1020 | 7480 | 1000 | 120 | 880
8.3 | Ø ½" (Ø 15mm) Shredder Fitting for Air Vent/Pressure Testing |  |  | 2 | Nos. | 8800 | 17600 | 1760 | 3520 | 21120 |  |  |  | 10000 | 1200 | 8800 | 2000 | 240 | 1760
8.4 | Pressure Switch |  |  | 1 | No. | 21120 | 21120 | 2640 | 2640 | 23760 | 5 Weeks | Danfoss |  | 24000 | 2880 | 21120 | 3000 | 360 | 2640
8.5 | Control Wiring Between Indoor and Thermostat |  |  | 1 | Lot | 8800 | 8800 | 2200 | 2200 | 11000 | Ready Stock | INDUS / FAST |  | 10000 | 1200 | 8800 | 2500 | 300 | 2200
8.6 | Support System for Water Cooled Package Units with Lindapter Type/TR60 complete in all respect |  |  | 1 | Lot | 13200 | 13200 | 2640 | 2640 | 15840 | Ready Stock | INDEX |  | 15000 | 1800 | 13200 | 3000 | 360 | 2640
8.7 | Commissioning & Testing of Water Cooled Package Units |  |  | 1 | Lot | 0 | 0 | 17600 | 17600 | 17600 |  |  |  | 0 | 0 | 0 | 20000 | 2400 | 17600
Sub-total Carried to Summary | [14 empty] | 0 | 0 |  | 0 | 0
9 | METER & GAUGES (SECTION 23 05 19) | [13 empty] | 0 | 0 |  | 0 | 0
9.1 | Thermometers with Wells for Pipe Thermometer |  |  | 4 | Nos. | 11000 | 44000 | 880 | 3520 | 47520 | Ready Stock | WEISS / WEKSLER |  | 12500 | 1500 | 11000 | 1000 | 120 | 880
9.2 | Pressure Gauges on Pipes |  |  | 4 | Nos. | 8360 | 33440 | 880 | 3520 | 36960 | Ready Stock | WEISS / WEKSLER |  | 9500 | 1140 | 8360 | 1000 | 120 | 880
9.3 | Gauge Outlets with Cock |  |  | 4 | Nos. | 1760 | 7040 | 880 | 3520 | 10560 | Ready Stock | WEISS / WEKSLER |  | 2000 | 240 | 1760 | 1000 | 120 | 880
Sub-total Carried to Summary | [14 empty] | 0 | 0 |  | 0 | 0
10 | HVAC CONTROLS (SECTION 23 09 20) | [13 empty] | 0 | 0 |  | 0 | 0
10.1 | DDC Controller (BACnet/IP) for FCU-21-01 (Refer FND Drawing # FND-1831-XX-H-XX-XX-700-00) |  |  | 1 | No. | 154000 | Rate Only | 4400 | Rate Only | Rate Only | 10 Weeks | JES |  | 175000 | 21000 | 154000 | 5000 | 600 | 4400
10.2 | DDC Controller (BACnet/IP) for CWPU-21-01 (Refer FND Drawing # FND-1831-XX-H-XX-XX-700-00) |  |  | 1 | No. | 154000 | Rate Only | 4400 | Rate Only | Rate Only | 10 Weeks | JES |  | 175000 | 21000 | 154000 | 5000 | 600 | 4400
10.3 | Installation of Differential Pressure Switch (DPS) with pressure adjustment range of .5 to 4 mbar and switching difference of 0.2 mbar or less. |  |  | 2 | Nos. | 0 | Rate Only | 13200 | Rate Only | Rate Only | 10 Weeks | JES |  | 0 | 0 | 0 | 15000 | 1800 | 13200
10.4 | Wiring of PS from Duct Index Point to AHU DDC Panel (3 Core x 18AWG Shielded Wire-Belden Cable) |  |  | 1 | Lot | 154000 | Rate Only | 22000 | Rate Only | Rate Only | 10 Weeks | JES |  | 175000 | 21000 | 154000 | 25000 | 3000 | 22000
10.5 | Master/Network Controller that will host the connected devices (VAV's Controllers and thermostat) and can work as a standalone server. (complete set along with Power Supply) |  |  | 1 | No. | 0 | Rate Only | 88000 | Rate Only | Rate Only | 10 Weeks | JES |  | 0 | 0 | 0 | 100000 | 12000 | 88000
10.6 | Integration & comissioning of Pressure Independent Control Valve with Modulating Proportional Valve Actuator with Reversible Synchronous Motor 0-10 VDC. (Chilled Water Application) |  |  | 1 | No. | 66000 | Rate Only | 13200 | Rate Only | Rate Only | 10 Weeks | JES |  | 75000 | 9000 | 66000 | 15000 | 1800 | 13200
10.7 | Integration of Wall Mounted Room Thermostat for FCU-21-01 - Supplied with FCU |  |  | 1 | No. | 66000 | Rate Only | 8800 | Rate Only | Rate Only | 10 Weeks | JES |  | 75000 | 9000 | 66000 | 10000 | 1200 | 8800
10.8 | Integration of Wall Mounted Room Thermostat for CWPU-21/01 - Supplied with CWPU |  |  | 1 | No. | 66000 | Rate Only | 8800 | Rate Only | Rate Only | 10 Weeks | JES |  | 75000 | 9000 | 66000 | 10000 | 1200 | 8800
10.9 | Integration of Pressure Switch - Supplied with CWPU |  |  | 1 | No. | 66000 | Rate Only | 13200 | Rate Only | Rate Only | 10 Weeks | JES |  | 75000 | 9000 | 66000 | 15000 | 1800 | 13200
10.1 | Integration of Motorized Fire Damper Actuator (2 Nos.) with power & control cable 1.5mm2 installed in (Ø 20mm) PVC Conduit, complete in all respect (Size of Damper 525 x 150mm & Airflow is 500 cfm) - Material Covered in BOQ item # 3.7 |  |  | 1 | Lot | 88000 | Rate Only | 39600 | Rate Only | Rate Only | 10 Weeks | JES |  | 100000 | 12000 | 88000 | 45000 | 5400 | 39600
10.11 | Integration of Motorized Fire Damper Actuator (1 No.) with power & control cable 1.5mm2 installed in (Ø 20mm) PVC Conduit, complete in all respect (Size of Damper 1050mm x 150mm & Airflow is 1000 cfm) - Material Covered in BOQ item # 3.7 |  |  | 1 | Lot | 88000 | Rate Only | 39600 | Rate Only | Rate Only | 10 Weeks | JES |  | 100000 | 12000 | 88000 | 45000 | 5400 | 39600
10.12 | Integration of Motorized Damper Actuator (2 Nos.) with power & control cable 1.5mm2 installed in (Ø 20mm) PVC Conduit, complete in all respect (Size of Damper 500mm x 200mm & Airflow is 1000cfm) - Material Covered in BOQ item # 3.8 |  |  | 1 | Lot | 88000 | Rate Only | 44000 | Rate Only | Rate Only | 10 Weeks | JES |  | 100000 | 12000 | 88000 | 50000 | 6000 | 44000
10.13 | Networking, Cabling, Receway Support, Hanger, Sleeves, Core Drilling etc. |  |  | 1 | Lot | 242000 | Rate Only | 66000 | Rate Only | Rate Only | 10 Weeks | JES |  | 275000 | 33000 | 242000 | 75000 | 9000 | 66000
Sub-total Carried to Summary | [14 empty] | 0 | 0 |  | 0 | 0
11 | HOT WATER SUPPLY SYSTEM | [13 empty] | 0 | 0 |  | 0 | 0
11.1 | Supply & Installation of Instant Electric Operated Hot Water Heaters (Section 22 33 30 & DS/1831-22 33 30) | [13 empty] | 0 | 0 |  | 0 | 0
11.1.1 | Supply, Installation and Comissioning of Electric Operated Hot Water Heater HWH/01-02, 30L heating capacity. Including all fittings and accessories required from installation till comissioning of Hot Water Heater (Refer DS/1831-22 33 30) | 2 | Nos. | 2 | Nos. | 68640 | 137280 | 4400 | 8800 | 146080 | Ready Stock | ARISTON |  | 78000 | 9360 | 68640 | 5000 | 600 | 4400
11.2 | Poly Propylene Pipe for Cold Water Supply (PPR Pipe PN-20 with PN-20 Fittings including all Fittings and Accessories Required for Piping Installation) (Section 22 11 16 & DS/1831-22 11 16) |  |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
11.2.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 3960 | Rate Only | 704 | Rate Only | Rate Only | Ready Stock | RECKTHERM |  | 4500 | 540 | 3960 | 800 | 96 | 704
11.2.2 | Ø 1 ½" (Ø 40mm) |  |  | - | Rm | 3080 | Rate Only | 704 | Rate Only | Rate Only | Ready Stock | RECKTHERM |  | 3500 | 420 | 3080 | 800 | 96 | 704
11.2.3 | Ø 1 ¼" (Ø 32mm) |  |  | - | Rm | 2640 | Rate Only | 704 | Rate Only | Rate Only | Ready Stock | RECKTHERM |  | 3000 | 360 | 2640 | 800 | 96 | 704
11.2.4 | Ø 1" (Ø 25mm) |  |  | 6 | Rm | 1936 | 11616 | 704 | 4224 | 15840 | Ready Stock | RECKTHERM |  | 2200 | 264 | 1936 | 800 | 96 | 704
11.3 | Poly Propylene Pipe for Hot Water Supply (PPR Pipe PN-20 with PN-20 Fittings including all Fittings and Accessories Required for Piping Installation) (Section 22 11 16 & DS/1831-22 11 16) |  |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
11.3.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 3960 | Rate Only | 704 | Rate Only | Rate Only | Ready Stock | RECKTHERM |  | 4500 | 540 | 3960 | 800 | 96 | 704
11.3.2 | Ø 1 ½" (Ø 40mm) |  |  | 13 | Rm | 3080 | 40040 | 704 | 9152 | 49192 | Ready Stock | RECKTHERM |  | 3500 | 420 | 3080 | 800 | 96 | 704
11.3.3 | Ø 1 ¼" (Ø 32mm) |  |  | 23 | Rm | 2640 | 60720 | 704 | 16192 | 76912 | Ready Stock | RECKTHERM |  | 3000 | 360 | 2640 | 800 | 96 | 704
11.3.4 | Ø 1" (Ø 25mm) |  |  | 12 | Rm | 1936 | 23232 | 704 | 8448 | 31680 | Ready Stock | RECKTHERM |  | 2200 | 264 | 1936 | 800 | 96 | 704
11.4 | Valve & Specialities (Section 22 05 23) |  |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
11.4.1 | Gate Valves - PPR PN-20 (Including all Fittings and Accessories Required for Valve Installation) (Section 22 05 23) |  |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
11.4.1.1 | Ø 2" (Ø 50mm) |  |  | - | No. | 22000 | Rate Only | 880 | Rate Only | Rate Only | Ready Stock | RECKTHERM |  | 25000 | 3000 | 22000 | 1000 | 120 | 880
11.4.1.2 | Ø 1 ½" (Ø 40mm) |  |  | 2 | Nos. | 15840 | 31680 | 880 | 1760 | 33440 | Ready Stock | RECKTHERM |  | 18000 | 2160 | 15840 | 1000 | 120 | 880
11.4.1.3 | Ø 1 ¼" (Ø 32mm) |  |  | 4 | Nos. | 9504 | 38016 | 880 | 3520 | 41536 | Ready Stock | RECKTHERM |  | 10800 | 1296 | 9504 | 1000 | 120 | 880
11.4.1.4 | Ø 1" (Ø 25mm) |  |  | 10 | Nos. | 7480 | 74800 | 880 | 8800 | 83600 | Ready Stock | RECKTHERM |  | 8500 | 1020 | 7480 | 1000 | 120 | 880
11.4.2 | Insulation of Hot Water Piping Including Vapor Barrier, Jacketing & Cladding (Section 22 07 19 & DS/1831-22 07 19) |  |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
11.4.2.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 1936 | Rate Only | 123.2 | Rate Only | Rate Only | 2 to 3 weeks | AEROFOAM |  | 2200 | 264 | 1936 | 140 | 16.8 | 123.2
11.4.2.2 | Ø 1 ½" (Ø 40mm) |  |  | 13 | Rm | 1584 | 20592 | 114.4 | 1487.2 | 22079.2 | 2 to 3 weeks | AEROFOAM |  | 1800 | 216 | 1584 | 130 | 15.6 | 114.4
11.4.2.3 | Ø 1 ¼" (Ø 32mm) |  |  | 23 | Rm | 1496 | 34408 | 105.6 | 2428.8 | 36836.8 | 2 to 3 weeks | AEROFOAM |  | 1700 | 204 | 1496 | 120 | 14.4 | 105.6
11.4.2.4 | Ø 1" (Ø 25mm) |  |  | 12 | Rm | 1320 | 15840 | 88 | 1056 | 16896 | 2 to 3 weeks | AEROFOAM |  | 1500 | 180 | 1320 | 100 | 12 | 88
11.5 | Cladding of Valves & Specialities (Openable Boxes with Insulation) |  |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
11.5.1 | Ø 2" (Ø 50mm) |  |  | - | No. | 4400 | Rate Only | 528 | Rate Only | Rate Only |  |  |  | 5000 | 600 | 4400 | 600 | 72 | 528
11.5.2 | Ø 1 ½" (Ø 40mm) |  |  | 2 | Nos. | 3520 | Rate Only | 528 | Rate Only | Rate Only |  |  |  | 4000 | 480 | 3520 | 600 | 72 | 528
11.5.3 | Ø 1 ¼" (Ø 32mm) |  |  | 4 | Nos. | 2640 | Rate Only | 528 | Rate Only | Rate Only |  |  |  | 3000 | 360 | 2640 | 600 | 72 | 528
11.5.4 | Ø 1" (Ø 25mm) |  |  | 8 | Nos. | 1760 | Rate Only | 528 | Rate Only | Rate Only |  |  |  | 2000 | 240 | 1760 | 600 | 72 | 528
11.6 | Pressure Testing of Water Supply Piping (1.5 times of operating pressure) (Including all arrangements required for Pressure Testing) |  |  | 1 | Lot | 0 | 0 | 22000 | 22000 | 22000 |  |  |  | 0 | 0 | 0 | 25000 | 3000 | 22000
11.7 | Engineered Support system with Lindapter Type/TR60 Complete in all Respect |  |  | 1 | Lot | 66000 | 66000 | 13200 | 13200 | 79200 |  |  |  | 75000 | 9000 | 66000 | 15000 | 1800 | 13200
Sub-total Carried to Summary | [17 empty] | 0 | 0
12 | PLUMBING FIXTURES & FITTINGS | [16 empty] | 0 | 0
12.1 | Fixtures (Section 22 41 10 & DS/1831-22 41 10) | [16 empty] | 0 | 0
12.1.1 | Supply & Installation of Wall Hung Western WC, Concealed Flush Tank Operated (Section 22 41 10 & DS/1831-22 41 10) |  |  | 10 | Nos. | 134640 | 1346400 | 6600 | 66000 | 1412400 | 12 weeks | Porta & Grohe |  | 153000 | 18360 | 134640 | 7500 | 900 | 6600
12.1.2 | Supply & Installation of Vanity Wash Basin with, Waste, Bottle Trap & Tee Stop-Cock (Section 22 41 10 & DS/1831-22 41 10) |  |  | 10 | Nos. | 66000 | 660000 | 5720 | 57200 | 717200 | 12 weeks | Porta & Grohe |  | 75000 | 9000 | 66000 | 6500 | 780 | 5720
12.1.3 | Supply & Installation of Disabled Toilet Set (Basin, WC) (Section 22 41 10 & DS/1831-22 41 10) |  |  | 2 | Nos. | 66000 | 132000 | 5720 | 11440 | 143440 | 12 weeks | Porta & Grohe |  | 75000 | 9000 | 66000 | 6500 | 780 | 5720
12.1.4 | Supply & Installation of Wash Basin Single Lever Faucet with Flexible Hoses (For Cold & Hot Water). (Section 22 41 10 & DS/1831-22 41 10) |  |  | 12 | Nos. | 48400 | 580800 | 3960 | 47520 | 628320 | 12 weeks | Porta & Grohe |  | 55000 | 6600 | 48400 | 4500 | 540 | 3960
12.1.5 | Supply & Installation of Stainless Steel Kitchen Sink including stop cocks, P-trap / bottle trap, waste pipe etc. |  |  | 1 | Nos. | 83600 | 83600 | 5280 | 5280 | 88880 | 12 weeks | Porta & Grohe |  | 95000 | 11400 | 83600 | 6000 | 720 | 5280
12.1.6 | Supply & Installation of Hot and Cold Water Mixer for Stainless Steel Kitchen Sink |  |  | 1 | Nos. | 42240 | 42240 | 3960 | 3960 | 46200 | 12 weeks | Porta & Grohe |  | 48000 | 5760 | 42240 | 4500 | 540 | 3960
12.1.7 | Supply & Installation of WC Hand Operated Shower Spray With Angle Valve and Flexible Hose. (Section 22 41 10 & DS/1831-22 41 10) |  |  | 12 | Nos. | 12760 | 153120 | 1320 | 15840 | 168960 | 12 weeks | Porta & Grohe |  | 14500 | 1740 | 12760 | 1500 | 180 | 1320
12.1.8 | Supply & Installation of Bib Cocks for (Janitor, Cleaning Area) (Section 22 41 10 & DS/1831-22 41 10) |  |  | 2 | Nos. | 2200 | 4400 | 880 | 1760 | 6160 | 12 weeks | Porta & Grohe |  | 2500 | 300 | 2200 | 1000 | 120 | 880
12.1.9 | Supply & Installation of Single Lever Faucet Wall Mounted for (Hot & Cold Water) (Ablution Area) (Section 22 41 10 & DS/1831-22 41 10) |  |  | 6 | Nos. | 42240 | 253440 | 3960 | 23760 | 277200 | 12 weeks | Porta & Grohe |  | 48000 | 5760 | 42240 | 4500 | 540 | 3960
12.1.10 | Supply & Installation of Toilet Roll Holder (Section 22 41 10 & DS/1831-22 41 10) |  |  | 12 | Nos. | 12056 | 144672 | 880 | 10560 | 155232 | 12 weeks | Porta & Grohe |  | 13700 | 1644 | 12056 | 1000 | 120 | 880
12.1.11 | Supply & Installation of Wall Mounted Soap Dispenser (Section 22 41 10 & DS/1831-22 41 10) |  |  | 10 | Nos. | 12760 | 127600 | 880 | 8800 | 136400 | 12 weeks | Porta & Grohe |  | 14500 | 1740 | 12760 | 1000 | 120 | 880
12.2 | Drainage & Vent Pipe (uPVC - Non Pressure Class; Solvent Welded) Including all Fittings and Accessories Required for Piping Installation e.g Elbows, Y, Double Y, Ceiling Cleanouts, Reducers, Sockets etc. (Section 22 13 20 & DS/1831-22 13 20) | [12 empty] | 3500 | 420 | 3080 | 600 | 72 | 528
12.2.1 | Ø 4" (Ø 100mm) |  |  | - | Rm | 3080 | Rate Only | 528 | Rate Only | Rate Only | Ready Stock | AGM |  | 2200 | 264 | 1936 | 600 | 72 | 528
12.2.2 | Ø 3" (Ø 75mm) |  |  | - | Rm | 1936 | Rate Only | 528 | Rate Only | Rate Only | Ready Stock | AGM |  | 1600 | 192 | 1408 | 600 | 72 | 528
12.2.3 | Ø 2" (Ø 50mm) |  |  | - | Rm | 1408 | Rate Only | 528 | Rate Only | Rate Only | Ready Stock | AGM |  | 1250 | 150 | 1100 | 600 | 72 | 528
12.2.4 | Ø 1 ½" (Ø 40mm) |  |  | - | Rm | 1100 | Rate Only | 528 | Rate Only | Rate Only | Ready Stock | AGM |  |  | 0 | 0 |  | 0 | 0
12.3 | Drain Accessories (Section 22 11 19) |  |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
12.3.1 | SS Floor Drain (Section 22 11 19) |  |  |  |  | 0 |  | 0 | [5 empty] | 8800 | 1056 | 7744 | 1000 | 120 | 880
12.3.1.1 | Ø 6" x 6" (Ø 150 x 150 mm) |  |  | 20 | Nos. | 7744 | 154880 | 880 | 17600 | 172480 | Ready Stock | QABIL |  |  | 0 | 0 |  | 0 | 0
12.3.2 | SS Floor Clean Out (Section 22 11 19) |  |  |  |  | 0 |  | 0 | [5 empty] | 7500 | 900 | 6600 | 1000 | 120 | 880
12.3.2.1 | Ø 4" (Ø 100mm) |  |  | 12 | Nos. | 6600 | 79200 | 880 | 10560 | 89760 | Ready Stock | QABIL |  | 7500 | 900 | 6600 | 1000 | 120 | 880
12.3.2.2 | Ø 3" (Ø 75mm) |  |  | - | No. | 6600 | Rate Only | 880 | Rate Only | Rate Only | Ready Stock | QABIL |  | 42000 | 5040 | 36960 | 1000 | 120 | 880
12.4 | 350mm Wide Drain Channel with SS Grating for Ablution Area (Refer FND Detail # FND/SDS/24) |  |  | 6 | Rm | 36960 | 221760 | 880 | 5280 | 227040 | Ready Stock | QABIL |  |  | 0 | 0 | 30000 | 3600 | 26400
12.5 | Gravity Testing of Drainage Piping (Including all arrangements required for Gravity Testing) |  |  | 1 | Lot | 0 | 0 | 26400 | 26400 | 26400 |  |  |  | 50000 | 6000 | 44000 | 15000 | 1800 | 13200
12.6 | Engineered Support system Complete in all Respect |  |  | 1 | Lot | 44000 | 44000 | 13200 | 13200 | 57200 | Ready Stock | INDEX |  |  | 0 | 0 |  | 0 | 0
Sub-total Carried to Summary | [14 empty] | 0 | 0 |  | 0 | 0
13 | CLEANING & BALANCING OF HVAC SYSTEM (SECTION 23 05 93) | [13 empty] | 0 | 0 | 150000 | 18000 | 132000
13.1 | Cleaning & Balancing of HVAC System (Water + Air) |  |  | 1 | Lot |  | 0 | 132000 | 132000 | 132000 |  |  |  |  | 0 | 0 |  | 0 | 0
Sub-total Carried to Summary | [14 empty] | 0 | 0 |  | 0 | 0
14 | PAINTING & FINISHING AND MECHANICAL IDENTIFICATION (SECTION 23 05 50 & 23 05 53) | [12 empty] | 100000 | 12000 | 88000 | 15000 | 1800 | 13200
14.1 | Painting & Finishing, Stenciling of Pipes & Ducts, Identification Tags on Valves etc. and Equipment Data Plates (Section 23 05 50) |  |  | 1 | Lot | 88000 | 88000 | 13200 | 13200 | 101200 | Ready Stock | ICI / BERGER |  |  | 0 | 0 |  | 0 | 0
Sub-total Carried to Summary | [14 empty] | 0 | 0 |  | 0 | 0
15 | MISCELLANEOUS | [12 empty] | 25000 | 3000 | 22000 | 15000 | 1800 | 13200
15.1 | Pipe Sleeves/Core Cutting Where Required |  |  | 1 | Lot | 22000 | 22000 | 13200 | 13200 | 35200 |  |  |  | 25000 | 3000 | 22000 | 15000 | 1800 | 13200
15.2 | Shop Drawings, As Built Drawings, Operation & Maintenance Manuals |  |  | 1 | Lot | 22000 | 22000 | 13200 | 13200 | 35200 |  |  |  | 100000 | 12000 | 88000 | 75000 | 9000 | 66000
15.3 | Fire Stopping Material for all HVAC & Plumbing Pipes, Duct, Trays etc. Crossing a Fire Barrier Wall/Floor/Partition as per Required Fire Rating (Refer Fire Strategy Drawings for Fire Barrier Wall/Floor) |  |  | 1 | Lot | 88000 | 88000 | 66000 | 66000 | 154000
Sub-total Carried to Summary | [6 empty] | 21822670.4608 |  | 2953729.1872 | 24776399.648
32686090.448
109200260.048

## 21FF
EY Karachi - 21st Floor - FF
ITEM NO. | DESCRIPTION | ESTIMATED QUANTITY | UNIT | MATERIAL |  | INSTALLATION |  | AMOUNT | Lead Time | Brands | Remarks
|  |  |  | RATE | AMOUNT | RATE | AMOUNT
1 | FIRE SPRINKLERS (SECTION 21 13 10 & DS/1831-21 13 10)
1.1 | Fire Sprinkler- Upright, Quick Response (SP-01) | 220 | Nos. | 2464 | 542080 | 880 | 193600 | 735680 | 10 Weeks | SHIELD
1.2 | Fire Sprinkler- Pendent Concealed, Quick Response (SP-02) | 60 | Nos. | 6600 | 396000 | 880 | 52800 | 448800 | 10 Weeks | SHIELD
1.3 | Fire Sprinkler- Pendent Sprinkler, Quick Response (SP-03) | 12 | Nos. | 3960 | 47520 | 880 | 10560 | 58080 | 10 Weeks | SHIELD
1.4 | Cabinet Complete with 06 Spare Sprinklers (Upright) (SP-01) | 1 | Nos. | 30800 | 30800 | 2640 | 2640 | 33440 | 10 Weeks | SHIELD
1.5 | Cabinet Complete with 06 Spare Sprinklers (Concealed Pendent) (SP-02) | 1 | No. | 39600 | 39600 | 1760 | 1760 | 41360 | 10 Weeks | SHIELD
1.6 | Cabinet Complete with 06 Spare Sprinklers (Pendent) (SP-03) | 1 | No. | 35200 | 35200 | 1760 | 1760 | 36960 | 10 Weeks | SHIELD
Sub-total Carried to Summary
2 | CORRUGATED STAINLESS STEEL FLEXIBLE CONNECTOR
2.1 | Corrugated Stainless Steel Flexible Connector Ø 1" X 3 ft (UL/FM) (Braided) | 60 | Nos. | 10120 | 607200 | 880 | 52800 | 660000 | 10 Weeks | SHIELD / SEUNG JIN IND
Sub-total Carried to Summary
3 | PORTABLE FIRE EXTINGUISHER FOR FIRE TYPES A, B, C & AFFF (SECTION 21 21 10 & DS/1831-21 21 10)
3.1 | Supply & Installation of 6 Kg Dry Powder Extinguisher (ABC) | 2 | Nos. | 12760 | 25520 | 616 | 1232 | 26752 | 10 Weeks | NAFCO
3.2 | Supply & Installation of 6 Kg CO2 Fire Extinguisher | 2 | Nos. | 22440 | 44880 | 616 | 1232 | 46112 | 10 Weeks | NAFCO
Sub-total Carried to Summary
4 | BLACK STEEL SCHEDULE-40 PIPING (SECTION 21 10 10)
4.1 | Welded Piping System |  |  | 0 |  | 0
4.1.1 | Ø 4" (100mm) | - | Rm | 11000 | Rate Only | 1100 | Rate Only | Rate Only | ReadyStock | Protek
4.1.2 | Ø 3" (75mm) | 100 | Rm | 8624 | 862400 | 774.4 | 77440 | 939840 | ReadyStock | Protek
4.1.3 | Ø 2½" (65mm) | - | Rm | 6864 | Rate Only | 704 | Rate Only | Rate Only | ReadyStock | Protek
4.2 | Threaded Piping System |  |  | 0 |  | 0
4.2.1 | Ø 2" (50mm) | 170 | Rm | 4136 | 703120 | 624.8 | 106216 | 809336 | ReadyStock | Protek
4.2.2 | Ø 1½" (40mm) | 157 | Rm | 2983.2 | 468362.4 | 616 | 96712 | 565074.4 | ReadyStock | Protek
4.2.3 | Ø 1¼" (32mm) | 96 | Rm | 2552 | 244992 | 607.2 | 58291.2 | 303283.2 | ReadyStock | Protek
4.2.4 | Ø 1" (25mm) | 500 | Rm | 1848 | 924000 | 598.4 | 299200 | 1223200 | ReadyStock | Protek
Sub-total Carried to Summary
5 | GATE VALVE (SECTION 21 05 23)
5.1 | Ø2 inch (50 mm) | 2 | Nos. | 83600 | 167200 | 4400 | 8800 | 176000 | 10 Weeks | SHILED
Sub-total Carried to Summary
6 | SIESMIC BRACING
6.1 | Transverse Seismic Bracing (As per FND Detail No. FND/SS/10)
6.1.1 | Ø 4" (100mm) | - | No. | 0 | Rate Only | 0 | Rate Only | Rate Only | 6 weeks | Index
6.1.2 | Ø 3" (75mm) | 11 | Nos. | 8690 | 95590 | 2640 | 29040 | 124630 | 6 weeks | Index
6.1.3 | Ø 2½" (65mm) | - | No. | 0 | Rate Only | 0 | Rate Only | Rate Only | 6 weeks | Index
6.2 | Longitudinal Seismic Bracing (As per FND Detail No. FND/SS/11)
6.2.1 | Ø 4" (100mm) | - | No. | 0 | Rate Only | 0 | Rate Only | Rate Only | 6 weeks | Index
6.2.2 | Ø 3" (75mm) | 7 | Nos. | 10780 | 75460 | 2640 | 18480 | 93940 | 6 weeks | Index
6.2.3 | Ø 2½" (65mm) | - | No. | 0 | Rate Only | 0 | Rate Only | Rate Only | 6 weeks | Index
6.3 | Seismic Restraint (As per FND Detail No. FND/ADD/08)
6.3.1 | Ø 2" (50mm) | 17 | Nos. | 5121.6 | 87067.2 | 1320 | 22440 | 109507.2 | 6 weeks | Index
6.3.2 | Ø 1½" (40mm) | 34 | Nos. | 4664 | 158576 | 1320 | 44880 | 203456 | 6 weeks | Index
6.3.3 | Ø 1¼" (32mm) | 10 | Nos. | 4576 | 45760 | 1320 | 13200 | 58960 | 6 weeks | Index
6.3.4 | Ø 1" (25mm) | 70 | Nos. | 4224 | 295680 | 1320 | 92400 | 388080 | 6 weeks | Index
Sub-total Carried to Summary
7 | FIRE SPRINKLER SYSTEM ACCEPTANCE TEST (SECTION 21 13 17)
7.1 | Fire Sprinkler System Acceptance Test | 1 | Lot | 0 | 0 | 22000 | 22000 | 22000
Sub-total Carried to Summary
8 | PAINTING COATING & STENCILING (SECTION 21 05 50)
8.1 | Painting, Coating, Stenciling & Identification of Fire Piping | 1 | Lot | 176000 | 176000 | 30800 | 30800 | 206800 | Ready Stock | ICI / BERGER
Sub-total Carried to Summary
9 | PIPE SUPPORT SYSTEM (SECTION 21 05 29)
9.1 | Engineered Support system with Lindapter Type/TR60 Complete in all Respect | 1 | Lot | 330000 | 330000 | 48400 | 48400 | 378400 | ReadyStock | Index
Sub-total Carried to Summary
10 | MISCELLANEOUS
10.1 | Hydrostatic Testing | 1 | Lot | 0 | 0 | 44000 | 44000 | 44000
10.2 | Shop Drawings, As Built Drawings, Operation & Maintenance Manuals | 1 | Lot | 0 | 0 | 22000 | 22000 | 22000
10.3 | Fire Stopping of Paritions, Walls & Structure Openings (For Small Openings - Hilti FS - ONE or Approved Equivalent) | 1 | Lot | 88000 | 88000 | 22000 | 22000 | 110000
10.4 | Pipe Sleeves / Core Cutting Wherever Required | 1 | Lot | 22000 | 22000 | 22000 | 22000 | 44000
Sub-total Carried to Summary |  |  |  |  | 6513007.6 |  | 1396683.2 | 7909690.8

## 22HVAC
EY Karachi - 22nd Floor - M&P
ITEM NO. | DESCRIPTION |  |  | ESTIMATED QUANTITY | UNIT | MATERIAL |  | INSTALLATION |  | AMOUNT | Lead Time | Brands
[6 empty] | RATE | AMOUNT | RATE | AMOUNT
1 | FAN COIL UNITS (SECTION 23 73 20 & DS/1831-23 73 20)
1.1 | Supply & Installation of Fan Coil Units FCU/22-01 Ceiling Hung Type with Wall Mounted Room Thermostat (3.0 TR) with Scheduling Feature |  |  | 1 | Nos. | 514800 | 514800 | 17600 | 17600 | 532400 | 5 Weeks | SABRO
1.2 | Supply & Installation of Automatic Air Vents |  |  | 2 | Nos. | 7480 | 14960 | 880 | 1760 | 16720 | Ready Stock | SCON
1.3 | Ø ½" (Ø 15mm) Shredder Fitting for Air Vent/Pressure Testing |  |  | 2 | Nos. | 11440 | 22880 | 1760 | 3520 | 26400
1.4 | Lifting & Shifting of Equipments to the Location Designated for Installation as Specified in the Drawings |  |  | 1 | No. | 0 | 0 | 8800 | 8800 | 8800
1.5 | Engineered Supports as per Hitli/Sikla/Walraven/Fischer with Lindapter Type/TR60 complete in all respect |  |  | 1 | Lot | 13200 | 13200 | 2640 | 2640 | 15840 | - | -
1.6 | Commissioning & Testing |  |  | 1 | Lot | 0 | 0 | 17600 | 17600 | 17600 | - | -
Sub-total Carried to Summary
2 | VAV TERMINALS (SECTION 23 36 10 & 23 36 15 & DS/1831-23 36 10 & 23 36 15)
2.1 | Supply & installation of Variable Air Volume (VAV) Terminals with Wall Mounted Thermostat having temperature (Inc./dec.) (Section 23 36 10 & DS/1676-23 36 10) |  |  | 10 | Nos. | 168960 | 1689600 | 6160 | 61600 | 1751200 | 8 to 10 Weeks | JES
2.2 | Engineered Supports System with Lindapter Type/TR60 complete in all respect. |  |  | 1 | Lot | 88000 | 88000 | 13200 | 13200 | 101200 | - | -
2.3 | Commissioning & Testing of VAV Terminals |  |  | 1 | Lot | 0 | 0 | 88000 | 88000 | 88000
Sub-total Carried to Summary
3 | DUCT WORK (MACHINE MADE) (SECTION 23 31 13)
3.1 | Sheet Metal Duct Work (Air Conditioning) (Supply Air), Machine made Ducts (Section 23 31 13) |  |  | 970 | m² | 4356 | 4225320 | 792 | 768240 | 4993560 | Ready Stock | ISL
3.2 | Sheet Metal Duct Work (Air Conditioning) (Return Air), Machine made Ducts (Section 23 31 13) |  |  | 4 | m² | 4136 | 16544 | 792 | 3168 | 19712 | Ready Stock | ISL
3.3 | Sheet Metal Duct Work (Exhaust Air) Machine made Ducts (Section 23 31 13) |  |  | 57 | m² | 4356 | 248292 | 792 | 45144 | 293436 | Ready Stock | ISL
3.4 | Quadrant Volume Damper |  |  | 14 | m² | 37400 | 523600 | 6160 | 86240 | 609840 | 8 Weeks | Steel Craft/ Air guide
3.5 | Flexible Ducts (Section 23 33 46) with Supports, Complete in all respect
3.5.1 | Ø 10" (Ø 250mm) |  |  | - | Rm | 2200 | Rate Only | 352 | Rate Only | Rate Only | Ready Stock | FLEXIVA / Thermoflex
3.5.2 | Ø 8" (Ø 200mm) |  |  | - | Rm | 1936 | Rate Only | 352 | Rate Only | Rate Only | Ready Stock | FLEXIVA / Thermoflex
3.5.3 | Ø 6" (Ø 150mm) |  |  | 16 | Rm | 1056 | 16896 | 352 | 5632 | 22528 | Ready Stock | FLEXIVA / Thermoflex
3.6 | Butterfly Dampers
3.6.1 | Ø 10" (Ø 250mm) |  |  | - | No. | 4400 | Rate Only | 880 | Rate Only | Rate Only | 3 to 4 weeks | Steel Craft/ Air guide
3.6.2 | Ø 8" (Ø 200mm) |  |  | - | No. | 3520 | Rate Only | 880 | Rate Only | Rate Only | 3 to 4 weeks | Steel Craft/ Air guide
3.6.3 | Ø 6" (Ø 150mm) |  |  | 16 | Nos. | 3080 | 49280 | 880 | 14080 | 63360 | 3 to 4 weeks | Steel Craft/ Air guide
3.7 | Fire Damper - Motorized (UL - Listed)
3.7.1 | 42" x 6" (1050mm x 150mm) |  |  | 4 | No. | 162800 | 651200 | 13200 | 52800 | 704000 | 7 Weeks | LOCAL
3.8 | Damper - Motorized
3.8.1 | 14" x 12" (350mm x 300mm) |  |  | 1 | Nos. | 101200 | 101200 | 4400 | 4400 | 105600 | 13 Weeks | LOCAL
3.8.2 | 20" x 8" (500mm x 200mm) |  |  | 1 | Nos. | 105600 | 105600 | 4400 | 4400 | 110000 | 13 Weeks | LOCAL
3.8.3 | 20" x 12" (500mm x 300mm) |  |  | 1 | Nos. | 110000 | 110000 | 4400 | 4400 | 114400 | 13 Weeks | LOCAL
3.9 | Engineered Support system for Ducts with Lindapter Type/TR60 Complete in all Respect. |  |  | 1 | Lot | 528000 | 528000 | 66000 | 66000 | 594000
3.1 | Sound Trap Air Duct Z-Piece for Return Air Intake Size 450mm x 200mm - Refer FND Detail FND/D/35 |  |  | 9 | Nos. | 9680 | 87120 | 2640 | 23760 | 110880
3.11 | G.I Frame as Duct Sleeves - As per FND Detail |  |  | 1 | Lot | 44000 | 44000 | 22000 | 22000 | 66000 | As per required | LOCAL
3.12 | Wire Mesh on all Duct Openings |  |  | 1 | Lot | 22000 | 22000 | 13200 | 13200 | 35200 | As per required | LOCAL
3.13 | Light Testing for Ducting |  |  | 1 | Lot | 0 | 0 | 66000 | 66000 | 66000
Sub-total Carried to Summary
4 | PIPING (SECTION 23 21 13 & DS/1831-23 21 13)
4.1 | Supply & Installation Chilled Water Piping
4.1.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 3784 | Rate Only | 704 | Rate Only | Rate Only | Ready Stock | PROTEK - China
4.1.2 | Ø 1 ½" (Ø 40mm) |  |  | - | Rm | 2904 | Rate Only | 660 | Rate Only | Rate Only | Ready Stock | PROTEK - China
4.1.3 | Ø 1 ¼" (Ø 32mm) |  |  | - | Rm | 2464 | Rate Only | 642.4 | Rate Only | Rate Only | Ready Stock | PROTEK - China
4.1.4 | Ø 1" (Ø 25mm) |  |  | 20 | Rm | 2024 | 40480 | 580.8 | 11616 | 52096 | Ready Stock | PROTEK - China
4.2 | Supply & Installation Cooling Water Piping
4.2.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 6424 | Rate Only | 704 | Rate Only | Rate Only | Ready Stock | Aquatherm
4.2.2 | Ø 1 ½" (Ø 40mm) |  |  | - | Rm | 4840 | Rate Only | 660 | Rate Only | Rate Only | Ready Stock | Aquatherm
4.2.3 | Ø 1 ¼" (Ø 32mm) |  |  | 8 | Rm | 3080 | 24640 | 642.4 | 5139.2 | 29779.2 | Ready Stock | Aquatherm
4.2.4 | Ø 1" (Ø 25mm) |  |  | - | Rm | 2640 | Rate Only | 580.8 | Rate Only | Rate Only | Ready Stock | Aquatherm
4.3 | Condensate Drain Piping
4.3.1 | Ø 1 ¼" (Ø 32mm) |  |  | - | Rm | 1056 | Rate Only | 264 | Rate Only | Rate Only
4.3.2 | Ø 1" (Ø 25mm) |  |  | 22 | Rm | 1012 | 22264 | 246.4 | 5420.8 | 27684.8 | Ready Stock | AGM
4.4 | Pipe Pressure Testing |  |  | 1 | Lot | 0 | 0 | 22000 | 22000 | 22000 | Ready Stock | AGM
4.5 | Engineered Support system with Lindapter Type/TR60 Complete in all Respect. |  |  | 1 | Lot | 88000 | 88000 | 13200 | 13200 | 101200
Sub-total Carried to Summary
5 | VALVES & SPECIALITIES (SECTION 23 05 23, 23 86 20 & 23 86 35)
5.1 | Supply and Installation of Gate Valves for Cooling Water with Material/Flanges/Unions etc. (Section 23 05 23)
5.1.1 | Ø 2" (Ø 50mm) |  |  | - | No. | 22000 | Rate Only | 1320 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.1.2 | Ø 1 ½" (Ø 40mm) |  |  | - | No. | 15840 | Rate Only | 1320 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.1.3 | Ø 1 ¼" (Ø 32mm) |  |  | 4 | No. | 10120 | 40480 | 1320 | 5280 | 45760 | 4 to 6 weeks | SCON / WATTS
5.1.4 | Ø 1" (Ø 25mm) |  |  | 3 | Nos. | 8360 | 25080 | 1320 | 3960 | 29040 | 4 to 6 weeks | SCON / WATTS
5.1.5 | Ø ¾" (Ø 20mm) |  |  | - | No. | 5720 | Rate Only | 1320 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.2 | Supply and Installation of Ball Valve for Cooling Water with Material/Flanges/Unions etc. (Section 23 05 23)
5.2.1 | Ø 1" (Ø 25mm) |  |  | - | No. | 7920 | Rate Only | 1320 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.2.2 | Ø ¾" (Ø 20mm) |  |  | - | Nos. | 6160 | Rate Only | 1320 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.3 | Supply and Installation of Strainer Cooling Water with Material/Flanges/Unions etc.
5.3.1 | Ø 2" (Ø 50mm) |  |  | - | No. | 18040 | Rate Only | 880 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.3.2 | Ø 1 ½" (Ø 40mm) |  |  | - | No. | 14080 | Rate Only | 880 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.3.3 | Ø 1 ¼" (Ø 32mm) |  |  | 1 | No. | 10560 | 10560 | 880 | 880 | 11440 | 4 to 6 weeks | SCON / WATTS
5.3.4 | Ø 1" (Ø 25mm) |  |  | 1 | No. | 6600 | 6600 | 880 | 880 | 7480 | 4 to 6 weeks | SCON / WATTS
5.4 | Supply and Installation of Flow Balancing & Shut-off Valve for Cooling Water with Material/Flanges/Unions etc.
5.4.1 | Ø 1 ½" (Ø 40mm) |  |  | - | No. | 27720 | Rate Only | 1320 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.4.2 | Ø 1 ¼" (Ø 32mm) |  |  | 2 | Nos. | 20944 | 41888 | 1320 | 2640 | 44528 | 4 to 6 weeks | SCON / WATTS
5.4.3 | Ø 1" (Ø 25mm) |  |  | - | No. | 17600 | Rate Only | 1320 | Rate Only | Rate Only | 4 to 6 weeks | SCON / WATTS
5.5 | Supply and Installation of Pressure Independent Control Valve (PICV) for Fan Coil Unit with Material/Flanges/Unions etc.
5.5.1 | Ø 1 ½" (Ø 40mm) |  |  | - | No. | 345840 | Rate Only | 7040 | Rate Only | Rate Only | 8 to 10 Weeks | SCON / WATTS
5.5.2 | Ø 1 ¼" (Ø 32mm) |  |  | - | No. | 162800 | Rate Only | 7040 | Rate Only | Rate Only | 8 to 10 Weeks | SCON / WATTS
5.5.3 | Ø 1" (Ø 25mm) |  |  | 1 | No. | 130680 | 130680 | 7040 | 7040 | 137720 | 8 to 10 Weeks | SCON / WATTS
Sub-total Carried to Summary
6 | THERMAL INSULATION (SECTION 23 07 13 & 23 07 19 & DS/1831-23 07 13 & 23 07 19)
6.1 | Insulation of Supply Air Duct-Air Conditioned Space/Air Conditioned Ceiling Cavity |  |  | 970 | m² | 4664 | 4524080 | 660 | 640200 | 5164280 | Ready Stock | AEROFOAM
6.2 | Insulation of Return Air Duct-Air Conditioned Space/Air Conditioned Ceiling Cavity |  |  | 4 | m² | 4576 | 18304 | 660 | 2640 | 20944 | Ready Stock | AEROFOAM
6.3 | Supply & Installation Chilled Water Piping (Section 23 07 19 & DS/1831-23 07 19)
6.3.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 3168 | Rate Only | 202.4 | Rate Only | Rate Only | Ready Stock | AEROFOAM
6.3.2 | Ø 1 ½" (Ø 40mm) |  |  | - | Rm | 2904 | Rate Only | 202.4 | Rate Only | Rate Only | Ready Stock | AEROFOAM
6.3.3 | Ø 1 ¼" (Ø 32mm) |  |  | - | Rm | 2640 | Rate Only | 202.4 | Rate Only | Rate Only | Ready Stock | AEROFOAM
6.3.4 | Ø 1" (Ø 25mm) |  |  | 20 | Rm | 2446.4 | 48928 | 202.4 | 4048 | 52976 | Ready Stock | AEROFOAM
6.4 | Condensate Drain Piping Insulation (Section 23 07 19 & DS/1831-23 07 19)
6.4.1 | Ø 1 ¼" (Ø 32mm) |  |  | - | Rm | 1672 | Rate Only | 264 | Rate Only | Rate Only | Ready Stock | AEROFOAM
6.4.2 | Ø 1" (Ø 25mm) |  |  | 22 | Rm | 1645.6 | 36203.2 | 290.4 | 6388.8 | 42592 | Ready Stock | AEROFOAM
6.5 | Cladding of Valves & Specialities (Openable Boxes with Insulation)
6.5.1 | Ø 2" (Ø 50mm) |  |  | - | No. | 0 | Rate Only | 0 | Rate Only | Rate Only | - | -
6.5.2 | Ø 1 ½" (Ø 40mm) |  |  | - | No. | 0 | Rate Only | 0 | Rate Only | Rate Only | - | -
6.5.3 | Ø 1 ¼" (Ø 32mm) |  |  | - | No. | 0 | Rate Only | 0 | Rate Only | Rate Only | - | -
6.5.4 | Ø 1" (Ø 25mm) |  |  | 5 | Nos. | 6160 | 'Rate Only | 1320 | 'Rate Only | 'Rate Only | - | -
Sub-total Carried to Summary
7 | AIR DEVICES (SECTION 23 37 13)
7.1 | Supply Air Linear (Tuttle & Bailey) (Series 7000 1" - 25mm x 3 Slots) with Factory Supplied & Field Installed Plenum with Insulation |  |  | 17 | Rm | 5016 | 85272 | 616 | 10472 | 95744 | 8 to 10 weeks | Steel Craft/ Air guide
7.2 | Return Air Linear (Tuttle & Bailey) (Series 7000 1" - 25mm x 3 Slots) with Factory Supplied & Field Installed Plenum with Insulation |  |  | 17 | Rm | 5016 | 85272 | 616 | 10472 | 95744 | 8 to 10 weeks | Steel Craft/ Air guide
7.3 | Supply / Return Air Fixed Bar Grill & Register (Tuttle & Bailey - A50 Series) 21" x 6" (525mm x 150mm) with Damper |  |  | 6 | Nos. | 3960 | 23760 | 616 | 3696 | 27456 | 8 to 10 weeks | Steel Craft/ Air guide
7.4 | Supply Air Fixed Bar Grill & Register (Tuttle & Bailey - A50 Series) 42" x 6" (1050mm x 150mm) with Damper |  |  | 2 | Nos. | 10560 | 21120 | 4400 | 8800 | 29920 | 8 to 10 weeks | Steel Craft/ Air guide
7.5 | Supply / Return Air Fixed Bar Grill & Register (Tuttle & Bailey - A50 Series) 232" x 18" (5800mm x 450mm) with Damper |  |  | 1 | No. | 92400 | 92400 | 4400 | 4400 | 96800 | 8 to 10 weeks | Steel Craft/ Air guide
7.6 | Supply Air Round Diffusers Ø 12" (Tuttle & Bailey) (Series AVJR 3-Cone) with Dampers |  |  | 89 | Nos. | 21560 | 1918840 | 1320 | 117480 | 2036320 | 8 to 10 weeks | Steel Craft/ Air guide
7.7 | Supply Air Round Diffusers Ø 10" (Tuttle & Bailey) (Series AVJR 3-Cone) with Dampers |  |  | - | No. | 19360 | Rate Only | 1320 | Rate Only | Rate Only | 8 to 10 weeks | Steel Craft/ Air guide
7.8 | Exhaust Air Disc Valve for Toilet Exhaust (Ø 6") |  |  | 24 | Nos. | 2816 | 67584 | 880 | 21120 | 88704 | 8 to 10 weeks | Steel Craft/ Air guide
Sub-total Carried to Summary
8 | WATER COOLED PACKAGED AIR CONDITIONER (SECTION 23 81 30 & DS/1831-23 81 30)
8.1 | Supply and Installation of Water Cooled Packaged Air Conditioner (CWPU-22/01-02) Ceiling Hung Type with Wall Mounted Room Thermostat (3.0 TR) with Scheduling feature |  |  | 2 | Nos. | 941600 | 1883200 | 22000 | 44000 | 1927200 | 12 Weeks | SABRO / COOLMAX
8.2 | Supply and Installation of Automatic Air Vents |  |  | 4 | Nos. | 7480 | 29920 | 880 | 3520 | 33440 | Ready Stock | SCON / WATTS
8.3 | Ø ½" (Ø 15mm) Shredder Fitting for Air Vent/Pressure Testing |  |  | 4 | Nos. | 8800 | 35200 | 1760 | 7040 | 42240
8.4 | Pressure Switch |  |  | 1 | No. | 21120 | 21120 | 2640 | 2640 | 23760 | 5 Weeks | Danfoss
8.5 | Control Wiring Between Indoor and Thermostat |  |  | 1 | Lot. | 8800 | 8800 | 2200 | 2200 | 11000 | Ready Stock | INDUS / FAST
8.6 | Support System with Lindapter Type/TR60 complete in all respect |  |  | 1 | Lot. | 13200 | 13200 | 2640 | 2640 | 15840 | Ready Stock | INDEX
8.7 | Commissioning & Testing of Water Cooled Package Units |  |  | 1 | Lot. | 0 | 0 | 17600 | 17600 | 17600
Sub-total Carried to Summary
9 | METER & GAUGES (SECTION 23 05 19)
9.1 | Thermometers with Wells for Pipe Thermometer |  |  | 6 | Nos. | 11000 | 66000 | 880 | 5280 | 71280 | Ready Stock | WEISS / WEKSLER
9.2 | Pressure Gauges on Pipes |  |  | 6 | Nos. | 8360 | 50160 | 880 | 5280 | 55440 | Ready Stock | WEISS / WEKSLER
9.3 | Gauge Outlets with Cock |  |  | 6 | Nos. | 1760 | 10560 | 880 | 5280 | 15840 | Ready Stock | WEISS / WEKSLER
Sub-total Carried to Summary
10 | HVAC CONTROLS (SECTION 23 09 20)
10.1 | DDC Controller (BACnet/IP) for FCU-22-01 (Refer FND Drawing # FND-1831-XX-H-XX-XX-700-00) |  |  | 1 | No. | 154000 | Rate Only | 4400 | Rate Only | Rate Only | 10 Weeks | JES
10.2 | DDC Controller (BACnet/IP) for CWPU-22-01&02 (Refer FND Drawing # FND-1831-XX-H-XX-XX-700-00) |  |  | 2 | Nos. | 154000 | Rate Only | 4400 | Rate Only | Rate Only | 10 Weeks | JES
10.3 | Installation of Differential Pressure Switch (DPS) with pressure adjustment range of .5 to 4 mbar and switching difference of 0.2 mbar or less. |  |  | 2 | Nos. | 0 | Rate Only | 13200 | Rate Only | Rate Only | 10 Weeks | JES
10.4 | Wiring of PS from Duct Index Point to AHU DDC Panel (3 Core x 18AWG Shielded Wire-Belden Cable) |  |  | 1 | Lot | 154000 | Rate Only | 22000 | Rate Only | Rate Only | 10 Weeks | JES
10.5 | Master/Network Controller that will host the connected devices (VAV's Controllers and thermostat) and can work as a standalone server. (complete set along with Power Supply) |  |  | 1 | No. | 1276000 | Rate Only | 67760 | Rate Only | Rate Only | 10 Weeks | JES
10.6 | Server Platform that work as single point of administration through WebStation for BMS Centralized alarms and data management |  |  | 1 | No. | 396000 | Rate Only | 64240 | Rate Only | Rate Only | 10 Weeks | JES
10.7 | Server Machine - Intel Corei5- 3.0 GHz or better processor, 8 GB or better of memory, and a hard drive of 1 TB. Supported with Microsoft Windows Server 2016 and Microsoft .NET Framework 4.5 or 4.6 |  |  | 1 | No. | 347600 | Rate Only | 58960 | Rate Only | Rate Only | 10 Weeks | JES
10.8 | License for enabling its WebServices on Internet |  |  | 1 | No. | 859760 | Rate Only | 64240 | Rate Only | Rate Only | 10 Weeks | JES
10.9 | Deployement of Mobile Application with its all customised mimics along with the comissioning as per control matrix / scheme (Platform:Apple iOS 11, Android 5.0 (Lollipop) and later) |  |  | 1 | No. | 127600 | Rate Only | 19800 | Rate Only | Rate Only | 10 Weeks | JES
10.1 | Deployement of Cat-6 cable infrastructure with all accessories throughout the facility in a Daisy Chain Pattern |  |  | 1 | Job | 859760 | Rate Only | 118800 | Rate Only | Rate Only | 10 Weeks | JES
10.11 | Layer 2 Manageable Switch with dual power supply , high-performance, standalone, 10/100 autosensing Fast Ethernet that should have 24-10/100 ports plus 2 fixed 100BASE-FX port |  |  | 1 | Lot | 83600 | Rate Only | 22000 | Rate Only | Rate Only | 10 Weeks | JES
10.12 | Integration & comissioning of Pressure Independent Control Valve with Modulating Proportional Valve Actuator with Reversible Synchronous Motor 0-10 VDC. (Chilled Water Application) |  |  | 1 | No. | 66000 | Rate Only | 13200 | Rate Only | Rate Only | 10 Weeks | JES
10.13 | Integration of Wall Mounted Room Thermostat for FCU-22-01 - Supplied with FCU |  |  | 1 | No. | 66000 | Rate Only | 8800 | Rate Only | Rate Only | 10 Weeks | JES
10.14 | Integration of Wall Mounted Room Thermostat for CWPU-22/01-02 - Supplied with CWPU |  |  | 2 | Nos. | 66000 | Rate Only | 8800 | Rate Only | Rate Only | 10 Weeks | JES
10.15 | Integration of Pressure Switch - Supplied with CWPU |  |  | 1 | No. | 66000 | Rate Only | 13200 | Rate Only | Rate Only | 10 Weeks | JES
10.16 | Integration of VAV-01 |  |  | 1 | No. | 118800 | Rate Only | 15840 | Rate Only | Rate Only | 10 Weeks | JES
10.17 | Integration of Motorized Fire Damper Actuator (4 Nos.) with power & control cable 1.5mm2 installed in (Ø 20mm) PVC Conduit, complete in all respect (Size of Damper 525 x 150mm & Airflow is 500 cfm) - Material Covered in BOQ item # 3.7 |  |  | 1 | Lot | 127600 | Rate Only | 39600 | Rate Only | Rate Only | 10 Weeks | JES
10.18 | Integration of Motorized Fire Damper Actuator (2 Nos.) with power & control cable 1.5mm2 installed in (Ø 20mm) PVC Conduit, complete in all respect (Size of Damper 1050mm x 150mm & Airflow is 1000 cfm) - Material Covered in BOQ item # 3.7 |  |  | 1 | Lot | 127600 | Rate Only | 39600 | Rate Only | Rate Only | 10 Weeks | JES
10.19 | Integration of Motorized Damper Actuator (2 No.) with power & control cable 1.5mm2 installed in (Ø 20mm) PVC Conduit, complete in all respect (Size of Damper 500mm x 200mm & Airflow is 1000cfm) - Material Covered in BOQ item # 3.8 |  |  | 1 | Lot | 88000 | Rate Only | 44000 | Rate Only | Rate Only | 10 Weeks | JES
10.2 | Networking, Cabling, Receway Support, Hanger, Sleeves, Core Drilling etc. |  |  | 1 | Lot | 308000 | Rate Only | 66000 | Rate Only | Rate Only | 10 Weeks | JES
Sub-total Carried to Summary
11 | HOT WATER SUPPLY SYSTEM
11.1 | Supply & Installation of Instant Electric Operated Hot Water Heaters (Section 22 33 30 & DS/1831-22 33 30)
11.1.1 | Supply, Installation and Comissioning of Electric Operated Hot Water Heater HWH/01-02, 30L heating capacity. Including all fittings and accessories required from installation till comissioning of Hot Water Heater (Refer DS/1831-22 33 30) | 2 | Nos. | 2 | Nos. | 68640 | 137280 | 4400 | 8800 | 146080 | Ready Stock | ARISTON
11.2 | Poly Propylene Pipe for Cold Water Supply (PPR Pipe PN-20 with PN-20 Fittings including all Fittings and Accessories Required for Piping Installation) (Section 22 11 16 & DS/1831-22 11 16)
11.2.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 3960 | Rate Only | 704 | Rate Only | Rate Only | Ready Stock | RECKTHERM
11.2.2 | Ø 1 ½" (Ø 40mm) |  |  | - | Rm | 3080 | Rate Only | 704 | Rate Only | Rate Only | Ready Stock | RECKTHERM
11.2.3 | Ø 1 ¼" (Ø 32mm) |  |  | - | Rm | 2640 | Rate Only | 704 | Rate Only | Rate Only | Ready Stock | RECKTHERM
11.2.4 | Ø 1" (Ø 25mm) |  |  | 6 | Rm | 1936 | 11616 | 704 | 4224 | 15840 | Ready Stock | RECKTHERM
11.3 | Poly Propylene Pipe for Hot Water Supply (PPR Pipe PN-20 with PN-20 Fittings including all Fittings and Accessories Required for Piping Installation) (Section 22 11 16 & DS/1831-22 11 16)
11.3.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 3960 | Rate Only | 704 | Rate Only | Rate Only | Ready Stock | RECKTHERM
11.3.2 | Ø 1 ½" (Ø 40mm) |  |  | 13 | Rm | 3080 | 40040 | 704 | 9152 | 49192 | Ready Stock | RECKTHERM
11.3.3 | Ø 1 ¼" (Ø 32mm) |  |  | 23 | Rm | 2640 | 60720 | 704 | 16192 | 76912 | Ready Stock | RECKTHERM
11.3.4 | Ø 1" (Ø 25mm) |  |  | 12 | Rm | 1936 | 23232 | 704 | 8448 | 31680 | Ready Stock | RECKTHERM
11.4 | Valve & Specialities (Section 22 05 23)
11.4.1 | Gate Valves - PPR PN-20 (Including all Fittings and Accessories Required for Valve Installation) (Section 22 05 23)
11.4.1.1 | Ø 2" (Ø 50mm) |  |  | - | No. | 22000 | Rate Only | 880 | Rate Only | Rate Only | Ready Stock | RECKTHERM
11.4.1.2 | Ø 1 ½" (Ø 40mm) |  |  | 2 | Nos. | 15840 | 31680 | 880 | 1760 | 33440 | Ready Stock | RECKTHERM
11.4.1.3 | Ø 1 ¼" (Ø 32mm) |  |  | 4 | Nos. | 9504 | 38016 | 880 | 3520 | 41536 | Ready Stock | RECKTHERM
11.4.1.4 | Ø 1" (Ø 25mm) |  |  | 10 | Nos. | 7480 | 74800 | 880 | 8800 | 83600 | Ready Stock | RECKTHERM
11.4.2 | Insulation of Hot Water Piping Including Vapor Barrier, Jacketing & Cladding (Section 22 07 19 & DS/1831-22 07 19)
11.4.2.1 | Ø 2" (Ø 50mm) |  |  | - | Rm | 1936 | Rate Only | 123.2 | Rate Only | Rate Only | 2 to 3 weeks | AEROFOAM
11.4.2.2 | Ø 1 ½" (Ø 40mm) |  |  | 13 | Rm | 1584 | 20592 | 114.4 | 1487.2 | 22079.2 | 2 to 3 weeks | AEROFOAM
11.4.2.3 | Ø 1 ¼" (Ø 32mm) |  |  | 23 | Rm | 1496 | 34408 | 105.6 | 2428.8 | 36836.8 | 2 to 3 weeks | AEROFOAM
11.4.2.4 | Ø 1" (Ø 25mm) |  |  | 12 | Rm | 1320 | 15840 | 88 | 1056 | 16896 | 2 to 3 weeks | AEROFOAM
11.5 | Cladding of Valves & Specialities (Openable Boxes with Insulation)
11.5.1 | Ø 2" (Ø 50mm) |  |  | - | No. | 4400 | Rate Only | 528 | Rate Only | Rate Only
11.5.2 | Ø 1 ½" (Ø 40mm) |  |  | 2 | Nos. | 3520 | Rate Only | 528 | Rate Only | Rate Only
11.5.3 | Ø 1 ¼" (Ø 32mm) |  |  | 4 | Nos. | 2640 | Rate Only | 528 | Rate Only | Rate Only
11.5.4 | Ø 1" (Ø 25mm) |  |  | 8 | Nos. | 1760 | Rate Only | 528 | Rate Only | Rate Only
11.6 | Pressure Testing of Water Supply Piping (1.5 times of operating pressure) (Including all arrangements required for Pressure Testing) |  |  | 1 | Lot | 0 | 0 | 22000 | 22000 | 22000
11.7 | Engineered Support system with Lindapter Type/TR60 Complete in all Respect. |  |  | 1 | Lot | 66000 | 66000 | 13200 | 13200 | 79200
Sub-total Carried to Summary
12 | PLUMBING FIXTURES & FITTINGS
12.1 | Fixtures (Section 22 41 10 & DS/1831-22 41 10)
12.1.1 | Supply & Installation of Wall Hung Western WC, Concealed Flush Tank Operated (Section 22 41 10 & DS/1831-22 41 10) |  |  | 10 | Nos. | 134640 | 1346400 | 6600 | 66000 | 1412400 | 12 weeks | Porta & Grohe
12.1.2 | Supply & Installation of Vanity Wash Basin with, Waste, Bottle Trap & Tee Stop-Cock (Section 22 41 10 & DS/1831-22 41 10) |  |  | 10 | Nos. | 66000 | 660000 | 5720 | 57200 | 717200 | 12 weeks | Porta & Grohe
12.1.3 | Supply & Installation of Disabled Toilet Set (Basin, WC) (Section 22 41 10 & DS/1831-22 41 10) |  |  | 2 | Nos. | 66000 | 132000 | 5720 | 11440 | 143440 | 12 weeks | Porta & Grohe
12.1.4 | Supply & Installation of Wash Basin Single Lever Faucet with Flexible Hoses (For Cold & Hot Water). (Section 22 41 10 & DS/1831-22 41 10) |  |  | 12 | Nos. | 48400 | 580800 | 3960 | 47520 | 628320 | 12 weeks | Porta & Grohe
12.1.5 | Supply & Installation of Stainless Steel Kitchen Sink including stop cocks, P-trap / bottle trap, waste pipe etc. |  |  | 1 | Nos. | 83600 | 83600 | 5280 | 5280 | 88880 | 12 weeks | Porta & Grohe
12.1.6 | Supply & Installation of Hot and Cold Water Mixer for Stainless Steel Kitchen Sink |  |  | 1 | Nos. | 42240 | 42240 | 3960 | 3960 | 46200 | 12 weeks | Porta & Grohe
12.1.7 | Supply & Installation of WC Hand Operated Shower Spray With Angle Valve and Flexible Hose. (Section 22 41 10 & DS/1831-22 41 10) |  |  | 12 | Nos. | 12760 | 153120 | 1320 | 15840 | 168960 | 12 weeks | Porta & Grohe
12.1.8 | Supply & Installation of Bib Cocks for (Janitor, Cleaning Area) (Section 22 41 10 & DS/1831-22 41 10) |  |  | 2 | Nos. | 2200 | 4400 | 880 | 1760 | 6160 | 12 weeks | Porta & Grohe
12.1.9 | Supply & Installation of Single Lever Faucet Wall Mounted for (Hot & Cold Water) (Ablution Area) (Section 22 41 10 & DS/1831-22 41 10) |  |  | 6 | Nos. | 42240 | 253440 | 3960 | 23760 | 277200 | 12 weeks | Porta & Grohe
12.1.10 | Supply & Installation of Toilet Roll Holder (Section 22 41 10 & DS/1831-22 41 10) |  |  | 12 | Nos. | 12056 | 144672 | 880 | 10560 | 155232 | 12 weeks | Porta & Grohe
12.1.11 | Supply & Installation of Wall Mounted Soap Dispenser (Section 22 41 10 & DS/1831-22 41 10) |  |  | 10 | Nos. | 12760 | 127600 | 880 | 8800 | 136400 | 12 weeks | Porta & Grohe
12.2 | Drainage & Vent Pipe (uPVC - Non Pressure Class; Solvent Welded) Including all Fittings and Accessories Required for Piping Installation e.g Elbows, Y, Double Y, Ceiling Cleanouts, Reducers, Sockets etc. (Section 22 13 20 & DS/1831-22 13 20)
12.2.1 | Ø 4" (Ø 100mm) |  |  | - | Rm | 3080 | Rate Only | 528 | Rate Only | Rate Only | Ready Stock | AGM
12.2.2 | Ø 3" (Ø 75mm) |  |  | - | Rm | 1936 | Rate Only | 528 | Rate Only | Rate Only | Ready Stock | AGM
12.2.3 | Ø 2" (Ø 50mm) |  |  | - | Rm | 1408 | Rate Only | 528 | Rate Only | Rate Only | Ready Stock | AGM
12.2.4 | Ø 1 ½" (Ø 40mm) |  |  | - | Rm | 1100 | Rate Only | 528 | Rate Only | Rate Only | Ready Stock | AGM
12.3 | Drain Accessories (Section 22 11 19)
12.3.1 | SS Floor Drain (Section 22 11 19)
12.3.1.1 | Ø 6" x 6" (Ø 150 x 150 mm) |  |  | 20 | Nos. | 7744 | 154880 | 880 | 17600 | 172480 | Ready Stock | QABIL
12.3.2 | SS Floor Clean Out (Section 22 11 19)
12.3.2.1 | Ø 4" (Ø 100mm) |  |  | 12 | Nos. | 6600 | 79200 | 880 | 10560 | 89760 | Ready Stock | QABIL
12.3.2.2 | Ø 3" (Ø 75mm) |  |  | - | No. | 6600 | Rate Only | 880 | Rate Only | Rate Only | Ready Stock | QABIL
12.4 | 350mm Wide Drain Channel with SS Grating for Ablution Area (Refer FND Detail # FND/SDS/24) |  |  | 6 | Rm | 36960 | 221760 | 880 | 5280 | 227040 | Ready Stock | QABIL
12.5 | Gravity Testing of Drainage Piping (Including all arrangements required for Gravity Testing) |  |  | 1 | Lot | 0 | 0 | 26400 | 26400 | 26400
12.6 | Engineered Support system Complete in all Respect. |  |  | 1 | Lot | 44000 | 44000 | 13200 | 13200 | 57200 | Ready Stock | INDEX
Sub-total Carried to Summary
13 | CLEANING & BALANCING OF HVAC SYSTEM (SECTION 23 05 93)
13.1 | Cleaning & Balancing of HVAC System |  |  | 1 | Lot | 0 | 0 | 132000 | 132000 | 132000
Sub-total Carried to Summary
14 | PAINTING & FINISHING AND MECHANICAL IDENTIFICATION (SECTION 23 05 50 & 23 05 53)
14.1 | Painting & Finishing, Stenciling of Pipes & Ducts, Identification Tags on Valves etc. and Equipment Data Plates (Section 23 05 50) |  |  | 1 | Lot | 88000 | 88000 | 13200 | 13200 | 101200 | Ready Stock | ICI / BERGER
Sub-total Carried to Summary
15 | MISCELLANEOUS
15.1 | Pipe Sleeves/Core Cutting Where Required |  |  | 1 | Lot | 22000 | 22000 | 13200 | 13200 | 35200
15.2 | Shop Drawings, As Built Drawings, Operation & Maintenance Manuals |  |  | 1 | Lot | 22000 | 22000 | 13200 | 13200 | 35200
15.3 | Fire Stopping Material for all HVAC & Plumbing Pipes, Duct, Trays etc. Crossing a Fire Barrier Wall/Floor/Partition as per Required Fire Rating (Refer Fire Strategy Drawings for Fire Barrier Wall/Floor) |  |  | 1 | Lot | 88000 | 88000 | 66000 | 66000 | 154000
Sub-total Carried to Summary | [6 empty] | 23345423.2 |  | 3061264.8 | 26406688
34411348.4

## 22F
EY Karachi - 22nd Floor - FF
ITEM NO. | DESCRIPTION | ESTIMATED QUANTITY | UNIT | MATERIAL |  | INSTALLATION |  | AMOUNT | Lead Time | Brands
|  |  |  | RATE | AMOUNT | RATE | AMOUNT
1 | FIRE SPRINKLERS (SECTION 21 13 10 & DS/1831-21 13 10)
1.1 | Fire Sprinkler- Upright, Quick Response (SP-01) | 215 | Nos. | 2464 | 529760 | 880 | 189200 | 718960 | 10 Weeks | SHIELD
1.2 | Fire Sprinkler- Pendent Concealed, Quick Response (SP-02) | 65 | Nos. | 6600 | 429000 | 880 | 57200 | 486200 | 10 Weeks | SHIELD
1.3 | Fire Sprinkler- Pendent Sprinkler, Quick Response (SP-03) | 12 | Nos. | 3960 | 47520 | 880 | 10560 | 58080 | 10 Weeks | SHIELD
1.4 | Cabinet Complete with 06 Spare Sprinklers (Upright) (SP-01) | 1 | Nos. | 30800 | 30800 | 2640 | 2640 | 33440 | 10 Weeks | SHIELD
1.5 | Cabinet Complete with 06 Spare Sprinklers (Concealed Pendent) (SP-02) | 1 | No. | 39600 | 39600 | 1760 | 1760 | 41360 | 10 Weeks | SHIELD
1.6 | Cabinet Complete with 06 Spare Sprinklers (Pendent) (SP-03) | 1 | No. | 35200 | 35200 | 1760 | 1760 | 36960 | 10 Weeks | SHIELD
Sub-total Carried to Summary
2 | CORRUGATED STAINLESS STEEL FLEXIBLE CONNECTOR
2.1 | Corrugated Stainless Steel Flexible Connector Ø 1" X 3 ft (UL/FM) (Braided) | 65 | Nos. | 10120 | 657800 | 880 | 57200 | 715000 | 10 Weeks | SHIELD / SEUNG JIN IND
Sub-total Carried to Summary
3 | PORTABLE FIRE EXTINGUISHER FOR FIRE TYPES A, B, C & AFFF (SECTION 21 21 10 & DS/1831-21 21 10)
3.1 | Supply & Installation of 6 Kg Dry Powder Extinguisher (ABC) | 2 | Nos. | 12760 | 25520 | 616 | 1232 | 26752 | 10 Weeks | NAFCO
3.2 | Supply & Installation of 6 Kg CO2 Fire Extinguisher | 2 | Nos. | 22440 | 44880 | 616 | 1232 | 46112 | 10 Weeks | NAFCO
Sub-total Carried to Summary
4 | BLACK STEEL SCHEDULE-40 PIPING (SECTION 21 10 10)
4.1 | Welded Piping System
4.1.1 | Ø 4" (100mm) | - | Rm | 11000 | Rate Only | 1100 | Rate Only | Rate Only | ReadyStock | Protek
4.1.2 | Ø 3" (75mm) | 100 | Rm | 8624 | 862400 | 774.4 | 77440 | 939840 | ReadyStock | Protek
4.1.3 | Ø 2½" (65mm) | - | Rm | 6864 | Rate Only | 704 | Rate Only | Rate Only | ReadyStock | Protek
4.2 | Threaded Piping System |  |  | 0 |  | 0
4.2.1 | Ø 2" (50mm) | 178 | Rm | 4136 | 736208 | 624.8 | 111214.4 | 847422.4 | ReadyStock | Protek
4.2.2 | Ø 1½" (40mm) | 143 | Rm | 2983.2 | 426597.6 | 616 | 88088 | 514685.6 | ReadyStock | Protek
4.2.3 | Ø 1¼" (32mm) | 110 | Rm | 2552 | 280720 | 607.2 | 66792 | 347512 | ReadyStock | Protek
4.2.4 | Ø 1" (25mm) | 496 | Rm | 1848 | 916608 | 598.4 | 296806.4 | 1213414.4 | ReadyStock | Protek
Sub-total Carried to Summary
5 | GATE VALVE (SECTION 21 05 23)
5.1 | Ø2 inch (50 mm) | 2 | Nos. | 83600 | 167200 | 4400 | 8800 | 176000 | 10 Weeks | SHILED
Sub-total Carried to Summary
6 | SIESMIC BRACING
6.1 | Transverse Seismic Bracing (As per FND Detail No. FND/SS/10)
6.1.1 | Ø 4" (100mm) | - | No. | 0 | Rate Only | 0 | Rate Only | Rate Only | 6 weeks | Index
6.1.2 | Ø 3" (75mm) | 11 | Nos. | 8690 | 95590 | 2640 | 29040 | 124630 | 6 weeks | Index
6.1.3 | Ø 2½" (65mm) | - | No. | 0 | Rate Only | 0 | Rate Only | Rate Only | 6 weeks | Index
6.2 | Longitudinal Seismic Bracing (As per FND Detail No. FND/SS/11)
6.2.1 | Ø 4" (100mm) | - | No. | 0 | Rate Only | 0 | Rate Only | Rate Only | 6 weeks | Index
6.2.2 | Ø 3" (75mm) | 7 | Nos. | 10780 | 75460 | 2640 | 18480 | 93940 | 6 weeks | Index
6.2.3 | Ø 2½" (65mm) | - | No. | 0 | Rate Only | 0 | Rate Only | Rate Only | 6 weeks | Index
6.3 | Seismic Restraint (As per FND Detail No. FND/ADD/08)
6.3.1 | Ø 2" (50mm) | 20 | Nos. | 5121.6 | 102432 | 1320 | 26400 | 128832 | 6 weeks | Index
6.3.2 | Ø 1½" (40mm) | 34 | Nos. | 4664 | 158576 | 1320 | 44880 | 203456 | 6 weeks | Index
6.3.3 | Ø 1¼" (32mm) | 10 | Nos. | 4576 | 45760 | 1320 | 13200 | 58960 | 6 weeks | Index
6.3.4 | Ø 1" (25mm) | 66 | Nos. | 4224 | 278784 | 1320 | 87120 | 365904 | 6 weeks | Index
Sub-total Carried to Summary
7 | FIRE SPRINKLER SYSTEM ACCEPTANCE TEST (SECTION 21 13 17)
7.1 | Fire Sprinkler System Acceptance Test | 1 | Lot | 0 | 0 | 22000 | 22000 | 22000
Sub-total Carried to Summary
8 | PAINTING COATING & STENCILING (SECTION 21 05 50)
8.1 | Painting, Coating, Stenciling & Identification of Fire Piping | 1 | Lot | 176000 | 176000 | 30800 | 30800 | 206800 | Ready Stock | ICI / BERGER
Sub-total Carried to Summary
9 | PIPE SUPPORT SYSTEM (SECTION 21 05 29)
9.1 | Engineered Support system with Lindapter Type/TR60 Complete in all Respect | 1 | Lot | 330000 | 330000 | 48400 | 48400 | 378400 | ReadyStock | Index
Sub-total Carried to Summary
10 | MISCELLANEOUS
10.1 | Hydrostatic Testing | 1 | Lot | 0 | 0 | 44000 | 44000 | 44000
10.2 | Shop Drawings, As Built Drawings, Operation & Maintenance Manuals | 1 | Lot | 0 | 0 | 22000 | 22000 | 22000
10.3 | Fire Stopping of Paritions, Walls & Structure Openings (For Small Openings - Hilti FS - ONE or Approved Equivalent) | 1 | Lot | 88000 | 88000 | 22000 | 22000 | 110000
10.4 | Pipe Sleeves / Core Cutting Wherever Required | 1 | Lot | 22000 | 22000 | 22000 | 22000 | 44000
Sub-total Carried to Summary |  |  |  |  | 6602415.6 |  | 1402244.8 | 8004660.4