## Sheet1
2024-05-06
Mr. Taha Ghaznavi
BILL
Unit Installation Work - Riazeda Office (Clifton Karachi)
S. No | Description | Unit | Qty | Rate | Amount
1 | HVAC Units installation . | TR | 109 | 85000 | 9265000
Total Amount Rs |  |  |  |  | 9265000
Tax 4.5% |  |  |  |  | 416925
Grand Total Amount Rs |  |  |  |  | 9681925
| HVAC Ducting & Fans & MCC Variation Amount |  |  |  | 1179300
Grand Total Amount Rs |  |  |  |  | 10444300
Add Tax 5% |  |  |  |  | 522215 | 7705250
Grand Total After Tax Rs |  |  |  |  | 10966515
95% |  |  |  |  | 10418189.25
Received amount |  |  |  |  | 8631750
Payable Amount Rs |  |  |  |  | 1786439.25
Thanking you,
Sincerely yours,
For PIONEER ENGINEERING SERVICES.
The supply, installation, and designing of M.S fire fighting pipes and Sprinklers system with related fittings such as elbow, clamp, rods bush etc will be carried out at a rate of Rs 650 per square foot (sft).
We believe that our proposed rate is best market competitive.
If this proposal aligns with your budget and project requirements, we are prepared to proceed with further discussions and arrangements to commence work promptly.

## Sheet2
List of Manufacturer
Particular | Brand
Chiller | York, Carrier, SKM, Petra
Pumps | K.S.B, Wilo, Lowara
Air Handling Units | York, Carrier, SKM, Petra
M.S Piping | Lontrin
Valves | Gala / Enonosto
Ducts | Local Made
Insulation | Afico
Jet Diffuser | Inported
Air Devices | Local
Control Wiring | Local