## Sheet1
15-2-2025
Summary of Variation Orders - J outlet Zeta Mall Islamabad
Sr # | DESCRIPTION | AMOUNT
1 | Variation order of OS & Y Fire Gate valve | 433650
2 | Variation order of Balancing Valves | 102361.6
3 | Variation order of Chemical flushing for chilled water piping | 105888
4 | Variation order of canvas cloth, anti fungus and glue | 708480
5 | Variation order of Thermostat and wiring | 1680627.2
6 | Variation order of Fire flexible Pipe | 226048
| Total amount Rs. | 3257054.8
Sr # | Variations | Pioneer Comments
1 | Variation order of OS & Y Fire Gate valve | As per mall requirements, each inlet and outlet connection must be equipped with an individual gate valve for isolation and control.
2 | Variation order of Balancing Valves | This is Mall requirement and instruction received from Client to installed balancing valve for chilled water system.
3 | Variation order of Chemical flushing for chilled water piping | Mall requirement to flush chilled water pipe network with chemical.
4 | Variation order of canvas cloth, anti fungus and glue | Instruction received from the Client to cover insulation with canvas cloth and related material for painting.
5 | Variation order of Thermostat and wiring | This is OFM item not delivered by vendor, instructioun received from Client to supply and fix.
6 | Variation order of Fire flexible Pipe | Mall requirement to install Fire flexbile pipe with Concealed sprinkler.