## Table 1
HVAC & Fire Fighting Work Schedule
Description | Duration | Start Date | End Date | Remarks | March 2023 |  |  |  | 2023-04-01 |  |  |  | 2023-05-01 |  |  |  | 2023-06-01
[5 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
10th FLOOR
Submission of submittal | 8 Days | 2023-03-08 | 2023-03-15
Shop Drawings | 11 Days | 2023-03-22 | 2023-04-02
Installation of Ducted Units (OFM) | 37 Days | 2023-04-08 | 2023-05-15 | OFM
Installation of VAVs (OFM) | 37 Days | 2023-04-08 | 2023-05-15 | OFM
Installation of Ventilation Fan (OFM) | 37 Days | 2023-04-08 | 2023-05-15 | OFM
Installation of Hanger & Support | 16 Days | 2023-03-22 | 2023-04-08
Installation of Chilled water Pipe | 37 Days | 2023-04-08 | 2023-05-15
Insulation Of Chilled water Pipe | 10 Days | 2023-05-15 | 2023-05-25
Installation of ducting | 37 Days | 2023-04-08 | 2023-05-15
Duct Insulation work | 10 Days | 2023-05-15 | 2023-05-25
Installation of MS Fire Pipe | 37 Days | 2023-04-08 | 2023-05-15
Condensate Drain Piping with insulation | 25 Days | 2023-04-01 | 2023-04-25
Installation of air devices | 5 Days | 2023-05-25 | 2023-05-30
Painting / Identification | 5 Days | 2023-05-25 | 2023-05-30
Fire Sprinkler & Fire Extinguishers | 10 Days | 2023-05-20 | 2023-05-30
Testing & Commissioning | 2 Days | 2023-05-30 | 2023-06-02