## HVAC 16th Floor
BOQ ITEM No | Description | Unit | BOQ Qty | Billed Qty | Verified Qty | Action | Remarks
3.1 i | Ball Valve 25mm dia | Nos | 8 | 4 | 2 |  | #REF!
3.7 | Digital Decorative Thermostat Controller (BMS Interfacable) with Duct Mounted Sensor | Nos | 2 | 2 | 0 |  | #REF!
3.8 | Control wiring from controller to sensors, motorized valve and Power wiring up to 15’ radius | Job | 2 | 2 | 0 |  | #REF!
4.1 | 25mm dia | Rm | 25 | 48 | 22 |  | #REF!
4.2 | 32mm dia | Rm | 15 | 13 | 13 |  | #REF!
5 | Thermopore insulation | Rm | 25 | 48 | 22 |  | #REF!
i | 32mm dia | Rm | 15 | 13 | 13 |  | #REF!
8 | pre-insulated ductwork | Sqm | 875 | 875 | 830 |  | #REF!
BOQ ITEM No | Description | Unit | BOQ Qty | Billed Qty | Client response | Action | Remarks
1.1 | ACMV Works i.e; FCU, Pipe, Vlaves, accessories, duct, insulation etc complete job as required. | Job | 1 | 1 | No response | Verified | Agreed
2.1 | FCU-01 | Nos | 2 | 2 | No response | The client didn't verify, hasn't been deleted either | Awaiting from the verification
3.2 i | Strainers 25mm dia | Nos | 2 | 2 | No response |  | #REF!
3.3 i | Balancing Valve (with selI sealing measuring nipples) 25mm dia | Nos | 2 | 2 | No response |  | #REF!
9.1 (ii) | 350mm dia Jet Diffuser | Nos | 8 | 4 | No response |  | #REF! | 15.463
9.2 | S.S Wire mech with G.I Frame | Sqm | 4 | 3.5 | No response |  | #REF!
9.3 (i) | Linear slot 6000 series 2 Slots of 20mm | Rm | 135 | 131 | No response |  | #REF!
10 | flexible duct | Rm | 200 | 190 | No response |  | #REF!
11 | butterfly damper | Nos | 167 | 165 | No response |  | #REF!
15 | Shop drawings on Auto CAD | Job | 1 | 1 | No response |  | #REF!